## Activities PCS
ActID | ActivityName | Disc | Fami | Area | Module | CWP | BaseLine | Estimated Hours | EarnedHours | ResourceID | Total units | Completed Units
A1810 | U23 - Leak Test (573) (Fire Water) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PR.PR.MH
C111131ISEQ000020 | U11 - Equipment Insulation (Loop 2 - Unit 517) | IS | ISEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2954 | 0 | 10780.IS.IS.MH
C111131ISPI000010 | U11 - Piping Insulation (Loop 3 - Unit 516) | IS | ISPI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7454 | 0 | 10610.IS.PI.M2 | 5466 | 0
C111131ISPI000020 | U11 - Piping Insulation (Loop 2 - Unit 517) | IS | ISPI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7890 | 0 | 10610.IS.PI.M2 | 4049 | 0
C111131NITR000010 | U11 - Nitrogen Leak Test (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1116 | 0 | 10780.PR.PR.MH
C111131NITR000020 | U11 - Nitrogen Leak Test (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 565 | 0 | 10780.PR.PR.MH
C111131NITR000030 | U11 - Nitrogen Leak Test (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 594 | 0 | 10780.PR.PR.MH
C111131PIBB000010 | U11 - Big Bore Piping A/Equip. Erection - From Batt. Limit SUB-522 to 516-PR-001 (Loop 3 - Unit 516) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15015 | 0 | 10610.PI.BB.DI | 1501.49 | 0
C111131PIBB000040 | U11 - Big Bore Piping A/Equip. Erection - From 518-PR-002 to 518-PR-001 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIBB000050 | U11 - Big Bore Piping A/Equip. Erection - From 518-PR-001 to Batt. Limit U500 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIBB000060 | U11 - Big Bore Piping A/Equip. Erection - From 516-PR-001 to Batt. Limit U517 (Loop 3 - Unit 516) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15015 | 0 | 10610.PI.BB.DI | 1501.49 | 0
C111131PIPR000030 | U11 - Piping Prefabrication (Loop 3 - Unit 518) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 219153 | 42194.9103 | 10610.PI.FB.DI | 54788.36 | 27230.0053
C111131PIPR000050 | U11 - UG Piping Prefabrication (Loop 2 - Unit 517) | PI | PIPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3312 | 14.985 | 10610.PI.FB.DI | 828 | 1192.4625
C111131PIPR000050 | U11 - UG Piping Prefabrication (Loop 2 - Unit 517) | PI | PIPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3312 | 14.985 | 10610.PI.FB.DI | 828 | 1192.4625
C111131PIPR000060 | U11 - UG Piping Prefabrication (Loop 3 - Unit 516) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4960 | 31.1768 | 10610.PI.FB.DI | 1240 | 1112.3702
C111131PIRA000060 | U11 - Piping Erection on Rack 577-PR-107 (Unit 518) (518-E-201) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000080 | U11 - Piping Erection on Secondary Rack 518-PR-001 (Loop 3 - Unit 518) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000090 | U11 - Piping Erection on Rack 577-PR-109 (Unit 517) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
C111131PIRA000100 | U11 - Piping Erection on Secondary Rack 517-PR-001 (Loop 2 - Unit 517) | PI | PIRA | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
A1740 | U22 - Pumps MRT with potable water | PR | PRMR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2229 | 0 | 10780.PR.PR.MH
A1790 | U23 - Leak Test (568) (Nitrogen) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PR.PR.MH
C1110PRPRWT000030 | U11 - Walkthrough (Loop 3 - Unit 518) | PR | PRWT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2634 | 0 | 10780.PR.PR.MH
C111131ISPI000030 | U11 - Piping Insulation (Loop 3 - Unit 518) | IS | ISPI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10000 | 0 | 10780.IS.IS.MH
C111131MEMC000090 | U11 - Miscellaneous Piping (Unit 517) | PI | PISU2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9778 | 0 | 10780.PI.PI.MH
C111131NIPR000020 | U11 - Nitrogen Purging & Inerting (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 989 | 0 | 10780.PR.PR.MH
C111131NIPR000030 | U11 - Nitrogen Purging & Inerting (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1426 | 0 | 10780.PR.PR.MH
C111131PIBB000020 | U11 - Big Bore Piping A/Equip. Erection (Loop 2 - Unit 517) | PI | PIBB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34999 | 0 | 10610.PI.BB.DI | 3499.88 | 0
C111131PIBB000030 | U11 - Big Bore Piping A/Equip. Erection - From Barr. Limit U517 to 518-PR-002 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIBB000050 | U11 - Big Bore Piping A/Equip. Erection - From 518-PR-001 to Batt. Limit U500 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIBB000060 | U11 - Big Bore Piping A/Equip. Erection - From 516-PR-001 to Batt. Limit U517 (Loop 3 - Unit 516) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15015 | 0 | 10610.PI.BB.DI | 1501.49 | 0
C111131PIRA000010 | U11 - Piping Erection on Rack 577-PR-110 (Unit 516) (516-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41664 | 0 | 10610.PI.PR.DI | 4629.3 | 0
C111131PIRA000020 | U11 - Piping Erection on Rack 577-PR-108 (Unit 517) (517-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
C111131PIRA000030 | U11 - Piping Erection on Rack 577-PR-104 (Unit 518) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000040 | U11 - Piping Erection on Rack 577-PR-105 (Unit 518) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000050 | U11 - Piping Erection on Rack 577-PR-106 (Unit 518) (518-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 59.7905 | 10610.PI.PR.DI | 2830.41 | 159.5219
C111131PIRA000070 | U11 - Piping Erection on Secondary Rack 518-PR-002 (Loop 3 - Unit 518) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000080 | U11 - Piping Erection on Secondary Rack 518-PR-001 (Loop 3 - Unit 518) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PISB000020 | U11 - Small Bore Piping A/Equip. Erection (Loop 2 - Unit 517) | PI | PISB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4656 | 0 | 10610.PI.SB.DI | 423.3 | 0
A1760 | U23 - Leak Test (566) (Coolling water) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.PR.PR.MH
A1800 | U23 - Leak Test (531) (Utility & Potable Water) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PR.PR.MH
C1110PRPRPL000030 | U11 - Punch List (Loop 3 - Unit 518) | PR | PRPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6146 | 0 | 10780.PR.PR.MH
C1110PRPRWT000010 | U11 - Walkthrough (Loop 3 - Unit 516) | PR | PRWT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1444 | 0 | 10780.PR.PR.MH
C111131ISEQ000010 | U11 - Equipment Insulation (Loop 3 - Unit 518) | IS | ISEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4431 | 0 | 10780.IS.IS.MH
C111131MEMC000060 | U11 - Miscellaneous Piping (Unit 518) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19373 | 0 | 10780.PI.PI.MH
C111131NIPR000040 | U11 - Nitrogen Purging & Inerting (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2584 | 0 | 10780.PR.PR.MH
C111131PIBB000020 | U11 - Big Bore Piping A/Equip. Erection (Loop 2 - Unit 517) | PI | PIBB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34999 | 0 | 10610.PI.BB.DI | 3499.88 | 0
C111131PIBB000040 | U11 - Big Bore Piping A/Equip. Erection - From 518-PR-002 to 518-PR-001 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIPR000010 | U11 - Piping Prefabrication (Loop 3 - Unit 516) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 113583 | 12956.1517 | 10610.PI.FB.DI | 28395.87 | 16948.2669
C111131PIPR000020 | U11 - Piping Prefabrication (Loop 2 - Unit 517) | PI | PIPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 113605 | 11029.7688 | 10610.PI.FB.DI | 28401.37 | 15214.7936
C111131PIPR000030 | U11 - Piping Prefabrication (Loop 3 - Unit 518) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 219153 | 42194.9103 | 10610.PI.FB.DI | 54788.36 | 27230.0053
C111131PIPR000040 | U11 - UG Piping Prefabrication (Loop 3 - Unit 518) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9192 | 114.473 | 10610.PI.FB.DI | 2298 | 2666.5906
C111131PIRA000010 | U11 - Piping Erection on Rack 577-PR-110 (Unit 516) (516-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41664 | 0 | 10610.PI.PR.DI | 4629.3 | 0
C111131PIRA000020 | U11 - Piping Erection on Rack 577-PR-108 (Unit 517) (517-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
C111131PIRA000040 | U11 - Piping Erection on Rack 577-PR-105 (Unit 518) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000060 | U11 - Piping Erection on Rack 577-PR-107 (Unit 518) (518-E-201) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000070 | U11 - Piping Erection on Secondary Rack 518-PR-002 (Loop 3 - Unit 518) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000100 | U11 - Piping Erection on Secondary Rack 517-PR-001 (Loop 2 - Unit 517) | PI | PIRA | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
C111131PISB000010 | U11 - Small Bore Piping A/Equip. Erection - From Batt. Limit SUB-522 to 516-PR-001 (Loop 3 - Unit 516) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4213 | 0 | 10610.PI.SB.DI | 383.03 | 0
A1750 | U23 - Leak Test (575) (Waste Water) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PR.PR.MH
A1770 | U23 - Leak Test (572) (Sour Water) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PR.PR.MH
A1780 | U23 - Leak Test (567) (Instrument Air) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3207 | 0 | 10780.PR.PR.MH
C1110PRPRPL000010 | U11 - Punch List (Loop 3 - Unit 516) | PR | PRPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3370 | 0 | 10780.PR.PR.MH
C1110PRPRPL000020 | U11 - Punch List (Loop 2 - Unit 517) | PR | PRPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2821 | 0 | 10780.PR.PR.MH
C1110PRPRWT000020 | U11 - Walkthrough (Loop 2 - Unit 517) | PR | PRWT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1209 | 0 | 10780.PR.PR.MH
C111131ISEQ000030 | U11 - Equipment Insulation (Loop 3 - Unit 516) | IS | ISEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10780.IS.IS.MH
C111131ISPI000010 | U11 - Piping Insulation (Loop 3 - Unit 516) | IS | ISPI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7454 | 0 | 10610.IS.PI.M2 | 5466 | 0
C111131ISPI000020 | U11 - Piping Insulation (Loop 2 - Unit 517) | IS | ISPI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7890 | 0 | 10610.IS.PI.M2 | 4049 | 0
C111131MEMC000010 | U11 - Miscellaneous Piping (Unit 516) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12414 | 0 | 10780.PI.PI.MH
C111131PIBB000010 | U11 - Big Bore Piping A/Equip. Erection - From Batt. Limit SUB-522 to 516-PR-001 (Loop 3 - Unit 516) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15015 | 0 | 10610.PI.BB.DI | 1501.49 | 0
C111131PIBB000030 | U11 - Big Bore Piping A/Equip. Erection - From Barr. Limit U517 to 518-PR-002 (Loop 3 - Unit 518) | PI | PIBB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38561 | 0 | 10610.PI.BB.DI | 3856.12 | 0
C111131PIPR000010 | U11 - Piping Prefabrication (Loop 3 - Unit 516) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 113583 | 12956.1517 | 10610.PI.FB.DI | 28395.87 | 16948.2669
C111131PIPR000020 | U11 - Piping Prefabrication (Loop 2 - Unit 517) | PI | PIPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 113605 | 11029.7688 | 10610.PI.FB.DI | 28401.37 | 15214.7936
C111131PIPR000040 | U11 - UG Piping Prefabrication (Loop 3 - Unit 518) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9192 | 114.473 | 10610.PI.FB.DI | 2298 | 2666.5906
C111131PIPR000060 | U11 - UG Piping Prefabrication (Loop 3 - Unit 516) | PI | PIPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4960 | 31.1768 | 10610.PI.FB.DI | 1240 | 1112.3702
C111131PIRA000030 | U11 - Piping Erection on Rack 577-PR-104 (Unit 518) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 0 | 10610.PI.PR.DI | 2830.41 | 0
C111131PIRA000050 | U11 - Piping Erection on Rack 577-PR-106 (Unit 518) (518-E-101) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25474 | 59.7905 | 10610.PI.PR.DI | 2830.41 | 159.5219
C111131PIRA000090 | U11 - Piping Erection on Rack 577-PR-109 (Unit 517) | PI | PIRA | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25977 | 0 | 10610.PI.PR.DI | 2886.32 | 0
C111131PIRA000110 | U11 - Piping Erection on Secondary Rack 516-PR-001 (Loop 3 - Unit 516) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41664 | 0 | 10610.PI.PR.DI | 4629.3 | 0
C111131PISB000030 | U11 - Small Bore Piping A/Equip. Erection - From Barr. Limit U517 to 518-PR-002 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISB000060 | U11 - Small Bore Piping A/Equip. Erection - From 516-PR-001 to Batt. Limit U517 (Loop 3 - Unit 516) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4213 | 0 | 10610.PI.SB.DI | 383.03 | 0
C111131PISU000040 | U11 - Piping Supports Prefabrication (Loop 3 - Unit 518) | PI | PISU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42425 | 1118.5755 | 10610.PI.PU.TN | 163.17 | 64.3148
C111131PISU000050 | U11 - Piping Supports Erection (Loop 2 - Unit 517) | PI | PISU2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33134 | 0 | 10610.PI.SU.TN | 73.63 | 0
C111131PIUG000010 | U11 - Piping Erection UG (Loop 3 - Unit 516) | PI | PIUG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 558 | 0 | 10610.PI.UG.DI | 372 | 0
C111131PIUG000020 | U11 - Piping Erection UG (Loop 2 - Unit 517) | PI | PIUG | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 492 | 0 | 10610.PI.UG.DI | 328 | 0
C111131PIUG000030 | U11 - Piping Erection UG (Loop 3 - Unit 518) | PI | PIUG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1269 | 0 | 10610.PI.UG.DI | 846 | 0
C111131PRBO000030 | U11 - Static Box Up (Loop 2 - Unit 517) | PR | PRBO1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3258 | 0 | 10780.PR.PR.MH
C111131PRFL000010 | U11 - Piping Flushing/Blowing (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1931 | 0 | 10610.PR.FL.DI | 44028 | 0
C111131PRFL000030 | U11 - Piping Flushing/Blowing (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5286 | 0 | 10610.PR.FL.DI | 82041 | 0
C111131PRFL000150 | U11 - Lube Oil Flushing for Compressors (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2467 | 0 | 10780.PR.PR.MH
C111131PRHT000020 | U11 - Piping Hydrotesting (Loop 2 - Unit 517) | PR | PRHT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29705 | 0 | 10610.PR.HT.DI | 44028 | 0
C111131PRHT000030 | U11 - Piping Hydrotesting (Loop 3 - Unit 518) | PR | PRHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 64611 | 0 | 10610.PR.HT.DI | 82041 | 0
C111131PRRE000070 | U49 - Piping Reinstatement | PR | PRRE | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5061 | 0 | 10610.PR.RE.DI | 14453 | 0
C111132CIDB000023 | U11 - Duct Banks Precast Fabrication (Loop 2 - Unit 517) | CI | CIDB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2365 | 8.1034 | 10780.CI.CI.MH
C111132CIDM000010 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 3 - Unit 516) | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7283 | 72.0853 | 10610.CI.CO.M3 | 121.38 | 107.5901
C111132CIGR000030 | U11 - Grounding Network Execution (Loop 3 - Unit 518) | CI | CIGR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2965 | 1.4284 | 10610.CI.GR.LM | 4941 | 0
C111132CIGR000030 | U11 - Grounding Network Execution (Loop 3 - Unit 518) | CI | CIGR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2965 | 1.4284 | 10610.CI.GR.LM | 4941 | 0
C111132CIGT000030 | U11 - Equipment Grouting Execution (Loop 2 - Unit 517) | CI | CIGT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10780.CI.CI.MH
C111131PIRA000110 | U11 - Piping Erection on Secondary Rack 516-PR-001 (Loop 3 - Unit 516) | PI | PIRA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41664 | 0 | 10610.PI.PR.DI | 4629.3 | 0
C111131PISB000010 | U11 - Small Bore Piping A/Equip. Erection - From Batt. Limit SUB-522 to 516-PR-001 (Loop 3 - Unit 516) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4213 | 0 | 10610.PI.SB.DI | 383.03 | 0
C111131PISB000040 | U11 - Small Bore Piping A/Equip. Erection - From 518-PR-002 to 518-PR-001 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISB000050 | U11 - Small Bore Piping A/Equip. Erection - From 518-PR-001 to Batt. Limit U500 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISB000060 | U11 - Small Bore Piping A/Equip. Erection - From 516-PR-001 to Batt. Limit U517 (Loop 3 - Unit 516) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4213 | 0 | 10610.PI.SB.DI | 383.03 | 0
C111131PISU000020 | U11 - Piping Supports Erection (Loop 3 - Unit 516) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31957 | 0 | 10610.PI.SU.TN | 71.02 | 0
C111131PISU000030 | U11 - Piping Supports Prefabrication (Loop 2 - Unit 517) | PI | PISU1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19144 | 198.0621 | 10610.PI.PU.TN | 73.63 | 23.0589
C111131PISU000050 | U11 - Piping Supports Erection (Loop 2 - Unit 517) | PI | PISU2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33134 | 0 | 10610.PI.SU.TN | 73.63 | 0
C111131PISU000060 | U11 - Piping Supports Erection (Loop 3 - Unit 518) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 73428 | 0 | 10610.PI.SU.TN | 163.17 | 0
C111131PIUG000010 | U11 - Piping Erection UG (Loop 3 - Unit 516) | PI | PIUG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 558 | 0 | 10610.PI.UG.DI | 372 | 0
C111131PIUG000020 | U11 - Piping Erection UG (Loop 2 - Unit 517) | PI | PIUG | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 492 | 0 | 10610.PI.UG.DI | 328 | 0
C111131PRBO000050 | U11 - Rotary Box Up (Loop 2 - Unit 517) | PR | PRBO2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6338 | 0 | 10780.PR.PR.MH
C111131PRFL000010 | U11 - Piping Flushing/Blowing (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1931 | 0 | 10610.PR.FL.DI | 44028 | 0
C111131PRFL000020 | U11 - Piping Flushing/Blowing (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2656 | 0 | 10610.PR.FL.DI | 78325 | 0
C111131PRFL000030 | U11 - Piping Flushing/Blowing (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5286 | 0 | 10610.PR.FL.DI | 82041 | 0
C111131PRFL000140 | U11 - Lube Oil Flushing for Compressors (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1187 | 0 | 10780.PR.PR.MH
C111131PRFL000160 | U11 - Chemical Cleaning for Compressor Suction Lines (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 743 | 0 | 10780.PR.PR.MH
C111131PRFL000180 | U11 - Chemical Cleaning for Compressor Suction Lines (Loop 3 - Unit 518) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1468 | 0 | 10780.PR.PR.MH
C111131PRHT000030 | U11 - Piping Hydrotesting (Loop 3 - Unit 518) | PR | PRHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 64611 | 0 | 10610.PR.HT.DI | 82041 | 0
C111131PISB000020 | U11 - Small Bore Piping A/Equip. Erection (Loop 2 - Unit 517) | PI | PISB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4656 | 0 | 10610.PI.SB.DI | 423.3 | 0
C111131PISU000010 | U11 - Piping Supports Prefabrication (Loop 3 - Unit 516) | PI | PISU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18464 | 189.574 | 10610.PI.PU.TN | 71.02 | 22.3422
C111131PISU000060 | U11 - Piping Supports Erection (Loop 3 - Unit 518) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 73428 | 0 | 10610.PI.SU.TN | 163.17 | 0
C111131PRBO000040 | U11 - Static Box Up (Loop 3 - Unit 518) | PR | PRBO1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9213 | 0 | 10780.PR.PR.MH
C111131PRBO000060 | U11 - Rotary Box Up (Loop 3 - Unit 518) | PR | PRBO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13988 | 0 | 10780.PR.PR.MH
C111131PRFL000020 | U11 - Piping Flushing/Blowing (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2656 | 0 | 10610.PR.FL.DI | 78325 | 0
C111131PRFL000130 | U11 - Lube Oil Flushing for Compressors (Loop 2 - Unit 517) | PR | PRFL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1248 | 0 | 10780.PR.PR.MH
C111131PRFL000170 | U11 - Chemical Cleaning for Compressor Suction Lines (Loop 3 - Unit 516) | PR | PRFL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 678 | 0 | 10780.PR.PR.MH
C111131PRHT000010 | U11 - Piping Hydrotesting (Loop 3 - Unit 516) | PR | PRHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30372 | 0 | 10610.PR.HT.DI | 78325 | 0
C111131PRHT000020 | U11 - Piping Hydrotesting (Loop 2 - Unit 517) | PR | PRHT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29705 | 0 | 10610.PR.HT.DI | 44028 | 0
C111131PRRE000030 | U11 - Piping Reinstatement (Loop 3 - Unit 518) | PR | PRRE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51689 | 0 | 10610.PR.RE.DI | 82041 | 0
C111132CICT000050 | U11 - Electrical earth Trenches Execution (Loop 2 - Unit 517) | CI | CICT2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1252 | 0.30104 | 10610.CI.ET.M3 | 313 | 313
C111132CICT000070 | U11 - Covered Concrete Trenches Execution (Loop 2 - Unit 517) | CI | CICT1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16903 | 347.2911 | 10610.CI.CO.M3 | 338.06 | 305.5393
C111132CICT000090 | U11 - Covered Concrete Trenches Execution (Loop 3 - Unit 518) | CI | CICT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 70303 | 5922.2372 | 10610.CI.CO.M3 | 1406.05 | 1214.3197
C111132CICT000120 | U11 - Electrical earth Trenches Execution (Loop 3 - Unit 518) | CI | CICT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1252 | 0.30104 | 10610.CI.ET.M3 | 313 | 313
C111132CIDB000025 | U11 - Duct Banks Precast Installation (Loop 3 - Unit 516) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35761 | 1874.6605 | 10610.CI.CO.M3 | 715.21 | 706.6257
C111132CIDB000026 | U11 - Duct Banks Precast Installation (Loop 2 - Unit 517) | CI | CIDB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10750 | 159.7935 | 10610.CI.CO.M3 | 215 | 215.0006
C111132CIDB000035 | U11 - Duct Banks Precast Fabrication (Loop 3 - Unit 518) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12898 | 240.8457 | 10780.CI.CI.MH
C111132CIDB000045 | U11 - Duct Banks Precast Installation (Loop 3 - Unit 518) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10422 | 157.2514 | 10610.CI.CO.M3 | 173.7 | 173.7
C111131PISB000030 | U11 - Small Bore Piping A/Equip. Erection - From Barr. Limit U517 to 518-PR-002 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISB000040 | U11 - Small Bore Piping A/Equip. Erection - From 518-PR-002 to 518-PR-001 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISB000050 | U11 - Small Bore Piping A/Equip. Erection - From 518-PR-001 to Batt. Limit U500 (Loop 3 - Unit 518) | PI | PISB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4248 | 0 | 10610.PI.SB.DI | 386.15 | 0
C111131PISU000010 | U11 - Piping Supports Prefabrication (Loop 3 - Unit 516) | PI | PISU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18464 | 189.574 | 10610.PI.PU.TN | 71.02 | 22.3422
C111131PISU000020 | U11 - Piping Supports Erection (Loop 3 - Unit 516) | PI | PISU2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31957 | 0 | 10610.PI.SU.TN | 71.02 | 0
C111131PISU000030 | U11 - Piping Supports Prefabrication (Loop 2 - Unit 517) | PI | PISU1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19144 | 198.0621 | 10610.PI.PU.TN | 73.63 | 23.0589
C111131PISU000040 | U11 - Piping Supports Prefabrication (Loop 3 - Unit 518) | PI | PISU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42425 | 1118.5755 | 10610.PI.PU.TN | 163.17 | 64.3148
C111131PIUG000030 | U11 - Piping Erection UG (Loop 3 - Unit 518) | PI | PIUG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1269 | 0 | 10610.PI.UG.DI | 846 | 0
C111131PRHT000010 | U11 - Piping Hydrotesting (Loop 3 - Unit 516) | PR | PRHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30372 | 0 | 10610.PR.HT.DI | 78325 | 0
C111131PRRE000010 | U11 - Piping Reinstatement (Loop 3 - Unit 516) | PR | PRRE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24298 | 0 | 10610.PR.RE.DI | 78325 | 0
C111131PRRE000020 | U11 - Piping Reinstatement (Loop 2 - Unit 517) | PR | PRRE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23764 | 0 | 10610.PR.RE.DI | 44028 | 0
C111131PRRE000080 | U41 - Piping Reinstatement | PR | PRRE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 39533 | 0 | 10610.PR.RE.DI | 51425 | 0
C111132CICT000010 | U11 - Covered Concrete Trenches Execution (Loop 3 - Unit 516) | CI | CICT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18445 | 412.2886 | 10610.CI.CO.M3 | 368.9 | 328.2513
C111132CICT000011 | U11 - Electrical earth Trenches Execution (Loop 3 - Unit 516) | CI | CICT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33953 | 357.6366 | 10780.CI.CI.MH
C111132CICT000020 | U11 - Instrument earth Trenches Execution (Loop 3 - Unit 516) | CI | CICT3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6403 | 11.3865 | 10780.CI.CI.MH
C111132CICT000050 | U11 - Electrical earth Trenches Execution (Loop 2 - Unit 517) | CI | CICT2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1252 | 0.30104 | 10610.CI.ET.M3 | 313 | 313
C111132CICT000090 | U11 - Covered Concrete Trenches Execution (Loop 3 - Unit 518) | CI | CICT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 70303 | 5922.2372 | 10610.CI.CO.M3 | 1406.05 | 1214.3197
C111132CIDB000025 | U11 - Duct Banks Precast Installation (Loop 3 - Unit 516) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35761 | 1874.6605 | 10610.CI.CO.M3 | 715.21 | 706.6257
C111132CIDM000010 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 3 - Unit 516) | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7283 | 72.0853 | 10610.CI.CO.M3 | 121.38 | 107.5901
C111132CIGT000050 | U11 - Equipment Grouting Execution (Loop 3 - Unit 518) | CI | CIGT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2650 | 0.7179 | 10780.CI.CI.MH
C111132CIGT000060 | U11 - Steel Structure Grouting Execution (Loop 3 - Unit 518) | CI | CIGT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2650 | 0 | 10780.CI.CI.MH
C111132CIHE000020 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 516) 516-F-101 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2218 | 7.2663 | 10610.CI.CO.M3 | 36.96 | 36.96
C111132CIHE000060 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 518) 518-F-101 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1745 | 4.3634 | 10610.CI.CO.M3 | 29.08 | 29.08
C111132CIHE000070 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 518) 518-F-201 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1715 | 4.2146 | 10610.CI.CO.M3 | 28.58 | 28.58
C111132CIMF000010 | U11 - Miscellaneous Foundations Execution (Loop 3 - Unit 516) | CI | CIMF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1810 | 4.8403 | 10610.CI.CO.M3 | 30.17 | 30.17
C111132CIPD000010 | U11 - Fabrication Precast Drainage Man Holes & Catchbasins (Loop 3 - Unit 516) | CI | CIPD | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6577 | 63.9022 | 10780.CI.CI.MH
C111132CIPE000030 | U11 - 542-ME-001 Sales Gas Custody Meter Packaged Equipment Foundation Execution (Loop 3 - Unit 518) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47361 | 3313.6614 | 10610.CI.CO.M3 | 947.22 | 947.22
C111132CIPE000080 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-201 (inside 518-SH-002) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5137 | 38.9854 | 10610.CI.CO.M3 | 85.62 | 85.62
C111132CIPR000010 | U11 - 577-PR-110 Piperack Foundations Execution (Unit 516) (516-E-101) | CI | CIPR1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27435 | 1111.9069 | 10610.CI.CO.M3 | 548.69 | 548.69
C111132CIPR000050 | U11 - 517-PR-001 Secondary Piperack Foundations Execution (Loop 2 - Unit 517) | CI | CIPR2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20514 | 621.6651 | 10610.CI.CO.M3 | 410.27 | 410.27
C111132CIPR000070 | U11 - 577-PR-105 Piperack Foundations Execution (Unit 518) (518-E-301) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 46341 | 3172.4334 | 10610.CI.CO.M3 | 926.81 | 926.81
C111132CIPR000100 | U11 - 518-PR-002 Secondary Piperack Foundations Execution (Loop 3 - Unit 518) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24494 | 886.3104 | 10610.CI.CO.M3 | 489.88 | 489.88
C111132CIPS000010 | U11 - 516-SU-001 Pit construction (Loop 3 - Unit 516) (516-SU-001; 516-V-001; 516-P-001A/B) | CI | CIPS1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13419 | 266.0154 | 10610.CI.CO.M3 | 268.38 | 268.38
C111132CIPV000010 | U11 - Concrete Paving Execution (Loop 3 - Unit 516) | CI | CIPV1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13167 | 132.0308 | 10610.CI.PV.M2 | 7315.11 | 3657.555
C111132CIPV000070 | U11 - Gravel Paving Execution (Loop 3 - Unit 518) | CI | CIPV2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7324 | 0 | 10610.CI.GV.M2 | 12206 | 0
C111132CIRE200030 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-101; 518-CM-101 (Loop 3 - Unit 518) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29513 | 1286.7468 | 10610.CI.CO.M3 | 590.26 | 590.26
C111132CIRE200030 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-101; 518-CM-101 (Loop 3 - Unit 518) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29513 | 1286.7468 | 10610.CI.CO.M3 | 590.26 | 590.26
C111131PRRE000010 | U11 - Piping Reinstatement (Loop 3 - Unit 516) | PR | PRRE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24298 | 0 | 10610.PR.RE.DI | 78325 | 0
C111131PRRE000020 | U11 - Piping Reinstatement (Loop 2 - Unit 517) | PR | PRRE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23764 | 0 | 10610.PR.RE.DI | 44028 | 0
C111131PRRE000030 | U11 - Piping Reinstatement (Loop 3 - Unit 518) | PR | PRRE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51689 | 0 | 10610.PR.RE.DI | 82041 | 0
C111131PRRE000070 | U49 - Piping Reinstatement | PR | PRRE | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5061 | 0 | 10610.PR.RE.DI | 14453 | 0
C111131PRRE000080 | U41 - Piping Reinstatement | PR | PRRE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 39533 | 0 | 10610.PR.RE.DI | 51425 | 0
C111132CICT000010 | U11 - Covered Concrete Trenches Execution (Loop 3 - Unit 516) | CI | CICT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18445 | 412.2886 | 10610.CI.CO.M3 | 368.9 | 328.2513
C111132CICT000060 | U11 - Instrument earth Trenches Execution (Loop 2 - Unit 517) | CI | CICT3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1403 | 0.60775 | 10780.CI.CI.MH
C111132CICT000070 | U11 - Covered Concrete Trenches Execution (Loop 2 - Unit 517) | CI | CICT1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16903 | 347.2911 | 10610.CI.CO.M3 | 338.06 | 305.5393
C111132CICT000110 | U11 - Instrument earth Trenches Execution (Loop 3 - Unit 518) | CI | CICT3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1773 | 0.54102 | 10780.CI.CI.MH
C111132CICT000120 | U11 - Electrical earth Trenches Execution (Loop 3 - Unit 518) | CI | CICT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1252 | 0.30104 | 10610.CI.ET.M3 | 313 | 313
C111132CIDB000015 | U11 - Duct Banks Precast Fabrication (Loop 3 - Unit 516) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 45829 | 3102.773 | 10780.CI.CI.MH
C111132CIDB000026 | U11 - Duct Banks Precast Installation (Loop 2 - Unit 517) | CI | CIDB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10750 | 159.7935 | 10610.CI.CO.M3 | 215 | 215.0006
C111132CIDM100051 | U500 - Manholes & Catchbasins / Buildings and Common Area / Valve Pits CatchBasins | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 145950 | 4720.2593 | 10610.CI.CO.M3 | 2919 | 437.8372
C111132CIGR000010 | U11 - Grounding Network Execution (Loop 3 - Unit 516) | CI | CIGR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0.36563 | 10780.CI.CI.MH
C111132CIGT000020 | U11 - Steel Structure Grouting Execution (Loop 3 - Unit 516) | CI | CIGT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10780.CI.CI.MH
C111132CIGT000040 | U11 - Steel Structure Grouting Execution (Loop 2 - Unit 517) | CI | CIGT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10780.CI.CI.MH
C111132CIHE000020 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 516) 516-F-101 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2218 | 7.2663 | 10610.CI.CO.M3 | 36.96 | 36.96
C111132CIHE000050 | U11 - Horizontal Vessels Foundation Execution (Loop 2 - Unit 517) 517-F-101 A/B | CI | CIHE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2329 | 8.0118 | 10610.CI.CO.M3 | 38.81 | 38.81
C111132CIMF000020 | U11 - Miscellaneous Foundations Execution (Loop 2 - Unit 517) | CI | CIMF | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 937 | 1.2537 | 10610.CI.CO.M3 | 13.38 | 13.38
C111132CIDB000045 | U11 - Duct Banks Precast Installation (Loop 3 - Unit 518) | CI | CIDB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10422 | 157.2514 | 10610.CI.CO.M3 | 173.7 | 173.7
C111132CIDM000030 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 2 - Unit 517) | CI | CIDM1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11966 | 194.9254 | 10610.CI.CO.M3 | 239.32 | 212.1235
C111132CIDM000030 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 2 - Unit 517) | CI | CIDM1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11966 | 194.9254 | 10610.CI.CO.M3 | 239.32 | 212.1235
C111132CIDM000050 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 3 - Unit 518) | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18364 | 472.0415 | 10610.CI.CO.M3 | 367.28 | 325.5427
C111132CIGR000020 | U11 - Grounding Network Execution (Loop 2 - Unit 517) | CI | CIGR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1848 | 0.55484 | 10610.CI.GR.LM | 3079.31 | 0
C111132CIGR000020 | U11 - Grounding Network Execution (Loop 2 - Unit 517) | CI | CIGR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1848 | 0.55484 | 10610.CI.GR.LM | 3079.31 | 0
C111132CIGT000010 | U11 - Equipment Grouting Execution (Loop 3 - Unit 516) | CI | CIGT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2000 | 0.37996 | 10780.CI.CI.MH
C111132CIHE000050 | U11 - Horizontal Vessels Foundation Execution (Loop 2 - Unit 517) 517-F-101 A/B | CI | CIHE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2329 | 8.0118 | 10610.CI.CO.M3 | 38.81 | 38.81
C111132CIHE000060 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 518) 518-F-101 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1745 | 4.3634 | 10610.CI.CO.M3 | 29.08 | 29.08
C111132CIMF000010 | U11 - Miscellaneous Foundations Execution (Loop 3 - Unit 516) | CI | CIMF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1810 | 4.8403 | 10610.CI.CO.M3 | 30.17 | 30.17
C111132CIMF000030 | U11 - Miscellaneous Foundations Execution (Loop 3 - Unit 518) | CI | CIMF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1991 | 4.8088 | 10610.CI.CO.M3 | 33.19 | 28.2097
C111132CIPD000020 | U11 - Fabrication Precast Drainage Man Holes & Catchbasins (Loop 2 - Unit 517) | CI | CIPD | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10524 | 163.6208 | 10780.CI.CI.MH
C111132CIPE000080 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-201 (inside 518-SH-002) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5137 | 38.9854 | 10610.CI.CO.M3 | 85.62 | 85.62
C111132CIPE200000 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-101 (inside 518-SH-001) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5137 | 38.9854 | 10610.CI.CO.M3 | 85.62 | 85.62
C111132CIPE300050 | U11 - Skid for ERE Feed Gas Compressor-02 Foundation Execution 517-C-101 (inside 517-SH-001) | CI | CIPE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5888 | 51.219 | 10610.CI.CO.M3 | 98.14 | 98.14
C111132CIPR000030 | U11 - 577-PR-108 Piperack Foundations Execution (Unit 517) (517-E-101) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50266 | 3732.6309 | 10610.CI.CO.M3 | 1005.32 | 1005.32
C111132CIPR000030 | U11 - 577-PR-108 Piperack Foundations Execution (Unit 517) (517-E-101) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50266 | 3732.6309 | 10610.CI.CO.M3 | 1005.32 | 1005.32
C111132CIPR000040 | U11 - 577-PR-104 Piperack Foundations Execution (Unit 518) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40622 | 2437.7191 | 10610.CI.CO.M3 | 812.43 | 812.43
C111132CIDM000050 | U11 - Manholes & Catchbasins Installation (Precast) (Loop 3 - Unit 518) | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18364 | 472.0415 | 10610.CI.CO.M3 | 367.28 | 325.5427
C111132CIDM100051 | U500 - Manholes & Catchbasins / Buildings and Common Area / Valve Pits CatchBasins | CI | CIDM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 145950 | 4720.2593 | 10610.CI.CO.M3 | 2919 | 437.8372
C111132CIHE000070 | U11 - Horizontal Vessels Foundation Execution (Loop 3 - Unit 518) 518-F-201 A/B | CI | CIHE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1715 | 4.2146 | 10610.CI.CO.M3 | 28.58 | 28.58
C111132CIMF000020 | U11 - Miscellaneous Foundations Execution (Loop 2 - Unit 517) | CI | CIMF | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 937 | 1.2537 | 10610.CI.CO.M3 | 13.38 | 13.38
C111132CIMF000030 | U11 - Miscellaneous Foundations Execution (Loop 3 - Unit 518) | CI | CIMF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1991 | 4.8088 | 10610.CI.CO.M3 | 33.19 | 28.2097
C111132CIPR000010 | U11 - 577-PR-110 Piperack Foundations Execution (Unit 516) (516-E-101) | CI | CIPR1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27435 | 1111.9069 | 10610.CI.CO.M3 | 548.69 | 548.69
C111132CIPR000011 | U11 - 577-PR-111 Piperack Foundations Execution (Unit 516) | CI | CIPR1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38211 | 2156.9373 | 10610.CI.CO.M3 | 764.21 | 764.21
C111132CIPR000011 | U11 - 577-PR-111 Piperack Foundations Execution (Unit 516) | CI | CIPR1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38211 | 2156.9373 | 10610.CI.CO.M3 | 764.21 | 764.21
C111132CIPR000020 | U11 - 516-PR-001 Secondary Piperack Foundations Execution (Loop 3 - Unit 516) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21227 | 665.6308 | 10610.CI.CO.M3 | 424.53 | 424.53
C111132CIPR000080 | U11 - 577-PR-106 Piperack Foundations Execution (Unit 518) (518-E-101) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67055 | 6642.4567 | 10610.CI.CO.M3 | 1341.1 | 1341.1
C111132CIPS000050 | U11 - 516-SU-002 Pit construction (Loop 3 - Unit 516) (516-SU-002; 516-P-002A/B) | CI | CIPS1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2739 | 11.0828 | 10610.CI.CO.M3 | 45.65 | 45.65
C111132CIPV000040 | U11 - Concrete Paving Execution (Loop 2 - Unit 517) | CI | CIPV1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14850 | 36.9766 | 10610.CI.PV.M2 | 8250.22 | 0
C111132CIPV000050 | U11 - Gravel Paving Execution (Loop 2 - Unit 517) | CI | CIPV2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1267 | 0 | 10610.CI.GV.M2 | 2112 | 0
C111132CISF000020 | U11 - Stairs & Small Foundations Execution (Loop 3 - Unit 516) | CI | CISF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1225 | 1.3829 | 10610.CI.CO.M3 | 20.41 | 12.2501
C111132CISF300010 | U11 - Stairs & Small Foundations Execution (Loop 2 - Unit 517) | CI | CISF | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1752 | 2.7071 | 10610.CI.CO.M3 | 29.2 | 17.5199
C111132CIST000080 | U11 - Compressor Shelter 518-SH-002 Foundation Execution (518-C-201; 518-CM-201; 518-EOT-201) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24824 | 910.3349 | 10610.CI.CO.M3 | 496.47 | 496.47
C111132CIST300030 | U11 - Structure foundation for Lube Oil Cooler (close to 517-SH-001) (Loop 2 - Unit 517) | CI | CIST | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2718 | 10.9135 | 10610.CI.CO.M3 | 45.3 | 45.3
C111132CIST300040 | U11 - Analyzer Shelters Foundation Execution 565-ANS-402 | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5885 | 50.8035 | 10610.CI.CO.M3 | 98.08 | 98.08
C111132CIPD000030 | U11 - Fabrication Precast Drainage Man Holes & Catchbasins (Loop 3 - Unit 518) | CI | CIPD | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9304 | 127.8782 | 10780.CI.CI.MH
C111132CIPE000030 | U11 - 542-ME-001 Sales Gas Custody Meter Packaged Equipment Foundation Execution (Loop 3 - Unit 518) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47361 | 3313.6614 | 10610.CI.CO.M3 | 947.22 | 947.22
C111132CIPE200000 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-101 (inside 518-SH-001) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5137 | 38.9854 | 10610.CI.CO.M3 | 85.62 | 85.62
C111132CIPE300050 | U11 - Skid for ERE Feed Gas Compressor-02 Foundation Execution 517-C-101 (inside 517-SH-001) | CI | CIPE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5888 | 51.219 | 10610.CI.CO.M3 | 98.14 | 98.14
C111132CIPR000020 | U11 - 516-PR-001 Secondary Piperack Foundations Execution (Loop 3 - Unit 516) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21227 | 665.6308 | 10610.CI.CO.M3 | 424.53 | 424.53
C111132CIPR000050 | U11 - 517-PR-001 Secondary Piperack Foundations Execution (Loop 2 - Unit 517) | CI | CIPR2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20514 | 621.6651 | 10610.CI.CO.M3 | 410.27 | 410.27
C111132CIPR000060 | U11 - 518-PR-001 Secondary Piperack Foundations Execution (Loop 3 - Unit 518) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31356 | 1452.4486 | 10610.CI.CO.M3 | 627.11 | 627.11
C111132CIPR000080 | U11 - 577-PR-106 Piperack Foundations Execution (Unit 518) (518-E-101) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67055 | 6642.4567 | 10610.CI.CO.M3 | 1341.1 | 1341.1
C111132CIPR000090 | U11 - 577-PR-107 Piperack Foundations Execution (Unit 518) (518-E-201) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14071 | 292.4832 | 10610.CI.CO.M3 | 281.41 | 281.41
C111132CIPR000090 | U11 - 577-PR-107 Piperack Foundations Execution (Unit 518) (518-E-201) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14071 | 292.4832 | 10610.CI.CO.M3 | 281.41 | 281.41
C111132CIPR000100 | U11 - 518-PR-002 Secondary Piperack Foundations Execution (Loop 3 - Unit 518) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24494 | 886.3104 | 10610.CI.CO.M3 | 489.88 | 489.88
C111132CIPS000010 | U11 - 516-SU-001 Pit construction (Loop 3 - Unit 516) (516-SU-001; 516-V-001; 516-P-001A/B) | CI | CIPS1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13419 | 266.0154 | 10610.CI.CO.M3 | 268.38 | 268.38
C111132CIPV000020 | U11 - Gravel Paving Execution (Loop 3 - Unit 516) | CI | CIPV2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2050 | 0 | 10610.CI.GV.M2 | 3417 | 0
C111132CIPV000040 | U11 - Concrete Paving Execution (Loop 2 - Unit 517) | CI | CIPV1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14850 | 36.9766 | 10610.CI.PV.M2 | 8250.22 | 0
C111132CIPV000050 | U11 - Gravel Paving Execution (Loop 2 - Unit 517) | CI | CIPV2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1267 | 0 | 10610.CI.GV.M2 | 2112 | 0
C111132CIPV000060 | U11 - Concrete Paving Execution (Loop 3 - Unit 518) | CI | CIPV1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22119 | 104.0762 | 10610.CI.PV.M2 | 12288.1 | 368.643
C111132CIPV000070 | U11 - Gravel Paving Execution (Loop 3 - Unit 518) | CI | CIPV2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7324 | 0 | 10610.CI.GV.M2 | 12206 | 0
C111132CIRE000040 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-201; 518-CM-201 (Loop 3 - Unit 518) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30411 | 1366.2425 | 10610.CI.CO.M3 | 608.22 | 608.22
C111132CIRE300010 | U11 - ERE Feed Gas Compressor-01 Foundation Execution 516-C-101; 516-CM-101 (Loop 3 - Unit 516) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28154 | 1170.9723 | 10610.CI.CO.M3 | 563.08 | 563.08
C111132CISF300010 | U11 - Stairs & Small Foundations Execution (Loop 2 - Unit 517) | CI | CISF | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1752 | 2.7071 | 10610.CI.CO.M3 | 29.2 | 17.5199
C111132CIST000070 | U11 - Structure foundation for Lube Oil Cooler (close to 518-SH-002) (Loop 3 - Unit 518) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7543 | 84.0488 | 10610.CI.CO.M3 | 125.71 | 125.71
C111132CIST000090 | U11 - Shelters Foundation Execution 542-ANS-404 | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2313 | 7.843 | 10610.CI.CO.M3 | 38.56 | 38.56
C111132CIST200040 | U11 - Structure foundation for Lube Oil Cooler (close to 518-SH-001) (Loop 3 - Unit 518) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7543 | 84.0488 | 10610.CI.CO.M3 | 125.71 | 125.71
C111132CIST200060 | U11 - Compressor Shelter 518-SH-001 Foundation Execution (Loop 3 - Unit 518) (518-C-101; 518-CM-101; 518-EOT-101) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24725 | 903.1066 | 10610.CI.CO.M3 | 494.5 | 494.5
C111132CIST300020 | U11 - Compressor Shelters 516-SH-001 Foundation Execution (Loop 3 - Unit 516) (516-C-101; 516-CM-101; 516-EOT-101) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22400 | 741.2296 | 10610.CI.CO.M3 | 447.99 | 447.99
C111132CIUG000030 | U11 - UG Civil Works (Loop 3 - Unit 516) | CI | CIUG1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6180 | 41.6107 | 10780.CI.CI.MH
C111132CIUG000060 | U11 - UG Civil Works (Loop 2 - Unit 517) | CI | CIUG1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22280 | 540.8275 | 10780.CI.CI.MH
C111132CIUG000090 | U11 - UG Civil Works (Loop 3 - Unit 518) | CI | CIUG1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22380 | 563.4514 | 10780.CI.CI.MH
C111132CIUG000170 | U11 - UG Pipe Installation (Loop 2 - Unit 517) (OD) | CI | CIUG2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17678 | 443.6706 | 10610.CI.UG.LM | 883.91 | 883.9125
C111132CIVE000020 | U11 - ERE Feed Gas Compressor-01 Suction KO Drum Foundation Execution (Loop 3 - Unit 516) 516-V-101 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5863 | 50.7833 | 10610.CI.CO.M3 | 97.72 | 97.72
C111132CIVE000040 | U11 - Columns (ERE Feed Gas Compressor-03 Suction KO Drum) Foundation Execution (Loop 3 - Unit 518) 518-V-101 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6125 | 55.1425 | 10610.CI.CO.M3 | 102.09 | 102.09
C111132CIVE000060 | U11 - Vertical Vessel (MP Fuel Gas Balance Drum) Foundation Execution (Loop 3 - Unit 516) 565-V-201 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6930 | 70.9468 | 10610.CI.CO.M3 | 115.5 | 115.5
C111132CIVE000060 | U11 - Vertical Vessel (MP Fuel Gas Balance Drum) Foundation Execution (Loop 3 - Unit 516) 565-V-201 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6930 | 70.9468 | 10610.CI.CO.M3 | 115.5 | 115.5
C111132CIVE000070 | U11 - Columns (ERE Feed Gas Compressor-03 Suction KO Drum) Foundation Execution (Loop 3 - Unit 518) 518-V-201 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8012 | 94.3446 | 10610.CI.CO.M3 | 133.53 | 133.53
C111132CIVE300010 | U11 - ERE Feed Gas Compressor-01 Foundation Execution 516-C-101 (inside 516-SH-001) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 622 | 0.57182 | 10610.CI.CO.M3 | 8.89 | 8.89
C111132CIPR000040 | U11 - 577-PR-104 Piperack Foundations Execution (Unit 518) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40622 | 2437.7191 | 10610.CI.CO.M3 | 812.43 | 812.43
C111132CIPR000060 | U11 - 518-PR-001 Secondary Piperack Foundations Execution (Loop 3 - Unit 518) | CI | CIPR2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31356 | 1452.4486 | 10610.CI.CO.M3 | 627.11 | 627.11
C111132CIPR000070 | U11 - 577-PR-105 Piperack Foundations Execution (Unit 518) (518-E-301) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 46341 | 3172.4334 | 10610.CI.CO.M3 | 926.81 | 926.81
C111132CIPR000110 | U11 - 577-PR-109 Piperack Foundations Execution (Unit 517) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72000 | 7658.2826 | 10610.CI.CO.M3 | 1440 | 1440
C111132CIPR000110 | U11 - 577-PR-109 Piperack Foundations Execution (Unit 517) | CI | CIPR1 | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72000 | 7658.2826 | 10610.CI.CO.M3 | 1440 | 1440
C111132CIPS000050 | U11 - 516-SU-002 Pit construction (Loop 3 - Unit 516) (516-SU-002; 516-P-002A/B) | CI | CIPS1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2739 | 11.0828 | 10610.CI.CO.M3 | 45.65 | 45.65
C111132CIPV000010 | U11 - Concrete Paving Execution (Loop 3 - Unit 516) | CI | CIPV1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13167 | 132.0308 | 10610.CI.PV.M2 | 7315.11 | 3657.555
C111132CIPV000020 | U11 - Gravel Paving Execution (Loop 3 - Unit 516) | CI | CIPV2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2050 | 0 | 10610.CI.GV.M2 | 3417 | 0
C111132CIPV000060 | U11 - Concrete Paving Execution (Loop 3 - Unit 518) | CI | CIPV1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22119 | 104.0762 | 10610.CI.PV.M2 | 12288.1 | 368.643
C111132CIRE000040 | U11 - ERE Feed Gas Compressor-03 Foundation Execution 518-C-201; 518-CM-201 (Loop 3 - Unit 518) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30411 | 1366.2425 | 10610.CI.CO.M3 | 608.22 | 608.22
C111132CIRE300010 | U11 - ERE Feed Gas Compressor-01 Foundation Execution 516-C-101; 516-CM-101 (Loop 3 - Unit 516) | CI | CIRE2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28154 | 1170.9723 | 10610.CI.CO.M3 | 563.08 | 563.08
C111132CIRE300020 | U11 - ERE Feed Gas Compressor-02 Foundation Execution 517-C-101; 517-CM-101 (Loop 2 - Unit 517) | CI | CIRE2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40242 | 2392.3544 | 10610.CI.CO.M3 | 804.84 | 804.84
C111132CISF200010 | U11 - Stairs & Small Foundations Execution (Loop 3 - Unit 518) | CI | CISF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4792 | 20.2531 | 10610.CI.CO.M3 | 79.87 | 47.9217
C111132CIST000090 | U11 - Shelters Foundation Execution 542-ANS-404 | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2313 | 7.843 | 10610.CI.CO.M3 | 38.56 | 38.56
C111132CIST200040 | U11 - Structure foundation for Lube Oil Cooler (close to 518-SH-001) (Loop 3 - Unit 518) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7543 | 84.0488 | 10610.CI.CO.M3 | 125.71 | 125.71
C111132CIST300030 | U11 - Structure foundation for Lube Oil Cooler (close to 517-SH-001) (Loop 2 - Unit 517) | CI | CIST | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2718 | 10.9135 | 10610.CI.CO.M3 | 45.3 | 45.3
C111132CIUG000010 | U11 - UG GRE Pipe Installation (Loop 3 - Unit 516) (FW) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2160 | 5.2348 | 10780.CI.CI.MH
C111132CIUG000050 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 2 - Unit 517) | CI | CIUG3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7856 | 68.5913 | 10610.CI.CO.M3 | 130.94 | 124.3904
C111132CIRE300020 | U11 - ERE Feed Gas Compressor-02 Foundation Execution 517-C-101; 517-CM-101 (Loop 2 - Unit 517) | CI | CIRE2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40242 | 2392.3544 | 10610.CI.CO.M3 | 804.84 | 804.84
C111132CISF000020 | U11 - Stairs & Small Foundations Execution (Loop 3 - Unit 516) | CI | CISF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1225 | 1.3829 | 10610.CI.CO.M3 | 20.41 | 12.2501
C111132CISF200010 | U11 - Stairs & Small Foundations Execution (Loop 3 - Unit 518) | CI | CISF | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4792 | 20.2531 | 10610.CI.CO.M3 | 79.87 | 47.9217
C111132CIST000070 | U11 - Structure foundation for Lube Oil Cooler (close to 518-SH-002) (Loop 3 - Unit 518) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7543 | 84.0488 | 10610.CI.CO.M3 | 125.71 | 125.71
C111132CIST000080 | U11 - Compressor Shelter 518-SH-002 Foundation Execution (518-C-201; 518-CM-201; 518-EOT-201) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24824 | 910.3349 | 10610.CI.CO.M3 | 496.47 | 496.47
C111132CIST200060 | U11 - Compressor Shelter 518-SH-001 Foundation Execution (Loop 3 - Unit 518) (518-C-101; 518-CM-101; 518-EOT-101) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24725 | 903.1066 | 10610.CI.CO.M3 | 494.5 | 494.5
C111132CIST300010 | U11 - Structure foundation for Lube Oil Cooler (close to 516-SH-001) (Loop 3 - Unit 516) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10522 | 163.5547 | 10610.CI.CO.M3 | 210.44 | 210.44
C111132CIST300010 | U11 - Structure foundation for Lube Oil Cooler (close to 516-SH-001) (Loop 3 - Unit 516) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10522 | 163.5547 | 10610.CI.CO.M3 | 210.44 | 210.44
C111132CIST300020 | U11 - Compressor Shelters 516-SH-001 Foundation Execution (Loop 3 - Unit 516) (516-C-101; 516-CM-101; 516-EOT-101) | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22400 | 741.2296 | 10610.CI.CO.M3 | 447.99 | 447.99
C111132CIST300050 | U11 - Compressor Shelter 517-SH-001 Foundation Execution (Loop 2 - Unit 517) (517-C-101; 517-CM-101; 517-EOT-101) | CI | CIST | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14926 | 329.1192 | 10610.CI.CO.M3 | 298.52 | 298.52
C111132CIUG000050 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 2 - Unit 517) | CI | CIUG3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7856 | 68.5913 | 10610.CI.CO.M3 | 130.94 | 124.3904
C111132CIUG000070 | U11 - UG GRE Pipe Installation (Loop 3 - Unit 518) (FW) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6400 | 46.2659 | 10780.CI.CI.MH
C111132CIUG000080 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 3 - Unit 518) | CI | CIUG3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 48653 | 2557.6281 | 10610.CI.CO.M3 | 973.05 | 895.2099
C111132CIUG000100 | U11 - UG Pipe Installation (Loop 3 - Unit 518) (CD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3776 | 17.0972 | 10780.CI.CI.MH
C111132CIUG000110 | U11 - UG Pipe Installation (Loop 3 - Unit 518) (OD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31920 | 1406.018 | 10610.CI.UG.LM | 1596.02 | 1564.1041
C111132CIUG000150 | U11 - UG Pipe Installation (Loop 3 - Unit 516) (OD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10743 | 156.0027 | 10610.CI.UG.LM | 537.14 | 537.1409
C111132CIUG000160 | U11 - UG Pipe Installation (Loop 2 - Unit 517) (CD) | CI | CIUG2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4736 | 24.6758 | 10780.CI.CI.MH
C111132CIST300040 | U11 - Analyzer Shelters Foundation Execution 565-ANS-402 | CI | CIST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5885 | 50.8035 | 10610.CI.CO.M3 | 98.08 | 98.08
C111132CIST300050 | U11 - Compressor Shelter 517-SH-001 Foundation Execution (Loop 2 - Unit 517) (517-C-101; 517-CM-101; 517-EOT-101) | CI | CIST | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14926 | 329.1192 | 10610.CI.CO.M3 | 298.52 | 298.52
C111132CIUG000020 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 3 - Unit 516) | CI | CIUG3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16376 | 293.5708 | 10610.CI.CO.M3 | 327.53 | 320.9798
C111132CIUG000020 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 3 - Unit 516) | CI | CIUG3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16376 | 293.5708 | 10610.CI.CO.M3 | 327.53 | 320.9798
C111132CIUG000040 | U11 - UG GRE Pipe Installation (Loop 2 - Unit 517) (FW) | CI | CIUG2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5856 | 36.8453 | 10780.CI.CI.MH
C111132CIUG000110 | U11 - UG Pipe Installation (Loop 3 - Unit 518) (OD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31920 | 1406.018 | 10610.CI.UG.LM | 1596.02 | 1564.1041
C111132CIVE000030 | U11 - Columns (ERE Feed Gas Compressor-02 Suction KO Drum) Foundation Execution (Loop 2 - Unit 517) 517-V-101 | CI | CIVE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7074 | 73.5489 | 10610.CI.CO.M3 | 117.9 | 117.9
C111132CIVE000050 | U11 - Vertical Vessel (LP Fuel Gas Balance Drum) Foundation Execution (Loop 3 - Unit 516) 565-V-202 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6930 | 70.9468 | 10610.CI.CO.M3 | 115.5 | 115.5
C111132CIVE000050 | U11 - Vertical Vessel (LP Fuel Gas Balance Drum) Foundation Execution (Loop 3 - Unit 516) 565-V-202 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6930 | 70.9468 | 10610.CI.CO.M3 | 115.5 | 115.5
C111132STMS000010 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 3 - Unit 516) | ST | STMS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 335 | 0 | 10610.ST.PL.TN | 5.59 | 0
C111132STMS000020 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 2 - Unit 517) | ST | STMS | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1225 | 0 | 10610.ST.PL.TN | 20.41 | 0
C111132STMS000030 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 3 - Unit 518) | ST | STMS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2264 | 0 | 10610.ST.PL.TN | 37.73 | 0
C111132STPL000040 | U11 - 577-PR-107 Piperack Platforms, Ladders & Handrails Erection (Unit 518) (518-E-201) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2832 | 0 | 10610.ST.PL.TN | 35.4 | 0
C111132STPL000050 | U11 - 577-PR-108 Piperack Platforms, Ladders & Handrails Erection (Unit 517) (517-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10334 | 0 | 10610.ST.PL.TN | 129.18 | 0
C111132STPL000070 | U11 - 577-PR-106 Piperack Platforms, Ladders & Handrails Erection (Unit 518) (518-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11100 | 0 | 10610.ST.PL.TN | 138.76 | 0
C111132STPL000100 | U11 - 577-PR-105 Piperack Platforms, Ladders & Handrails Erection (Unit 518) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9984 | 0 | 10610.ST.PL.TN | 124.8 | 0
C111132STPL000120 | U11 - 518-PR-002 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2445 | 0 | 10610.ST.PL.TN | 30.57 | 0
C111132STEQ000040 | U11 - Structure Erection for Lube Oil Cooler (close to 518-SH-002) | ST | STEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10610.ST.ER.TN | 0.63 | 0
C111132STMS000010 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 3 - Unit 516) | ST | STMS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 335 | 0 | 10610.ST.PL.TN | 5.59 | 0
C111132STPL000010 | U11 - 577-PR-110 Piperack Platforms, Ladders & Handrails Erection (Unit 516) (516-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.ST.PL.TN | 64.39 | 0
C111132STPL000020 | U11 - 516-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2663 | 0 | 10610.ST.PL.TN | 33.29 | 0
C111132STPL000030 | U11 - Lube Oil Cooler for 516-SH-001 Structure Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 50 | 0 | 10610.ST.PL.TN | 0.63 | 0
C111132STPL000080 | U11 - 517-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 2 - Unit 517) | ST | STPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2452 | 0 | 10610.ST.PL.TN | 30.65 | 0
C111132STPL000090 | U11 - Lube Oil Cooler for 518-SH-001 Structure Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 50 | 0 | 10610.ST.PL.TN | 0.63 | 0
C111132STPL000110 | U11 - 001-PR-104 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8116 | 0 | 10610.ST.PL.TN | 101.44 | 0
C111132STPL000180 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 2 - Unit 517) | ST | STPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13080 | 0 | 10610.ST.PL.TN | 163.5 | 0
C111132STPR000030 | U11 - 577-PR-108 Main Piperack Erection (Unit 517) (517-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61617 | 4416.8847 | 10610.ST.PR.TN | 1162.58 | 988.1888
C111132STPR000090 | U11 - 577-PR-105 Main Piperack Erection (Unit 518) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 59532 | 3376.9596 | 10610.ST.PR.TN | 1123.24 | 842.4315
C111132STSH200070 | U11 - 518-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 518) for 518-C-101 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.72 | 0
C111132STSH300020 | U11 - 516-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 516) for 516-C-101 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.71 | 0
C111132STSH300040 | U11 - 517-SH-001 Compressor Shelter Structure Erection (Loop 2 - Unit 517) for 517-C-101 | ST | STSH1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23135 | 118.6007 | 10610.ST.ER.TN | 436.5 | 0
C111132STSP000020 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 2 - Unit 517) | ST | STSP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4853 | 0 | 10610.ST.PL.TN | 80.89 | 0
C111132STSP000030 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 3 - Unit 518) | ST | STSP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8233 | 0 | 10610.ST.PL.TN | 137.21 | 0
C111133PAEQ000030 | U11 - Equipment Painting (Loop 3 - Unit 518) | PA | PAEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 322 | 0 | 10780.PA.PA.MH
C111133PAFP000010 | U11 - Piping Final Coat & Touch-Up Painting (Loop 3 - Unit 516) | PA | PAFP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1802 | 0 | 10610.PA.FP.M2 | 7510 | 0
C111133PAPP000030 | U11 - Piping SandBl. & Priming (Loop 3 - Unit 518) | PA | PAPP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1153 | 1.3817 | 10610.PA.PP.M2 | 0 | 0
C111133PASP000010 | U11 - Piping Supports SandBl. & Priming (Loop 3 - Unit 516) | PA | PASP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 361 | 0.0077586 | 10610.PA.SU.TN | 0 | 0
C111133PASP000030 | U11 - Piping Supports SandBl. & Priming (Loop 3 - Unit 518) | PA | PASP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 355 | 0.0080502 | 10610.PA.SU.TN | 0 | 0
C111134ELCI000020 | U11 - Conduits Installation (Loop 2 - Unit 517) | EL | ELCI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4292 | 0 | 10780.EL.EL.MH
C111134ELCL000010 | U11 - Lighting Cable Laying (Loop 3 - Unit 516) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9118 | 11.8525 | 10610.EL.LC.LM | 47514.11 | 0
C111134ELCL000020 | U11 - Electrical Cable Laying (Loop 3 - Unit 516) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44579 | 0 | 10610.EL.PL.LM | 62581.74 | 0
C111134ELCL000050 | U11 - Lighting Cable Laying (Loop 2 - Unit 517) | EL | ELCL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7726 | 0 | 10610.EL.LC.LM | 39165.47 | 0
C111134ELCO000010 | U11 - Lighting Cable Gland & Conn./Testing (Loop 3 - Unit 516) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6079 | 0 | 10610.EL.CO.UN | 310 | 0
C111134ELCO000020 | U11 - Electrical Cable Gland & Conn./Testing (Loop 3 - Unit 516) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24316 | 0 | 10610.EL.CO.UN | 1242 | 0
C111134ELCO000030 | U11 - Electrical Cable Gland & Conn./Testing (Loop 2 - Unit 517) | EL | ELCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20602 | 0 | 10610.EL.CO.UN | 1228 | 0
C111134ELCO000050 | U11 - Lighting Cable Gland & Conn./Testing (Loop 2 - Unit 517) | EL | ELCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.EL.CO.UN | 310 | 0
C111134ELCO000060 | U11 - Lighting Cable Gland & Conn./Testing (Loop 3 - Unit 518) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11136 | 0 | 10610.EL.CO.UN | 634 | 0
C111134ELEL000015 | U11 - Earthing Works (Loop 3 - Unit 516) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8105 | 42.1768 | 10610.EL.ES.LM | 11178.22 | 6531.8811
C111134ELEL000025 | U11 - Lightning Works (Loop 3 - Unit 516) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8105 | 0 | 10780.EL.EL.MH
C111134ELEL000120 | U11 - Earthing Works (Loop 2 - Unit 517) | EL | ELEL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6867 | 2.3339 | 10610.EL.ES.LM | 6246.65 | 312.3325
C111134ELPL000010 | U11 - Plant Lighting - (Lighting poles and fixtures) Installation (Loop 3 - Unit 516) | EL | ELPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13171 | 0 | 10780.EL.EL.MH
C111134ELTI000020 | U11 - Electrical Cable Trays Installation (Loop 3 - Unit 516) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20263 | 0 | 10610.EL.CT.LM | 6639.46 | 0
C111134ELTI000060 | U11 - Lighting Cable Trays Installation (Loop 3 - Unit 518) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11136 | 0 | 10610.EL.CT.LM | 4183.8 | 0
C111132CIUG000080 | U11 - UG Process Channel Execution (Closed Drain System) (Loop 3 - Unit 518) | CI | CIUG3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 48653 | 2557.6281 | 10610.CI.CO.M3 | 973.05 | 895.2099
C111132CIUG000140 | U11 - UG Pipe Installation (Loop 3 - Unit 516) (CD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2160 | 5.099 | 10780.CI.CI.MH
C111132CIUG000150 | U11 - UG Pipe Installation (Loop 3 - Unit 516) (OD) | CI | CIUG2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10743 | 156.0027 | 10610.CI.UG.LM | 537.14 | 537.1409
C111132CIUG000170 | U11 - UG Pipe Installation (Loop 2 - Unit 517) (OD) | CI | CIUG2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17678 | 443.6706 | 10610.CI.UG.LM | 883.91 | 883.9125
C111132CIVE000020 | U11 - ERE Feed Gas Compressor-01 Suction KO Drum Foundation Execution (Loop 3 - Unit 516) 516-V-101 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5863 | 50.7833 | 10610.CI.CO.M3 | 97.72 | 97.72
C111132CIVE000030 | U11 - Columns (ERE Feed Gas Compressor-02 Suction KO Drum) Foundation Execution (Loop 2 - Unit 517) 517-V-101 | CI | CIVE | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7074 | 73.5489 | 10610.CI.CO.M3 | 117.9 | 117.9
C111132CIVE000040 | U11 - Columns (ERE Feed Gas Compressor-03 Suction KO Drum) Foundation Execution (Loop 3 - Unit 518) 518-V-101 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6125 | 55.1425 | 10610.CI.CO.M3 | 102.09 | 102.09
C111132STEQ000020 | U11 - Structure Erection for Lube Oil Cooler (close to 517-SH-001) | ST | STEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10610.ST.ER.TN | 0.67 | 0
C111132STEQ000030 | U11 - Structure Erection for Lube Oil Cooler (close to 518-SH-001) | ST | STEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10610.ST.ER.TN | 0.63 | 0
C111132STMS000020 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 2 - Unit 517) | ST | STMS | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1225 | 0 | 10610.ST.PL.TN | 20.41 | 0
C111132STPL000010 | U11 - 577-PR-110 Piperack Platforms, Ladders & Handrails Erection (Unit 516) (516-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.ST.PL.TN | 64.39 | 0
C111132STPL000020 | U11 - 516-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2663 | 0 | 10610.ST.PL.TN | 33.29 | 0
C111132STPL000060 | U11 - 577-PR-109 Piperack Platforms, Ladders & Handrails Erection (Unit 517) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12691 | 0 | 10610.ST.PL.TN | 158.64 | 0
C111132STPL000070 | U11 - 577-PR-106 Piperack Platforms, Ladders & Handrails Erection (Unit 518) (518-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11100 | 0 | 10610.ST.PL.TN | 138.76 | 0
C111132STPL000080 | U11 - 517-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 2 - Unit 517) | ST | STPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2452 | 0 | 10610.ST.PL.TN | 30.65 | 0
C111132STPL000120 | U11 - 518-PR-002 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2445 | 0 | 10610.ST.PL.TN | 30.57 | 0
C111132STPL000160 | U11 - Pits Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) (516-SU-001; 516-SU-002) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 414 | 0 | 10610.ST.PL.TN | 5.17 | 0
C111132CIVE000070 | U11 - Columns (ERE Feed Gas Compressor-03 Suction KO Drum) Foundation Execution (Loop 3 - Unit 518) 518-V-201 | CI | CIVE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8012 | 94.3446 | 10610.CI.CO.M3 | 133.53 | 133.53
C111132CIVE300010 | U11 - ERE Feed Gas Compressor-01 Foundation Execution 516-C-101 (inside 516-SH-001) | CI | CIPE | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 622 | 0.57182 | 10610.CI.CO.M3 | 8.89 | 8.89
C111132STEQ000010 | U11 - Structure Erection for Lube Oil Cooler (close to 516-SH-001) | ST | STEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33 | 0.00021077 | 10610.ST.ER.TN | 0.63 | 0.037374
C111132STMS000030 | U11 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Loop 3 - Unit 518) | ST | STMS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2264 | 0 | 10610.ST.PL.TN | 37.73 | 0
C111132STPL000040 | U11 - 577-PR-107 Piperack Platforms, Ladders & Handrails Erection (Unit 518) (518-E-201) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2832 | 0 | 10610.ST.PL.TN | 35.4 | 0
C111132STPL000050 | U11 - 577-PR-108 Piperack Platforms, Ladders & Handrails Erection (Unit 517) (517-E-101) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10334 | 0 | 10610.ST.PL.TN | 129.18 | 0
C111132STPL000060 | U11 - 577-PR-109 Piperack Platforms, Ladders & Handrails Erection (Unit 517) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12691 | 0 | 10610.ST.PL.TN | 158.64 | 0
C111132STPL000100 | U11 - 577-PR-105 Piperack Platforms, Ladders & Handrails Erection (Unit 518) | ST | STPL | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9984 | 0 | 10610.ST.PL.TN | 124.8 | 0
C111132STPL000110 | U11 - 001-PR-104 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8116 | 0 | 10610.ST.PL.TN | 101.44 | 0
C111132STPL000130 | U11 - 518-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2819 | 0 | 10610.ST.PL.TN | 35.24 | 0
C111132STPL000150 | U11 - Lube Oil Cooler for 517-SH-001 Structure Platforms, Ladders & Handrails Erection (Loop 2 - Unit 517) | ST | STPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 53 | 0 | 10610.ST.PL.TN | 0.67 | 0
C111132STPL000160 | U11 - Pits Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) (516-SU-001; 516-SU-002) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 414 | 0 | 10610.ST.PL.TN | 5.17 | 0
C111132STPL000190 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23947 | 0 | 10610.ST.PL.TN | 299.34 | 0
C111132STPR000010 | U11 - 577-PR-110 Main Piperack Erection (Unit 516) (516-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30716 | 923.1944 | 10610.ST.PR.TN | 579.54 | 436.0699
C111132STPR000010 | U11 - 577-PR-110 Main Piperack Erection (Unit 516) (516-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30716 | 923.1944 | 10610.ST.PR.TN | 579.54 | 436.0699
C111132STPR000020 | U11 - 516-PR-001 Secondary Piperack Erection (Loop 3 - Unit 516) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15880 | 225.2722 | 10610.ST.PR.TN | 299.63 | 189.241
C111132STPR000040 | U11 - 577-PR-104 Main Piperack Erection (Unit 518) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 48389 | 3005.5985 | 10610.ST.PR.TN | 913 | 858.2086
C111134FPEQ000021 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-C-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000023 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-V-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000033 | U11 - Equipment Fireproofing (Loop 2 - Unit 517) 517-V-101 | FP | FPEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5390 | 0 | 10780.FP.FP.MH
C111134FPSS000030 | U11 - Secondary PR Steel Structure Fireproofing (Loop 3 - Unit 516) | FP | FPSS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10421 | 0 | 10610.FP.ST.M2 | 553.61 | 0
C111134FPSS000040 | U11 - Secondary PR Steel Structure Fireproofing (Loop 2 - Unit 517) | FP | FPSS | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24256 | 0 | 10610.FP.ST.M2 | 552.94 | 0
C111134MEMC000030 | U11 - Miscellaneous Electrical (Unit 517) | EL | ELEQ2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2575 | 0 | 10780.EL.EL.MH
C111134PRMR000020 | U11 - Motor Run (Loop 2 - Unit 517) | PR | PRMR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2113 | 0 | 10780.PR.PR.MH
C111136MEAC000050 | U11 - ERE Feed Gas Compressor-03 After Cooler Erection 518-E-101 (Loop 3 - Unit 518) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23600 | 0 | 10610.ME.ER.TN | 236 | 0
C111136MECO200030 | U11 - ERE Feed Gas Compressor-03 Erection 518-C-101 (Loop 3 - Unit 518) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 18.8993 | 10610.ME.ER.TN | 120 | 83.0796
C111136MECO200040 | U11 - ERE Feed Gas Compressor-03 Erection 518-C-201 (Loop 3 - Unit 518) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 18.8993 | 10610.ME.ER.TN | 120 | 83.0796
C111136MEHM000380 | U11 - Oily Water Sump Pump with Electrical Motor Erection 516-P-002B (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHV000010 | U11 - ERE Feed Gas Compressor-01 Inlet Filter Erection 516-F-101A (Loop 3 - Unit 516) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000020 | U11 - ERE Feed Gas Compressor-02 Inlet Filter Erection 517-F-101A (Loop 2 - Unit 517) | ME | MEHV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 120 | 0.0021273 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000040 | U11 - Closed Drain Drum Erection 516-V-001 (Loop 3 - Unit 516) inside 516-SU-001 | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 440 | 0 | 10610.ME.ER.TN | 11 | 0
C111136MEMC000010 | U11 - Miscellaneous Erection (Loop 3 - Unit 516) | ME | MEMC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C111136MEMC000020 | U11 - Miscellaneous Erection (Loop 2 - Unit 517) | ME | MEMC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3780 | 0 | 10610.ME.ER.TN | 63 | 0
C111136MEMC000030 | U11 - Miscellaneous Erection (Loop 3 - Unit 518) | ME | MEMC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7440 | 0 | 10610.ME.ER.TN | 124 | 0
C111136MEPA200030 | U11 - Skid Package Installation for 518-C-101 (Loop 3 - Unit 518) 518-C-101-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 38.2914 | 10610.ME.ER.TN | 120 | 60
C111132STPL000130 | U11 - 518-PR-001 Piperack Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2819 | 0 | 10610.ST.PL.TN | 35.24 | 0
C111132STPL000140 | U11 - Lube Oil Cooler for 518-SH-002 Structure Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 50 | 0 | 10610.ST.PL.TN | 0.63 | 0
C111132STPL000170 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12581 | 0 | 10610.ST.PL.TN | 157.26 | 0
C111132STPL000190 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 3 - Unit 518) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23947 | 0 | 10610.ST.PL.TN | 299.34 | 0
C111132STPR000011 | U11 - 577-PB-111 Main Piperack Erection (Unit 516) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35917 | 1008.9121 | 10610.ST.PR.TN | 677.68 | 365.9472
C111132STPR000020 | U11 - 516-PR-001 Secondary Piperack Erection (Loop 3 - Unit 516) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15880 | 225.2722 | 10610.ST.PR.TN | 299.63 | 189.241
C111132STPR000040 | U11 - 577-PR-104 Main Piperack Erection (Unit 518) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 48389 | 3005.5985 | 10610.ST.PR.TN | 913 | 858.2086
C111132STPR000050 | U11 - 517-PR-001 Secondary Piperack Erection (Loop 2 - Unit 517) | ST | STPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14620 | 34.7344 | 10610.ST.PR.TN | 275.85 | 0
C111132STPR000050 | U11 - 517-PR-001 Secondary Piperack Erection (Loop 2 - Unit 517) | ST | STPR | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14620 | 34.7344 | 10610.ST.PR.TN | 275.85 | 0
C111132STPR000060 | U11 - 518-PR-001 Secondary Piperack Erection (Loop 3 - Unit 518) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16808 | 278.6571 | 10610.ST.PR.TN | 317.13 | 195.988
C111132STPR000070 | U11 - 577-PR-107 Main Piperack Erection (Unit 518) (518-E-201) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16884 | 301.9885 | 10610.ST.PR.TN | 318.56 | 231.6899
C111132STPR000080 | U11 - 577-PR-106 Main Piperack Erection (Unit 518) (518-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65640 | 4360.0687 | 10610.ST.PR.TN | 1238.49 | 1238.4874
C111132STPR000090 | U11 - 577-PR-105 Main Piperack Erection (Unit 518) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 59532 | 3376.9596 | 10610.ST.PR.TN | 1123.24 | 842.4315
C111132STSH000100 | U11 - 518-SH-002 Compressor Shelter Structure Erection (Loop 3 - Unit 518) for 518-C-201 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19901 | 87.762 | 10610.ST.ER.TN | 375.49 | 0
C111132STSH000110 | U11 - 518-SH-002 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 518) for 518-C-201 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.72 | 0
C111132STSH200050 | U11 - 518-SH-001 Compressor Shelter Structure Erection (Loop 3 - Unit 518) for 518-C-101 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19901 | 147.442 | 10610.ST.ER.TN | 375.49 | 56.3191
C111132STSH300040 | U11 - 517-SH-001 Compressor Shelter Structure Erection (Loop 2 - Unit 517) for 517-C-101 | ST | STSH1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23135 | 118.6007 | 10610.ST.ER.TN | 436.5 | 0
C111132STSH300060 | U11 - 517-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 2 - Unit 517) for 517-C-101 | ST | STSH2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 116 | 0 | 10610.ST.ER.TN | 48.5 | 0
C111132STPL000170 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 3 - Unit 516) | ST | STPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12581 | 0 | 10610.ST.PL.TN | 157.26 | 0
C111132STPL000180 | U11 - Rest of Equipment Platforms, Ladders & Handrails Erection (Loop 2 - Unit 517) | ST | STPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13080 | 0 | 10610.ST.PL.TN | 163.5 | 0
C111132STPR000030 | U11 - 577-PR-108 Main Piperack Erection (Unit 517) (517-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61617 | 4416.8847 | 10610.ST.PR.TN | 1162.58 | 988.1888
C111132STPR000060 | U11 - 518-PR-001 Secondary Piperack Erection (Loop 3 - Unit 518) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16808 | 278.6571 | 10610.ST.PR.TN | 317.13 | 195.988
C111132STPR000100 | U11 - 518-PR-002 Secondary Piperack Erection (Loop 3 - Unit 518) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14580 | 125.1995 | 10610.ST.PR.TN | 275.09 | 101.0336
C111132STPR000110 | U11 - 577-PR-109 Main Piperack Erection (Unit 517) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 75670 | 4999.1817 | 10610.ST.PR.TN | 1427.73 | 928.0217
C111132STSH000100 | U11 - 518-SH-002 Compressor Shelter Structure Erection (Loop 3 - Unit 518) for 518-C-201 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19901 | 87.762 | 10610.ST.ER.TN | 375.49 | 0
C111132STSH000110 | U11 - 518-SH-002 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 518) for 518-C-201 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.72 | 0
C111132STSH200070 | U11 - 518-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 518) for 518-C-101 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.72 | 0
C111132STSH300010 | U11 - 516-SH-001 Compressor Shelter Structure Erection (Loop 3 - Unit 516) for 516-C-101 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19894 | 185.6946 | 10610.ST.ER.TN | 375.35 | 95.3993
C111132STSH300020 | U11 - 516-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 3 - Unit 516) for 516-C-101 | ST | STSH2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10610.ST.ER.TN | 41.71 | 0
C111132STSP000010 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 3 - Unit 516) | ST | STSP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7439 | 0 | 10610.ST.PL.TN | 123.99 | 0
C111132STSP000030 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 3 - Unit 518) | ST | STSP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8233 | 0 | 10610.ST.PL.TN | 137.21 | 0
C111133PAEQ000010 | U11 - Equipment Painting (Loop 3 - Unit 516) | PA | PAEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 328 | 0 | 10610.PA.EQ.M2 | 131 | 0
C111133PAPP000020 | U11 - Piping SandBl. & Priming (Loop 2 - Unit 517) | PA | PAPP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 734 | 0.31803 | 10610.PA.PP.M2 | 0 | 0
C111133PASP000010 | U11 - Piping Supports SandBl. & Priming (Loop 3 - Unit 516) | PA | PASP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 361 | 0.0077586 | 10610.PA.SU.TN | 0 | 0
C111133PASP000020 | U11 - Piping Supports SandBl. & Priming (Loop 2 - Unit 517) | PA | PASP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 227 | 0.0027054 | 10610.PA.SU.TN | 0 | 0
C111133PAST000030 | U11 - Steel Structure Painting Touch Up (Loop 3 - Unit 518) | PA | PAST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1428 | 0 | 10780.PA.PA.MH
C111136MEPA200030 | U11 - Skid Package Installation for 518-C-101 (Loop 3 - Unit 518) 518-C-101-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 38.2914 | 10610.ME.ER.TN | 120 | 60
C111136METC000020 | U11 - EOT Crane For ERE Feed Gas Compressor-02 Erection (Loop 2 - Unit 517) 517-EOT-101 in 517-SH-001 | ME | METC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136METC000030 | U11 - Cranes (EOT Crane For ERE Feed Gas Compressor-03) Erection (Loop 3 - Unit 518) 518-EOT-101 in 518-SH-001 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136MEVV000010 | U11 - (MP Fuel Gas Balance Drum) 565-V-201 (Loop 3 - Unit 516) | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 3.0633 | 10610.ME.ER.TN | 36 | 36
C111136MEVV000020 | U11 - Vertical Vessels (Ere Feed Gas Compressor-02 Suction Ko Drum) Erection 517-V-101 (Loop 2 - Unit 517) (HL) 800+400 | ME | MEVV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9000 | 0 | 10610.ME.ER.TN | 225 | 0
C111136MEVV000425 | U11 - Vertical Vessels (LP Fuel Gas Balance Drum) Erection 565-V-202 (Loop 3 - Unit 516) | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1480 | 3.2359 | 10610.ME.ER.TN | 37 | 37
C111136MEVV000435 | U11 - Vertical Vessels (ERE Feed Gas Compressor-03 Suction KO Drum) Erection 518-V-101 (Loop 3 - Unit 518) (HL) 800+400 | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6640 | 0 | 10610.ME.ER.TN | 166 | 0
C111137INAI000030 | U11 - Analyzers Equipment Installation (Loop 3 - Unit 518) | IN | INAI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3370 | 0 | 10610.IN.AI.UN | 1 | 0
C111137INCI000030 | U11 - Conduits Installation (Loop 3 - Unit 518) | IN | INCT3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1618 | 0 | 10780.IN.IN.MH
C111137INCO000030 | U11 - Communication System Installation (Comp. Shelter 517-SH-001) (Loop 2 - Unit 517) | IN | INCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 704 | 0 | 10780.IN.IN.MH
C111137INCO000050 | U11 - Communication System Installation (Loop 2 - Unit 517) | IN | INCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 704 | 0 | 10780.IN.IN.MH
C111137INCT000010 | U11 - Primary Cable Trays Installation (Loop 3 - Unit 516) | IN | INCT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18648 | 0 | 10610.IN.CT.LM | 890 | 0
C111137INCT000030 | U11 - Primary Cable Trays Installation (Loop 2 - Unit 517) | IN | INCT1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.IN.CT.LM | 890 | 0
C111137INCT000040 | U11 - Primary Cable Trays Installation (Loop 3 - Unit 518) | IN | INCT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15602 | 0 | 10610.IN.CT.LM | 930 | 0
C111137INCT000050 | U11 - Secondary Cable Trays Installation (Loop 2 - Unit 517) | IN | INCT2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4480 | 0 | 10610.IN.CT.LM | 560 | 0
C111137INFC000020 | U11 - Fiber Optic Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INFC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 768 | 0 | 10610.IN.CO.UN | 310 | 0
C111137INFC000030 | U11 - Fiber Optic Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INFC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1498 | 0 | 10610.IN.CO.UN | 350 | 0
C111137INFG000010 | U11 - Fire & Gas System Installation (Loop 3 - Unit 516) | IN | INFG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 970 | 0 | 10780.IN.IN.MH
C111137INFG000020 | U11 - Fire & Gas System Installation (Comp. Shelter 516-SH-001) (Loop 3 - Unit 516) | IN | INFG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 970 | 0 | 10780.IN.IN.MH
C111137INFG000040 | U11 - Fire & Gas System Installation (Comp. Shelter 518-SH-001) (Loop 3 - Unit 518) | IN | INFG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 541 | 0 | 10780.IN.IN.MH
C111137INGC000010 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11637 | 0 | 10610.IN.CO.UN | 510 | 0
C111137INGC000020 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7758 | 0 | 10610.IN.CO.UN | 490 | 0
C111137INGC000050 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INGC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3328 | 0 | 10610.IN.CO.UN | 410 | 0
C111137ININ000010 | U11 - Instruments Installation (Loop 3 - Unit 516) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5967 | 0 | 10610.IN.IN.UN | 610 | 0
C111137ININ000021 | U11 - Valve Installation (Loop 2 - Unit 517) | IN | ININ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.IN.IN.UN | 500 | 0
C111137ININ000031 | U11 - Valve Installation (Loop 3 - Unit 518) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4993 | 0 | 10610.IN.IN.UN | 820 | 0
C111137INIP000021 | U11 - Valve Calibration (Loop 2 - Unit 517) | IN | INIP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 832 | 0 | 10780.IN.IN.MH
C111137INIP000030 | U11 - Instruments Calibration (Loop 3 - Unit 518) | IN | INIP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1623 | 0 | 10780.IN.IN.MH
C111137INML000020 | U11- Multi Pair Cable Pulling (Loop 2 - Unit 517) | IN | INML | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9984 | 0 | 10610.IN.MC.LM | 51440.94 | 0
C111137INML000030 | U11- Multi Pair Cable Pulling (Loop 3 - Unit 518) | IN | INML | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19471 | 0 | 10610.IN.MC.LM | 100542.87 | 0
C111137MEMC000030 | U11 - Miscellaneous Instrumetation (Unit 517) | IN | ININ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10780.IN.IN.MH
C111137MEMC000040 | U11 - Miscellaneous Instrumetation (Unit 518) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4993 | 0 | 10780.IN.IN.MH
C112131DEGR000700 | U12 - Degreasing | PR | PRFL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2933 | 0 | 10780.PR.PR.MH
C112131MEMC000050 | U12 - Miscellaneous Piping | PI | PISU2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27 | 0 | 10780.PI.PI.MH
C112131NITR000040 | U12 - Nitrogen Leak Test (Unit 537) | PR | PRFL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4399 | 0 | 10780.PR.PR.MH
C112131PIBB000040 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-001 to 537-STR-002 | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIBB000050 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-005 to Sumps | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIBB000060 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-003 to 537-STR-004 | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C111132STPR000070 | U11 - 577-PR-107 Main Piperack Erection (Unit 518) (518-E-201) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16884 | 301.9885 | 10610.ST.PR.TN | 318.56 | 231.6899
C111132STPR000080 | U11 - 577-PR-106 Main Piperack Erection (Unit 518) (518-E-101) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65640 | 4360.0687 | 10610.ST.PR.TN | 1238.49 | 1238.4874
C111132STPR000100 | U11 - 518-PR-002 Secondary Piperack Erection (Loop 3 - Unit 518) | ST | STPR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14580 | 125.1995 | 10610.ST.PR.TN | 275.09 | 101.0336
C111132STPR000110 | U11 - 577-PR-109 Main Piperack Erection (Unit 517) | ST | STPR | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 75670 | 4999.1817 | 10610.ST.PR.TN | 1427.73 | 928.0217
C111132STSH200050 | U11 - 518-SH-001 Compressor Shelter Structure Erection (Loop 3 - Unit 518) for 518-C-101 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19901 | 147.442 | 10610.ST.ER.TN | 375.49 | 56.3191
C111132STSH300010 | U11 - 516-SH-001 Compressor Shelter Structure Erection (Loop 3 - Unit 516) for 516-C-101 | ST | STSH1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19894 | 185.6946 | 10610.ST.ER.TN | 375.35 | 95.3993
C111132STSH300060 | U11 - 517-SH-001 Compressor Shelter Roofing & Wall Erection (Loop 2 - Unit 517) for 517-C-101 | ST | STSH2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 116 | 0 | 10610.ST.ER.TN | 48.5 | 0
C111133PAEQ000020 | U11 - Equipment Painting (Loop 2 - Unit 517) | PA | PAEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 205 | 0 | 10780.PA.PA.MH
C111133PAPP000010 | U11 - Piping SandBl. & Priming (Loop 3 - Unit 516) | PA | PAPP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1171 | 1.2136 | 10610.PA.PP.M2 | 0 | 0
C111133PAPP000010 | U11 - Piping SandBl. & Priming (Loop 3 - Unit 516) | PA | PAPP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1171 | 1.2136 | 10610.PA.PP.M2 | 0 | 0
C111133PAPP000020 | U11 - Piping SandBl. & Priming (Loop 2 - Unit 517) | PA | PAPP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 734 | 0.31803 | 10610.PA.PP.M2 | 0 | 0
C111133PASP000020 | U11 - Piping Supports SandBl. & Priming (Loop 2 - Unit 517) | PA | PASP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 227 | 0.0027054 | 10610.PA.SU.TN | 0 | 0
C111133PASP000030 | U11 - Piping Supports SandBl. & Priming (Loop 3 - Unit 518) | PA | PASP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 355 | 0.0080502 | 10610.PA.SU.TN | 0 | 0
C111134ELCI000030 | U11 - Conduits Installation (Loop 3 - Unit 518) | EL | ELCI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9280 | 0 | 10780.EL.EL.MH
C111134ELCL000010 | U11 - Lighting Cable Laying (Loop 3 - Unit 516) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9118 | 11.8525 | 10610.EL.LC.LM | 47514.11 | 0
C111134ELCL000030 | U11 - Electrical Cable Laying (Loop 2 - Unit 517) | EL | ELCL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37771 | 310.8695 | 10610.EL.PL.LM | 54118.04 | 0
C111134ELCL000050 | U11 - Lighting Cable Laying (Loop 2 - Unit 517) | EL | ELCL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7726 | 0 | 10610.EL.LC.LM | 39165.47 | 0
C111134ELCL000060 | U11 - Lighting Cable Laying (Loop 3 - Unit 518) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16704 | 0 | 10610.EL.LC.LM | 76626.35 | 0
C111134ELCO000010 | U11 - Lighting Cable Gland & Conn./Testing (Loop 3 - Unit 516) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6079 | 0 | 10610.EL.CO.UN | 310 | 0
C111132STSP000010 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 3 - Unit 516) | ST | STSP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7439 | 0 | 10610.ST.PL.TN | 123.99 | 0
C111132STSP000020 | U11 - Steel Structure Stair Ways & Floors Erection (Loop 2 - Unit 517) | ST | STSP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4853 | 0 | 10610.ST.PL.TN | 80.89 | 0
C111133PAEQ000010 | U11 - Equipment Painting (Loop 3 - Unit 516) | PA | PAEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 328 | 0 | 10610.PA.EQ.M2 | 131 | 0
C111133PAFP000010 | U11 - Piping Final Coat & Touch-Up Painting (Loop 3 - Unit 516) | PA | PAFP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1802 | 0 | 10610.PA.FP.M2 | 7510 | 0
C111133PAFP000020 | U11 - Piping Final Coat & Touch-Up Painting (Loop 2 - Unit 517) | PA | PAFP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 169 | 0 | 10780.PA.PA.MH
C111133PAFP000030 | U11 - Piping Final Coat & Touch-Up Painting (Loop 3 - Unit 518) | PA | PAFP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 267 | 0 | 10780.PA.PA.MH
C111133PAPP000030 | U11 - Piping SandBl. & Priming (Loop 3 - Unit 518) | PA | PAPP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1153 | 1.3817 | 10610.PA.PP.M2 | 0 | 0
C111133PAST000010 | U11 - Steel Structure Painting Touch Up (Loop 3 - Unit 516) | PA | PAST | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1450 | 0 | 10780.PA.PA.MH
C111133PAST000020 | U11 - Steel Structure Painting Touch Up (Loop 2 - Unit 517) | PA | PAST | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 909 | 0 | 10780.PA.PA.MH
C111134ELCL000020 | U11 - Electrical Cable Laying (Loop 3 - Unit 516) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44579 | 0 | 10610.EL.PL.LM | 62581.74 | 0
C111134ELCL000030 | U11 - Electrical Cable Laying (Loop 2 - Unit 517) | EL | ELCL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37771 | 310.8695 | 10610.EL.PL.LM | 54118.04 | 0
C111134ELCL000040 | U11 - Electrical Cable Laying (Loop 3 - Unit 518) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 81665 | 125.3217 | 10610.EL.PL.LM | 125061.78 | 1988.4823
C111134ELCL000060 | U11 - Lighting Cable Laying (Loop 3 - Unit 518) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16704 | 0 | 10610.EL.LC.LM | 76626.35 | 0
C111134ELCO000040 | U11 - Electrical Cable Gland & Conn./Testing (Loop 3 - Unit 518) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44545 | 0 | 10610.EL.CO.UN | 1228 | 0
C111134ELCO000060 | U11 - Lighting Cable Gland & Conn./Testing (Loop 3 - Unit 518) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11136 | 0 | 10610.EL.CO.UN | 634 | 0
C111134ELCP000010 | U11 - Cathodic Protection Piping (Loop 3 - Unit 516) | EL | ELCP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4053 | 0 | 10780.EL.EL.MH
C111134ELCP000030 | U11 - Cathodic Protection Piping (Loop 3 - Unit 518) | EL | ELCP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7424 | 0 | 10780.EL.EL.MH
C111134ELEL000015 | U11 - Earthing Works (Loop 3 - Unit 516) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8105 | 42.1768 | 10610.EL.ES.LM | 11178.22 | 6531.8811
C111134ELEL000035 | U11 - Earthing Works (Loop 3 - Unit 518) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14848 | 87.3574 | 10610.EL.ES.LM | 11342.61 | 3416.2807
C112131PIRA000050 | U12 - Piping Erection on Rack 537-PR-101_103 (537-E-101) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000060 | U12 - Piping Erection on Rack 537-PR-104 (537-E-104) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000070 | U12 - Piping Erection on Rack 537-PR-105 (537-E-102; 537-E-104) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA120000 | U12 - Piping Erection on Rack 537-PR-201 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA130000 | U12 - Piping Erection on Rack 537-PR-301 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PISB000060 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-003 to 537-STR-004 | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISU000070 | U12 - Piping Supports Prefabrication | PI | PISU1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 62488 | 1959.2634 | 10610.PI.PU.TN | 240.34 | 66.7965
C112131PISU000080 | U12 - Piping Supports Erection | PI | PISU2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 108153 | 0 | 10610.PI.SU.TN | 240.34 | 0
C112131PRFL000040 | U12 - Piping Flushing/Blowing | PR | PRFL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10998 | 0 | 10610.PR.FL.DI | 180783 | 0
C112131PRHT000040 | U12 - Piping Hydrotesting | PR | PRHT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 86216 | 0 | 10610.PR.HT.DI | 180783 | 0
C112132CICT000140 | U12 - Instrument earth Trenches Execution | CI | CICT3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1379 | 0.29357 | 10610.CI.ET.M3 | 344.75 | 317.17
C112132CICT000150 | U12 - Covered Concrete Trenches Execution | CI | CICT1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44174 | 947.9372 | 10610.CI.CO.M3 | 883.47 | 273.0717
C112132CIDM000070 | U12 - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29114 | 704.2681 | 10610.CI.CO.M3 | 582.29 | 335.4796
C112132CIPD000040 | U12 - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1083 | 1.7326 | 10780.CI.CI.MH
C112132CIPE000030 | U12 - Lean Solvent Filtration Package 537-ME-101 Foundation Execution | CI | CIPE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12352 | 19.7211 | 10610.CI.CO.M3 | 247.03 | 0
C112132CIPR000083 | U12 - Pipe Rack 537-PR-303 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1374 | 1.6078 | 10610.CI.CO.M3 | 22.9 | 7.69
C112132CIPR000100 | U12 - Pipe Rack 537-PB-101 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63499 | 5918.9779 | 10610.CI.CO.M3 | 1269.98 | 1269.9851
C112132CIPR000120 | U12 - Pipe Rack 537-PR-104 Foundations Execution (537-E-104) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30766 | 1398.3034 | 10610.CI.CO.M3 | 615.31 | 615.31
C112132CIPS000060 | U12 - 537-SU-101 Solvent Drain Sump Pit Constrution (537-V-107; 537-P-108A/B) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 18.2937 | 10610.CI.CO.M3 | 120.34 | 24.0704
C112132CIRE000130 | U12 - Lean Solvent Circulation Pump 537-P-101A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C111134ELCI000010 | U11 - Conduits Installation (Loop 3 - Unit 516) | EL | ELCI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5066 | 0 | 10780.EL.EL.MH
C111134ELCL000040 | U11 - Electrical Cable Laying (Loop 3 - Unit 518) | EL | ELCL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 81665 | 125.3217 | 10610.EL.PL.LM | 125061.78 | 1988.4823
C111134ELCO000020 | U11 - Electrical Cable Gland & Conn./Testing (Loop 3 - Unit 516) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24316 | 0 | 10610.EL.CO.UN | 1242 | 0
C111134ELEL000035 | U11 - Earthing Works (Loop 3 - Unit 518) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14848 | 87.3574 | 10610.EL.ES.LM | 11342.61 | 3416.2807
C111134ELEL000045 | U11 - Lightning Works (Loop 3 - Unit 518) | EL | ELEL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14848 | 0 | 10780.EL.EL.MH
C111134ELEQ000010 | U11 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Loop 3 - Unit 516) | EL | ELEQ3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6079 | 0 | 10780.EL.EL.MH
C111134ELEQ000020 | U11 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Loop 2 - Unit 517) | EL | ELEQ3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10780.EL.EL.MH
C111134ELPL000020 | U11 - Plant Lighting - (Lighting poles and fixtures) Installation (Loop 2 - Unit 517) | EL | ELPL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11160 | 0 | 10780.EL.EL.MH
C111134ELTI000040 | U11 - Electrical Cable Trays Installation (Loop 3 - Unit 518) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37121 | 0 | 10610.EL.CT.LM | 7769.91 | 0
C111134FPEQ000021 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-C-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000023 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-V-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000024 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-F-101 A/B | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000042 | U11 - Equipment Fireproofing (Loop 3 - Unit 518) 518-E-101 / 201 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15252 | 0 | 10780.FP.FP.MH
C111134FPEQ000044 | U11 - Equipment Fireproofing (Loop 3 - Unit 518) 518-F-101 A/B | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15252 | 0 | 10780.FP.FP.MH
C111134FPSS000040 | U11 - Secondary PR Steel Structure Fireproofing (Loop 2 - Unit 517) | FP | FPSS | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24256 | 0 | 10610.FP.ST.M2 | 552.94 | 0
C111134FPSS000130 | U11 - Main PR Steel Structure Fireproofing (577-PR-110) (Unit 516) | FP | FPSS | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23447 | 0 | 10780.FP.FP.MH
C111134MEMC000040 | U11 - Miscellaneous Electrical (Unit 518) | EL | ELEQ2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5568 | 0 | 10780.EL.EL.MH
C111136MEAC000040 | U11 - ERE Feed Gas Compressor-02 After Cooler Pre-Assembly 517-E-101 (Loop 2 - Unit 517) | ME | MEAC1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15130 | 67.6354 | 10780.ME.ME.MH
C111136MEAC000050 | U11 - ERE Feed Gas Compressor-03 After Cooler Erection 518-E-101 (Loop 3 - Unit 518) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23600 | 0 | 10610.ME.ER.TN | 236 | 0
C111134ELCO000030 | U11 - Electrical Cable Gland & Conn./Testing (Loop 2 - Unit 517) | EL | ELCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20602 | 0 | 10610.EL.CO.UN | 1228 | 0
C111134ELCO000040 | U11 - Electrical Cable Gland & Conn./Testing (Loop 3 - Unit 518) | EL | ELCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44545 | 0 | 10610.EL.CO.UN | 1228 | 0
C111134ELCO000050 | U11 - Lighting Cable Gland & Conn./Testing (Loop 2 - Unit 517) | EL | ELCO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.EL.CO.UN | 310 | 0
C111134ELCP000020 | U11 - Cathodic Protection Piping (Loop 2 - Unit 517) | EL | ELCP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3434 | 0 | 10780.EL.EL.MH
C111134ELEQ000030 | U11 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Loop 3 - Unit 518) | EL | ELEQ3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11136 | 0 | 10780.EL.EL.MH
C111134ELHT000010 | U11 - Electrical Heat Tracing (Loop 3 - Unit 516) | EL | ELHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7092 | 0 | 10780.EL.EL.MH
C111134ELHT000020 | U11 - Electrical Heat Tracing (Loop 2 - Unit 517) | EL | ELHT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6009 | 0 | 10780.EL.EL.MH
C111134ELHT000030 | U11 - Electrical Heat Tracing (Loop 3 - Unit 516) | EL | ELHT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12992 | 0 | 10780.EL.EL.MH
C111134ELPL000030 | U11 - Plant Lighting - (Lighting poles and fixtures) Installation (Loop 3 - Unit 518) | EL | ELPL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24128 | 0 | 10780.EL.EL.MH
C111134ELTI000010 | U11 - Lighting Cable Trays Installation (Loop 3 - Unit 516) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6079 | 0 | 10610.EL.CT.LM | 3575.09 | 0
C111134ELTI000020 | U11 - Electrical Cable Trays Installation (Loop 3 - Unit 516) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20263 | 0 | 10610.EL.CT.LM | 6639.46 | 0
C111134ELTI000030 | U11 - Electrical Cable Trays Installation (Loop 2 - Unit 517) | EL | ELTI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17169 | 0 | 10610.EL.CT.LM | 4807.59 | 0
C111134ELTI000050 | U11 - Lighting Cable Trays Installation (Loop 2 - Unit 517) | EL | ELTI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.EL.CT.LM | 2588.7 | 0
C111134FPEQ000022 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-E-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000031 | U11 - Equipment Fireproofing (Loop 2 - Unit 517) 517-C-101 | FP | FPEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5390 | 0 | 10780.FP.FP.MH
C111134FPSS000030 | U11 - Secondary PR Steel Structure Fireproofing (Loop 3 - Unit 516) | FP | FPSS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10421 | 0 | 10610.FP.ST.M2 | 553.61 | 0
C111134FPSS000050 | U11 - Main PR Steel Structure Fireproofing (577-PR-104 TO 577-PR-107) (Unit 518) | FP | FPSS | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 45755 | 0 | 10780.FP.FP.MH
C111134FPSS000090 | U11 - Secondary PR Steel Structure Fireproofing (Loop 3 - Unit 518) | FP | FPSS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33045 | 0 | 10780.FP.FP.MH
C111134FPSS000110 | U11 - Main PR Steel Structure Fireproofing (577-PR-108 TO 577-PR-109) (Unit 517) | FP | FPSS | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24256 | 0 | 10610.FP.ST.M2 | 12768.72 | 0
C112132CIRE000140 | U12 - Sweet Gas Water Wash Pump 537-P-104B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 607 | 0.061224 | 10610.CI.CO.M3 | 8.67 | 0
C112132CIRE000160 | U12 - Lean Solvent Circulation Pump 537-P-101C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C112132CIRE000170 | U12 - Absorber Water Wash Make-up Pump 537-P-121A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0.069587 | 10610.CI.CO.M3 | 9.25 | 0
C112132CIRE000180 | U12 - Absorber Water Wash Make-up Pump 537-P-121B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0.069587 | 10610.CI.CO.M3 | 9.25 | 0
C112132CIRE000190 | U12 - Steam Condensate Pump 537-P-107B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 370 | 0.022771 | 10610.CI.CO.M3 | 5.29 | 0
C112132CIRE000230 | U12 - Lean Solvent Pump 537-P-106B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIRE000240 | U12 - Lean Solvent Pump 537-P-106C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIST000100 | U12 - 537-STR-001 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31831 | 1493.3898 | 10610.CI.CO.M3 | 636.61 | 636.61
C112132CIST000110 | U12 - 537-STR-004 Structure Foundation Execution (537-V-102; 537-V-106; 537-E-105A/B; 537-ME-104) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 71315 | 7360.3845 | 10610.CI.CO.M3 | 1426.29 | 1418.7656
C112132CIST000111 | U12 - 537-STR-007 Structure Foundation Execution (ESD Platform) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1502 | 0.38155 | 10610.CI.CO.M3 | 25.03 | 0
C112132CIST000150 | U12 - Shelters Foundation Execution 537-ANS-401 | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4769 | 2.2681 | 10610.CI.CO.M3 | 79.49 | 0
C112132CIST000170 | U12 - 537-STR-005 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6466 | 48.9189 | 10610.CI.CO.M3 | 107.77 | 90.5296
C112132CIST000180 | U12 - 537-STR-006 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 411 | 0.18646 | 10610.CI.CO.M3 | 5.87 | 4.9308
C112132CITF000010 | U12 - Lean Solvent Storage Tank 537-TK-101 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5388 | 42.8866 | 10610.CI.CO.M3 | 89.8 | 89.8
C112132CITF000030 | U12 - Make-Up Water Break Tank 537-V-121 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 680 | 0.33442 | 10610.CI.CO.M3 | 9.72 | 4.8003
C112132CIUG000110 | U12 - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37799 | 237.4546 | 10610.CI.CO.M3 | 755.98 | 0
C112132CIUG000140 | U12 - UG Pipe Installation (OD) | CI | CIUG2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51170 | 2373.4787 | 10610.CI.UG.LM | 2558.52 | 1842.1257
C112132CIVE000130 | U12 - Rich Solvent Flash Drum 537-V-104 Foundation Execution | CI | CIHE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11285 | 185.5895 | 10610.CI.CO.M3 | 225.7 | 225.6998
C112132CIVE000130 | U12 - Rich Solvent Flash Drum 537-V-104 Foundation Execution | CI | CIHE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11285 | 185.5895 | 10610.CI.CO.M3 | 225.7 | 225.6998
C111136MEAC000060 | U11 - ERE Feed Gas Compressor-03 After Cooler Pre-Assembly 518-E-101 (Loop 3 - Unit 518) | ME | MEAC1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18226 | 98.1475 | 10780.ME.ME.MH
C111136MECO200030 | U11 - ERE Feed Gas Compressor-03 Erection 518-C-101 (Loop 3 - Unit 518) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 18.8993 | 10610.ME.ER.TN | 120 | 83.0796
C111136MECO200040 | U11 - ERE Feed Gas Compressor-03 Erection 518-C-201 (Loop 3 - Unit 518) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 18.8993 | 10610.ME.ER.TN | 120 | 83.0796
C111136MECO300010 | U11 - ERE Feed Gas Compressor-01 Erection 516-C-101 (Loop 3 - Unit 516) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4720 | 17.8418 | 10610.ME.ER.TN | 118 | 79.4199
C111136MEHM000010 | U11 - Closed Drain Drum Pump with Electrical Motor Erection 516-P-001A (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHM000370 | U11 - Closed Drain Drum Pump with Electrical Motor Erection 516-P-001B (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHM000380 | U11 - Oily Water Sump Pump with Electrical Motor Erection 516-P-002B (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHV000020 | U11 - ERE Feed Gas Compressor-02 Inlet Filter Erection 517-F-101A (Loop 2 - Unit 517) | ME | MEHV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 120 | 0.0021273 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000030 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-101A (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000140 | U11 - ERE Feed Gas Compressor-02 Inlet Filter Erection 517-F-101B (Loop 2 - Unit 517) | ME | MEHV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 120 | 0.0021273 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000150 | U11 - ERE Feed Gas Compressor-01 Inlet Filter Erection 516-F-101B (Loop 3 - Unit 516) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000170 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-201A (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C111136MEMC000010 | U11 - Miscellaneous Erection (Loop 3 - Unit 516) | ME | MEMC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C111136METC000010 | U11 - EOT Crane For ERE Feed Gas Compressor-01 Erection (Loop 3 - Unit 516) 516-EOT-101 in 516-SH-001 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136METC000020 | U11 - EOT Crane For ERE Feed Gas Compressor-02 Erection (Loop 2 - Unit 517) 517-EOT-101 in 517-SH-001 | ME | METC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136METC000030 | U11 - Cranes (EOT Crane For ERE Feed Gas Compressor-03) Erection (Loop 3 - Unit 518) 518-EOT-101 in 518-SH-001 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136MEVV000020 | U11 - Vertical Vessels (Ere Feed Gas Compressor-02 Suction Ko Drum) Erection 517-V-101 (Loop 2 - Unit 517) (HL) 800+400 | ME | MEVV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9000 | 0 | 10610.ME.ER.TN | 225 | 0
C111134ELEL000120 | U11 - Earthing Works (Loop 2 - Unit 517) | EL | ELEL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6867 | 2.3339 | 10610.EL.ES.LM | 6246.65 | 312.3325
C111134ELEL000125 | U11 - Lightning Works (Loop 2 - Unit 517) | EL | ELEL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6867 | 0 | 10780.EL.EL.MH
C111134ELTI000010 | U11 - Lighting Cable Trays Installation (Loop 3 - Unit 516) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6079 | 0 | 10610.EL.CT.LM | 3575.09 | 0
C111134ELTI000030 | U11 - Electrical Cable Trays Installation (Loop 2 - Unit 517) | EL | ELTI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17169 | 0 | 10610.EL.CT.LM | 4807.59 | 0
C111134ELTI000040 | U11 - Electrical Cable Trays Installation (Loop 3 - Unit 518) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37121 | 0 | 10610.EL.CT.LM | 7769.91 | 0
C111134ELTI000050 | U11 - Lighting Cable Trays Installation (Loop 2 - Unit 517) | EL | ELTI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5151 | 0 | 10610.EL.CT.LM | 2588.7 | 0
C111134ELTI000060 | U11 - Lighting Cable Trays Installation (Loop 3 - Unit 518) | EL | ELTI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11136 | 0 | 10610.EL.CT.LM | 4183.8 | 0
C111134FPEQ000022 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-E-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000024 | U11 - Equipment Fireproofing (Loop 3 - Unit 516) 516-F-101 A/B | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5210 | 0 | 10610.FP.EQ.M2 | 169 | 0
C111134FPEQ000032 | U11 - Equipment Fireproofing (Loop 2 - Unit 517) 517-E-101 | FP | FPEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5390 | 0 | 10780.FP.FP.MH
C111134FPEQ000034 | U11 - Equipment Fireproofing (Loop 2 - Unit 517) 517-F-101 A7B | FP | FPEQ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5390 | 0 | 10780.FP.FP.MH
C111134FPEQ000041 | U11 - Equipment Fireproofing (Loop 3 - Unit 518) 518-C-101 / 201 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15252 | 0 | 10780.FP.FP.MH
C111134FPEQ000043 | U11 - Equipment Fireproofing (Loop 3 - Unit 518) 518-V-101 | FP | FPEQ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15252 | 0 | 10780.FP.FP.MH
C111134FPSS000110 | U11 - Main PR Steel Structure Fireproofing (577-PR-108 TO 577-PR-109) (Unit 517) | FP | FPSS | 11 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24256 | 0 | 10610.FP.ST.M2 | 12768.72 | 0
C111134MEMC000020 | U11 - Miscellaneous Electrical (Unit 516) | EL | ELEQ2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3039 | 0 | 10780.EL.EL.MH
C111136MEAC000010 | U11 - ERE Feed Gas Compressor-01 After Cooler Erection 516-E-101 (Loop 3 - Unit 516) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22900 | 0 | 10610.ME.ER.TN | 229 | 0
C111136MEAC000020 | U11 - ERE Feed Gas Compressor-01 After Cooler Pre-Assembly 516-E-101 (Loop 3 - Unit 516) | ME | MEAC1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18816 | 104.6047 | 10780.ME.ME.MH
C111136MEAC000030 | U11 - ERE Feed Gas Compressor-02 After Cooler Erection 517-E-101 (Loop 2 - Unit 517) | ME | MEAC2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22400 | 0 | 10610.ME.ER.TN | 224 | 0
C111136MEAC000070 | U11 - ERE Feed Gas Compressor-03 After Cooler Erection 518-E-201 (Loop 3 - Unit 518) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23600 | 0 | 10610.ME.ER.TN | 236 | 0
C111134PRMR000010 | U11 - Motor Run (Loop 3 - Unit 516) | PR | PRMR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2370 | 0 | 10780.PR.PR.MH
C111134PRMR000030 | U11 - Motor Run (Loop 3 - Unit 518) | PR | PRMR | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4663 | 0 | 10780.PR.PR.MH
C111136MEAC000010 | U11 - ERE Feed Gas Compressor-01 After Cooler Erection 516-E-101 (Loop 3 - Unit 516) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22900 | 0 | 10610.ME.ER.TN | 229 | 0
C111136MEAC000030 | U11 - ERE Feed Gas Compressor-02 After Cooler Erection 517-E-101 (Loop 2 - Unit 517) | ME | MEAC2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22400 | 0 | 10610.ME.ER.TN | 224 | 0
C111136MEAC000070 | U11 - ERE Feed Gas Compressor-03 After Cooler Erection 518-E-201 (Loop 3 - Unit 518) | ME | MEAC2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23600 | 0 | 10610.ME.ER.TN | 236 | 0
C111136MECO300010 | U11 - ERE Feed Gas Compressor-01 Erection 516-C-101 (Loop 3 - Unit 516) (800 TON) | ME | MECO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4720 | 17.8418 | 10610.ME.ER.TN | 118 | 79.4199
C111136MECO300020 | U11 - ERE Feed Gas Compressor-02 Erection 517-C-101 (Loop 2 - Unit 517) (800 TON) | ME | MECO2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4720 | 1.7321 | 10610.ME.ER.TN | 118 | 0
C111136MEHM000020 | U11 - Oily Water Sump Pump with Electrical Motor Erection 516-P-002A (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHM000370 | U11 - Closed Drain Drum Pump with Electrical Motor Erection 516-P-001B (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHV000010 | U11 - ERE Feed Gas Compressor-01 Inlet Filter Erection 516-F-101A (Loop 3 - Unit 516) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000030 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-101A (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000140 | U11 - ERE Feed Gas Compressor-02 Inlet Filter Erection 517-F-101B (Loop 2 - Unit 517) | ME | MEHV | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 120 | 0.0021273 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000170 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-201A (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C111136MEHV000180 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-201B (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C111136MEMC000030 | U11 - Miscellaneous Erection (Loop 3 - Unit 518) | ME | MEMC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7440 | 0 | 10610.ME.ER.TN | 124 | 0
C111136MEPA300020 | U11 - Skid Package Installation for ERE Feed Gas Compressor-02 517-C-101 (Loop 2 - Unit 517) 517-C-101-ME | ME | MEPA | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7200 | 0 | 10610.ME.ER.TN | 120 | 0
C111136METC000040 | U11 - Cranes (EOT Crane For ERE Feed Gas Compressor-03) Erection (Loop 3 - Unit 518) 518-EOT-201 in 518-SH-002 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 24 | 0
C112132CIVE000150 | U12 - HP Absorber Column 537-V-101 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13204 | 257.5594 | 10610.CI.CO.M3 | 264.08 | 264.08
C112132CIVE000160 | U12 - Fresh Solvent Filter 537-F-103 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 411 | 0.12537 | 10610.CI.CO.M3 | 5.87 | 4.1929
C112132FPEQ000011 | U12 - Equipment Fireproofing 537-E-101 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18595 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132FPEQ000012 | U12 - Equipment Fireproofing 537-V-101 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20661 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132FPSS000010 | U12 - Main PR Steel Structure Fireproofing (537-PR-101 TO 573-PR-111) | FP | FPSS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49585 | 0 | 10780.FP.FP.MH
C112132STEQ000080 | U12 - 537-STR-004 Structure Erection 1st Phase (pre 537-V-102 Erect) (537-V-102; 537-V-106; 537-E-105A/B; 537-ME-104) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30025 | 0 | 10610.ST.ER.TN | 566.51 | 0
C112132STEQ000090 | U12 - 537-STR-002 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32824 | 0 | 10610.ST.ER.TN | 619.33 | 0
C112132STEQ000110 | U12 - 537-STR-001 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20431 | 0 | 10610.ST.ER.TN | 385.5 | 0
C112132STEQ000120 | U12 - 537-STR-004 Structure Erection 2nd Phase (post 537-V-102 Erect) (537-E-105B) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30025 | 0 | 10610.ST.ER.TN | 566.51 | 0
C112132STPL000120 | U12- Rest of Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3381 | 0 | 10610.ST.PL.TN | 42.26 | 0
C112132STPL000180 | U12 - 537-PR-105 Piperack Platforms, Ladders & Handrails Erection (537-E-102; 537-E-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4018 | 0 | 10610.ST.PL.TN | 50.23 | 0
C112132STPL000190 | U12 - 537-PR-104 Piperack Platforms, Ladders & Handrails Erection (537-E-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4759 | 0 | 10610.ST.PL.TN | 59.49 | 0
C112132STPL000200 | U12 - 537-PR-101_103 Piperack Platforms, Ladders & Handrails Erection (537-E-101) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10610.ST.PL.TN | 24.61 | 0
C112132STPL000220 | U12 - 537-STR-006 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23 | 0 | 10610.ST.PL.TN | 0.29 | 0
C112132STPL000270 | U12 - 537-STR-001 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3427 | 0 | 10610.ST.PL.TN | 42.83 | 0
C112132STPL000300 | U12 - Bund Walls Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5576 | 0 | 10610.ST.PL.TN | 69.7 | 0
C112132STPR000070 | U12 - 537-PB-101 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18828 | 126.1563 | 10610.ST.PR.TN | 355.24 | 49.7296
C112132STPR000080 | U12 - 537-PR-101 Main Piperack Erection (537-E-101) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11737 | 78.6582 | 10610.ST.PR.TN | 221.46 | 87.5828
C112132STPR000100 | U12 - 537-PR-105 Main Piperack Erection (537-E-102; 537-E-104) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23957 | 557.2995 | 10610.ST.PR.TN | 452.03 | 321.274
C111136MEAC000080 | U11 - ERE Feed Gas Compressor-03 After Cooler Pre-Assembly 518-E-201 (Loop 3 - Unit 518) | ME | MEAC1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18226 | 98.1475 | 10780.ME.ME.MH
C111136MECO300020 | U11 - ERE Feed Gas Compressor-02 Erection 517-C-101 (Loop 2 - Unit 517) (800 TON) | ME | MECO2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4720 | 1.7321 | 10610.ME.ER.TN | 118 | 0
C111136MEHM000010 | U11 - Closed Drain Drum Pump with Electrical Motor Erection 516-P-001A (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHM000020 | U11 - Oily Water Sump Pump with Electrical Motor Erection 516-P-002A (Loop 3 - Unit 516) | ME | MEHM1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 4 | 0
C111136MEHV000040 | U11 - Closed Drain Drum Erection 516-V-001 (Loop 3 - Unit 516) inside 516-SU-001 | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 440 | 0 | 10610.ME.ER.TN | 11 | 0
C111136MEHV000150 | U11 - ERE Feed Gas Compressor-01 Inlet Filter Erection 516-F-101B (Loop 3 - Unit 516) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000160 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-101B (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000160 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-101B (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C111136MEHV000180 | U11 - Horizontal Vessels (ERE Feed Gas Compressor-03 Inlet Filter) Erection 518-F-201B (Loop 3 - Unit 518) | ME | MEHV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C111136MEMC000020 | U11 - Miscellaneous Erection (Loop 2 - Unit 517) | ME | MEMC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3780 | 0 | 10610.ME.ER.TN | 63 | 0
C111136MEPA000040 | U11 - Skid Package Installation for 518-C-201 (Loop 3 - Unit 518) 518-C-201-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 38.2914 | 10610.ME.ER.TN | 120 | 60
C111136MEPA000040 | U11 - Skid Package Installation for 518-C-201 (Loop 3 - Unit 518) 518-C-201-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 38.2914 | 10610.ME.ER.TN | 120 | 60
C111136MEPA300010 | U11 - Skid Package Installation for 516-C-101 (Loop 3 - Unit 516) 516-C-101-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 1.9146 | 10610.ME.ER.TN | 120 | 0
C111136MEPA300010 | U11 - Skid Package Installation for 516-C-101 (Loop 3 - Unit 516) 516-C-101-ME | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7200 | 1.9146 | 10610.ME.ER.TN | 120 | 0
C111136MEPA300020 | U11 - Skid Package Installation for ERE Feed Gas Compressor-02 517-C-101 (Loop 2 - Unit 517) 517-C-101-ME | ME | MEPA | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7200 | 0 | 10610.ME.ER.TN | 120 | 0
C111136METC000010 | U11 - EOT Crane For ERE Feed Gas Compressor-01 Erection (Loop 3 - Unit 516) 516-EOT-101 in 516-SH-001 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C111136METC000040 | U11 - Cranes (EOT Crane For ERE Feed Gas Compressor-03) Erection (Loop 3 - Unit 518) 518-EOT-201 in 518-SH-002 | ME | METC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 24 | 0
C111136MEVV000425 | U11 - Vertical Vessels (LP Fuel Gas Balance Drum) Erection 565-V-202 (Loop 3 - Unit 516) | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1480 | 3.2359 | 10610.ME.ER.TN | 37 | 37
C111136MEVV000435 | U11 - Vertical Vessels (ERE Feed Gas Compressor-03 Suction KO Drum) Erection 518-V-101 (Loop 3 - Unit 518) (HL) 800+400 | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6640 | 0 | 10610.ME.ER.TN | 166 | 0
C111137INAI000010 | U11 - Analyzers Equipment Installation (Loop 3 - Unit 516) | IN | INAI | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4028 | 0 | 10610.IN.AI.UN | 1 | 0
C111137INAI000020 | U11 - Analyzers Equipment Installation (Loop 2 - Unit 517) | IN | INAI | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1728 | 0 | 10610.IN.AI.UN | 1 | 0
C111137INCI000010 | U11 - Conduits Installation (Loop 3 - Unit 516) | IN | INCT3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1933 | 0 | 10780.IN.IN.MH
C111137INCI000020 | U11 - Conduits Installation (Loop 2 - Unit 517) | IN | INCT3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 829 | 0 | 10780.IN.IN.MH
C111137INCO000040 | U11 - Communication System Installation (Comp. Shelter 518-SH-001) (Loop 3 - Unit 518) | IN | INCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 915 | 0 | 10780.IN.IN.MH
C111137INCO000060 | U11 - Communication System Installation (Loop 3 - Unit 518) | IN | INCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 915 | 0 | 10780.IN.IN.MH
C111137INCO000070 | U11 - Communication System Installation (Comp. Shelter 518-SH-002) (Loop 3 - Unit 518) | IN | INCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 915 | 0 | 10780.IN.IN.MH
C111137INCT000020 | U11 - Secondary Cable Trays Installation (Loop 3 - Unit 516) | IN | INCT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10443 | 0 | 10610.IN.CT.LM | 680 | 0
C111137INCT000050 | U11 - Secondary Cable Trays Installation (Loop 2 - Unit 517) | IN | INCT2 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4480 | 0 | 10610.IN.CT.LM | 560 | 0
C111137INFC000010 | U11 - Fiber Optic Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INFC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1790 | 0 | 10610.IN.CO.UN | 320 | 0
C111137INFG000050 | U11 - Fire & Gas System Installation (Loop 2 - Unit 517) | IN | INFG | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10780.IN.IN.MH
C111137INFG000060 | U11 - Fire & Gas System Installation (Loop 3 - Unit 518) | IN | INFG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 541 | 0 | 10780.IN.IN.MH
C111137INFO000010 | U11 - Fiber Optic Cable Pulling (Loop 3 - Unit 516) | IN | INFO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2536 | 0 | 10610.IN.FO.LM | 820 | 0
C111137INFO000020 | U11 - Fiber Optic Cable Pulling (Loop 2 - Unit 517) | IN | INFO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1088 | 0 | 10610.IN.FO.LM | 840 | 0
C111137INFO000030 | U11 - Fiber Optic Cable Pulling (Loop 3 - Unit 518) | IN | INFO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2122 | 0 | 10610.IN.FO.LM | 870 | 0
C111137INFS000020 | U11 - Fire Fighting Equipments Installation (Loop 2 - Unit 517) | IN | INFS | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 832 | 0 | 10780.IN.IN.MH
C111137INGC000020 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7758 | 0 | 10610.IN.CO.UN | 490 | 0
C112132STPR000110 | U12 - 537-PR-106 Main Piperack Erection (537-E-102) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24545 | 625.0054 | 10610.ST.PR.TN | 463.11 | 358.2406
C112132STPR000120 | U12 - 537-PR-301 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1455 | 0 | 10610.ST.PR.TN | 27.46 | 0
C112132STSP000040 | U12 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27074 | 0 | 10610.ST.PL.TN | 451.23 | 0
C112133PAFP000040 | U12 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1268 | 0 | 10610.PA.FP.M2 | 5285 | 0
C112133PAPP000040 | U12 - Piping SandBl. & Priming | PA | PAPP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10570 | 60.6081 | 10610.PA.PP.M2 | 5285 | 2050.9921
C112133PAST000040 | U12 - Steel Structure Painting Touch Up | PA | PAST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6050 | 0 | 10780.PA.PA.MH
C112134ELCL000080 | U12 - Electrical Cable Laying | EL | ELCL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102234 | 0 | 10610.EL.PL.LM | 156153.74 | 0
C112134ELCO000070 | U12 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.CO.UN | 432 | 0
C112134ELCO000080 | U12 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55764 | 0 | 10610.EL.CO.UN | 567 | 0
C112134ELEL000045 | U12 - Earthing Works | EL | ELEL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18588 | 0 | 10610.EL.ES.LM | 13808.39 | 0
C112134ELEQ000040 | U12 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.EQ.UN | 238 | 0
C112134ELTI000080 | U12 - Electrical Cable Trays Installation | EL | ELTI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 46470 | 0 | 10610.EL.CT.LM | 8374 | 0
C112134PRMR000040 | U12 - Motor Run | PR | PRMR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4751 | 0 | 10780.PR.PR.MH
C112136MEAC000110 | U12 - Air Coolers (Lean Solvent Cooler) Erection 537-E-102 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24800 | 0 | 10610.ME.ER.TN | 248 | 0
C112136MEAC000120 | U12 - Air Coolers (Lean Solvent Cooler)Pre-Assembly 537-E-102 | ME | MEAC1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25919 | 0 | 10780.ME.ME.MH
C112136MEHE000020 | U12 - Regenerator Reboiler Erection 537-E-105B (537-STR-003) | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C112136MEHE000110 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103B | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHE000111 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103C | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHM000030 | U12 - Horizontal Pump (Lean Solvent Storage Tank Pump) with Electrical Motor Erection 537-P-102A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000040 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C111136METO000010 | U11 - Columns (Ere Feed Gas Compressor-01 Suction Ko Drum) Erection 516-V-101 (Loop 3 - Unit 516) (HL) (800 + 400 TON) | ME | METO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10344 | 7.9034 | 10780.ME.ME.MH
C111136MEVV000010 | U11 - (MP Fuel Gas Balance Drum) 565-V-201 (Loop 3 - Unit 516) | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 3.0633 | 10610.ME.ER.TN | 36 | 36
C111136MEVV000440 | U11 - Vertical Vessels (Ere Feed Gas Compressor -03 Suction Ko Drum) Erection 518-V-201 (Loop 3 - Unit 518) (HL) 800+400 | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6640 | 0 | 10610.ME.ER.TN | 166 | 0
C111136PRBO000010 | U11 - Static Box Up (Loop 3 - Unit 516) | PR | PRBO1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3937 | 0 | 10780.PR.PR.MH
C111137INCO000010 | U11 - Communication System Installation (Loop 3 - Unit 516) | IN | INCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1641 | 0 | 10780.IN.IN.MH
C111137INCT000060 | U11 - Secondary Cable Trays Installation (Loop 3 - Unit 518) | IN | INCT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8737 | 0 | 10610.IN.CT.LM | 880 | 0
C111137INFC000020 | U11 - Fiber Optic Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INFC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 768 | 0 | 10610.IN.CO.UN | 310 | 0
C111137INFC000030 | U11 - Fiber Optic Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INFC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1498 | 0 | 10610.IN.CO.UN | 350 | 0
C111137INFG000030 | U11 - Fire & Gas System Installation (Comp. Shelter 517-SH-001) (Loop 2 - Unit 517) | IN | INFG | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10780.IN.IN.MH
C111137INFG000070 | U11 - Fire & Gas System Installation (Comp. Shelter 518-SH-002) (Loop 3 - Unit 518) | IN | INFG | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 541 | 0 | 10780.IN.IN.MH
C111137INFO000010 | U11 - Fiber Optic Cable Pulling (Loop 3 - Unit 516) | IN | INFO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2536 | 0 | 10610.IN.FO.LM | 820 | 0
C111137INFO000030 | U11 - Fiber Optic Cable Pulling (Loop 3 - Unit 518) | IN | INFO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2122 | 0 | 10610.IN.FO.LM | 870 | 0
C111137INFS000010 | U11 - Fire Fighting Equipments Installation (Loop 3 - Unit 516) | IN | INFS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1939 | 0 | 10780.IN.IN.MH
C111137INGC000030 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INGC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4992 | 0 | 10610.IN.CO.UN | 500 | 0
C111137INGC000050 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INGC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3328 | 0 | 10610.IN.CO.UN | 410 | 0
C111137INHU000020 | U11 - Process Hook Up´s Erection (Loop 3 - Unit 516) | IN | INHU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8205 | 0 | 10780.IN.IN.MH
C111137INHU000030 | U11 - Pneumatic Hook Up´s Erection (Loop 2 - Unit 517) | IN | INHU3 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 767 | 0 | 10780.IN.IN.MH
C111137ININ000010 | U11 - Instruments Installation (Loop 3 - Unit 516) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5967 | 0 | 10610.IN.IN.UN | 610 | 0
C111137ININ000020 | U11 - Instruments Installation (Loop 2 - Unit 517) | IN | ININ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.IN.IN.UN | 610 | 0
C111136MEVV000440 | U11 - Vertical Vessels (Ere Feed Gas Compressor -03 Suction Ko Drum) Erection 518-V-201 (Loop 3 - Unit 518) (HL) 800+400 | ME | MEVV | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6640 | 0 | 10610.ME.ER.TN | 166 | 0
C111136PRBO000020 | U11 - Rotary Box Up (Loop 3 - Unit 516) | PR | PRBO2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7109 | 0 | 10780.PR.PR.MH
C111137INCO000020 | U11 - Communication System Installation (Comp. Shelter 516-SH-001) (Loop 3 - Unit 516) | IN | INCO | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1641 | 0 | 10780.IN.IN.MH
C111137INCT000010 | U11 - Primary Cable Trays Installation (Loop 3 - Unit 516) | IN | INCT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18648 | 0 | 10610.IN.CT.LM | 890 | 0
C111137INCT000020 | U11 - Secondary Cable Trays Installation (Loop 3 - Unit 516) | IN | INCT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10443 | 0 | 10610.IN.CT.LM | 680 | 0
C111137INCT000030 | U11 - Primary Cable Trays Installation (Loop 2 - Unit 517) | IN | INCT1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.IN.CT.LM | 890 | 0
C111137INCT000040 | U11 - Primary Cable Trays Installation (Loop 3 - Unit 518) | IN | INCT1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15602 | 0 | 10610.IN.CT.LM | 930 | 0
C111137INCT000060 | U11 - Secondary Cable Trays Installation (Loop 3 - Unit 518) | IN | INCT2 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8737 | 0 | 10610.IN.CT.LM | 880 | 0
C111137INFC000010 | U11 - Fiber Optic Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INFC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1790 | 0 | 10610.IN.CO.UN | 320 | 0
C111137INFO000020 | U11 - Fiber Optic Cable Pulling (Loop 2 - Unit 517) | IN | INFO | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1088 | 0 | 10610.IN.FO.LM | 840 | 0
C111137INFS000030 | U11 - Fire Fighting Equipments Installation (Loop 3 - Unit 518) | IN | INFS | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1623 | 0 | 10780.IN.IN.MH
C111137INGC000010 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 3 - Unit 516) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11637 | 0 | 10610.IN.CO.UN | 510 | 0
C111137INGC000040 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9736 | 0 | 10610.IN.CO.UN | 740 | 0
C111137INGC000060 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10610.IN.CO.UN | 710 | 0
C111137INHU000010 | U11 - Pneumatic Hook Up´s Erection (Loop 3 - Unit 516) | IN | INHU3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1817 | 0 | 10780.IN.IN.MH
C111137INHU000040 | U11 - Pneumatic Hook Up´s Erection (Loop 3 - Unit 518) | IN | INHU3 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1609 | 0 | 10780.IN.IN.MH
C111137ININ000011 | U11 - Valve Installation (Loop 3 - Unit 516) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5967 | 0 | 10610.IN.IN.UN | 450 | 0
C111137ININ000020 | U11 - Instruments Installation (Loop 2 - Unit 517) | IN | ININ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.IN.IN.UN | 610 | 0
C111137ININ000030 | U11 - Instruments Installation (Loop 3 - Unit 518) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4993 | 0 | 10610.IN.IN.UN | 910 | 0
C111137INGC000030 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 2 - Unit 517) | IN | INGC | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4992 | 0 | 10610.IN.CO.UN | 500 | 0
C111137INGC000040 | U11 - Multi Pair Cable Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9736 | 0 | 10610.IN.CO.UN | 740 | 0
C111137INGC000060 | U11 - Single Pair Cable Gland & Conn./Testing (Loop 3 - Unit 518) | IN | INGC | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10610.IN.CO.UN | 710 | 0
C111137INHU000050 | U11 - Process Hook Up´s Erection (Loop 2 - Unit 517) | IN | INHU1 | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3520 | 0 | 10780.IN.IN.MH
C111137INHU000060 | U11 - Process Hook Up´s Erection (Loop 3 - Unit 518) | IN | INHU1 | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6865 | 0 | 10780.IN.IN.MH
C111137ININ000011 | U11 - Valve Installation (Loop 3 - Unit 516) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5967 | 0 | 10610.IN.IN.UN | 450 | 0
C111137ININ000021 | U11 - Valve Installation (Loop 2 - Unit 517) | IN | ININ | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.IN.IN.UN | 500 | 0
C111137INIP000011 | U11 - Valve Calibration (Loop 3 - Unit 516) | IN | INIP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1939 | 0 | 10780.IN.IN.MH
C111137INIP000020 | U11 - Instruments Calibration (Loop 2 - Unit 517) | IN | INIP | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 832 | 0 | 10780.IN.IN.MH
C111137INJB000010 | U11 - Junction Boxes & Local Panels Install. (Loop 3 - Unit 516) | IN | INJB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7758 | 0 | 10780.IN.IN.MH
C111137INJB000020 | U11 - Junction Boxes & Local Panels Install. (Loop 2 - Unit 517) | IN | INJB | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3328 | 0 | 10780.IN.IN.MH
C111137INML000010 | U11- Multi Pair Cable Pulling (Loop 3 - Unit 516) | IN | INML | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23273 | 224.0424 | 10610.IN.MC.LM | 120720.91 | 42252.3185
C111137INML000030 | U11- Multi Pair Cable Pulling (Loop 3 - Unit 518) | IN | INML | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19471 | 0 | 10610.IN.MC.LM | 100542.87 | 0
C111137INSL000010 | U11 - Single Pair Cable Pulling (Loop 3 - Unit 516) | IN | INSL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18648 | 0 | 10610.IN.SC.LM | 612.3 | 0
C111137INSL000020 | U11 - Single Pair Cable Pulling (Loop 2 - Unit 517) | IN | INSL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.IN.SC.LM | 612.3 | 0
C1120PRPRPL000040 | U12 - Punch List | PR | PRPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10809 | 0 | 10780.PR.PR.MH
C112131ISEQ000010 | U12 - Equipment Insulation | IS | ISEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3257 | 0 | 10610.IS.EQ.M2 | 3053 | 0
C112131ISPI000040 | U12 - Piping Insulation | IS | ISPI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 43221 | 0 | 10780.IS.IS.MH
C112131PIBB000040 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-001 to 537-STR-002 | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIBB000070 | U12 - Big Bore Piping A/Equip. Erection - From Sumps (537-SU-101/103/104) to Batt. Limit | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112136MEHM000110 | U12 - Horizontal Pump (Hydrocarbon Drain Sump Pump) with Electrical Motor Erection 537-P-113A in 537-SU-103 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000140 | U12 - Horizontal Pump (Solvent Drain Sump Pump) with Electrical Motor Erection 537-P-108A in 537-SU-101 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000150 | U12 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 537-P-112A in 537-SU-104 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000170 | U12 - Horizontal Pump (Absorber Water Wash Make-Up Pump) with Electrical Motor Erection 537-P-121A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000190 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000220 | U12 - Horizontal Pump (Steam Condensate Pump) with Electrical Motor Erection 537-P-107B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000240 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000290 | U12 - Horizontal Pump (Solvent Drain Sump Pump) with Electrical Motor Erection 537-P-108B in 537-SU-101 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000300 | U12 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 537-P-112B in 537-SU-104 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHV000040 | U12 - Horizontal Vessels (Solvent Drain Sump Filter) Erection 537-F-103 | ME | MEHV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C112136MEPA000060 | U12 - Antifoam Package Installation 537-ME-102 | ME | MEPA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C112136METO000020 | U12 - Columns (Regenerator) Erection 537-V-102 (HL) (1600 + 800 TON) | ME | METO1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20940 | 647.7684 | 10610.ME.ER.TN | 349 | 349
C112136MEVV000040 | U12 - Vertical Vessels (Solvent Reflux Drum) Erection 537-V-105 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C112136MEVV000060 | U12 - Vertical (Sweet Gas Ko Drum) Vessels Erection 537-V-103 (HL) (800 + 400 TON) | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5720 | 0 | 10610.ME.ER.TN | 143 | 0
C112136MEVV000210 | U12 - Vertical Vessels (Hydrocarbon Drain Sump Drum) Erection 537-V-113 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 880 | 0 | 10610.ME.ER.TN | 22 | 0
C112136MEVV000220 | U12 - Vertical Vessels (Solvent Drain Sump Drum) Erection 537-V-107 / 537-V-108A/B | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C112136MEVV000240 | U12 - Vertical Vessels (Make-Up Water Break Tank) Erection 537-V-121 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C111137ININ000031 | U11 - Valve Installation (Loop 3 - Unit 518) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4993 | 0 | 10610.IN.IN.UN | 820 | 0
C111137INIP000031 | U11 - Valve Calibration (Loop 3 - Unit 518) | IN | INIP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1623 | 0 | 10780.IN.IN.MH
C111137INJB000030 | U11 - Junction Boxes & Local Panels Install. (Loop 3 - Unit 518) | IN | INJB | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10780.IN.IN.MH
C111137INML000020 | U11- Multi Pair Cable Pulling (Loop 2 - Unit 517) | IN | INML | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9984 | 0 | 10610.IN.MC.LM | 51440.94 | 0
C111137INSL000010 | U11 - Single Pair Cable Pulling (Loop 3 - Unit 516) | IN | INSL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18648 | 0 | 10610.IN.SC.LM | 612.3 | 0
C111137INSL000020 | U11 - Single Pair Cable Pulling (Loop 2 - Unit 517) | IN | INSL | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.IN.SC.LM | 612.3 | 0
C111137INSL000030 | U11 - Single Pair Cable Pulling (Loop 3 - Unit 518) | IN | INSL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15602 | 0 | 10610.IN.SC.LM | 968.55 | 0
C1120PRPRWT000040 | U12 - Walkthrough | PR | PRWT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4632 | 0 | 10780.PR.PR.MH
C112131ISEQ000010 | U12 - Equipment Insulation | IS | ISEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3257 | 0 | 10610.IS.EQ.M2 | 3053 | 0
C112131PIBB000050 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-005 to Sumps | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIBB000060 | U12 - Big Bore Piping A/Equip. Erection - From 537-STR-003 to 537-STR-004 | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIBB000070 | U12 - Big Bore Piping A/Equip. Erection - From Sumps (537-SU-101/103/104) to Batt. Limit | PI | PIBB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66374 | 0 | 10610.PI.BB.DI | 6637.45 | 0
C112131PIRA000040 | U12 - Piping Erection on Rack 537-PB-101 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000070 | U12 - Piping Erection on Rack 537-PR-105 (537-E-102; 537-E-104) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA130000 | U12 - Piping Erection on Rack 537-PR-301 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA160000 | U12 - Piping Erection on Rack 537-PR-304 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PISB000040 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-001 to 537-STR-002 | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISB000050 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-005 to Sumps | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISB000060 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-003 to 537-STR-004 | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C111137ININ000030 | U11 - Instruments Installation (Loop 3 - Unit 518) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4993 | 0 | 10610.IN.IN.UN | 910 | 0
C111137INIP000010 | U11 - Instruments Calibration (Loop 3 - Unit 516) | IN | INIP | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1939 | 0 | 10780.IN.IN.MH
C111137INML000010 | U11- Multi Pair Cable Pulling (Loop 3 - Unit 516) | IN | INML | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23273 | 224.0424 | 10610.IN.MC.LM | 120720.91 | 42252.3185
C111137INSL000030 | U11 - Single Pair Cable Pulling (Loop 3 - Unit 518) | IN | INSL | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15602 | 0 | 10610.IN.SC.LM | 968.55 | 0
C111137MEMC000010 | U11 - Miscellaneous Instrumetation (Unit 516) | IN | ININ | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5967 | 0 | 10780.IN.IN.MH
C111137PRLT000010 | U11 - Loops Testing (Loop 3 - Unit 516) | PR | PRLT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22113 | 0 | 10780.PR.PR.MH
C111137PRLT000020 | U11 - Loops Testing (Loop 2 - Unit 517) | PR | PRLT | 11 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9485 | 0 | 10780.PR.PR.MH
C111137PRLT000030 | U11 - Loops Testing (Loop 3 - Unit 518) | PR | PRLT | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18513 | 0 | 10780.PR.PR.MH
C112131NIPR000050 | U12 - Nitrogen Purging & Inerting (Unit 537) | PR | PRFL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4399 | 0 | 10780.PR.PR.MH
C112131PIPR000040 | U12 - Piping Prefabrication | PI | PIPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 492310 | 220487.0326 | 10610.PI.FB.DI | 123077.4 | 66374.6715
C112131PIPR000040 | U12 - Piping Prefabrication | PI | PIPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 492310 | 220487.0326 | 10610.PI.FB.DI | 123077.4 | 66374.6715
C112131PIPR000050 | U12 - UG Piping Prefabrication | PI | PIPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16984 | 363.2368 | 10610.PI.FB.DI | 4246 | 4367.326
C112131PIRA000050 | U12 - Piping Erection on Rack 537-PR-101_103 (537-E-101) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000060 | U12 - Piping Erection on Rack 537-PR-104 (537-E-104) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000080 | U12 - Piping Erection on Rack 537-PR-106 (537-E-102) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA140000 | U12 - Piping Erection on Rack 537-PR-302 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA150000 | U12 - Piping Erection on Rack 537-PR-303 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PISB000050 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-005 to Sumps | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISB000070 | U12 - Small Bore Piping A/Equip. Erection - From Sumps (537-SU-101/103/104) to Batt. Limit | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISU000070 | U12 - Piping Supports Prefabrication | PI | PISU1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 62488 | 1959.2634 | 10610.PI.PU.TN | 240.34 | 66.7965
C112131PIST000020 | U12 - Manifolds Installation | PI | PIST1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3276 | 0 | 10780.PI.PI.MH
C112131PRBO000080 | U12 - Rotary Box Up | PR | PRBO2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14254 | 0 | 10780.PR.PR.MH
C112131PRFL000040 | U12 - Piping Flushing/Blowing | PR | PRFL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10998 | 0 | 10610.PR.FL.DI | 180783 | 0
C112131PRHT000040 | U12 - Piping Hydrotesting | PR | PRHT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 86216 | 0 | 10610.PR.HT.DI | 180783 | 0
C112131PRRE000040 | U12 - Piping Reinstatement | PR | PRRE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 90919 | 0 | 10610.PR.RE.DI | 180783 | 0
C112132CICT000130 | U12 - Electrical earth Trenches Execution | CI | CICT2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2003 | 0.69361 | 10610.CI.ET.M3 | 500.87 | 460.8004
C112132CIDB000045 | U12 - Duct Banks Precast Fabrication | CI | CIDB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1103 | 1.5601 | 10780.CI.CI.MH
C112132CIGT000070 | U12 - Equipment Grouting Execution | CI | CIGT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4260 | 0.92438 | 10780.CI.CI.MH
C112132CIGT000080 | U12 - Steel Structure Grouting Execution | CI | CIGT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4260 | 0 | 10780.CI.CI.MH
C112132CIMF000040 | U12 - Miscellaneous Foundations Execution | CI | CIMF | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8501 | 100.4494 | 10610.CI.CO.M3 | 141.69 | 141.69
C112132CIPR000070 | U12 - Pipe Rack 537-PR-105 Foundations Execution (537-E-102; 537-E-104) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26904 | 1069.3013 | 10610.CI.CO.M3 | 538.08 | 538.08
C112132CIPR000070 | U12 - Pipe Rack 537-PR-105 Foundations Execution (537-E-102; 537-E-104) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26904 | 1069.3013 | 10610.CI.CO.M3 | 538.08 | 538.08
C112132CIPR000080 | U12 - Pipe Rack 537-PR-106 Foundations Execution (537-E-102) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28747 | 1220.7983 | 10610.CI.CO.M3 | 574.93 | 574.93
C112132CIPR000100 | U12 - Pipe Rack 537-PB-101 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63499 | 5918.9779 | 10610.CI.CO.M3 | 1269.98 | 1269.9851
C112132CIPR000110 | U12 - Pipe Rack 537-PR-101 / 537-PR-102 / 537-PR-103 Foundations Execution (537-E-101) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 65915 | 6377.9067 | 10610.CI.CO.M3 | 1318.29 | 1318.2953
C112132CIPR000110 | U12 - Pipe Rack 537-PR-101 / 537-PR-102 / 537-PR-103 Foundations Execution (537-E-101) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 65915 | 6377.9067 | 10610.CI.CO.M3 | 1318.29 | 1318.2953
C112132CIPV000110 | U12 - Gravel Paving Execution | CI | CIPV2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7991 | 0 | 10610.CI.GV.M2 | 13319 | 0
C112132CIRD000040 | U12 - Road Early Base & Sub Base Execution | CI | CIRD1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5000 | 0 | 10780.CI.CI.MH
C112132CIRE000060 | U12 - Fresh Solvent Transfer Pump 537-P-122A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 354 | 0.020839 | 10610.CI.CO.M3 | 5.06 | 0
C112132CIRE000060 | U12 - Fresh Solvent Transfer Pump 537-P-122A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 354 | 0.020839 | 10610.CI.CO.M3 | 5.06 | 0
C112131PIPR000050 | U12 - UG Piping Prefabrication | PI | PIPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16984 | 363.2368 | 10610.PI.FB.DI | 4246 | 4367.326
C112131PIRA000040 | U12 - Piping Erection on Rack 537-PB-101 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA000080 | U12 - Piping Erection on Rack 537-PR-106 (537-E-102) | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA120000 | U12 - Piping Erection on Rack 537-PR-201 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA140000 | U12 - Piping Erection on Rack 537-PR-302 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA150000 | U12 - Piping Erection on Rack 537-PR-303 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PIRA160000 | U12 - Piping Erection on Rack 537-PR-304 | PI | PIRA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15418 | 0 | 10610.PI.PR.DI | 1713.14 | 0
C112131PISB000040 | U12 - Small Bore Piping A/Equip. Erection - From 537-STR-001 to 537-STR-002 | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PISB000070 | U12 - Small Bore Piping A/Equip. Erection - From Sumps (537-SU-101/103/104) to Batt. Limit | PI | PISB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6598 | 0 | 10610.PI.SB.DI | 599.79 | 0
C112131PIST000010 | U12 - Piping Steam Tracing Installation | PI | PIST2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4888 | 0 | 10780.PI.PI.MH
C112131PIUG000040 | U12 - Piping Erection UG | PI | PIUG | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2289 | 0 | 10610.PI.UG.DI | 1526 | 0
C112131PRRE000040 | U12 - Piping Reinstatement | PR | PRRE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 90919 | 0 | 10610.PR.RE.DI | 180783 | 0
C112132CIBW000020 | U12 - Concrete Bund Walls Execution for Fresh Solvent Storage Tank (537-TK-102) | CI | CIBW1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7656 | 86.5905 | 10610.CI.CO.M3 | 127.6 | 127.6
C112132CIBW000020 | U12 - Concrete Bund Walls Execution for Fresh Solvent Storage Tank (537-TK-102) | CI | CIBW1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7656 | 86.5905 | 10610.CI.CO.M3 | 127.6 | 127.6
C112132CICT000140 | U12 - Instrument earth Trenches Execution | CI | CICT3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1379 | 0.29357 | 10610.CI.ET.M3 | 344.75 | 317.17
C112132CIDB000055 | U12 - Duct Banks Precast Installation | CI | CIDB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16100 | 344.1658 | 10610.CI.CO.M3 | 321.99 | 293.0121
C112132CIDB000055 | U12 - Duct Banks Precast Installation | CI | CIDB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16100 | 344.1658 | 10610.CI.CO.M3 | 321.99 | 293.0121
C112132CIDM000070 | U12 - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29114 | 704.2681 | 10610.CI.CO.M3 | 582.29 | 335.4796
C112132CIGR000040 | U12 - Grounding Network Execution | CI | CIGR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6665 | 6.7261 | 10610.CI.GR.LM | 11107.56 | 0
C112132CIGR000040 | U12 - Grounding Network Execution | CI | CIGR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6665 | 6.7261 | 10610.CI.GR.LM | 11107.56 | 0
C112137INCI000040 | U12 - Conduits Installation | IN | INCT3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4078 | 0 | 10780.IN.IN.MH
C112137INCO000070 | U12 - Communication System Installation | IN | INCO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6923 | 0 | 10780.IN.IN.MH
C112137INCT000080 | U12 - Secondary Cable Trays Installation | IN | INCT2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22028 | 0 | 10610.IN.CT.LM | 570 | 0
C112137INFC000040 | U12 - Fiber Optic Gland & Conn./Testing | IN | INFC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3776 | 0 | 10610.IN.CO.UN | 310 | 0
C112137INGC000070 | U12 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24545 | 0 | 10610.IN.CO.UN | 500 | 0
C112137ININ000040 | U12 - Instruments Installation | IN | ININ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12587 | 0 | 10610.IN.IN.UN | 750 | 0
C112137INIP000040 | U12 - Instruments Calibration | IN | INIP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4091 | 0 | 10780.IN.IN.MH
C112137INJB000040 | U12 - Junction Boxes & Local Panels Install | IN | INJB | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16364 | 0 | 10780.IN.IN.MH
C112137INSL000040 | U12 - Single Pair Cable Pulling | IN | INSL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39336 | 0 | 10610.IN.SC.LM | 79333.94 | 0
C112137MEMC000070 | U12 - Miscellaneous Instrumetation | IN | ININ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12587 | 0 | 10780.IN.IN.MH
C1130PRPRPL200010 | U13 - Punch List (Train 2) | PR | PRPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23708 | 0 | 10780.PR.PR.MH
C1130PRPRWT200010 | U13 - Walkthrough (Train 2) | PR | PRWT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10161 | 0 | 10780.PR.PR.MH
C113131ISPI100010 | U13 - Piping Insulation (Train 1) | IS | ISPI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 165306 | 0 | 10610.IS.PI.M2 | 29090 | 0
C113131ISPI300010 | U13 - Piping Insulation (Train 3) | IS | ISPI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63648 | 0 | 10610.IS.PI.M2 | 29090 | 0
C113131PIBB100010 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-201 to 542-PR-301 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100030 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-301 to 542-PR-401 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100040 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-401 to 542-PR-501 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100050 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-501 to 542-PR-601 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100060 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-601 to 542-PR-701 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100080 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-801 to 542-PR-901 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C112131PISU000080 | U12 - Piping Supports Erection | PI | PISU2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 108153 | 0 | 10610.PI.SU.TN | 240.34 | 0
C112131PIUG000040 | U12 - Piping Erection UG | PI | PIUG | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2289 | 0 | 10610.PI.UG.DI | 1526 | 0
C112131PRBO000070 | U12 - Static Box Up | PR | PRBO1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16126 | 0 | 10780.PR.PR.MH
C112132CIBW000010 | U12 - Concrete Bund Walls Execution for Lean Solvent Storage Tank (537-TK-101) | CI | CIBW1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7656 | 8.4426 | 10610.CI.CO.M3 | 127.6 | 0
C112132CIBW000010 | U12 - Concrete Bund Walls Execution for Lean Solvent Storage Tank (537-TK-101) | CI | CIBW1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7656 | 8.4426 | 10610.CI.CO.M3 | 127.6 | 0
C112132CICT000130 | U12 - Electrical earth Trenches Execution | CI | CICT2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2003 | 0.69361 | 10610.CI.ET.M3 | 500.87 | 460.8004
C112132CICT000150 | U12 - Covered Concrete Trenches Execution | CI | CICT1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44174 | 947.9372 | 10610.CI.CO.M3 | 883.47 | 273.0717
C112132CIMF000040 | U12 - Miscellaneous Foundations Execution | CI | CIMF | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8501 | 100.4494 | 10610.CI.CO.M3 | 141.69 | 141.69
C112132CIPE000030 | U12 - Lean Solvent Filtration Package 537-ME-101 Foundation Execution | CI | CIPE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12352 | 19.7211 | 10610.CI.CO.M3 | 247.03 | 0
C112132CIPR000081 | U12 - Pipe Rack 537-PR-302 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8288 | 60.28 | 10610.CI.CO.M3 | 138.14 | 46.4206
C112132CIPR000081 | U12 - Pipe Rack 537-PR-302 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8288 | 60.28 | 10610.CI.CO.M3 | 138.14 | 46.4206
C112132CIPR000083 | U12 - Pipe Rack 537-PR-303 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1374 | 1.6078 | 10610.CI.CO.M3 | 22.9 | 7.69
C112132CIPR000090 | U12 - Pipe Rack 537-PR-301 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4371 | 3.1753 | 10610.CI.CO.M3 | 72.85 | 0
C112132CIPR000120 | U12 - Pipe Rack 537-PR-104 Foundations Execution (537-E-104) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30766 | 1398.3034 | 10610.CI.CO.M3 | 615.31 | 615.31
C112132CIPS000070 | U12 - 537-SU-103 Hydrocarbon Drain Sump Pit Constrution (537-V-113; 537-P-113A) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 18.2937 | 10610.CI.CO.M3 | 120.34 | 24.0704
C112132CIPS000080 | U12 - 537-SU-104 Oily Water Sump Constrution (537-P-112A/B) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 12.9727 | 10610.CI.CO.M3 | 120.34 | 0
C112132CIPV000100 | U12 - Concrete Paving Execution | CI | CIPV1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 43190 | 310.0204 | 10610.CI.PV.M2 | 23994.72 | 0
C112132CIPV000100 | U12 - Concrete Paving Execution | CI | CIPV1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 43190 | 310.0204 | 10610.CI.PV.M2 | 23994.72 | 0
C112132CIRE000140 | U12 - Sweet Gas Water Wash Pump 537-P-104B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 607 | 0.061224 | 10610.CI.CO.M3 | 8.67 | 0
C112132CIRE000150 | U12 - Lean Solvent Circulation Pump 537-P-101B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C112132CIPE000040 | U12 - AntiFoam Injection Package 537-ME-102 Foundation Execution | CI | CIPE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1639 | 0.34728 | 10610.CI.CO.M3 | 27.32 | 0
C112132CIPE000040 | U12 - AntiFoam Injection Package 537-ME-102 Foundation Execution | CI | CIPE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1639 | 0.34728 | 10610.CI.CO.M3 | 27.32 | 0
C112132CIPR000080 | U12 - Pipe Rack 537-PR-106 Foundations Execution (537-E-102) | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28747 | 1220.7983 | 10610.CI.CO.M3 | 574.93 | 574.93
C112132CIPR000082 | U12 - Pipe Rack 537-PR-304 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2542 | 6.289 | 10610.CI.CO.M3 | 42.36 | 28.8001
C112132CIPR000082 | U12 - Pipe Rack 537-PR-304 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2542 | 6.289 | 10610.CI.CO.M3 | 42.36 | 28.8001
C112132CIPR000090 | U12 - Pipe Rack 537-PR-301 Foundations Execution | CI | CIPR1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4371 | 3.1753 | 10610.CI.CO.M3 | 72.85 | 0
C112132CIPS000060 | U12 - 537-SU-101 Solvent Drain Sump Pit Constrution (537-V-107; 537-P-108A/B) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 18.2937 | 10610.CI.CO.M3 | 120.34 | 24.0704
C112132CIPS000070 | U12 - 537-SU-103 Hydrocarbon Drain Sump Pit Constrution (537-V-113; 537-P-113A) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 18.2937 | 10610.CI.CO.M3 | 120.34 | 24.0704
C112132CIPS000080 | U12 - 537-SU-104 Oily Water Sump Constrution (537-P-112A/B) | CI | CIPS1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7221 | 12.9727 | 10610.CI.CO.M3 | 120.34 | 0
C112132CIPV000110 | U12 - Gravel Paving Execution | CI | CIPV2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7991 | 0 | 10610.CI.GV.M2 | 13319 | 0
C112132CIRE000080 | U12 - Lean Solvent Pump 537-P-106A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIRE000080 | U12 - Lean Solvent Pump 537-P-106A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIRE000090 | U12 - Lean Solvent Storage Tank Pump 537-P-102A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 447 | 0.033178 | 10610.CI.CO.M3 | 6.38 | 0
C112132CIRE000100 | U12 - Steam Condensate Pump 537-P-107A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 370 | 0.022771 | 10610.CI.CO.M3 | 5.29 | 0
C112132CIRE000100 | U12 - Steam Condensate Pump 537-P-107A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 370 | 0.022771 | 10610.CI.CO.M3 | 5.29 | 0
C112132CIRE000130 | U12 - Lean Solvent Circulation Pump 537-P-101A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C112132CIRE000230 | U12 - Lean Solvent Pump 537-P-106B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIRE000260 | U12 - Solvent Reflux Pump 537-P-103C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000280 | U12 - Lean Solvent Storage Tank Pump 537-P-102B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 447 | 0.033178 | 10610.CI.CO.M3 | 6.38 | 0
C112132CIRE000070 | U12 - Solvent Reflux Pump 537-P-103A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000070 | U12 - Solvent Reflux Pump 537-P-103A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000090 | U12 - Lean Solvent Storage Tank Pump 537-P-102A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 447 | 0.033178 | 10610.CI.CO.M3 | 6.38 | 0
C112132CIRE000110 | U12 - Sweet Gas Water Wash Pump 537-P-104A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 607 | 0.061224 | 10610.CI.CO.M3 | 8.67 | 0
C112132CIRE000110 | U12 - Sweet Gas Water Wash Pump 537-P-104A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 607 | 0.061224 | 10610.CI.CO.M3 | 8.67 | 0
C112132CIRE000150 | U12 - Lean Solvent Circulation Pump 537-P-101B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C112132CIRE000160 | U12 - Lean Solvent Circulation Pump 537-P-101C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4249 | 3.0004 | 10610.CI.CO.M3 | 70.81 | 0
C112132CIRE000170 | U12 - Absorber Water Wash Make-up Pump 537-P-121A Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0.069587 | 10610.CI.CO.M3 | 9.25 | 0
C112132CIRE000180 | U12 - Absorber Water Wash Make-up Pump 537-P-121B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0.069587 | 10610.CI.CO.M3 | 9.25 | 0
C112132CIRE000190 | U12 - Steam Condensate Pump 537-P-107B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 370 | 0.022771 | 10610.CI.CO.M3 | 5.29 | 0
C112132CIRE000250 | U12 - Solvent Reflux Pump 537-P-103B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000250 | U12 - Solvent Reflux Pump 537-P-103B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000260 | U12 - Solvent Reflux Pump 537-P-103C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 207 | 0.0071282 | 10610.CI.CO.M3 | 2.96 | 0
C112132CIRE000280 | U12 - Lean Solvent Storage Tank Pump 537-P-102B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 447 | 0.033178 | 10610.CI.CO.M3 | 6.38 | 0
C112132CIST000110 | U12 - 537-STR-004 Structure Foundation Execution (537-V-102; 537-V-106; 537-E-105A/B; 537-ME-104) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 71315 | 7360.3845 | 10610.CI.CO.M3 | 1426.29 | 1418.7656
C112132CIST000120 | U12 - 537-STR-002 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30510 | 1323.0478 | 10610.CI.CO.M3 | 610.2 | 610.2
C112132CIST000160 | U12 - Shelters Foundation Execution 537-ANS-402 | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4315 | 1.8565 | 10610.CI.CO.M3 | 71.91 | 0
C112132CIUG000100 | U12 - UG GRE Pipe Installation (CD) | CI | CIUG2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12886 | 106.9557 | 10610.CI.UG.LM | 644.32 | 644.3198
C112132CIVE000090 | U12 - Solvent Reflux Drum 537-V-105 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2002 | 3.3789 | 10610.CI.CO.M3 | 33.37 | 23.8399
C112132CISF000010 | U12 - Stairs & Small Foundations Execution | CI | CISF | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 934 | 0.14495 | 10610.CI.CO.M3 | 13.34 | 0
C112132CISF000010 | U12 - Stairs & Small Foundations Execution | CI | CISF | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 934 | 0.14495 | 10610.CI.CO.M3 | 13.34 | 0
C112132CIST000100 | U12 - 537-STR-001 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31831 | 1493.3898 | 10610.CI.CO.M3 | 636.61 | 636.61
C112132CIST000111 | U12 - 537-STR-007 Structure Foundation Execution (ESD Platform) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1502 | 0.38155 | 10610.CI.CO.M3 | 25.03 | 0
C112132CIST000120 | U12 - 537-STR-002 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30510 | 1323.0478 | 10610.CI.CO.M3 | 610.2 | 610.2
C112132CIST000130 | U12 - 537-STR-003 Structure Foundation Execution (537-P-101A/B/C) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13680 | 265.4483 | 10610.CI.CO.M3 | 273.59 | 273.5899
C112132CIST000130 | U12 - 537-STR-003 Structure Foundation Execution (537-P-101A/B/C) | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13680 | 265.4483 | 10610.CI.CO.M3 | 273.59 | 273.5899
C112132CIST000160 | U12 - Shelters Foundation Execution 537-ANS-402 | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4315 | 1.8565 | 10610.CI.CO.M3 | 71.91 | 0
C112132CIST000170 | U12 - 537-STR-005 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6466 | 48.9189 | 10610.CI.CO.M3 | 107.77 | 90.5296
C112132CIST000180 | U12 - 537-STR-006 Structure Foundation Execution | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 411 | 0.18646 | 10610.CI.CO.M3 | 5.87 | 4.9308
C112132CITF000020 | U12 - Fresh Solvent Storage Tank 537-TK-102 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1281 | 2.4242 | 10610.CI.CO.M3 | 21.35 | 21.35
C112132CITF000030 | U12 - Make-Up Water Break Tank 537-V-121 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 680 | 0.33442 | 10610.CI.CO.M3 | 9.72 | 4.8003
C112132CIVE000120 | U12 - Regenerator 537-V-102 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10942 | 176.8658 | 10610.CI.CO.M3 | 182.36 | 182.36
C112132FPEQ000011 | U12 - Equipment Fireproofing 537-E-101 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18595 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132FPEQ000012 | U12 - Equipment Fireproofing 537-V-101 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20661 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132SPSP000030 | U12 - U/G Detection Works and re-routing of existing services | SP | SPSP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1541 | 3.5081 | 10780.SP.SP.MH
C112132STEQ000070 | U12 - 537-STR-005 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5926 | 0 | 10610.ST.ER.TN | 111.81 | 0
C112132STEQ000090 | U12 - 537-STR-002 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32824 | 0 | 10610.ST.ER.TN | 619.33 | 0
C112132STEQ000100 | U12 - 537-STR-003 Structure Erection (537-P-101A/B/C) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6497 | 0 | 10610.ST.ER.TN | 122.58 | 0
C112132STEQ000120 | U12 - 537-STR-004 Structure Erection 2nd Phase (post 537-V-102 Erect) (537-E-105B) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30025 | 0 | 10610.ST.ER.TN | 566.51 | 0
C112132CIRE000240 | U12 - Lean Solvent Pump 537-P-106C Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1362 | 0.30834 | 10610.CI.CO.M3 | 19.46 | 0
C112132CIRE000270 | U12 - Fresh Solvent Transfer Pump 537-P-122B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 354 | 0.020839 | 10610.CI.CO.M3 | 5.06 | 0
C112132CIRE000270 | U12 - Fresh Solvent Transfer Pump 537-P-122B Foundation Execution | CI | CIRE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 354 | 0.020839 | 10610.CI.CO.M3 | 5.06 | 0
C112132CIST000150 | U12 - Shelters Foundation Execution 537-ANS-401 | CI | CIST | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4769 | 2.2681 | 10610.CI.CO.M3 | 79.49 | 0
C112132CITF000010 | U12 - Lean Solvent Storage Tank 537-TK-101 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5388 | 42.8866 | 10610.CI.CO.M3 | 89.8 | 89.8
C112132CITF000020 | U12 - Fresh Solvent Storage Tank 537-TK-102 Foundation Execution | CI | CITF1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1281 | 2.4242 | 10610.CI.CO.M3 | 21.35 | 21.35
C112132CIUG000100 | U12 - UG GRE Pipe Installation (CD) | CI | CIUG2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12886 | 106.9557 | 10610.CI.UG.LM | 644.32 | 644.3198
C112132CIUG000110 | U12 - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37799 | 237.4546 | 10610.CI.CO.M3 | 755.98 | 0
C112132CIUG000120 | U12 - UG Civil Works | CI | CIUG1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34900 | 485.8263 | 10780.CI.CI.MH
C112132CIUG000140 | U12 - UG Pipe Installation (OD) | CI | CIUG2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51170 | 2373.4787 | 10610.CI.UG.LM | 2558.52 | 1842.1257
C112132CIVE000090 | U12 - Solvent Reflux Drum 537-V-105 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2002 | 3.3789 | 10610.CI.CO.M3 | 33.37 | 23.8399
C112132CIVE000120 | U12 - Regenerator 537-V-102 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10942 | 176.8658 | 10610.CI.CO.M3 | 182.36 | 182.36
C112132CIVE000170 | U12 - Absorber Filter Inlet Coalescer 537-F-101 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1138 | 1.9123 | 10610.CI.CO.M3 | 16.25 | 16.2499
C112132CIVE000180 | U12 - Rich/Lean Solvent Exchanger 537-E-103A/B Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3563 | 2.1097 | 10610.CI.CO.M3 | 59.38 | 0
C112132CIVE000180 | U12 - Rich/Lean Solvent Exchanger 537-E-103A/B Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3563 | 2.1097 | 10610.CI.CO.M3 | 59.38 | 0
C112132FPEQ000013 | U12 - Equipment Fireproofing 537-V-103 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20661 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132FPSS000100 | U12 - Steel Structures Fireproofing (537-STR-001 TO 537-STR-007) | FP | FPSS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49585 | 0 | 10610.FP.ST.M2 | 17723.88 | 0
C112132STEQ000080 | U12 - 537-STR-004 Structure Erection 1st Phase (pre 537-V-102 Erect) (537-V-102; 537-V-106; 537-E-105A/B; 537-ME-104) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30025 | 0 | 10610.ST.ER.TN | 566.51 | 0
C112132STEQ000100 | U12 - 537-STR-003 Structure Erection (537-P-101A/B/C) | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6497 | 0 | 10610.ST.ER.TN | 122.58 | 0
C112132STEQ000110 | U12 - 537-STR-001 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20431 | 0 | 10610.ST.ER.TN | 385.5 | 0
C112132STEQ120000 | U12 - 537-STR-007 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 966 | 0 | 10610.ST.ER.TN | 18.22 | 0
C112132STPL000110 | U12 - Pits Platforms, Ladders & Handrails Erection (537-SU-101; 537-SU-103; 537-SU-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1678 | 0 | 10610.ST.PL.TN | 20.98 | 0
C112132STPL000120 | U12- Rest of Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3381 | 0 | 10610.ST.PL.TN | 42.26 | 0
C112132STPL000130 | U12 - 537-PR-304 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 86 | 0 | 10610.ST.PL.TN | 1.07 | 0
C112132STPL000150 | U12 - 537-PR-302 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 318 | 0 | 10610.ST.PL.TN | 3.98 | 0
C112132STPL000160 | U12 - 537-PR-301 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 244 | 0 | 10610.ST.PL.TN | 3.05 | 0
C112132STPL000170 | U12 - 537-PR-106 Piperack Platforms, Ladders & Handrails Erection (537-E-102) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4116 | 0 | 10610.ST.PL.TN | 51.46 | 0
C112132STPL000210 | U12 - 537-PB-101 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3158 | 0 | 10610.ST.PL.TN | 39.47 | 0
C112132STPL000260 | U12 - 537-STR-003 Piperack Platforms, Ladders & Handrails Erection (537-P-101A/B/C) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1090 | 0 | 10610.ST.PL.TN | 13.62 | 0
C112132STPR000110 | U12 - 537-PR-106 Main Piperack Erection (537-E-102) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24545 | 625.0054 | 10610.ST.PR.TN | 463.11 | 358.2406
C112132STPR000150 | U12 - 537-PR-304 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 511 | 0 | 10610.ST.PR.TN | 9.65 | 0
C112132STPR150000 | U12 - 537-PR-102 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29888 | 643.5794 | 10610.ST.PR.TN | 563.93 | 310.5773
C112132STPR160000 | U12 - 537-PR-103 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17493 | 290.9058 | 10610.ST.PR.TN | 330.06 | 231.0396
C112133PAPP000040 | U12 - Piping SandBl. & Priming | PA | PAPP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10570 | 60.6081 | 10610.PA.PP.M2 | 5285 | 2050.9921
C112133PASP000040 | U12 - Piping Supports SandBl. & Priming | PA | PASP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6602 | 6.4918 | 10610.PA.SU.TN | 0 | 0
C112134ELCI000040 | U12 - Conduits Installation | EL | ELCI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11617 | 0 | 10610.EL.CD.LM | 4604 | 0
C112134ELCL000070 | U12 - Lighting Cable Laying | EL | ELCL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20911 | 0 | 10610.EL.LC.LM | 102529.11 | 0
C112134ELCL000080 | U12 - Electrical Cable Laying | EL | ELCL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102234 | 0 | 10610.EL.PL.LM | 156153.74 | 0
C112132STEQ120000 | U12 - 537-STR-007 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 966 | 0 | 10610.ST.ER.TN | 18.22 | 0
C112132STMS000040 | U12 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3172 | 0 | 10610.ST.PL.TN | 52.86 | 0
C112132STPL000110 | U12 - Pits Platforms, Ladders & Handrails Erection (537-SU-101; 537-SU-103; 537-SU-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1678 | 0 | 10610.ST.PL.TN | 20.98 | 0
C112132STPL000140 | U12 - 537-PR-303 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63 | 0 | 10610.ST.PL.TN | 0.79 | 0
C112132STPL000170 | U12 - 537-PR-106 Piperack Platforms, Ladders & Handrails Erection (537-E-102) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4116 | 0 | 10610.ST.PL.TN | 51.46 | 0
C112132STPL000200 | U12 - 537-PR-101_103 Piperack Platforms, Ladders & Handrails Erection (537-E-101) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10610.ST.PL.TN | 24.61 | 0
C112132STPL000210 | U12 - 537-PB-101 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3158 | 0 | 10610.ST.PL.TN | 39.47 | 0
C112132STPL000230 | U12 - 537-STR-005 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 994 | 0 | 10610.ST.PL.TN | 12.42 | 0
C112132STPL000250 | U12 - 537-STR-002 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4320 | 0 | 10610.ST.PL.TN | 0 | 0
C112132STPL000260 | U12 - 537-STR-003 Piperack Platforms, Ladders & Handrails Erection (537-P-101A/B/C) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1090 | 0 | 10610.ST.PL.TN | 13.62 | 0
C112132STPR000070 | U12 - 537-PB-101 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18828 | 126.1563 | 10610.ST.PR.TN | 355.24 | 49.7296
C112132STPR000090 | U12 - 537-PR-104 Main Piperack Erection (537-E-104) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28378 | 678.953 | 10610.ST.PR.TN | 535.44 | 358.6022
C112132STPR000100 | U12 - 537-PR-105 Main Piperack Erection (537-E-102; 537-E-104) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23957 | 557.2995 | 10610.ST.PR.TN | 452.03 | 321.274
C112132STPR000140 | U12 - 537-PR-303 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 375 | 0 | 10610.ST.PR.TN | 7.07 | 0
C112132STPR160000 | U12 - 537-PR-103 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17493 | 290.9058 | 10610.ST.PR.TN | 330.06 | 231.0396
C112132STPR210000 | U12 - 537-PR-201 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4761 | 0 | 10610.ST.PR.TN | 89.83 | 0
C112133PAEQ000040 | U12 - Equipment Painting | PA | PAEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6050 | 0 | 10780.PA.PA.MH
C112133PAFP000040 | U12 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1268 | 0 | 10610.PA.FP.M2 | 5285 | 0
C112134ELCL000070 | U12 - Lighting Cable Laying | EL | ELCL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20911 | 0 | 10610.EL.LC.LM | 102529.11 | 0
C113131PIBB200010 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-201 to 543-PR-301 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200030 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-301 to 543-PR-401 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200040 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-401 to 543-PR-501 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200050 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-501 to 543-PR-601 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200060 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-601 to 543-PR-701 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200080 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB300010 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-201 to 544-PR-301 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300050 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-501 to 544-PR-601 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIPR100010 | U13 - Piping Prefabrication (Train 1) | PI | PIPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1047077 | 752493.634 | 10610.PI.FB.DI | 261769.24 | 96790.2104
C113131PIPR300010 | U13 - Piping Prefabrication (Train 3) | PI | PIPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1039855 | 1300597.7965 | 10610.PI.FB.DI | 259963.72 | 175473.5221
C113131PIPR300010 | U13 - Piping Prefabrication (Train 3) | PI | PIPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1039855 | 1300597.7965 | 10610.PI.FB.DI | 259963.72 | 175473.5221
C113131PIRA100020 | U13 - Piping Erection on Rack 542-PR-102 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100050 | U13 - Piping Erection on Rack 542-PR-105 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100110 | U13 - Piping Erection on Rack 542-PR-111 (Train 1) (542-E-112) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100120 | U13 - Piping Erection on Rack 542-PR-112 (Train 1) (542-E-112) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100130 | U13 - Piping Erection on Rack 542-PR-101 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100170 | U13 - Piping Erection on Secondary Rack 542-PR-501 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100180 | U13 - Piping Erection on Secondary Rack 542-PR-601 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C112132CIVE000140 | U12 - Sweet Gas KO Drum 537-V-103 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4452 | 29.2804 | 10610.CI.CO.M3 | 74.2 | 74.2
C112132CIVE000140 | U12 - Sweet Gas KO Drum 537-V-103 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4452 | 29.2804 | 10610.CI.CO.M3 | 74.2 | 74.2
C112132CIVE000150 | U12 - HP Absorber Column 537-V-101 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13204 | 257.5594 | 10610.CI.CO.M3 | 264.08 | 264.08
C112132CIVE000160 | U12 - Fresh Solvent Filter 537-F-103 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 411 | 0.12537 | 10610.CI.CO.M3 | 5.87 | 4.1929
C112132CIVE000170 | U12 - Absorber Filter Inlet Coalescer 537-F-101 Foundation Execution | CI | CIVE | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1138 | 1.9123 | 10610.CI.CO.M3 | 16.25 | 16.2499
C112132FPEQ000013 | U12 - Equipment Fireproofing 537-V-103 | FP | FPEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20661 | 0 | 10610.FP.EQ.M2 | 163 | 0
C112132FPSS000100 | U12 - Steel Structures Fireproofing (537-STR-001 TO 537-STR-007) | FP | FPSS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49585 | 0 | 10610.FP.ST.M2 | 17723.88 | 0
C112132STEQ000060 | U12 - 537-STR-006 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 138 | 0 | 10610.ST.ER.TN | 2.61 | 0
C112132STEQ000070 | U12 - 537-STR-005 Structure Erection | ST | STEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5926 | 0 | 10610.ST.ER.TN | 111.81 | 0
C112132STMS000040 | U12 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3172 | 0 | 10610.ST.PL.TN | 52.86 | 0
C112132STPL000150 | U12 - 537-PR-302 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 318 | 0 | 10610.ST.PL.TN | 3.98 | 0
C112132STPL000180 | U12 - 537-PR-105 Piperack Platforms, Ladders & Handrails Erection (537-E-102; 537-E-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4018 | 0 | 10610.ST.PL.TN | 50.23 | 0
C112132STPL000190 | U12 - 537-PR-104 Piperack Platforms, Ladders & Handrails Erection (537-E-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4759 | 0 | 10610.ST.PL.TN | 59.49 | 0
C112132STPL000230 | U12 - 537-STR-005 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 994 | 0 | 10610.ST.PL.TN | 12.42 | 0
C112132STPL000240 | U12 - 537-STR-004 Piperack Platforms, Ladders & Handrails Erection (537-V-102; 537-V-106; 537-E-105A/B 537-ME-104) | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24 | 0 | 10610.ST.PL.TN | 0.3 | 0
C112132STPL000270 | U12 - 537-STR-001 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3427 | 0 | 10610.ST.PL.TN | 42.83 | 0
C112132STPL000280 | U12- Lean Solvent Storage Tank 537-TK-101 Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23 | 0 | 10610.ST.PL.TN | 0.29 | 0
C112132STPL000290 | U12- Fresh Solvent Storage Tank 537-TK-102 Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23 | 0 | 10610.ST.PL.TN | 0.29 | 0
C112134ELCT000010 | U12 - Cathodic Protection Tanks | EL | ELCT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9294 | 103.361 | 10780.EL.EL.MH
C112134MEMC000080 | U12 - Miscellaneous Electrical | EL | ELEQ2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6970 | 0 | 10780.EL.EL.MH
C112136MEAC000130 | U12 - Air Coolers (Regenerator Overhead Condenser) Erection 537-E-104 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.ME.ER.TN | 115 | 0
C112136MEHE000010 | U12 - Regenerator Reboiler Erection 537-E-105A (537-STR-003) | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C112136MEHE000020 | U12 - Regenerator Reboiler Erection 537-E-105B (537-STR-003) | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C112136MEHE000110 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103B | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHE000112 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103D | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHM000090 | U12 - Horizontal Pump (Sweet Gas Water Wash Pump) with Electrical Motor Erection 537-P-104A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000120 | U12 - Horizontal Pump (Steam Condensate Pump) with Electrical Motor Erection 537-P-107A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000140 | U12 - Horizontal Pump (Solvent Drain Sump Pump) with Electrical Motor Erection 537-P-108A in 537-SU-101 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000150 | U12 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 537-P-112A in 537-SU-104 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000200 | U12 - Horizontal Pump (Sweet Gas Water Wash Pump) with Electrical Motor Erection 537-P-104B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000210 | U12 - Horizontal Pump (Absorber Water Wash Make-Up Pump) with Electrical Motor Erection 537-P-121B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000220 | U12 - Horizontal Pump (Steam Condensate Pump) with Electrical Motor Erection 537-P-107B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000270 | U12 - Horizontal Pump (Lean Solvent Storage Tank Pump) with Electrical Motor Erection 537-P-102B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000280 | U12 - Horizontal Pump (Fresh Solvent Transfer Pump) with Electrical Motor Erection 537-P-122B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000310 | U12 - Horizontal Pump (Hydrocarbon Drain Sump Pump) with Electrical Motor Erection 537-P-113B in 537-SU-103 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112134ELCO000070 | U12 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.CO.UN | 432 | 0
C112134ELEL000045 | U12 - Earthing Works | EL | ELEL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18588 | 0 | 10610.EL.ES.LM | 13808.39 | 0
C112134ELEL000055 | U12 - Lightning Works | EL | ELEL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18588 | 0 | 10780.EL.EL.MH
C112134ELPL000040 | U12 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30205 | 0 | 10780.EL.EL.MH
C112134ELTI000070 | U12 - Lighting Cable Trays Installation | EL | ELTI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.CT.LM | 4509.07 | 0
C112136MEAC000090 | U12 - Air Coolers (Sweet Gas Cooler) Erection 537-E-101 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7000 | 0 | 10610.ME.ER.TN | 70 | 0
C112136MEAC000100 | U12 - Air Coolers (Sweet Gas Cooler) Pre-Assembly 537-E-101 | ME | MEAC1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6528 | 0 | 10780.ME.ME.MH
C112136MEAC000110 | U12 - Air Coolers (Lean Solvent Cooler) Erection 537-E-102 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24800 | 0 | 10610.ME.ER.TN | 248 | 0
C112136MEAC000130 | U12 - Air Coolers (Regenerator Overhead Condenser) Erection 537-E-104 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.ME.ER.TN | 115 | 0
C112136MEHE000010 | U12 - Regenerator Reboiler Erection 537-E-105A (537-STR-003) | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C112136MEHE000100 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103A | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHM000030 | U12 - Horizontal Pump (Lean Solvent Storage Tank Pump) with Electrical Motor Erection 537-P-102A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000040 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000090 | U12 - Horizontal Pump (Sweet Gas Water Wash Pump) with Electrical Motor Erection 537-P-104A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000100 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000110 | U12 - Horizontal Pump (Hydrocarbon Drain Sump Pump) with Electrical Motor Erection 537-P-113A in 537-SU-103 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000120 | U12 - Horizontal Pump (Steam Condensate Pump) with Electrical Motor Erection 537-P-107A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000130 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113131PIRA200020 | U13 - Piping Erection on Rack 543-PR-102 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200030 | U13 - Piping Erection on Rack 543-PR-103 (Train 2) (543-E-106) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200060 | U13 - Piping Erection on Rack 543-PR-106 (Train 2) (543-E-120) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200080 | U13 - Piping Erection on Rack 543-PR-108 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200120 | U13 - Piping Erection on Rack 543-PR-112 (Train 2) (543-E-112) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200160 | U13 - Piping Erection on Secondary Rack 543-PR-401 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200190 | U13 - Piping Erection on Secondary Rack 543-PR-701 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200200 | U13 - Piping Erection on Secondary Rack 543-PR-801 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200210 | U13 - Piping Erection on Secondary Rack 543-PR-901 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA300020 | U13 - Piping Erection on Rack 544-PR-102 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 104.8236 | 10610.PI.PR.DI | 3718.05 | 532.0158
C113131PIRA300030 | U13 - Piping Erection on Rack 544-PR-103 (Train 3) (544-E-106) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 146.0782 | 10610.PI.PR.DI | 3718.05 | 538.0018
C113131PIRA300040 | U13 - Piping Erection on Rack 544-PR-104 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 390.0161 | 10610.PI.PR.DI | 3718.05 | 361.9893
C113131PIRA300060 | U13 - Piping Erection on Rack 544-PR-106 (Train 3) (544-E-120) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 233.3017 | 10610.PI.PR.DI | 3718.05 | 572.9887
C113131PIRA300070 | U13 - Piping Erection on Rack 544-PR-107 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 127.9983 | 10610.PI.PR.DI | 3718.05 | 363.9971
C113131PIRA300070 | U13 - Piping Erection on Rack 544-PR-107 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 127.9983 | 10610.PI.PR.DI | 3718.05 | 363.9971
C113131PIRA300080 | U13 - Piping Erection on Rack 544-PR-108 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 130.7938 | 10610.PI.PR.DI | 3718.05 | 699.9973
C113131PIRA300100 | U13 - Piping Erection on Rack 544-PR-110 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 93.4265 | 10610.PI.PR.DI | 3718.05 | 500.0034
C113131PIRA300130 | U13 - Piping Erection on Rack 544-PR-101 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300180 | U13 - Piping Erection on Secondary Rack 544-PR-601 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C112132STPL000300 | U12 - Bund Walls Platforms, Ladders & Handrails Erection | ST | STPL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5576 | 0 | 10610.ST.PL.TN | 69.7 | 0
C112132STPR000080 | U12 - 537-PR-101 Main Piperack Erection (537-E-101) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11737 | 78.6582 | 10610.ST.PR.TN | 221.46 | 87.5828
C112132STPR000090 | U12 - 537-PR-104 Main Piperack Erection (537-E-104) | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28378 | 678.953 | 10610.ST.PR.TN | 535.44 | 358.6022
C112132STPR000120 | U12 - 537-PR-301 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1455 | 0 | 10610.ST.PR.TN | 27.46 | 0
C112132STPR000130 | U12 - 537-PR-302 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1896 | 0 | 10610.ST.PR.TN | 35.78 | 0
C112132STPR150000 | U12 - 537-PR-102 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29888 | 643.5794 | 10610.ST.PR.TN | 563.93 | 310.5773
C112132STPR210000 | U12 - 537-PR-201 Main Piperack Erection | ST | STPR | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4761 | 0 | 10610.ST.PR.TN | 89.83 | 0
C112132STSP000040 | U12 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27074 | 0 | 10610.ST.PL.TN | 451.23 | 0
C112133PASP000040 | U12 - Piping Supports SandBl. & Priming | PA | PASP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6602 | 6.4918 | 10610.PA.SU.TN | 0 | 0
C112134ELCI000040 | U12 - Conduits Installation | EL | ELCI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11617 | 0 | 10610.EL.CD.LM | 4604 | 0
C112134ELCO000080 | U12 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55764 | 0 | 10610.EL.CO.UN | 567 | 0
C112134ELCP000040 | U12 - Cathodic Protection Piping | EL | ELCP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9294 | 0 | 10780.EL.EL.MH
C112134ELEQ000040 | U12 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.EQ.UN | 238 | 0
C112134ELHT000010 | U12 - Electrical Heat Tracing | EL | ELHT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16264 | 0 | 10780.EL.EL.MH
C112134ELTI000070 | U12 - Lighting Cable Trays Installation | EL | ELTI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13941 | 0 | 10610.EL.CT.LM | 4509.07 | 0
C112134ELTI000080 | U12 - Electrical Cable Trays Installation | EL | ELTI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 46470 | 0 | 10610.EL.CT.LM | 8374 | 0
C112136MEAC000090 | U12 - Air Coolers (Sweet Gas Cooler) Erection 537-E-101 | ME | MEAC2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7000 | 0 | 10610.ME.ER.TN | 70 | 0
C112136MEAC000140 | U12 - Air Coolers (Regenerator Overhead Condenser) Pre-Assembly 537-E-104 | ME | MEAC1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11780 | 0 | 10780.ME.ME.MH
C112136MEHE000100 | U12 - Heat Exchangers (Rich/Lean Solvent Exchanger) Erection 537-E-103A | ME | MEHE1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEHM000100 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHV000040 | U12 - Horizontal Vessels (Solvent Drain Sump Filter) Erection 537-F-103 | ME | MEHV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C112136MEMC000040 | U12 - Miscellaneous Erection | ME | MEMC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12900 | 0 | 10610.ME.ER.TN | 215 | 0
C112136MEMC000050 | U12 - Equipment Pre-Dressing before erection | IS | ISEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3076 | 12.4674 | 10780.IS.IS.MH
C112136MEPA000050 | U12 - LP steam Desuperheater Package Installation 537-ME-104 | ME | MEPA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 71 | 0 | 10780.ME.ME.MH
C112136METO000020 | U12 - Columns (Regenerator) Erection 537-V-102 (HL) (1600 + 800 TON) | ME | METO1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20940 | 647.7684 | 10610.ME.ER.TN | 349 | 349
C112136MEVV000050 | U12 - Vertical Vessels (Steam Condensate Surge Drum) Erection 537-V-106 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C112136MEVV000230 | U12 - Vertical (Rich Solvent Flash Drum) Vessels Erection 537-V-104 (HL) (800 TON) | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6160 | 0 | 10610.ME.ER.TN | 154 | 0
C112137INCT000080 | U12 - Secondary Cable Trays Installation | IN | INCT2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22028 | 0 | 10610.IN.CT.LM | 570 | 0
C112137INFG000070 | U12 - Fire & Gas System Installation | IN | INFG | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4091 | 0 | 10780.IN.IN.MH
C112137INFO000040 | U12 - Fiber Optic Cable Pulling | IN | INFO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5350 | 0 | 10610.IN.FO.LM | 580 | 0
C112137ININ000041 | U12 -Valve Installation | IN | ININ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12587 | 0 | 10610.IN.IN.UN | 620 | 0
C112137INIP000041 | U12 - Valve Calibration | IN | INIP | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4091 | 0 | 10780.IN.IN.MH
C112137INML000040 | U12 - Multi Pair Cable Pulling | IN | INML | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49091 | 0 | 10610.IN.MC.LM | 176599.34 | 0
C1130PRPRPL300010 | U13 - Punch List (Train 3) | PR | PRPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25852 | 0 | 10780.PR.PR.MH
C1130PRPRWT100010 | U13 - Walkthrough (Train 1) | PR | PRWT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10905 | 0 | 10780.PR.PR.MH
C113131ISEQ200010 | U13 - Equipment Insulation (Train 2) | IS | ISEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19393 | 0 | 10610.IS.EQ.M2 | 4055 | 0
C113131MEMC300020 | U13 - Miscellaneous Piping (Train 3) | PI | PISU2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 92240 | 0 | 10780.PI.PI.MH
C113131PIBB100060 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-601 to 542-PR-701 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100070 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-701 to 542-PR-801 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100090 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-901 to Batt. Limit (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIRA300190 | U13 - Piping Erection on Secondary Rack 544-PR-701 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 3.4903 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300200 | U13 - Piping Erection on Secondary Rack 544-PR-801 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 16.6077 | 10610.PI.PR.DI | 3718.05 | 0
C113131PISB100040 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-401 to 542-PR-501 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100060 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-601 to 542-PR-701 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100070 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-701 to 542-PR-801 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200010 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-201 to 543-PR-301 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200050 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-501 to 543-PR-601 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200070 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-701 to 543-PR-801 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200080 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200090 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-901 to Batt. Limit (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB300010 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-201 to 544-PR-301 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300030 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-301 to 544-PR-401 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300040 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-401 to 544-PR-501 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300060 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-601 to 544-PR-701 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300080 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-801 to 544-PR-901 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PIST100020 | U13 - Manifolds Installation (Train 1) | PI | PIST1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1027 | 0 | 10780.PI.PI.MH
C113131PISU100020 | U13 - Piping Supports Erection (Train 1) | PI | PISU2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 176752 | 0 | 10610.PI.SU.TN | 392.78 | 0
C113131PISU200010 | U13 - Piping Supports Prefabrication (Train 2) | PI | PISU1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 102123 | 2315.3414 | 10610.PI.PU.TN | 392.78 | 34.1323
C112136MEHM000160 | U12 - Horizontal Pump (Fresh Solvent Transfer Pump) with Electrical Motor Erection 537-P-122A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000170 | U12 - Horizontal Pump (Absorber Water Wash Make-Up Pump) with Electrical Motor Erection 537-P-121A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000180 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000200 | U12 - Horizontal Pump (Sweet Gas Water Wash Pump) with Electrical Motor Erection 537-P-104B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000210 | U12 - Horizontal Pump (Absorber Water Wash Make-Up Pump) with Electrical Motor Erection 537-P-121B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000250 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000280 | U12 - Horizontal Pump (Fresh Solvent Transfer Pump) with Electrical Motor Erection 537-P-122B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000300 | U12 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 537-P-112B in 537-SU-104 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000310 | U12 - Horizontal Pump (Hydrocarbon Drain Sump Pump) with Electrical Motor Erection 537-P-113B in 537-SU-103 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHV000050 | U12 - Horizontal Vessels (Absorber Filter Inlet Coalescer) Erection 537-F-101 | ME | MEHV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C112136MEIN000010 | U12 - Internals Erection | ME | MEIN | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2302 | 0 | 10780.ME.ME.MH
C112136MEMC000040 | U12 - Miscellaneous Erection | ME | MEMC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12900 | 0 | 10610.ME.ER.TN | 215 | 0
C112136METO000030 | U12 - Columns (Hp Absorber) Erection 537-V-101 (HL) (1600 + 800 TON) | ME | METO1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40680 | 2444.7153 | 10610.ME.ER.TN | 678 | 678
C112136MEVV000050 | U12 - Vertical Vessels (Steam Condensate Surge Drum) Erection 537-V-106 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C112136MEVV000220 | U12 - Vertical Vessels (Solvent Drain Sump Drum) Erection 537-V-107 / 537-V-108A/B | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C112136MEVV000230 | U12 - Vertical (Rich Solvent Flash Drum) Vessels Erection 537-V-104 (HL) (800 TON) | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6160 | 0 | 10610.ME.ER.TN | 154 | 0
C112137INAI000040 | U12 - Analyzers Equipment Installation | IN | INAI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8496 | 0 | 10610.IN.AI.UN | 2 | 0
C113131PIBB200050 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-501 to 543-PR-601 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB300030 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-301 to 544-PR-401 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300060 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-601 to 544-PR-701 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300070 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-701 to 544-PR-801 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300080 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-801 to 544-PR-901 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300090 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-901 to Batt. Limit (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIPR100020 | U13 - UG Piping Prefabrication (Train 1) | PI | PIPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17024 | 427.159 | 10610.PI.FB.DI | 4256 | 4321.0037
C113131PIPR200020 | U13 - UG Piping Prefabrication (Train 2) | PI | PIPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16976 | 425.7328 | 10610.PI.FB.DI | 4244 | 4334.9012
C113131PIPR300020 | U13 - UG Piping Prefabrication (Train 3) | PI | PIPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17812 | 421.077 | 10610.PI.FB.DI | 4453 | 5094.1591
C113131PIRA100020 | U13 - Piping Erection on Rack 542-PR-102 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100030 | U13 - Piping Erection on Rack 542-PR-103 (Train 1) (542-E-106) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100040 | U13 - Piping Erection on Rack 542-PR-104 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100070 | U13 - Piping Erection on Rack 542-PR-107 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100100 | U13 - Piping Erection on Rack 542-PR-110 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100150 | U13 - Piping Erection on Secondary Rack 542-PR-301 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100160 | U13 - Piping Erection on Secondary Rack 542-PR-401 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100200 | U13 - Piping Erection on Secondary Rack 542-PR-801 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA200020 | U13 - Piping Erection on Rack 543-PR-102 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200030 | U13 - Piping Erection on Rack 543-PR-103 (Train 2) (543-E-106) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C112136MEHM000130 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000160 | U12 - Horizontal Pump (Fresh Solvent Transfer Pump) with Electrical Motor Erection 537-P-122A | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000180 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000190 | U12 - Horizontal Pump (Lean Solvent Circulation Pump) with Electrical Motor Erection 537-P-101C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000230 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000230 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000240 | U12 - Horizontal Pump (Lean Solvent Pump) with Electrical Motor Erection 537-P-106C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000250 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000260 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000260 | U12 - Horizontal Pump (Solvent Reflux Pump) with Electrical Motor Erection 537-P-103C | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000270 | U12 - Horizontal Pump (Lean Solvent Storage Tank Pump) with Electrical Motor Erection 537-P-102B | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHM000290 | U12 - Horizontal Pump (Solvent Drain Sump Pump) with Electrical Motor Erection 537-P-108B in 537-SU-101 | ME | MEHM1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C112136MEHV000050 | U12 - Horizontal Vessels (Absorber Filter Inlet Coalescer) Erection 537-F-101 | ME | MEHV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C112136MEPA000060 | U12 - Antifoam Package Installation 537-ME-102 | ME | MEPA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C112136MEPA000070 | U12 - Lean Solvent Filtration Package Installation 537-ME-101 | ME | MEPA | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 354 | 0 | 10780.ME.ME.MH
C112136METO000030 | U12 - Columns (Hp Absorber) Erection 537-V-101 (HL) (1600 + 800 TON) | ME | METO1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40680 | 2444.7153 | 10610.ME.ER.TN | 678 | 678
C112136MEVV000040 | U12 - Vertical Vessels (Solvent Reflux Drum) Erection 537-V-105 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113131PISU300020 | U13 - Piping Supports Erection (Train 3) | PI | PISU2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 205685 | 0 | 10610.PI.SU.TN | 457.08 | 0
C113131PIUG300010 | U13 - Piping Erection UG (Train 3) (AOC/COC) | PI | PIUG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2834 | 2.6988 | 10610.PI.UG.DI | 1889 | 0
C113131PRBO100010 | U13 - Static Box Up (Train 1) | PR | PRBO1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39180 | 0 | 10780.PR.PR.MH
C113131PRBO200010 | U13 - Static Box Up (Train 2) | PR | PRBO1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 39216 | 0 | 10780.PR.PR.MH
C113131PRBO300020 | U13 - Rotary Box Up (Train 3) | PR | PRBO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33093 | 0 | 10780.PR.PR.MH
C113131PRFL000270 | U13 - Chemical Cleaning for Compressor Suction Lines (Unit 542) (Train 1) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4931 | 0 | 10780.PR.PR.MH
C113131PRFL000290 | U13 - Chemical Cleaning for Compressor Suction Lines (Unit 543) (Train 2) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5592 | 0 | 10780.PR.PR.MH
C113131PRFL100010 | U13 - Piping Flushing/Steam Blowing (Train 1) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19957 | 0 | 10610.PR.FL.DI | 286343 | 0
C113131PRFL200010 | U13 - Piping Flushing/Steam Blowing (Train 2) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20132 | 0 | 10610.PR.FL.DI | 280360 | 0
C113131PRFL300010 | U13 - Piping Flushing/Steam Blowing (Train 3) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22396 | 0 | 10610.PR.FL.DI | 281077 | 0
C113131PRHT100010 | U13 - Piping Hydrotesting (Train 1) | PR | PRHT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 244177 | 0 | 10610.PR.HT.DI | 286343 | 0
C113131PRRE200010 | U13 - Piping Reinstatement (Train 2) | PR | PRRE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 193270 | 0 | 10610.PR.RE.DI | 280360 | 0
C113132CICT100010 | U13 - Electrical earth Trenches Execution (Train 1) | CI | CICT2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2495 | 1.1955 | 10610.CI.ET.M3 | 623.74 | 623.74
C113132CICT100020 | U13 - Instrument earth Trenches Execution (Train 1) | CI | CICT3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9509 | 18.9013 | 10780.CI.CI.MH
C113132CICT100030 | U13 - Covered Concrete Trenches Execution (Train 1) | CI | CICT1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 105699 | 11074.7083 | 10610.CI.CO.M3 | 2113.99 | 1671.9779
C113132CICT100030 | U13 - Covered Concrete Trenches Execution (Train 1) | CI | CICT1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 105699 | 11074.7083 | 10610.CI.CO.M3 | 2113.99 | 1671.9779
C113132CICT200010 | U13 - Electrical earth Trenches Execution (Train 2) | CI | CICT2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9509 | 14.6936 | 10780.CI.CI.MH
C113132CICT200030 | U13 - Covered Concrete Trenches Execution (Train 2) | CI | CICT1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 70507 | 734.3933 | 10610.CI.CO.M3 | 1410.13 | 0
C113132CICT300010 | U13 - Electrical earth Trenches Execution (Train 3) | CI | CICT2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1900 | 0.62396 | 10610.CI.ET.M3 | 475 | 451.25
C113132CIDB200015 | U13 - Duct Banks Precast Fabrication (Train 2) | CI | CIDB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40938 | 1198.3029 | 10780.CI.CI.MH
C112137INCT000070 | U12 - Primary Cable Trays Installation | IN | INCT1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39336 | 0 | 10610.IN.CT.LM | 690 | 0
C112137INFO000040 | U12 - Fiber Optic Cable Pulling | IN | INFO | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5350 | 0 | 10610.IN.FO.LM | 580 | 0
C112137INFS000040 | U12 - Fire Fighting Equipments Installation | IN | INFS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4091 | 0 | 10610.IN.FG.UN | 71 | 0
C112137INGC000080 | U12 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16364 | 0 | 10610.IN.CO.UN | 4268 | 0
C112137INHU000080 | U12 - Process Hook Up´s Erection | IN | INHU1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17308 | 0 | 10780.IN.IN.MH
C112137ININ000040 | U12 - Instruments Installation | IN | ININ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12587 | 0 | 10610.IN.IN.UN | 750 | 0
C112137ININ000041 | U12 -Valve Installation | IN | ININ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12587 | 0 | 10610.IN.IN.UN | 620 | 0
C1130PRPRPL100010 | U13 - Punch List (Train 1) | PR | PRPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25446 | 0 | 10780.PR.PR.MH
C113131ISEQ100010 | U13 - Equipment Insulation (Train 1) | IS | ISEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19400 | 0 | 10780.IS.IS.MH
C113131ISEQ200010 | U13 - Equipment Insulation (Train 2) | IS | ISEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19393 | 0 | 10610.IS.EQ.M2 | 4055 | 0
C113131ISPI200010 | U13 - Piping Insulation (Train 2) | IS | ISPI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 94375 | 0 | 10780.IS.IS.MH
C113131MEMC100020 | U13 - Miscellaneous Piping (Train 1) | PI | PISU2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 92322 | 0 | 10780.PI.PI.MH
C113131NIPR000020 | U13 - Nitrogen Purging & Inerting (Train 3)(Unit 544) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5226 | 0 | 10780.PR.PR.MH
C113131NITR000060 | U13 - Nitrogen Leak Test (Train 2)(Unit 543) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4474 | 0 | 10780.PR.PR.MH
C113131NITR000070 | U13 - Nitrogen Leak Test (Train 3)(Unit 544) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5226 | 0 | 10780.PR.PR.MH
C113131PIBB100030 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-301 to 542-PR-401 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100070 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-701 to 542-PR-801 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100080 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-801 to 542-PR-901 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100090 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-901 to Batt. Limit (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB200010 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-201 to 543-PR-301 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIRA200060 | U13 - Piping Erection on Rack 543-PR-106 (Train 2) (543-E-120) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200110 | U13 - Piping Erection on Rack 543-PR-111 (Train 2) (543-E-112) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200120 | U13 - Piping Erection on Rack 543-PR-112 (Train 2) (543-E-112) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200130 | U13 - Piping Erection on Rack 543-PR-101 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200140 | U13 - Piping Erection on Secondary Rack 543-PR-201 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200170 | U13 - Piping Erection on Secondary Rack 543-PR-501 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200180 | U13 - Piping Erection on Secondary Rack 543-PR-601 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA300050 | U13 - Piping Erection on Rack 544-PR-105 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 347.2232 | 10610.PI.PR.DI | 3718.05 | 784.9919
C113131PIRA300090 | U13 - Piping Erection on Rack 544-PR-109 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 93.4265 | 10610.PI.PR.DI | 3718.05 | 500.0034
C113131PIRA300100 | U13 - Piping Erection on Rack 544-PR-110 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 93.4265 | 10610.PI.PR.DI | 3718.05 | 500.0034
C113131PIRA300110 | U13 - Piping Erection on Rack 544-PR-111 (Train 3) (544-E-112) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 131.8194 | 10610.PI.PR.DI | 3718.05 | 599.9817
C113131PIRA300120 | U13 - Piping Erection on Rack 544-PR-112 (Train 3) (544-E-112) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300160 | U13 - Piping Erection on Secondary Rack 544-PR-401 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 6.9971 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300160 | U13 - Piping Erection on Secondary Rack 544-PR-401 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 6.9971 | 10610.PI.PR.DI | 3718.05 | 0
C113131PISB100060 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-601 to 542-PR-701 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100070 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-701 to 542-PR-801 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100090 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-901 to Batt. Limit (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200030 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-301 to 543-PR-401 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C112136MEVV000060 | U12 - Vertical (Sweet Gas Ko Drum) Vessels Erection 537-V-103 (HL) (800 + 400 TON) | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5720 | 0 | 10610.ME.ER.TN | 143 | 0
C112136MEVV000210 | U12 - Vertical Vessels (Hydrocarbon Drain Sump Drum) Erection 537-V-113 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 880 | 0 | 10610.ME.ER.TN | 22 | 0
C112136MEVV000240 | U12 - Vertical Vessels (Make-Up Water Break Tank) Erection 537-V-121 | ME | MEVV | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C112137INAI000040 | U12 - Analyzers Equipment Installation | IN | INAI | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8496 | 0 | 10610.IN.AI.UN | 2 | 0
C112137INCT000070 | U12 - Primary Cable Trays Installation | IN | INCT1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39336 | 0 | 10610.IN.CT.LM | 690 | 0
C112137INFC000040 | U12 - Fiber Optic Gland & Conn./Testing | IN | INFC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3776 | 0 | 10610.IN.CO.UN | 310 | 0
C112137INFS000040 | U12 - Fire Fighting Equipments Installation | IN | INFS | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4091 | 0 | 10610.IN.FG.UN | 71 | 0
C112137INGC000070 | U12 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24545 | 0 | 10610.IN.CO.UN | 500 | 0
C112137INGC000080 | U12 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16364 | 0 | 10610.IN.CO.UN | 4268 | 0
C112137INHU000070 | U12 - Pneumatic Hook Up´s Erection | IN | INHU3 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2120 | 0 | 10780.IN.IN.MH
C112137INML000040 | U12 - Multi Pair Cable Pulling | IN | INML | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49091 | 0 | 10610.IN.MC.LM | 176599.34 | 0
C112137INSL000040 | U12 - Single Pair Cable Pulling | IN | INSL | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39336 | 0 | 10610.IN.SC.LM | 79333.94 | 0
C112137PRLT000040 | U12 - Loops Testing | PR | PRLT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 46386 | 0 | 10780.PR.PR.MH
C112137PRLT000540 | U27 - Loops Testing | PR | PRLT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 58 | 0 | 10780.PR.PR.MH
C1130PRPRWT300010 | U13 - Walkthrough (Train 3) | PR | PRWT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11079 | 0 | 10780.PR.PR.MH
C113131ISEQ300010 | U13 - Equipment Insulation (Train 3) | IS | ISEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19977 | 0 | 10780.IS.IS.MH
C113131ISPI100010 | U13 - Piping Insulation (Train 1) | IS | ISPI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 165306 | 0 | 10610.IS.PI.M2 | 29090 | 0
C113131ISPI300010 | U13 - Piping Insulation (Train 3) | IS | ISPI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63648 | 0 | 10610.IS.PI.M2 | 29090 | 0
C113131MEMC200020 | U13 - Miscellaneous Piping (Train 2) | PI | PISU2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 92236 | 0 | 10780.PI.PI.MH
C113131NIPR000060 | U13 - Nitrogen Purging & Inerting (Train 1)(Unit 542) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4931 | 0 | 10780.PR.PR.MH
C113131NIPR000070 | U13 - Nitrogen Purging & Inerting (Train 2)(Unit 543) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4698 | 0 | 10780.PR.PR.MH
C113132CIGR100010 | U13 - Grounding Network Execution (Train 1) | CI | CIGR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 156 | 0.0061477 | 10610.CI.GR.LM | 260 | 26
C113132CIGR200010 | U13 - Grounding Network Execution (Train 2) | CI | CIGR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8400 | 6.5149 | 10780.CI.CI.MH
C113132CIGT200010 | U13 - Equipment Grouting Execution (Train 2) | CI | CIGT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15500 | 5.4587 | 10780.CI.CI.MH
C113132CIHE100020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 1) 542-F-107A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1245 | 2.277 | 10610.CI.CO.M3 | 17.78 | 17.78
C113132CIHE100090 | U13 - Exchangers (Residue Gas Recycle Cooler) Foundation Execution (Train 1) for 542-E-126 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2840 | 11.9169 | 10610.CI.CO.M3 | 47.34 | 47.34
C113132CIHE200015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 2) for 543-E-128 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 603 | 0.35503 | 10610.CI.CO.M3 | 8.62 | 4.31
C113132CIHE200020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 2) 543-F-107A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1245 | 2.0957 | 10610.CI.CO.M3 | 17.78 | 17.7801
C113132CIHE300090 | U13 - Exchangers (Residue Gas Recycle Chiller) Foundation Execution (Train 3) for 544-E-126 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2840 | 11.9169 | 10610.CI.CO.M3 | 47.34 | 47.34
C113132CIHE300120 | U13 - Horizontal Vessels (Dehydration Outlet Gas Filter) Foundation Execution (Train 3) 544-F-108A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 865 | 1.1056 | 10610.CI.CO.M3 | 12.36 | 12.36
C113132CIHE300160 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 2) 543-F-110A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 818 | 0.68379 | 10610.CI.CO.M3 | 11.69 | 5.85
C113132CIHE300170 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 1) 542-F-110A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE300170 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 1) 542-F-110A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHF200010 | U13 - Regeneration Gas Heater Foundation Execution 543-ME-101 (TRAIN 2) | CI | CIHF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12780 | 241.2838 | 10610.CI.CO.M3 | 255.6 | 255.5999
C113132CIHF300010 | U13 - Regeneration Gas Heater Foundation Execution 544-ME-101 (TRAIN 3) | CI | CIHF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40617 | 2437.149 | 10610.CI.CO.M3 | 812.34 | 812.34
C113132CIHF300020 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution 542-E-109 (TRAIN 1) | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 767 | 0.86495 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIMF300010 | U13 - Miscellaneous Foundations Execution (Train 3) | CI | CIMF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10223 | 65.9238 | 10610.CI.CO.M3 | 170.38 | 60.0776
C113132CIPD100010 | U13 - Fabrication Precast Drainage Man Holes & Catchbasins (Train 1) | CI | CIPD | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7985 | 93.486 | 10780.CI.CI.MH
C113131PIBB200030 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-301 to 543-PR-401 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200070 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200080 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200090 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB300040 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-401 to 544-PR-501 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300070 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-701 to 544-PR-801 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300090 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-901 to Batt. Limit (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIPR100020 | U13 - UG Piping Prefabrication (Train 1) | PI | PIPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17024 | 427.159 | 10610.PI.FB.DI | 4256 | 4321.0037
C113131PIPR200010 | U13 - Piping Prefabrication (Train 2) | PI | PIPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1034634 | 870398.7356 | 10610.PI.FB.DI | 258658.46 | 136990.0959
C113131PIPR200020 | U13 - UG Piping Prefabrication (Train 2) | PI | PIPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16976 | 425.7328 | 10610.PI.FB.DI | 4244 | 4334.9012
C113131PIPR300020 | U13 - UG Piping Prefabrication (Train 3) | PI | PIPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17812 | 421.077 | 10610.PI.FB.DI | 4453 | 5094.1591
C113131PIRA100030 | U13 - Piping Erection on Rack 542-PR-103 (Train 1) (542-E-106) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100040 | U13 - Piping Erection on Rack 542-PR-104 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100050 | U13 - Piping Erection on Rack 542-PR-105 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100060 | U13 - Piping Erection on Rack 542-PR-106 (Train 1) (542-E-120) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100070 | U13 - Piping Erection on Rack 542-PR-107 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100080 | U13 - Piping Erection on Rack 542-PR-108 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100090 | U13 - Piping Erection on Rack 542-PR-109 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PISB200060 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-601 to 543-PR-701 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB300030 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-301 to 544-PR-401 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300050 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-501 to 544-PR-601 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300070 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-701 to 544-PR-801 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PIST300010 | U13 - Piping Steam Tracing Installation (Train 3) | PI | PIST2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5818 | 0 | 10780.PI.PI.MH
C113131PISU100020 | U13 - Piping Supports Erection (Train 1) | PI | PISU2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 176752 | 0 | 10610.PI.SU.TN | 392.78 | 0
C113131PISU200010 | U13 - Piping Supports Prefabrication (Train 2) | PI | PISU1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 102123 | 2315.3414 | 10610.PI.PU.TN | 392.78 | 34.1323
C113131PISU200020 | U13 - Piping Supports Erection (Train 2) | PI | PISU2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 176751 | 0 | 10610.PI.SU.TN | 392.78 | 0
C113131PIUG100010 | U13 - Piping Erection UG (Train 1) | PI | PIUG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3176 | 0 | 10610.PI.UG.DI | 2117 | 0
C113131PRBO200020 | U13 - Rotary Box Up (Train 2) | PR | PRBO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33813 | 0 | 10780.PR.PR.MH
C113131PRFL000190 | U13 - Lube Oil Flushing for Compressors (Unit 542) (Train 1) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14087 | 0 | 10780.PR.PR.MH
C113131PRFL000280 | U13 - Chemical Cleaning for Compressor Suction Lines (Unit 544) (Train 3) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6221 | 0 | 10780.PR.PR.MH
C113131PRHT200010 | U13 - Piping Hydrotesting (Train 2) | PR | PRHT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 241587 | 0 | 10610.PR.HT.DI | 280360 | 0
C113131PRRE100010 | U13 - Piping Reinstatement (Train 1) | PR | PRRE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 195342 | 0 | 10610.PR.RE.DI | 286343 | 0
C113131PRRE200010 | U13 - Piping Reinstatement (Train 2) | PR | PRRE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 193270 | 0 | 10610.PR.RE.DI | 280360 | 0
C113131PRRE300010 | U13 - Piping Reinstatement (Train 3) | PR | PRRE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 215995 | 0 | 10610.PR.RE.DI | 281077 | 0
C113132CICT200020 | U13 - Instrument earth Trenches Execution (Train 2) | CI | CICT3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9509 | 13.4914 | 10780.CI.CI.MH
C113132CIDB100015 | U13 - Duct Banks Precast Fabrication (Train 1) | CI | CIDB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11353 | 190.4091 | 10780.CI.CI.MH
C113132CIDB200025 | U13 - Duct Banks Precast Installation (Train 2) | CI | CIDB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37216 | 212.7953 | 10610.CI.CO.M3 | 744.33 | 0
C113132CIDB200025 | U13 - Duct Banks Precast Installation (Train 2) | CI | CIDB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37216 | 212.7953 | 10610.CI.CO.M3 | 744.33 | 0
C113131NITR000050 | U13 - Nitrogen Leak Test (Train 1)(Unit 542) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4931 | 0 | 10780.PR.PR.MH
C113131PIBB100010 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-201 to 542-PR-301 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100040 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-401 to 542-PR-501 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB100050 | U13 - Big Bore Piping A/Equip. Erection - From 542-PR-501 to 542-PR-601 (Train 1) | PI | PIBB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 55676 | 0 | 10610.PI.BB.DI | 5567.59 | 0
C113131PIBB200040 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-401 to 543-PR-501 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200060 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-601 to 543-PR-701 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200070 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB200090 | U13 - Big Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PIBB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54248 | 0 | 10610.PI.BB.DI | 5424.8 | 0
C113131PIBB300010 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-201 to 544-PR-301 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300030 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-301 to 544-PR-401 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300040 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-401 to 544-PR-501 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300050 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-501 to 544-PR-601 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300060 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-601 to 544-PR-701 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIBB300080 | U13 - Big Bore Piping A/Equip. Erection - From 544-PR-801 to 544-PR-901 (Train 3) | PI | PIBB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61900 | 0 | 10610.PI.BB.DI | 6190.02 | 0
C113131PIPR100010 | U13 - Piping Prefabrication (Train 1) | PI | PIPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1047077 | 752493.634 | 10610.PI.FB.DI | 261769.24 | 96790.2104
C113131PIPR200010 | U13 - Piping Prefabrication (Train 2) | PI | PIPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1034634 | 870398.7356 | 10610.PI.FB.DI | 258658.46 | 136990.0959
C113131PIRA100060 | U13 - Piping Erection on Rack 542-PR-106 (Train 1) (542-E-120) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100080 | U13 - Piping Erection on Rack 542-PR-108 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100100 | U13 - Piping Erection on Rack 542-PR-110 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100140 | U13 - Piping Erection on Secondary Rack 542-PR-201 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100150 | U13 - Piping Erection on Secondary Rack 542-PR-301 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100170 | U13 - Piping Erection on Secondary Rack 542-PR-501 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100190 | U13 - Piping Erection on Secondary Rack 542-PR-701 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100200 | U13 - Piping Erection on Secondary Rack 542-PR-801 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100210 | U13 - Piping Erection on Secondary Rack 542-PR-901 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA200040 | U13 - Piping Erection on Rack 543-PR-104 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200050 | U13 - Piping Erection on Rack 543-PR-105 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200070 | U13 - Piping Erection on Rack 543-PR-107 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200090 | U13 - Piping Erection on Rack 543-PR-109 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200100 | U13 - Piping Erection on Rack 543-PR-110 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200110 | U13 - Piping Erection on Rack 543-PR-111 (Train 2) (543-E-112) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200130 | U13 - Piping Erection on Rack 543-PR-101 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200140 | U13 - Piping Erection on Secondary Rack 543-PR-201 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200150 | U13 - Piping Erection on Secondary Rack 543-PR-301 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200160 | U13 - Piping Erection on Secondary Rack 543-PR-401 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200170 | U13 - Piping Erection on Secondary Rack 543-PR-501 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA300050 | U13 - Piping Erection on Rack 544-PR-105 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 347.2232 | 10610.PI.PR.DI | 3718.05 | 784.9919
C113131PIRA100090 | U13 - Piping Erection on Rack 542-PR-109 (Train 1) (542-E-119) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100110 | U13 - Piping Erection on Rack 542-PR-111 (Train 1) (542-E-112) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100120 | U13 - Piping Erection on Rack 542-PR-112 (Train 1) (542-E-112) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100130 | U13 - Piping Erection on Rack 542-PR-101 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100140 | U13 - Piping Erection on Secondary Rack 542-PR-201 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100160 | U13 - Piping Erection on Secondary Rack 542-PR-401 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100180 | U13 - Piping Erection on Secondary Rack 542-PR-601 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100190 | U13 - Piping Erection on Secondary Rack 542-PR-701 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA100210 | U13 - Piping Erection on Secondary Rack 542-PR-901 (Train 1) | PI | PIRA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26218 | 0 | 10610.PI.PR.DI | 2913.07 | 0
C113131PIRA200040 | U13 - Piping Erection on Rack 543-PR-104 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200050 | U13 - Piping Erection on Rack 543-PR-105 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200070 | U13 - Piping Erection on Rack 543-PR-107 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200080 | U13 - Piping Erection on Rack 543-PR-108 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200090 | U13 - Piping Erection on Rack 543-PR-109 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200100 | U13 - Piping Erection on Rack 543-PR-110 (Train 2) (543-E-119) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200150 | U13 - Piping Erection on Secondary Rack 543-PR-301 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200180 | U13 - Piping Erection on Secondary Rack 543-PR-601 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200190 | U13 - Piping Erection on Secondary Rack 543-PR-701 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200200 | U13 - Piping Erection on Secondary Rack 543-PR-801 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA200210 | U13 - Piping Erection on Secondary Rack 543-PR-901 (Train 2) | PI | PIRA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 26122 | 0 | 10610.PI.PR.DI | 2902.4 | 0
C113131PIRA300020 | U13 - Piping Erection on Rack 544-PR-102 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 104.8236 | 10610.PI.PR.DI | 3718.05 | 532.0158
C113131PIRA300030 | U13 - Piping Erection on Rack 544-PR-103 (Train 3) (544-E-106) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 146.0782 | 10610.PI.PR.DI | 3718.05 | 538.0018
C113131PIRA300040 | U13 - Piping Erection on Rack 544-PR-104 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 390.0161 | 10610.PI.PR.DI | 3718.05 | 361.9893
C113131PIRA300060 | U13 - Piping Erection on Rack 544-PR-106 (Train 3) (544-E-120) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 233.3017 | 10610.PI.PR.DI | 3718.05 | 572.9887
C113131PIRA300080 | U13 - Piping Erection on Rack 544-PR-108 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 130.7938 | 10610.PI.PR.DI | 3718.05 | 699.9973
C113131PIRA300110 | U13 - Piping Erection on Rack 544-PR-111 (Train 3) (544-E-112) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 131.8194 | 10610.PI.PR.DI | 3718.05 | 599.9817
C113131PIRA300150 | U13 - Piping Erection on Secondary Rack 544-PR-301 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 119.0824 | 10610.PI.PR.DI | 3718.05 | 507.9972
C113131PIRA300170 | U13 - Piping Erection on Secondary Rack 544-PR-501 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0.82708 | 10610.PI.PR.DI | 3718.05 | 2.0077
C113131PIRA300180 | U13 - Piping Erection on Secondary Rack 544-PR-601 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300200 | U13 - Piping Erection on Secondary Rack 544-PR-801 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 16.6077 | 10610.PI.PR.DI | 3718.05 | 0
C113131PISB100010 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-201 to 542-PR-301 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100040 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-401 to 542-PR-501 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100050 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-501 to 542-PR-601 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100080 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-801 to 542-PR-901 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100090 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-901 to Batt. Limit (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200010 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-201 to 543-PR-301 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200030 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-301 to 543-PR-401 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PIRA300090 | U13 - Piping Erection on Rack 544-PR-109 (Train 3) (544-E-119) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 93.4265 | 10610.PI.PR.DI | 3718.05 | 500.0034
C113131PIRA300120 | U13 - Piping Erection on Rack 544-PR-112 (Train 3) (544-E-112) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300130 | U13 - Piping Erection on Rack 544-PR-101 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300140 | U13 - Piping Erection on Secondary Rack 544-PR-201 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 1.7534 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300140 | U13 - Piping Erection on Secondary Rack 544-PR-201 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 1.7534 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300150 | U13 - Piping Erection on Secondary Rack 544-PR-301 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 119.0824 | 10610.PI.PR.DI | 3718.05 | 507.9972
C113131PIRA300170 | U13 - Piping Erection on Secondary Rack 544-PR-501 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 0.82708 | 10610.PI.PR.DI | 3718.05 | 2.0077
C113131PIRA300190 | U13 - Piping Erection on Secondary Rack 544-PR-701 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 3.4903 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300210 | U13 - Piping Erection on Secondary Rack 544-PR-901 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 2.1835 | 10610.PI.PR.DI | 3718.05 | 0
C113131PIRA300210 | U13 - Piping Erection on Secondary Rack 544-PR-901 (Train 3) | PI | PIRA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33462 | 2.1835 | 10610.PI.PR.DI | 3718.05 | 0
C113131PISB100010 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-201 to 542-PR-301 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100030 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-301 to 542-PR-401 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100030 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-301 to 542-PR-401 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100050 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-501 to 542-PR-601 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB100080 | U13 - Small Bore Piping A/Equip. Erection - From 542-PR-801 to 542-PR-901 (Train 1) | PI | PISB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200040 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-401 to 543-PR-501 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200060 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-601 to 543-PR-701 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200070 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-701 to 543-PR-801 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113132CIDM100010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 1) | CI | CIDM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44509 | 2688.9502 | 10610.CI.CO.M3 | 890.18 | 773.24
C113132CIGR300010 | U13 - Grounding Network Execution (Train 3) | CI | CIGR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8400 | 10.6322 | 10780.CI.CI.MH
C113132CIHE100010 | U13 - Demethanizer Reboiler Foundation Execution (Train 1) for 542-E-118 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIHE100015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 1) for 542-E-128 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 603 | 0.53612 | 10610.CI.CO.M3 | 8.62 | 8.62
C113132CIHE100015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 1) for 542-E-128 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 603 | 0.53612 | 10610.CI.CO.M3 | 8.62 | 8.62
C113132CIHE100030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 1) for 542-E-113 (Warehouse Spare) | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5923 | 51.5481 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE100030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 1) for 542-E-113 (Warehouse Spare) | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5923 | 51.5481 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE200015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 2) for 543-E-128 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 603 | 0.35503 | 10610.CI.CO.M3 | 8.62 | 4.31
C113132CIHE300010 | U13 - Demethanizer Reboiler Foundation Execution (Train 3) for 544-E-118 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIHE300015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 3) for 544-E-128 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 603 | 0.53751 | 10610.CI.CO.M3 | 8.62 | 8.62
C113132CIHE300030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 3) for 544-E-113 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5923 | 51.8228 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE300090 | U13 - Exchangers (Residue Gas Recycle Chiller) Foundation Execution (Train 3) for 544-E-126 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2840 | 11.9169 | 10610.CI.CO.M3 | 47.34 | 47.34
C113132CIHE300100 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution (Train 2) for 543-E-109 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 767 | 0.82721 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIHE300110 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution (Train 3) for 544-E-109 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 767 | 0.8693 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIHE300110 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution (Train 3) for 544-E-109 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 767 | 0.8693 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIHE300130 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 2) 543-F-108A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 865 | 0.76452 | 10610.CI.CO.M3 | 12.36 | 6.18
C113132CIHE300140 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 1) 542-F-108A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 865 | 1.1056 | 10610.CI.CO.M3 | 12.36 | 12.36
C113131PISB200040 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-401 to 543-PR-501 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200050 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-501 to 543-PR-601 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB200090 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-901 to Batt. Limit (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB300040 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-401 to 544-PR-501 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300060 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-601 to 544-PR-701 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300070 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-701 to 544-PR-801 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300090 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-901 to Batt. Limit (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PIST100010 | U13 - Piping Steam Tracing Installation (Train 1) | PI | PIST2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5818 | 0 | 10780.PI.PI.MH
C113131PIST200010 | U13 - Piping Steam Tracing Installation (Train 2) | PI | PIST2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5818 | 0 | 10780.PI.PI.MH
C113131PISU100010 | U13 - Piping Supports Prefabrication (Train 1) | PI | PISU1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102124 | 2602.4075 | 10610.PI.PU.TN | 392.78 | 38.203
C113131PISU300010 | U13 - Piping Supports Prefabrication (Train 3) | PI | PISU1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 118840 | 9422.0914 | 10610.PI.PU.TN | 457.08 | 101.3289
C113131PISU300020 | U13 - Piping Supports Erection (Train 3) | PI | PISU2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 205685 | 0 | 10610.PI.SU.TN | 457.08 | 0
C113131PIUG200010 | U13 - Piping Erection UG (Train 2) | PI | PIUG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3194 | 0 | 10610.PI.UG.DI | 2129 | 0
C113131PRFL000220 | U13 - Lube Oil Flushing for Compressors (Unit 543) (Train 2) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13422 | 0 | 10780.PR.PR.MH
C113131PRFL100010 | U13 - Piping Flushing/Steam Blowing (Train 1) | PR | PRFL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19957 | 0 | 10610.PR.FL.DI | 286343 | 0
C113131PRFL200010 | U13 - Piping Flushing/Steam Blowing (Train 2) | PR | PRFL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20132 | 0 | 10610.PR.FL.DI | 280360 | 0
C113131PRHT300010 | U13 - Piping Hydrotesting (Train 3) | PR | PRHT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 269993 | 0 | 10610.PR.HT.DI | 281077 | 0
C113131PRRE100010 | U13 - Piping Reinstatement (Train 1) | PR | PRRE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 195342 | 0 | 10610.PR.RE.DI | 286343 | 0
C113132CICT100010 | U13 - Electrical earth Trenches Execution (Train 1) | CI | CICT2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2495 | 1.1955 | 10610.CI.ET.M3 | 623.74 | 623.74
C113131PISB200080 | U13 - Small Bore Piping A/Equip. Erection - From 543-PR-801 to 543-PR-901 (Train 2) | PI | PISB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3337 | 0 | 10610.PI.SB.DI | 303.36 | 0
C113131PISB300010 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-201 to 544-PR-301 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300050 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-501 to 544-PR-601 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300080 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-801 to 544-PR-901 (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PISB300090 | U13 - Small Bore Piping A/Equip. Erection - From 544-PR-901 to Batt. Limit (Train 3) | PI | PISB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6422 | 0 | 10610.PI.SB.DI | 583.79 | 0
C113131PIST200020 | U13 - Manifolds Installation (Train 2) | PI | PIST1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1027 | 0 | 10780.PI.PI.MH
C113131PIST300020 | U13 - Manifolds Installation (Train 3) | PI | PIST1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1027 | 0 | 10780.PI.PI.MH
C113131PISU100010 | U13 - Piping Supports Prefabrication (Train 1) | PI | PISU1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102124 | 2602.4075 | 10610.PI.PU.TN | 392.78 | 38.203
C113131PISU200020 | U13 - Piping Supports Erection (Train 2) | PI | PISU2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 176751 | 0 | 10610.PI.SU.TN | 392.78 | 0
C113131PISU300010 | U13 - Piping Supports Prefabrication (Train 3) | PI | PISU1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 118840 | 9422.0914 | 10610.PI.PU.TN | 457.08 | 101.3289
C113131PIUG100010 | U13 - Piping Erection UG (Train 1) | PI | PIUG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3176 | 0 | 10610.PI.UG.DI | 2117 | 0
C113131PIUG200010 | U13 - Piping Erection UG (Train 2) | PI | PIUG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3194 | 0 | 10610.PI.UG.DI | 2129 | 0
C113131PIUG300010 | U13 - Piping Erection UG (Train 3) (AOC/COC) | PI | PIUG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2834 | 2.6988 | 10610.PI.UG.DI | 1889 | 0
C113131PRBO100020 | U13 - Rotary Box Up (Train 1) | PR | PRBO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47958 | 0 | 10780.PR.PR.MH
C113131PRBO300010 | U13 - Static Box Up (Train 3) | PR | PRBO1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39216 | 0 | 10780.PR.PR.MH
C113131PRFL000210 | U13 - Lube Oil Flushing for Compressors (Unit 544) (Train 3) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14931 | 0 | 10780.PR.PR.MH
C113131PRFL300010 | U13 - Piping Flushing/Steam Blowing (Train 3) | PR | PRFL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22396 | 0 | 10610.PR.FL.DI | 281077 | 0
C113131PRHT100010 | U13 - Piping Hydrotesting (Train 1) | PR | PRHT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 244177 | 0 | 10610.PR.HT.DI | 286343 | 0
C113131PRHT200010 | U13 - Piping Hydrotesting (Train 2) | PR | PRHT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 241587 | 0 | 10610.PR.HT.DI | 280360 | 0
C113131PRHT300010 | U13 - Piping Hydrotesting (Train 3) | PR | PRHT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 269993 | 0 | 10610.PR.HT.DI | 281077 | 0
C113132CIHE300140 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 1) 542-F-108A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 865 | 1.1056 | 10610.CI.CO.M3 | 12.36 | 12.36
C113132CIHE300150 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 3) 544-F-110A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHF300010 | U13 - Regeneration Gas Heater Foundation Execution 544-ME-101 (TRAIN 3) | CI | CIHF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40617 | 2437.149 | 10610.CI.CO.M3 | 812.34 | 812.34
C113132CIHF300020 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution 542-E-109 (TRAIN 1) | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 767 | 0.86495 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIPE100050 | U13 - Skidded Equipment (Sales Gas Compressor) Foundation Execution (Train 1) 542-C-101 (inside 542-SH-001) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPE200010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 2) 543-ME-104 | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9455 | 18.4888 | 10610.CI.CO.M3 | 157.58 | 0
C113132CIPE200020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 2) 543-C-102 (inside 543-SH-002) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE200040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 2) 543-C-103 (inside 543-SH-004) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE300010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 3) 544-ME-104 | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7542 | 12.2265 | 10610.CI.CO.M3 | 125.7 | 0
C113132CIPE300020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 3) 544-C-102 (inside 544-SH-002) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE300040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 3) 544-C-103 (inside 544-SH-004) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.9299
C113132CIPE300050 | U13 - Skidded Equipment (Slaes Gas Compressor) Foundation Execution (Train 3) 544-C-101 (inside 544-SH-001) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPR100100 | U13 - 542-PR-104 Piperack Foundations Execution (Train 1) (542-E-106) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30090 | 1337.5301 | 10610.CI.CO.M3 | 601.79 | 601.79
C113132CIPR100110 | U13 - 542-PR-901 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7489 | 82.8497 | 10610.CI.CO.M3 | 124.81 | 124.81
C113132CIPR100110 | U13 - 542-PR-901 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7489 | 82.8497 | 10610.CI.CO.M3 | 124.81 | 124.81
C113132CIPR100150 | U13 - 542-PR-801 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20297 | 608.5974 | 10610.CI.CO.M3 | 405.94 | 405.941
C113132CICT200030 | U13 - Covered Concrete Trenches Execution (Train 2) | CI | CICT1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 70507 | 734.3933 | 10610.CI.CO.M3 | 1410.13 | 0
C113132CICT300010 | U13 - Electrical earth Trenches Execution (Train 3) | CI | CICT2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1900 | 0.62396 | 10610.CI.ET.M3 | 475 | 451.25
C113132CICT300030 | U13 - Covered Concrete Trenches Execution (Train 3) | CI | CICT1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63167 | 4106.988 | 10610.CI.CO.M3 | 1263.34 | 936.0174
C113132CIDB100025 | U13 - Duct Banks Precast Installation (Train 1) | CI | CIDB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5814 | 49.9363 | 10780.CI.CI.MH
C113132CIDB300015 | U13 - Duct Banks Precast Fabrication (Train 3) | CI | CIDB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40938 | 2405.2711 | 10780.CI.CI.MH
C113132CIDM200010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 2) | CI | CIDM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 46965 | 1435.1236 | 10610.CI.CO.M3 | 939.29 | 374.6579
C113132CIDM300010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 3) | CI | CIDM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 45502 | 2664.4709 | 10610.CI.CO.M3 | 910.03 | 910.0298
C113132CIGR100010 | U13 - Grounding Network Execution (Train 1) | CI | CIGR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 156 | 0.0061477 | 10610.CI.GR.LM | 260 | 26
C113132CIGT100010 | U13 - Equipment Grouting Execution (Train 1) | CI | CIGT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15500 | 60.5493 | 10780.CI.CI.MH
C113132CIGT200020 | U13 - Steel Structure Grouting Execution (Train 2) | CI | CIGT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15500 | 0 | 10780.CI.CI.MH
C113132CIGT300010 | U13 - Equipment Grouting Execution (Train 3) | CI | CIGT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15500 | 173.9105 | 10780.CI.CI.MH
C113132CIHE100010 | U13 - Demethanizer Reboiler Foundation Execution (Train 1) for 542-E-118 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIHE100040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 1) for 542-E-141 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1637 | 3.948 | 10610.CI.CO.M3 | 27.28 | 27.28
C113132CIHE100060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 1) 542-F-117A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE100090 | U13 - Exchangers (Residue Gas Recycle Cooler) Foundation Execution (Train 1) for 542-E-126 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2840 | 11.9169 | 10610.CI.CO.M3 | 47.34 | 47.34
C113132CIHE200010 | U13 - Demethanizer Reboiler Foundation Execution (Train 2) for 543-E-118 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIHE200060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 2) 543-F-117A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 818 | 0.95177 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE300010 | U13 - Demethanizer Reboiler Foundation Execution (Train 3) for 544-E-118 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIPE100010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 1) 542-ME-104 | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7542 | 9.4115 | 10610.CI.CO.M3 | 125.7 | 0
C113132CIPE100040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 1) 542-C-103 (inside 542-SH-004) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1185 | 2.0723 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE200040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 2) 543-C-103 (inside 543-SH-004) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE200050 | U13 - Skidded Equipment (Sales Gas Compressor) Foundation Execution (Train 2) 543-C-101 (inside 543-SH-001) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPE300010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 3) 544-ME-104 | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7542 | 12.2265 | 10610.CI.CO.M3 | 125.7 | 0
C113132CIPE300040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 3) 544-C-103 (inside 544-SH-004) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.9299
C113132CIPR100140 | U13 - 542-PR-101 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40054 | 2370.0537 | 10610.CI.CO.M3 | 801.08 | 801.08
C113132CIPR100140 | U13 - 542-PR-101 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40054 | 2370.0537 | 10610.CI.CO.M3 | 801.08 | 801.08
C113132CIPR100180 | U13 - 542-PR-106 Piperack Foundations Execution (Train 1) (542-E-120) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34584 | 1766.9198 | 10610.CI.CO.M3 | 691.68 | 691.68
C113132CIPR100200 | U13 - 542-PR-601 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7600 | 85.3239 | 10610.CI.CO.M3 | 126.66 | 126.66
C113132CIPR100200 | U13 - 542-PR-601 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7600 | 85.3239 | 10610.CI.CO.M3 | 126.66 | 126.66
C113132CIPR100210 | U13 - 542-PR-501 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21341 | 672.8154 | 10610.CI.CO.M3 | 426.82 | 426.8192
C113132CIPR100230 | U13 - 542-PR-109 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41822 | 2583.9017 | 10610.CI.CO.M3 | 836.44 | 836.44
C113132CIPR100240 | U13 - 542-PR-110 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.72
C113132CIPR100260 | U13 - 542-PR-111 Piperack Foundations Execution (Train 1) (542-E-112) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15044 | 334.3325 | 10610.CI.CO.M3 | 300.87 | 300.87
C113132CIPR100260 | U13 - 542-PR-111 Piperack Foundations Execution (Train 1) (542-E-112) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15044 | 334.3325 | 10610.CI.CO.M3 | 300.87 | 300.87
C113132CIPR100290 | U13 - 542-PR-301 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15598 | 359.4216 | 10610.CI.CO.M3 | 311.96 | 311.96
C113131PRRE300010 | U13 - Piping Reinstatement (Train 3) | PR | PRRE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 215995 | 0 | 10610.PR.RE.DI | 281077 | 0
C113132CICT300020 | U13 - Instrument earth Trenches Execution (Train 3) | CI | CICT3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9509 | 14.1593 | 10780.CI.CI.MH
C113132CICT300030 | U13 - Covered Concrete Trenches Execution (Train 3) | CI | CICT1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63167 | 4106.988 | 10610.CI.CO.M3 | 1263.34 | 936.0174
C113132CIDB300025 | U13 - Duct Banks Installation (Train 3) | CI | CIDB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66678 | 5352.9201 | 10610.CI.CO.M3 | 1333.57 | 1066.852
C113132CIDB300025 | U13 - Duct Banks Installation (Train 3) | CI | CIDB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66678 | 5352.9201 | 10610.CI.CO.M3 | 1333.57 | 1066.852
C113132CIDM100010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 1) | CI | CIDM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44509 | 2688.9502 | 10610.CI.CO.M3 | 890.18 | 773.24
C113132CIDM200010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 2) | CI | CIDM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 46965 | 1435.1236 | 10610.CI.CO.M3 | 939.29 | 374.6579
C113132CIDM300010 | U13 - Manholes & Catchbasins Installation (Precast) (Train 3) | CI | CIDM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 45502 | 2664.4709 | 10610.CI.CO.M3 | 910.03 | 910.0298
C113132CIGT100020 | U13 - Steel Structure Grouting Execution (Train 1) | CI | CIGT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15500 | 0 | 10780.CI.CI.MH
C113132CIGT300020 | U13 - Steel Structure Grouting Execution (Train 3) | CI | CIGT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15500 | 299.9069 | 10780.CI.CI.MH
C113132CIHE100020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 1) 542-F-107A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1245 | 2.277 | 10610.CI.CO.M3 | 17.78 | 17.78
C113132CIHE100040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 1) for 542-E-141 | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1637 | 3.948 | 10610.CI.CO.M3 | 27.28 | 27.28
C113132CIHE100060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 1) 542-F-117A/B | CI | CIHE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE200010 | U13 - Demethanizer Reboiler Foundation Execution (Train 2) for 543-E-118 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1556 | 3.5763 | 10610.CI.CO.M3 | 25.93 | 25.93
C113132CIHE200020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 2) 543-F-107A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1245 | 2.0957 | 10610.CI.CO.M3 | 17.78 | 17.7801
C113132CIHE200030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 2) for 543-E-113 (Warehouse Spare) | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5923 | 49.3679 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE200030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 2) for 543-E-113 (Warehouse Spare) | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5923 | 49.3679 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE200040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 2) for 543-E-141 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1637 | 2.5907 | 10610.CI.CO.M3 | 27.28 | 13.6401
C113132CIPR100150 | U13 - 542-PR-801 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20297 | 608.5974 | 10610.CI.CO.M3 | 405.94 | 405.941
C113132CIPR100170 | U13 - 542-PR-105 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR100190 | U13 - 542-PR-107 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37070 | 2030.0452 | 10610.CI.CO.M3 | 741.39 | 741.39
C113132CIPR100220 | U13 - 542-PR-108 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35964 | 1910.7169 | 10610.CI.CO.M3 | 719.27 | 719.27
C113132CIPR100250 | U13 - 542-PR-401 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12501 | 230.8546 | 10610.CI.CO.M3 | 250.01 | 250.01
C113132CIPR200110 | U13 - 543-PR-901 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7489 | 81.0767 | 10610.CI.CO.M3 | 124.81 | 124.8104
C113132CIPR200120 | U13 - 543-PR-102 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30749 | 1396.7585 | 10610.CI.CO.M3 | 614.97 | 614.9717
C113132CIPR200120 | U13 - 543-PR-102 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30749 | 1396.7585 | 10610.CI.CO.M3 | 614.97 | 614.9717
C113132CIPR200130 | U13 - 543-PR-103 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIPR200160 | U13 - 543-PR-701 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11453 | 146.6262 | 10610.CI.CO.M3 | 229.06 | 192.4113
C113132CIPR200190 | U13 - 543-PR-107 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37070 | 2030.0452 | 10610.CI.CO.M3 | 741.39 | 741.39
C113132CIPR200200 | U13 - 543-PR-601 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7600 | 74.0193 | 10610.CI.CO.M3 | 126.66 | 106.3948
C113132CIPR200210 | U13 - 543-PR-501 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19081 | 472.3141 | 10610.CI.CO.M3 | 381.61 | 320.5532
C113132CIPR200270 | U13 - 543-PR-112 Piperack Foundations Execution (Train 2) (543-E-112) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 45823 | 3101.9064 | 10610.CI.CO.M3 | 916.45 | 916.4545
C113132CIPR200300 | U13 - 543-PR-201 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25565 | 963.0801 | 10610.CI.CO.M3 | 511.29 | 511.2912
C113132CIPR200300 | U13 - 543-PR-201 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25565 | 963.0801 | 10610.CI.CO.M3 | 511.29 | 511.2912
C113132CIPR300120 | U13 - 544-PR-102 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30749 | 1396.7585 | 10610.CI.CO.M3 | 614.97 | 614.97
C113132CIPR300130 | U13 - 544-PR-103 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIHE300015 | U13 - Heat Exchangers (Regeneration Gas Superheater) Foundation Execution (Train 3) for 544-E-128 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 603 | 0.53751 | 10610.CI.CO.M3 | 8.62 | 8.62
C113132CIHE300020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 3) 544-F-107A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1245 | 2.2891 | 10610.CI.CO.M3 | 17.78 | 17.78
C113132CIHE300020 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 3) 544-F-107A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1245 | 2.2891 | 10610.CI.CO.M3 | 17.78 | 17.78
C113132CIHE300030 | U13 - Gas/Gas Exchanger Foundation Execution (Train 3) for 544-E-113 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5923 | 51.8228 | 10610.CI.CO.M3 | 98.71 | 98.71
C113132CIHE300040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 3) for 544-E-141 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1637 | 3.9583 | 10610.CI.CO.M3 | 27.28 | 27.2799
C113132CIHE300160 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 2) 543-F-110A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 818 | 0.68379 | 10610.CI.CO.M3 | 11.69 | 5.85
C113132CIHF100010 | U13 - Regeneration Gas Heater Foundation Execution 542-ME-101 (TRAIN 1) | CI | CIHF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12780 | 241.2838 | 10610.CI.CO.M3 | 255.6 | 255.601
C113132CIHF200010 | U13 - Regeneration Gas Heater Foundation Execution 543-ME-101 (TRAIN 2) | CI | CIHF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12780 | 241.2838 | 10610.CI.CO.M3 | 255.6 | 255.5999
C113132CIMF100010 | U13 - Miscellaneous Foundations Execution (Train 1) | CI | CIMF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10223 | 58.6676 | 10610.CI.CO.M3 | 170.38 | 51.1147
C113132CIMF200010 | U13 - Miscellaneous Foundations Execution (Train 2) | CI | CIMF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 36356 | 750.7839 | 10610.CI.CO.M3 | 727.12 | 254.4935
C113132CIMF200010 | U13 - Miscellaneous Foundations Execution (Train 2) | CI | CIMF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 36356 | 750.7839 | 10610.CI.CO.M3 | 727.12 | 254.4935
C113132CIPD200010 | U13 - Fabrication Precast Drainage Man Holes & Catchbasins (Train 2) | CI | CIPD | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7565 | 76.614 | 10780.CI.CI.MH
C113132CIPD300010 | U13 - Fabrication Precast Drainage Man Holes & Catchbasins (Train 3) | CI | CIPD | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7320 | 76.6571 | 10780.CI.CI.MH
C113132CIPE100010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 1) 542-ME-104 | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7542 | 9.4115 | 10610.CI.CO.M3 | 125.7 | 0
C113132CIPE100020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 1) 542-C-102 (inside 542-SH-002) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE100040 | U13 - Skidded Equipment (Regeneration Gas Compressor) Foundation Execution (Train 1) 542-C-103 (inside 542-SH-004) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1185 | 2.0723 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE200010 | U13 - Packaged Equipment (Methanol Injection Package) Foundation Execution (Train 2) 543-ME-104 | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9455 | 18.4888 | 10610.CI.CO.M3 | 157.58 | 0
C113132CIHE200040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 2) for 543-E-141 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1637 | 2.5907 | 10610.CI.CO.M3 | 27.28 | 13.6401
C113132CIHE200060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 2) 543-F-117A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 818 | 0.95177 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE200090 | U13 - Exchangers (Residue Gas Recycle Cooler) Foundation Execution (Train 2) for 543-E-126 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2840 | 9.5837 | 10610.CI.CO.M3 | 47.34 | 23.6698
C113132CIHE200090 | U13 - Exchangers (Residue Gas Recycle Cooler) Foundation Execution (Train 2) for 543-E-126 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2840 | 9.5837 | 10610.CI.CO.M3 | 47.34 | 23.6698
C113132CIHE300040 | U13 - Exchangers (Habshan 1 Train 3 Feed Gas Chiller) Foundation Execution (Train 3) for 544-E-141 | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1637 | 3.9583 | 10610.CI.CO.M3 | 27.28 | 27.2799
C113132CIHE300060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 3) 544-F-117A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE300060 | U13 - Horizontal Vessels (Regeneration Gas Inlet Filter) Foundation Execution (Train 3) 544-F-117A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHE300100 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) Foundation Execution (Train 2) for 543-E-109 | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 767 | 0.82721 | 10610.CI.CO.M3 | 10.96 | 10.96
C113132CIHE300120 | U13 - Horizontal Vessels (Dehydration Outlet Gas Filter) Foundation Execution (Train 3) 544-F-108A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 865 | 1.1056 | 10610.CI.CO.M3 | 12.36 | 12.36
C113132CIHE300130 | U13 - Horizontal Vessels (Dehydration Inlet Gas Filter) Foundation Execution (Train 2) 543-F-108A/B | CI | CIHE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 865 | 0.76452 | 10610.CI.CO.M3 | 12.36 | 6.18
C113132CIHE300150 | U13 - Horizontal Vessels (Feed Gas Dust Filter) Foundation Execution (Train 3) 544-F-110A/B | CI | CIHE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0.98885 | 10610.CI.CO.M3 | 11.69 | 11.69
C113132CIHF100010 | U13 - Regeneration Gas Heater Foundation Execution 542-ME-101 (TRAIN 1) | CI | CIHF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12780 | 241.2838 | 10610.CI.CO.M3 | 255.6 | 255.601
C113132CIMF100010 | U13 - Miscellaneous Foundations Execution (Train 1) | CI | CIMF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10223 | 58.6676 | 10610.CI.CO.M3 | 170.38 | 51.1147
C113132CIMF300010 | U13 - Miscellaneous Foundations Execution (Train 3) | CI | CIMF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10223 | 65.9238 | 10610.CI.CO.M3 | 170.38 | 60.0776
C113132CIPE100020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 1) 542-C-102 (inside 542-SH-002) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE100050 | U13 - Skidded Equipment (Sales Gas Compressor) Foundation Execution (Train 1) 542-C-101 (inside 542-SH-001) | CI | CIPE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPR100300 | U13 - 542-PR-201 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25565 | 965.4938 | 10610.CI.CO.M3 | 511.29 | 511.29
C113132CIPR200130 | U13 - 543-PR-103 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIPR200140 | U13 - 543-PR-101 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40158 | 2382.3477 | 10610.CI.CO.M3 | 803.15 | 803.15
C113132CIPR200160 | U13 - 543-PR-701 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11453 | 146.6262 | 10610.CI.CO.M3 | 229.06 | 192.4113
C113132CIPR200230 | U13 - 543-PR-109 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41102 | 2495.6692 | 10610.CI.CO.M3 | 822.03 | 822.0311
C113132CIPR200240 | U13 - 543-PR-110 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.722
C113132CIPR200250 | U13 - 543-PR-401 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12338 | 220.0702 | 10610.CI.CO.M3 | 246.76 | 246.7611
C113132CIPR300100 | U13 - 544-PR-104 Piperack Foundations Execution (Train 3) (544-E-106) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29159 | 1256.0421 | 10610.CI.CO.M3 | 583.17 | 583.17
C113132CIPR300110 | U13 - 544-PR-901 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7489 | 82.8497 | 10610.CI.CO.M3 | 124.81 | 124.81
C113132CIPR300120 | U13 - 544-PR-102 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30749 | 1396.7585 | 10610.CI.CO.M3 | 614.97 | 614.97
C113132CIPR300140 | U13 - 544-PR-101 Piperack Foundations Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41617 | 2558.6327 | 10610.CI.CO.M3 | 832.34 | 832.34
C113132CIPR300150 | U13 - 544-PR-801 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20297 | 608.5974 | 10610.CI.CO.M3 | 405.94 | 405.94
C113132CIPR300200 | U13 - 544-PR-601 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7600 | 85.3239 | 10610.CI.CO.M3 | 126.66 | 126.66
C113132CIPR300230 | U13 - 544-PR-109 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41822 | 2583.9017 | 10610.CI.CO.M3 | 836.44 | 836.44
C113132CIPR300250 | U13 - 544-PR-401 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12338 | 224.8826 | 10610.CI.CO.M3 | 246.76 | 246.76
C113132CIPR300300 | U13 - 544-PR-201 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25565 | 965.4938 | 10610.CI.CO.M3 | 511.29 | 511.29
C113132CIPS100010 | U13 - Warm Closed Drain Sump 542-SU-101 (Train 1) (542-V-133; 542-P-110A/B) | CI | CIPS1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13433 | 223.1114 | 10610.CI.CO.M3 | 268.65 | 268.6491
C113132CIPS100020 | U13 - Oil Water Sump 542-SU-502 (Train 1) (542-P-501A/B) | CI | CIPS2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2632 | 7.6841 | 10610.CI.CO.M3 | 43.87 | 43.87
C113132CIPE200050 | U13 - Skidded Equipment (Sales Gas Compressor) Foundation Execution (Train 2) 543-C-101 (inside 543-SH-001) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPE300050 | U13 - Skidded Equipment (Slaes Gas Compressor) Foundation Execution (Train 3) 544-C-101 (inside 544-SH-001) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 729 | 0.78552 | 10610.CI.CO.M3 | 10.42 | 10.42
C113132CIPR100100 | U13 - 542-PR-104 Piperack Foundations Execution (Train 1) (542-E-106) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30090 | 1337.5301 | 10610.CI.CO.M3 | 601.79 | 601.79
C113132CIPR100130 | U13 - 542-PR-103 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIPR100180 | U13 - 542-PR-106 Piperack Foundations Execution (Train 1) (542-E-120) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34584 | 1766.9198 | 10610.CI.CO.M3 | 691.68 | 691.68
C113132CIPR100210 | U13 - 542-PR-501 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21341 | 672.8154 | 10610.CI.CO.M3 | 426.82 | 426.8192
C113132CIPR100220 | U13 - 542-PR-108 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35964 | 1910.7169 | 10610.CI.CO.M3 | 719.27 | 719.27
C113132CIPR100230 | U13 - 542-PR-109 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41822 | 2583.9017 | 10610.CI.CO.M3 | 836.44 | 836.44
C113132CIPR100270 | U13 - 542-PR-112 Piperack Foundations Execution (Train 1) (542-E-112) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 45349 | 3038.0983 | 10610.CI.CO.M3 | 906.98 | 906.98
C113132CIPR100270 | U13 - 542-PR-112 Piperack Foundations Execution (Train 1) (542-E-112) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 45349 | 3038.0983 | 10610.CI.CO.M3 | 906.98 | 906.98
C113132CIPR100300 | U13 - 542-PR-201 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25565 | 965.4938 | 10610.CI.CO.M3 | 511.29 | 511.29
C113132CIPR200100 | U13 - 543-PR-104 Piperack Foundations Execution (Train 2) (543-E-106) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31202 | 1438.2166 | 10610.CI.CO.M3 | 624.03 | 624.03
C113132CIPR200100 | U13 - 543-PR-104 Piperack Foundations Execution (Train 2) (543-E-106) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31202 | 1438.2166 | 10610.CI.CO.M3 | 624.03 | 624.03
C113132CIPR200110 | U13 - 543-PR-901 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7489 | 81.0767 | 10610.CI.CO.M3 | 124.81 | 124.8104
C113132CIPR200150 | U13 - 543-PR-801 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20297 | 595.5734 | 10610.CI.CO.M3 | 405.94 | 405.9413
C113132CIPR200190 | U13 - 543-PR-107 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37070 | 2030.0452 | 10610.CI.CO.M3 | 741.39 | 741.39
C113132CIPR200200 | U13 - 543-PR-601 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7600 | 74.0193 | 10610.CI.CO.M3 | 126.66 | 106.3948
C113132CIPR200220 | U13 - 543-PR-108 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 35994 | 1913.9059 | 10610.CI.CO.M3 | 719.87 | 719.8714
C113132CIPR300160 | U13 - 544-PR-701 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11453 | 113.1025 | 10610.CI.CO.M3 | 229.06 | 229.0599
C113132CIPR300190 | U13 - 544-PR-107 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36287 | 1945.1923 | 10610.CI.CO.M3 | 725.73 | 725.73
C113132CIPR300190 | U13 - 544-PR-107 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36287 | 1945.1923 | 10610.CI.CO.M3 | 725.73 | 725.73
C113132CIPR300220 | U13 - 544-PR-108 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35994 | 1913.9059 | 10610.CI.CO.M3 | 719.87 | 719.87
C113132CIPR300230 | U13 - 544-PR-109 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41822 | 2583.9017 | 10610.CI.CO.M3 | 836.44 | 836.44
C113132CIPR300240 | U13 - 544-PR-110 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.72
C113132CIPR300260 | U13 - 544-PR-111 Piperack Foundations Execution (Train 3) (544-E-112) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15217 | 342.0775 | 10610.CI.CO.M3 | 304.34 | 304.34
C113132CIPR300290 | U13 - 544-PR-301 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15598 | 359.4216 | 10610.CI.CO.M3 | 311.96 | 311.96
C113132CIPS200020 | U13 - Oil Water Sump 543-SU-502 (Train 2) (543-P-501A/B) | CI | CIPS2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2648 | 0.82882 | 10610.CI.CO.M3 | 44.14 | 0
C113132CIPV100020 | U13 - Gravel Paving Execution (Train 1) | CI | CIPV2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29374 | 0 | 10610.CI.GV.M2 | 48956 | 0
C113132CIPV100020 | U13 - Gravel Paving Execution (Train 1) | CI | CIPV2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29374 | 0 | 10610.CI.GV.M2 | 48956 | 0
C113132CIPV300010 | U13 - Concrete Paving Execution (Train 3) | CI | CIPV1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 58749 | 2948.0481 | 10610.CI.PV.M2 | 32638.08 | 17017.4949
C113132CIPV300020 | U13 - Gravel Paving Execution (Train 3) | CI | CIPV2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27334 | 573.9569 | 10610.CI.GV.M2 | 45557 | 0
C113132CIRE100010 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109A (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE100060 | U13 - Expander/Compressor Foundation Execution 542-EC-101 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3019 | 13.4062 | 10610.CI.CO.M3 | 50.32 | 50.32
C113132CIRE100070 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109B (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3761 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE100070 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109B (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3761 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE100080 | U13 - Propane Compressor Foundation Execution 542-C-102; 542-CM-102 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21954 | 712.0063 | 10610.CI.CO.M3 | 439.07 | 439.07
C113132CIRE100080 | U13 - Propane Compressor Foundation Execution 542-C-102; 542-CM-102 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21954 | 712.0063 | 10610.CI.CO.M3 | 439.07 | 439.07
C113132CIRE100090 | U13 - Regeneration Gas Compressor Foundation Execution 542-C-103; 542-CM-103 (Train 1) | CI | CIRE3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19184 | 543.6675 | 10610.CI.CO.M3 | 383.67 | 383.67
C113132CIRE100110 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109C (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200010 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109A (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1211 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200020 | U13 - Sales Gas Compressor Foundation Execution 543-C-101; 543-CM-101 (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23248 | 735.7545 | 10610.CI.CO.M3 | 464.96 | 464.962
C113132CIRE200090 | U13 - Regeneration Gas Compressor Foundation Execution 543-C-103; 543-CM-103 (Train 2) | CI | CIRE2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22118 | 685.8424 | 10610.CI.CO.M3 | 442.36 | 442.36
C113132CIRE300010 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109A (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE300060 | U13 - Expander/Compressor Foundation Execution 544-EC-101 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3019 | 12.8797 | 10610.CI.CO.M3 | 50.32 | 50.32
C113132CIRE300070 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109B (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE300080 | U13 - Propane Compressor Foundation Execution 544-C-102; 544-CM-102 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19019 | 534.3696 | 10610.CI.CO.M3 | 380.38 | 380.38
C113132CIRE300090 | U13 - Regeneration Gas Compressor Foundation Execution 544-C-103; 544-CM-103 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16249 | 373.0823 | 10610.CI.CO.M3 | 324.98 | 324.98
C113132CIRE300110 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109C (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CISF200010 | U13 - Stairs & Small Foundations Execution (Train 2) | CI | CISF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1553 | 0.36515 | 10610.CI.CO.M3 | 25.88 | 0
C113132CIST100080 | U13 - 542-STR-005 Structure Foundation Execution (Train 1) for 542-E-128; 542-E-129 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3318 | 16.1612 | 10610.CI.CO.M3 | 55.3 | 55.3
C113132CIST100140 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-402 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2184 | 6.9091 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST100221 | U13 - 542-STR-011 Structure Foundation Execution | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11095 | 180.1289 | 10610.CI.CO.M3 | 184.92 | 184.92
C113132CIST100230 | U13 - Compressor Shelter 542-SH-003 Foundation Execution (Train 1) (542-EC-101) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10016 | 146.8003 | 10610.CI.CO.M3 | 166.94 | 166.94
C113132CIPR200220 | U13 - 543-PR-108 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 35994 | 1913.9059 | 10610.CI.CO.M3 | 719.87 | 719.8714
C113132CIPR200230 | U13 - 543-PR-109 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41102 | 2495.6692 | 10610.CI.CO.M3 | 822.03 | 822.0311
C113132CIPR200250 | U13 - 543-PR-401 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12338 | 220.0702 | 10610.CI.CO.M3 | 246.76 | 246.7611
C113132CIPR200260 | U13 - 543-PR-111 Piperack Foundations Execution (Train 2) (543-E-112) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15245 | 343.3375 | 10610.CI.CO.M3 | 304.9 | 304.9013
C113132CIPR200290 | U13 - 543-PR-301 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15598 | 345.5839 | 10610.CI.CO.M3 | 311.96 | 311.9614
C113132CIPR300140 | U13 - 544-PR-101 Piperack Foundations Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41617 | 2558.6327 | 10610.CI.CO.M3 | 832.34 | 832.34
C113132CIPR300150 | U13 - 544-PR-801 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20297 | 608.5974 | 10610.CI.CO.M3 | 405.94 | 405.94
C113132CIPR300160 | U13 - 544-PR-701 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11453 | 113.1025 | 10610.CI.CO.M3 | 229.06 | 229.0599
C113132CIPR300170 | U13 - 544-PR-105 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR300180 | U13 - 544-PR-106 Piperack Foundations Execution (Train 3) (544-E-120) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34432 | 1751.4224 | 10610.CI.CO.M3 | 688.64 | 688.64
C113132CIPR300210 | U13 - 544-PR-501 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19081 | 537.8452 | 10610.CI.CO.M3 | 381.61 | 381.61
C113132CIPR300220 | U13 - 544-PR-108 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35994 | 1913.9059 | 10610.CI.CO.M3 | 719.87 | 719.87
C113132CIPR300240 | U13 - 544-PR-110 Piperack Foundations Execution (Train 3) (544-E-119) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.72
C113132CIPR300250 | U13 - 544-PR-401 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12338 | 224.8826 | 10610.CI.CO.M3 | 246.76 | 246.76
C113132CIPR300270 | U13 - 544-PR-112 Piperack Foundations Execution (Train 3) (544-E-112) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43681 | 2818.7174 | 10610.CI.CO.M3 | 873.62 | 873.62
C113132CIPR300290 | U13 - 544-PR-301 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15598 | 359.4216 | 10610.CI.CO.M3 | 311.96 | 311.96
C113132CIPR300300 | U13 - 544-PR-201 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25565 | 965.4938 | 10610.CI.CO.M3 | 511.29 | 511.29
C113132CIPS100010 | U13 - Warm Closed Drain Sump 542-SU-101 (Train 1) (542-V-133; 542-P-110A/B) | CI | CIPS1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13433 | 223.1114 | 10610.CI.CO.M3 | 268.65 | 268.6491
C113132CIPE200020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 2) 543-C-102 (inside 543-SH-002) | CI | CIPE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPE300020 | U13 - Skidded Equipment (Propane Compressor) Foundation Execution (Train 3) 544-C-102 (inside 544-SH-002) | CI | CIPE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1185 | 2.0746 | 10610.CI.CO.M3 | 16.93 | 16.93
C113132CIPR100120 | U13 - 542-PR-102 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30911 | 1411.515 | 10610.CI.CO.M3 | 618.21 | 618.21
C113132CIPR100120 | U13 - 542-PR-102 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30911 | 1411.515 | 10610.CI.CO.M3 | 618.21 | 618.21
C113132CIPR100130 | U13 - 542-PR-103 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIPR100160 | U13 - 542-PR-701 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10578 | 163.3332 | 10610.CI.CO.M3 | 176.3 | 176.3008
C113132CIPR100160 | U13 - 542-PR-701 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10578 | 163.3332 | 10610.CI.CO.M3 | 176.3 | 176.3008
C113132CIPR100170 | U13 - 542-PR-105 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR100190 | U13 - 542-PR-107 Piperack Foundations Execution (Train 1) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 37070 | 2030.0452 | 10610.CI.CO.M3 | 741.39 | 741.39
C113132CIPR100240 | U13 - 542-PR-110 Piperack Foundations Execution (Train 1) (542-E-119) | CI | CIPR1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.72
C113132CIPR100250 | U13 - 542-PR-401 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12501 | 230.8546 | 10610.CI.CO.M3 | 250.01 | 250.01
C113132CIPR100290 | U13 - 542-PR-301 Secondary Piperack Foundations Execution (Train 1) | CI | CIPR2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15598 | 359.4216 | 10610.CI.CO.M3 | 311.96 | 311.96
C113132CIPR200140 | U13 - 543-PR-101 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40158 | 2382.3477 | 10610.CI.CO.M3 | 803.15 | 803.15
C113132CIPR200150 | U13 - 543-PR-801 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20297 | 595.5734 | 10610.CI.CO.M3 | 405.94 | 405.9413
C113132CIPR200170 | U13 - 543-PR-105 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR200170 | U13 - 543-PR-105 Piperack Foundations Execution (Train 2) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR200180 | U13 - 543-PR-106 Piperack Foundations Execution (Train 2) (543-E-120) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34584 | 1766.9198 | 10610.CI.CO.M3 | 691.68 | 691.68
C113132CIPR200180 | U13 - 543-PR-106 Piperack Foundations Execution (Train 2) (543-E-120) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34584 | 1766.9198 | 10610.CI.CO.M3 | 691.68 | 691.68
C113132CIPS200020 | U13 - Oil Water Sump 543-SU-502 (Train 2) (543-P-501A/B) | CI | CIPS2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2648 | 0.82882 | 10610.CI.CO.M3 | 44.14 | 0
C113132CIPS300020 | U13 - Oil Water Sump 544-SU-502 (Train 3) (544-P-501A/B) | CI | CIPS2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2648 | 6.9621 | 10610.CI.CO.M3 | 44.14 | 44.14
C113132CIPV100010 | U13 - Concrete Paving Execution (Train 1) | CI | CIPV1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 58749 | 578.7085 | 10610.CI.PV.M2 | 32638.08 | 0
C113132CIPV200010 | U13 - Concrete Paving Execution (Train 2) | CI | CIPV1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 58749 | 560.8628 | 10610.CI.PV.M2 | 32638.08 | 0
C113132CIPV200010 | U13 - Concrete Paving Execution (Train 2) | CI | CIPV1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 58749 | 560.8628 | 10610.CI.PV.M2 | 32638.08 | 0
C113132CIPV300010 | U13 - Concrete Paving Execution (Train 3) | CI | CIPV1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 58749 | 2948.0481 | 10610.CI.PV.M2 | 32638.08 | 17017.4949
C113132CIRE100020 | U13 - Sales Gas Compressor Foundation Execution 542-C-101; 542-CM-101 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23248 | 798.4314 | 10610.CI.CO.M3 | 464.96 | 464.96
C113132CIRE100020 | U13 - Sales Gas Compressor Foundation Execution 542-C-101; 542-CM-101 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23248 | 798.4314 | 10610.CI.CO.M3 | 464.96 | 464.96
C113132CIRE100060 | U13 - Expander/Compressor Foundation Execution 542-EC-101 (Train 1) | CI | CIRE2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3019 | 13.4062 | 10610.CI.CO.M3 | 50.32 | 50.32
C113132CIRE200050 | U13 - Propane Return Pump Foundation Execution 543-P-112 (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1100 | 0.19211 | 10610.CI.CO.M3 | 15.71 | 0
C113132CIRE200060 | U13 - Expander/Compressor Foundation Execution 543-EC-101 (Train 2) | CI | CIRE2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3019 | 12.5565 | 10610.CI.CO.M3 | 50.32 | 50.3201
C113132CIRE300010 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109A (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE300020 | U13 - Sales Gas Compressor Foundation Execution 544-C-101; 544-CM-101 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23248 | 798.4314 | 10610.CI.CO.M3 | 464.96 | 464.96
C113132CIRE300020 | U13 - Sales Gas Compressor Foundation Execution 544-C-101; 544-CM-101 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23248 | 798.4314 | 10610.CI.CO.M3 | 464.96 | 464.96
C113132CIRE300050 | U13 - Propane Return Pump Foundation Execution 544-P-112 (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1100 | 1.787 | 10610.CI.CO.M3 | 15.71 | 15.71
C113132CIRE300110 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109C (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CISF200010 | U13 - Stairs & Small Foundations Execution (Train 2) | CI | CISF | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1553 | 0.36515 | 10610.CI.CO.M3 | 25.88 | 0
C113132CIST100110 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-401 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4304 | 26.7928 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST100240 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-004) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2106 | 6.4899 | 10610.CI.CO.M3 | 35.1 | 35.1
C113132CIST100270 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-002) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2477 | 9.0654 | 10610.CI.CO.M3 | 41.29 | 41.29
C113132CIST100280 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-001) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13574 | 272.1962 | 10610.CI.CO.M3 | 271.48 | 271.48
C113132CIST100281 | U13 - 542-STR-006 Structure Foundation Execution (Train 1) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1304 | 2.5116 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIST200140 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-402 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2184 | 6.4531 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST200190 | U13 - 543-STR-007 Structure Foundation Execution (Train 2) for 543-E-114A/B | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20284 | 498.5141 | 10610.CI.CO.M3 | 405.68 | 365.4413
C113132CIST200240 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-004) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2106 | 5.0026 | 10610.CI.CO.M3 | 35.1 | 29.484
C113132CIST300080 | U13 - 544-STR-005 Structure Foundation Execution (Train 3) for 544-E-128; 544-E-129 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3318 | 15.2147 | 10610.CI.CO.M3 | 55.3 | 55.3
C113132CIST300080 | U13 - 544-STR-005 Structure Foundation Execution (Train 3) for 544-E-128; 544-E-129 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3318 | 15.2147 | 10610.CI.CO.M3 | 55.3 | 55.3
C113132CIST300120 | U13 - Compressor Shelter 544-SH-002 Foundation Execution (Train 3) (544-C-102; 544-CM-102) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 48685 | 3429.7047 | 10610.CI.CO.M3 | 973.69 | 973.69
C113132CIST300140 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-402 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2184 | 6.5356 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST300150 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-403 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2184 | 6.5356 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST300270 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-002) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2815 | 11.7072 | 10610.CI.CO.M3 | 46.92 | 46.92
C113132CIST300290 | U13 - 544-STR-010 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 489 | 0.35347 | 10610.CI.CO.M3 | 6.99 | 6.99
C113132CIST300300 | U13 - 543-STR-010 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 489 | 0.26384 | 10610.CI.CO.M3 | 6.99 | 5.8716
C113132CIST300301 | U13 - 543-STR-006 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1304 | 2.3886 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIUG100040 | U13 - UG Pipe Installation (Train 1) (CD) | CI | CIUG2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16796 | 233.0499 | 10610.CI.UG.LM | 839.81 | 839.8102
C113132CIUG100040 | U13 - UG Pipe Installation (Train 1) (CD) | CI | CIUG2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16796 | 233.0499 | 10610.CI.UG.LM | 839.81 | 839.8102
C113132CIPR200210 | U13 - 543-PR-501 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19081 | 472.3141 | 10610.CI.CO.M3 | 381.61 | 320.5532
C113132CIPR200240 | U13 - 543-PR-110 Piperack Foundations Execution (Train 2) (543-E-119) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32436 | 1554.2504 | 10610.CI.CO.M3 | 648.72 | 648.722
C113132CIPR200260 | U13 - 543-PR-111 Piperack Foundations Execution (Train 2) (543-E-112) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15245 | 343.3375 | 10610.CI.CO.M3 | 304.9 | 304.9013
C113132CIPR200270 | U13 - 543-PR-112 Piperack Foundations Execution (Train 2) (543-E-112) | CI | CIPR1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 45823 | 3101.9064 | 10610.CI.CO.M3 | 916.45 | 916.4545
C113132CIPR200290 | U13 - 543-PR-301 Secondary Piperack Foundations Execution (Train 2) | CI | CIPR2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15598 | 345.5839 | 10610.CI.CO.M3 | 311.96 | 311.9614
C113132CIPR300100 | U13 - 544-PR-104 Piperack Foundations Execution (Train 3) (544-E-106) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29159 | 1256.0421 | 10610.CI.CO.M3 | 583.17 | 583.17
C113132CIPR300110 | U13 - 544-PR-901 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7489 | 82.8497 | 10610.CI.CO.M3 | 124.81 | 124.81
C113132CIPR300130 | U13 - 544-PR-103 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39514 | 2306.5793 | 10610.CI.CO.M3 | 790.28 | 790.28
C113132CIPR300170 | U13 - 544-PR-105 Piperack Foundations Execution (Train 3) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25913 | 991.9774 | 10610.CI.CO.M3 | 518.26 | 518.26
C113132CIPR300180 | U13 - 544-PR-106 Piperack Foundations Execution (Train 3) (544-E-120) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34432 | 1751.4224 | 10610.CI.CO.M3 | 688.64 | 688.64
C113132CIPR300200 | U13 - 544-PR-601 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7600 | 85.3239 | 10610.CI.CO.M3 | 126.66 | 126.66
C113132CIPR300210 | U13 - 544-PR-501 Secondary Piperack Foundations Execution (Train 3) | CI | CIPR2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19081 | 537.8452 | 10610.CI.CO.M3 | 381.61 | 381.61
C113132CIPR300260 | U13 - 544-PR-111 Piperack Foundations Execution (Train 3) (544-E-112) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15217 | 342.0775 | 10610.CI.CO.M3 | 304.34 | 304.34
C113132CIPR300270 | U13 - 544-PR-112 Piperack Foundations Execution (Train 3) (544-E-112) | CI | CIPR1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43681 | 2818.7174 | 10610.CI.CO.M3 | 873.62 | 873.62
C113132CIPS100020 | U13 - Oil Water Sump 542-SU-502 (Train 1) (542-P-501A/B) | CI | CIPS2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2632 | 7.6841 | 10610.CI.CO.M3 | 43.87 | 43.87
C113132CIPS200010 | U13 - Warm Closed Drain Sump 543-SU-101 (Train 2) (543-V-133; 543-P-110A/B) | CI | CIPS1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13433 | 41.9833 | 10610.CI.CO.M3 | 268.65 | 0
C113132CIPV100010 | U13 - Concrete Paving Execution (Train 1) | CI | CIPV1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 58749 | 578.7085 | 10610.CI.PV.M2 | 32638.08 | 0
C113132CIPV200020 | U13 - Gravel Paving Execution (Train 2) | CI | CIPV2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27334 | 195.918 | 10610.CI.GV.M2 | 45557 | 0
C113132CIPS200010 | U13 - Warm Closed Drain Sump 543-SU-101 (Train 2) (543-V-133; 543-P-110A/B) | CI | CIPS1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13433 | 41.9833 | 10610.CI.CO.M3 | 268.65 | 0
C113132CIPS300010 | U13 - Warm Closed Drain Sump 544-SU-101 (Train 3) (544-V-133; 544-P-110A/B) | CI | CIPS1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13433 | 214.0483 | 10610.CI.CO.M3 | 268.65 | 268.6502
C113132CIPS300010 | U13 - Warm Closed Drain Sump 544-SU-101 (Train 3) (544-V-133; 544-P-110A/B) | CI | CIPS1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13433 | 214.0483 | 10610.CI.CO.M3 | 268.65 | 268.6502
C113132CIPS300020 | U13 - Oil Water Sump 544-SU-502 (Train 3) (544-P-501A/B) | CI | CIPS2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2648 | 6.9621 | 10610.CI.CO.M3 | 44.14 | 44.14
C113132CIPV300020 | U13 - Gravel Paving Execution (Train 3) | CI | CIPV2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27334 | 573.9569 | 10610.CI.GV.M2 | 45557 | 0
C113132CIRE100010 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109A (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE100050 | U13 - Propane Return Pump Foundation Execution 542-P-112 (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2374 | 8.3265 | 10610.CI.CO.M3 | 39.57 | 39.57
C113132CIRE100090 | U13 - Regeneration Gas Compressor Foundation Execution 542-C-103; 542-CM-103 (Train 1) | CI | CIRE3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19184 | 543.6675 | 10610.CI.CO.M3 | 383.67 | 383.67
C113132CIRE100110 | U13 - Demethanizer Bottoms Pump Foundation Execution 542-P-109C (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200010 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109A (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1211 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200050 | U13 - Propane Return Pump Foundation Execution 543-P-112 (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1100 | 0.19211 | 10610.CI.CO.M3 | 15.71 | 0
C113132CIRE200060 | U13 - Expander/Compressor Foundation Execution 543-EC-101 (Train 2) | CI | CIRE2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3019 | 12.5565 | 10610.CI.CO.M3 | 50.32 | 50.3201
C113132CIRE200070 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109B (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1431 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200070 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109B (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1431 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200080 | U13 - Propane Compressor Foundation Execution 543-C-102; 543-CM-102 (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21954 | 665.7259 | 10610.CI.CO.M3 | 439.07 | 439.07
C113132CIRE200110 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109C (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1211 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE200110 | U13 - Demethanizer Bottoms Pump Foundation Execution 543-P-109C (Train 2) | CI | CIRE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1725 | 4.1211 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE300050 | U13 - Propane Return Pump Foundation Execution 544-P-112 (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1100 | 1.787 | 10610.CI.CO.M3 | 15.71 | 15.71
C113132CIST100150 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-403 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2184 | 6.9091 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST100220 | U13 - 542-STR-002 Structure Foundation Execution (Train 1) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14747 | 318.0599 | 10610.CI.CO.M3 | 294.94 | 294.9392
C113132CIST100221 | U13 - 542-STR-011 Structure Foundation Execution | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11095 | 180.1289 | 10610.CI.CO.M3 | 184.92 | 184.92
C113132CIST100250 | U13 - Auxiliary Structure foundation for Pumps 542-P-109A/B/C | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10701 | 169.1668 | 10610.CI.CO.M3 | 178.35 | 178.35
C113132CIST100281 | U13 - 542-STR-006 Structure Foundation Execution (Train 1) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1304 | 2.5116 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIST200080 | U13 - 543-STR-005 Structure Foundation Execution (Train 2) for 543-E-128; 543-E-129 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3318 | 11.7505 | 10610.CI.CO.M3 | 55.3 | 46.4519
C113132CIST200100 | U13 - Compressor Shelter 543-SH-001 Foundation Execution (Train 2) (543-C-101; 543-CM-101) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30708 | 1238.7574 | 10610.CI.CO.M3 | 614.15 | 560.101
C113132CIST200130 | U13 - Compressor Shelter 543-SH-004 Foundation Execution (Train 2) (543-C-103; 543-CM-103) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23633 | 652.8566 | 10610.CI.CO.M3 | 472.66 | 397.0358
C113132CIST200210 | U13 - 543-STR-001 Structure Foundation Execution (Train 2) (543-V-141) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 63754 | 5321.6207 | 10610.CI.CO.M3 | 1275.07 | 1132.2643
C113132CIST200250 | U13 - Auxiliary Structure foundation for Pumps 543-P-109A/B/C | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10701 | 158.4822 | 10610.CI.CO.M3 | 178.35 | 178.3501
C113132CIST200270 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-002) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2477 | 8.3266 | 10610.CI.CO.M3 | 41.29 | 36.6701
C113132CIST200280 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-001) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10804 | 153.065 | 10610.CI.CO.M3 | 180.06 | 151.2509
C113132CIST300081 | U13 - 544-STR-011 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11138 | 183.2721 | 10610.CI.CO.M3 | 185.64 | 185.64
C113132CIST300081 | U13 - 544-STR-011 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11138 | 183.2721 | 10610.CI.CO.M3 | 185.64 | 185.64
C113132CIST300120 | U13 - Compressor Shelter 544-SH-002 Foundation Execution (Train 3) (544-C-102; 544-CM-102) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 48685 | 3429.7047 | 10610.CI.CO.M3 | 973.69 | 973.69
C113132CIST300130 | U13 - Compressor Shelter 544-SH-004 Foundation Execution (Train 3) (544-C-103; 544-CM-103) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11719 | 195.9639 | 10610.CI.CO.M3 | 195.32 | 195.3199
C113132CIST300150 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-403 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2184 | 6.5356 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST300210 | U13 - 544-STR-001 Structure Foundation Execution (Train 3) (544-V-141) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63754 | 5966.9859 | 10610.CI.CO.M3 | 1275.07 | 1275.07
C113132CIPV200020 | U13 - Gravel Paving Execution (Train 2) | CI | CIPV2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27334 | 195.918 | 10610.CI.GV.M2 | 45557 | 0
C113132CIRE100050 | U13 - Propane Return Pump Foundation Execution 542-P-112 (Train 1) | CI | CIRE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2374 | 8.3265 | 10610.CI.CO.M3 | 39.57 | 39.57
C113132CIRE200020 | U13 - Sales Gas Compressor Foundation Execution 543-C-101; 543-CM-101 (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23248 | 735.7545 | 10610.CI.CO.M3 | 464.96 | 464.962
C113132CIRE200080 | U13 - Propane Compressor Foundation Execution 543-C-102; 543-CM-102 (Train 2) | CI | CIRE3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21954 | 665.7259 | 10610.CI.CO.M3 | 439.07 | 439.07
C113132CIRE200090 | U13 - Regeneration Gas Compressor Foundation Execution 543-C-103; 543-CM-103 (Train 2) | CI | CIRE2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22118 | 685.8424 | 10610.CI.CO.M3 | 442.36 | 442.36
C113132CIRE300060 | U13 - Expander/Compressor Foundation Execution 544-EC-101 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3019 | 12.8797 | 10610.CI.CO.M3 | 50.32 | 50.32
C113132CIRE300070 | U13 - Demethanizer Bottoms Pump Foundation Execution 544-P-109B (Train 3) | CI | CIRE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 4.3959 | 10610.CI.CO.M3 | 28.75 | 28.75
C113132CIRE300080 | U13 - Propane Compressor Foundation Execution 544-C-102; 544-CM-102 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19019 | 534.3696 | 10610.CI.CO.M3 | 380.38 | 380.38
C113132CISF100010 | U13 - Stairs & Small Foundations Execution (Train 1) | CI | CISF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1553 | 0.684 | 10610.CI.CO.M3 | 25.88 | 2.5901
C113132CISF300010 | U13 - Stairs & Small Foundations Execution (Train 3) | CI | CISF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1553 | 0.49697 | 10610.CI.CO.M3 | 25.88 | 0
C113132CIST100080 | U13 - 542-STR-005 Structure Foundation Execution (Train 1) for 542-E-128; 542-E-129 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3318 | 16.1612 | 10610.CI.CO.M3 | 55.3 | 55.3
C113132CIST100120 | U13 - Compressor Shelter 542-SH-002 Foundation Execution (Train 1) (542-C-102; 542-CM-102) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40516 | 2425.0434 | 10610.CI.CO.M3 | 810.32 | 810.32
C113132CIST100130 | U13 - Compressor Shelter 542-SH-004 Foundation Execution (Train 1) (542-C-103; 542-CM-103) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23633 | 819.8972 | 10610.CI.CO.M3 | 472.66 | 472.66
C113132CIST100190 | U13 - 542-STR-007 Structure Foundation Execution (Train 1) for 542-E-114A/B | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20284 | 602.0438 | 10610.CI.CO.M3 | 405.68 | 405.6818
C113132CIST100190 | U13 - 542-STR-007 Structure Foundation Execution (Train 1) for 542-E-114A/B | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20284 | 602.0438 | 10610.CI.CO.M3 | 405.68 | 405.6818
C113132CIST100240 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-004) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2106 | 6.4899 | 10610.CI.CO.M3 | 35.1 | 35.1
C113132CIST100250 | U13 - Auxiliary Structure foundation for Pumps 542-P-109A/B/C | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10701 | 169.1668 | 10610.CI.CO.M3 | 178.35 | 178.35
C113132CIST100270 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-002) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2477 | 9.0654 | 10610.CI.CO.M3 | 41.29 | 41.29
C113132CIUG100050 | U13 - UG Pipe Installation (Train 1) (OD) | CI | CIUG2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 98541 | 10189.2627 | 10610.CI.UG.LM | 4927.06 | 3574.6027
C113132CIUG100050 | U13 - UG Pipe Installation (Train 1) (OD) | CI | CIUG2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 98541 | 10189.2627 | 10610.CI.UG.LM | 4927.06 | 3574.6027
C113132CIUG200020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 2) | CI | CIUG3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40081 | 148.3264 | 10610.CI.CO.M3 | 801.61 | 0
C113132CIUG200040 | U13 - UG Pipe Installation (Train 2) (OD) | CI | CIUG2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 97868 | 1291.8637 | 10610.CI.UG.LM | 4893.38 | 48.9338
C113132CIUG300050 | U13 - UG Pipe Installation (Train 3) (CD) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 68226 | 4864.5656 | 10610.CI.UG.LM | 3411.3 | 3218.2245
C113132CIVE100020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 1) 542-V-123 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2450 | 8.8667 | 10610.CI.CO.M3 | 40.83 | 40.83
C113132CIVE100050 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 1) 542-V-127 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE100070 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 1) 542-V-124 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2901 | 12.4326 | 10610.CI.CO.M3 | 48.35 | 48.35
C113132CIVE100140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 1) 542-V-117 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2823 | 11.773 | 10610.CI.CO.M3 | 47.05 | 47.05
C113132CIVE100160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116B | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE100190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 1) 542-V-129 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1168 | 2.0147 | 10610.CI.CO.M3 | 16.68 | 16.68
C113132CIVE100210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116C | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE200090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 2) 543-V-115 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1522 | 1.7106 | 10610.CI.CO.M3 | 25.36 | 18.1144
C113132CIVE200150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116A | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 22.2812 | 10610.CI.CO.M3 | 73.09 | 52.21
C113132CIVE200160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116B | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 25.7947 | 10610.CI.CO.M3 | 73.09 | 73.0904
C113132CIVE200190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 2) 543-V-129 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1168 | 1.0073 | 10610.CI.CO.M3 | 16.68 | 11.9143
C113132CIVE200195 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 2) 543-V-110A/B/C/D | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 42578 | 2410.3462 | 10610.CI.CO.M3 | 851.56 | 851.5609
C113132CIRE300090 | U13 - Regeneration Gas Compressor Foundation Execution 544-C-103; 544-CM-103 (Train 3) | CI | CIRE2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16249 | 373.0823 | 10610.CI.CO.M3 | 324.98 | 324.98
C113132CISF100010 | U13 - Stairs & Small Foundations Execution (Train 1) | CI | CISF | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1553 | 0.684 | 10610.CI.CO.M3 | 25.88 | 2.5901
C113132CISF300010 | U13 - Stairs & Small Foundations Execution (Train 3) | CI | CISF | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1553 | 0.49697 | 10610.CI.CO.M3 | 25.88 | 0
C113132CIST100100 | U13 - Compressor Shelter 542-SH-001 Foundation Execution (Train 1) (542-C-101; 542-CM-101) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27283 | 1091.9428 | 10610.CI.CO.M3 | 545.66 | 545.66
C113132CIST100100 | U13 - Compressor Shelter 542-SH-001 Foundation Execution (Train 1) (542-C-101; 542-CM-101) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27283 | 1091.9428 | 10610.CI.CO.M3 | 545.66 | 545.66
C113132CIST100110 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-401 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4304 | 26.7928 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST100120 | U13 - Compressor Shelter 542-SH-002 Foundation Execution (Train 1) (542-C-102; 542-CM-102) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40516 | 2425.0434 | 10610.CI.CO.M3 | 810.32 | 810.32
C113132CIST100130 | U13 - Compressor Shelter 542-SH-004 Foundation Execution (Train 1) (542-C-103; 542-CM-103) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23633 | 819.8972 | 10610.CI.CO.M3 | 472.66 | 472.66
C113132CIST100140 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-402 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2184 | 6.9091 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST100150 | U13 - Shelters Foundation Execution (Train 1) 542-ANS-403 | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2184 | 6.9091 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST100210 | U13 - 542-STR-001 Structure Foundation Execution (Train 1) (542-V-141) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63754 | 5947.4712 | 10610.CI.CO.M3 | 1275.07 | 1275.0732
C113132CIST100210 | U13 - 542-STR-001 Structure Foundation Execution (Train 1) (542-V-141) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63754 | 5947.4712 | 10610.CI.CO.M3 | 1275.07 | 1275.0732
C113132CIST100220 | U13 - 542-STR-002 Structure Foundation Execution (Train 1) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14747 | 318.0599 | 10610.CI.CO.M3 | 294.94 | 294.9392
C113132CIST100230 | U13 - Compressor Shelter 542-SH-003 Foundation Execution (Train 1) (542-EC-101) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10016 | 146.8003 | 10610.CI.CO.M3 | 166.94 | 166.94
C113132CIST100280 | U13 - Structure foundation for Lube Oil Cooler (close to 542-SH-001) | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13574 | 272.1962 | 10610.CI.CO.M3 | 271.48 | 271.48
C113132CIST200080 | U13 - 543-STR-005 Structure Foundation Execution (Train 2) for 543-E-128; 543-E-129 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3318 | 11.7505 | 10610.CI.CO.M3 | 55.3 | 46.4519
C113132CIST200110 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-401 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4304 | 25.6818 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST200120 | U13 - Compressor Shelter 543-SH-002 Foundation Execution (Train 2) (543-C-102; 543-CM-102) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40479 | 2189.4474 | 10610.CI.CO.M3 | 809.58 | 718.9094
C113132CIST200100 | U13 - Compressor Shelter 543-SH-001 Foundation Execution (Train 2) (543-C-101; 543-CM-101) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30708 | 1238.7574 | 10610.CI.CO.M3 | 614.15 | 560.101
C113132CIST200110 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-401 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4304 | 25.6818 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST200120 | U13 - Compressor Shelter 543-SH-002 Foundation Execution (Train 2) (543-C-102; 543-CM-102) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40479 | 2189.4474 | 10610.CI.CO.M3 | 809.58 | 718.9094
C113132CIST200121 | U13 - 543-STR-011 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11095 | 158.0788 | 10610.CI.CO.M3 | 184.92 | 158.2897
C113132CIST200121 | U13 - 543-STR-011 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11095 | 158.0788 | 10610.CI.CO.M3 | 184.92 | 158.2897
C113132CIST200130 | U13 - Compressor Shelter 543-SH-004 Foundation Execution (Train 2) (543-C-103; 543-CM-103) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23633 | 652.8566 | 10610.CI.CO.M3 | 472.66 | 397.0358
C113132CIST200140 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-402 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2184 | 6.4531 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST200150 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-403 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2184 | 6.3641 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST200190 | U13 - 543-STR-007 Structure Foundation Execution (Train 2) for 543-E-114A/B | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20284 | 498.5141 | 10610.CI.CO.M3 | 405.68 | 365.4413
C113132CIST200210 | U13 - 543-STR-001 Structure Foundation Execution (Train 2) (543-V-141) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 63754 | 5321.6207 | 10610.CI.CO.M3 | 1275.07 | 1132.2643
C113132CIST200220 | U13 - 543-STR-002 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14747 | 272.5356 | 10610.CI.CO.M3 | 294.94 | 278.6656
C113132CIST200250 | U13 - Auxiliary Structure foundation for Pumps 543-P-109A/B/C | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10701 | 158.4822 | 10610.CI.CO.M3 | 178.35 | 178.3501
C113132CIST200280 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-001) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10804 | 153.065 | 10610.CI.CO.M3 | 180.06 | 151.2509
C113132CIST300100 | U13 - Compressor Shelter 544-SH-001 Foundation Execution (Train 3) (544-C-101; 544-CM-101) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30708 | 1364.4789 | 10610.CI.CO.M3 | 614.15 | 614.15
C113132CIST300130 | U13 - Compressor Shelter 544-SH-004 Foundation Execution (Train 3) (544-C-103; 544-CM-103) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11719 | 195.9639 | 10610.CI.CO.M3 | 195.32 | 195.3199
C113132CIST300140 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-402 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2184 | 6.5356 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST300190 | U13 - 544-STR-007 Structure Foundation Execution (Train 3) for 544-E-114A/B | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22944 | 777.6867 | 10610.CI.CO.M3 | 458.88 | 458.88
C113132CIST300221 | U13 - 544-STR-006 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1304 | 2.3245 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIVE200195 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 2) 543-V-110A/B/C/D | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 42578 | 2410.3462 | 10610.CI.CO.M3 | 851.56 | 851.5609
C113132CIVE300110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 3) 544-V-119 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25057 | 927.5042 | 10610.CI.CO.M3 | 501.13 | 501.13
C113132CIVE300140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 3) 544-V-117 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2823 | 11.773 | 10610.CI.CO.M3 | 47.05 | 47.05
C113132CIVE300180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 3) 544-V-120 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2159 | 6.8854 | 10610.CI.CO.M3 | 35.98 | 35.98
C113132CIVE300180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 3) 544-V-120 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2159 | 6.8854 | 10610.CI.CO.M3 | 35.98 | 35.98
C113132CIVE300200 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 3) 544-V-110 A/B/C/D | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 42578 | 2678.1624 | 10610.CI.CO.M3 | 851.56 | 851.56
C113132CIVE300210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116C | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132STEQ100010 | U13 - 542-STR-001 Structure Erection (Train 1) (542-V-141) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44838 | 0 | 10610.ST.ER.TN | 846 | 0
C113132STEQ100020 | U13 - 542-STR-002 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14787 | 0 | 10610.ST.ER.TN | 279 | 0
C113132STEQ100070 | U13 - 542-STR-007 Structure Erection (Train 1) (542-F-114A/B) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2386 | 0 | 10610.ST.ER.TN | 45.02 | 0
C113132STEQ100100 | U13 - Auxiliary Structure Erection for Pumps 542-P-109A/B/C | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10610.ST.ER.TN | 57.07 | 0
C113132STEQ100110 | U13 - Structure Erection for Lube Oil Cooler (close to 542-SH-002) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1643 | 0 | 10780.ST.ST.MH
C113132STEQ100150 | U13 - 542-STR-011 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4612 | 0 | 10610.ST.ER.TN | 87.01 | 0
C113132STEQ200010 | U13 - 543-STR-001 Structure Erection (Train 2) (543-V-141) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 44838 | 0 | 10610.ST.ER.TN | 846 | 0
C113132STEQ200020 | U13 - 543-STR-002 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14787 | 0 | 10610.ST.ER.TN | 279 | 0
C113132STEQ200070 | U13 - 543-STR-007 Structure Erection (Train 2) (543-E-114A/B) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2386 | 0 | 10610.ST.ER.TN | 45.02 | 0
C113132STEQ200080 | U13 - 543-STR-005 Structure Erection (Train 2) (543-E-128; 543-E-129) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2755 | 0 | 10610.ST.ER.TN | 51.97 | 0
C113132STEQ200100 | U13 - Auxiliary Structure Erection for Pumps 543-P-109A/B/C | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3085 | 0 | 10610.ST.ER.TN | 58.21 | 0
C113132CIST300210 | U13 - 544-STR-001 Structure Foundation Execution (Train 3) (544-V-141) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 63754 | 5966.9859 | 10610.CI.CO.M3 | 1275.07 | 1275.07
C113132CIST300220 | U13 - 544-STR-002 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14747 | 319.2647 | 10610.CI.CO.M3 | 294.94 | 294.94
C113132CIST300221 | U13 - 544-STR-006 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1304 | 2.3245 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIST300240 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-004) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11719 | 202.8821 | 10610.CI.CO.M3 | 195.32 | 195.32
C113132CIST300270 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-002) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2815 | 11.7072 | 10610.CI.CO.M3 | 46.92 | 46.92
C113132CIST300280 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-001) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11056 | 180.5803 | 10610.CI.CO.M3 | 184.27 | 184.2699
C113132CIST300280 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-001) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11056 | 180.5803 | 10610.CI.CO.M3 | 184.27 | 184.2699
C113132CIUG100020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 1) | CI | CIUG3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31005 | 671.7287 | 10610.CI.CO.M3 | 620.1 | 359.6595
C113132CIUG200010 | U13 - UG GRE Pipe Installation (Train 2) (FW) | CI | CIUG2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7200 | 12.0342 | 10780.CI.CI.MH
C113132CIUG200040 | U13 - UG Pipe Installation (Train 2) (OD) | CI | CIUG2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 97868 | 1291.8637 | 10610.CI.UG.LM | 4893.38 | 48.9338
C113132CIUG300010 | U13 - UG GRE Pipe Installation (Train 3) (FW) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11672 | 40.4955 | 10780.CI.CI.MH
C113132CIUG300030 | U13 - UG Civil Works (Train 3) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 99457 | 8357.4181 | 10610.CI.UG.LM | 4972.85 | 3926.5484
C113132CIUG300050 | U13 - UG Pipe Installation (Train 3) (CD) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 68226 | 4864.5656 | 10610.CI.UG.LM | 3411.3 | 3218.2245
C113132CIVE100030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 1) 542-V-134 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6224 | 56.7451 | 10610.CI.CO.M3 | 103.73 | 103.73
C113132CIVE100030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 1) 542-V-134 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6224 | 56.7451 | 10610.CI.CO.M3 | 103.73 | 103.73
C113132CIVE100040 | U13 - Vertical Vessels (Cold Closed Drain Drum) Foundation Execution (Train 1) 542-V-132 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1796 | 4.7462 | 10610.CI.CO.M3 | 29.94 | 29.94
C113132CIVE100070 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 1) 542-V-124 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2901 | 12.4326 | 10610.CI.CO.M3 | 48.35 | 48.35
C113132CIVE100100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 1) 542-V-118 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 114.6523 | 10610.CI.CO.M3 | 148.43 | 148.43
C113132CIST300230 | U13 - Compressor Shelter 544-SH-003 Foundation Execution (Train 3) (544-EC-101) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9451 | 126.0186 | 10610.CI.CO.M3 | 157.52 | 157.52
C113132CIST300230 | U13 - Compressor Shelter 544-SH-003 Foundation Execution (Train 3) (544-EC-101) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9451 | 126.0186 | 10610.CI.CO.M3 | 157.52 | 157.52
C113132CIST300240 | U13 - Structure foundation for Lube Oil Cooler (close to 544-SH-004) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11719 | 202.8821 | 10610.CI.CO.M3 | 195.32 | 195.32
C113132CIST300250 | U13 - Auxiliary Structure foundation for Pumps 544-P-109A/B/C | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10834 | 173.3916 | 10610.CI.CO.M3 | 180.56 | 180.56
C113132CIST300300 | U13 - 543-STR-010 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 489 | 0.26384 | 10610.CI.CO.M3 | 6.99 | 5.8716
C113132CIST300301 | U13 - 543-STR-006 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1304 | 2.3886 | 10610.CI.CO.M3 | 21.73 | 21.73
C113132CIUG100010 | U13 - UG GRE Pipe Installation (Train 1) (FW) | CI | CIUG2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11672 | 79.8397 | 10780.CI.CI.MH
C113132CIUG100030 | U13 - UG Civil Works (Train 1) | CI | CIUG1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 87540 | 5854.0175 | 10780.CI.CI.MH
C113132CIUG200020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 2) | CI | CIUG3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40081 | 148.3264 | 10610.CI.CO.M3 | 801.61 | 0
C113132CIUG200050 | U13 - UG Pipe Installation (Train 2) (CD) | CI | CIUG2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16796 | 30.8233 | 10610.CI.UG.LM | 839.81 | 9.5738
C113132CIUG300020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 3) | CI | CIUG3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26488 | 412.0108 | 10610.CI.CO.M3 | 529.77 | 299.9997
C113132CIUG300060 | U13 - UG Pipe Installation (Train 3) (PW) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11672 | 96.3269 | 10780.CI.CI.MH
C113132CIVE100010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 1) 542-V-125 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE100010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 1) 542-V-125 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE100020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 1) 542-V-123 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2450 | 8.8667 | 10610.CI.CO.M3 | 40.83 | 40.83
C113132CIVE100040 | U13 - Vertical Vessels (Cold Closed Drain Drum) Foundation Execution (Train 1) 542-V-132 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1796 | 4.7462 | 10610.CI.CO.M3 | 29.94 | 29.94
C113132CIVE100050 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 1) 542-V-127 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE100090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 1) 542-V-115 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1522 | 3.4212 | 10610.CI.CO.M3 | 25.36 | 25.36
C113132CIST200150 | U13 - Shelters Foundation Execution (Train 2) 543-ANS-403 | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2184 | 6.3641 | 10610.CI.CO.M3 | 36.4 | 36.4
C113132CIST200220 | U13 - 543-STR-002 Structure Foundation Execution (Train 2) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14747 | 272.5356 | 10610.CI.CO.M3 | 294.94 | 278.6656
C113132CIST200230 | U13 - Compressor Shelter 543-SH-003 Foundation Execution (Train 2) (543-EC-101) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9451 | 110.061 | 10610.CI.CO.M3 | 157.52 | 132.3207
C113132CIST200230 | U13 - Compressor Shelter 543-SH-003 Foundation Execution (Train 2) (543-EC-101) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9451 | 110.061 | 10610.CI.CO.M3 | 157.52 | 132.3207
C113132CIST200240 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-004) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2106 | 5.0026 | 10610.CI.CO.M3 | 35.1 | 29.484
C113132CIST200270 | U13 - Structure foundation for Lube Oil Cooler (close to 543-SH-002) | CI | CIST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2477 | 8.3266 | 10610.CI.CO.M3 | 41.29 | 36.6701
C113132CIST300100 | U13 - Compressor Shelter 544-SH-001 Foundation Execution (Train 3) (544-C-101; 544-CM-101) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30708 | 1364.4789 | 10610.CI.CO.M3 | 614.15 | 614.15
C113132CIST300110 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-401 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4304 | 25.3808 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST300110 | U13 - Shelters Foundation Execution (Train 3) 544-ANS-401 | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4304 | 25.3808 | 10610.CI.CO.M3 | 71.73 | 71.73
C113132CIST300190 | U13 - 544-STR-007 Structure Foundation Execution (Train 3) for 544-E-114A/B | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22944 | 777.6867 | 10610.CI.CO.M3 | 458.88 | 458.88
C113132CIST300220 | U13 - 544-STR-002 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14747 | 319.2647 | 10610.CI.CO.M3 | 294.94 | 294.94
C113132CIST300250 | U13 - Auxiliary Structure foundation for Pumps 544-P-109A/B/C | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10834 | 173.3916 | 10610.CI.CO.M3 | 180.56 | 180.56
C113132CIST300290 | U13 - 544-STR-010 Structure Foundation Execution (Train 3) | CI | CIST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 489 | 0.35347 | 10610.CI.CO.M3 | 6.99 | 6.99
C113132CIST300310 | U13 - 542-STR-010 Structure Foundation Execution | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 489 | 0.35347 | 10610.CI.CO.M3 | 6.99 | 6.99
C113132CIST300310 | U13 - 542-STR-010 Structure Foundation Execution | CI | CIST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 489 | 0.35347 | 10610.CI.CO.M3 | 6.99 | 6.99
C113132CIUG100020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 1) | CI | CIUG3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31005 | 671.7287 | 10610.CI.CO.M3 | 620.1 | 359.6595
C113132CIUG200030 | U13 - UG Civil Works (Train 2) | CI | CIUG1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 43770 | 234.9079 | 10780.CI.CI.MH
C113132CIUG200050 | U13 - UG Pipe Installation (Train 2) (CD) | CI | CIUG2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16796 | 30.8233 | 10610.CI.UG.LM | 839.81 | 9.5738
C113132CIUG300020 | U13 - UG Process Channel Execution (Closed Drain System) (Train 3) | CI | CIUG3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26488 | 412.0108 | 10610.CI.CO.M3 | 529.77 | 299.9997
C113132STEQ200120 | U13 - Structure Erection for Lube Oil Cooler (close to 543-SH-004) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1643 | 0 | 10780.ST.ST.MH
C113132STEQ200130 | U13 - Structure Erection for Lube Oil Cooler (close to 543-SH-001) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3180 | 0 | 10780.ST.ST.MH
C113132STEQ200140 | U13 - Structure Erection around Vessels 543-V-110A; 543-V-110B; 543-V-110C; 543-V-110D | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7628 | 0 | 10610.ST.ER.TN | 143.92 | 0
C113132STEQ300020 | U13 - 544-STR-002 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14787 | 93.378 | 10610.ST.ER.TN | 279 | 123.9853
C113132STEQ300070 | U13 - 544-STR-007 Structure Erection (Train 3) (544-E-114A/B) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2386 | 0.71367 | 10610.ST.ER.TN | 45.02 | 5.0066
C113132STEQ300140 | U13 - Structure Erection around Vessels 544-V-110A; 544-V-110B; 544-V-110C; 544-V-110D | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5464 | 9.3159 | 10610.ST.ER.TN | 103.1 | 43.6187
C113132STEQ300150 | U13 - 544-STR-006 Structure Erection (Train 3) (544-V-132) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 421 | 0 | 10610.ST.ER.TN | 7.95 | 0
C113132STEQ300160 | U13 - 544-STR-011 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4612 | 9.2513 | 10610.ST.ER.TN | 87.01 | 39.4052
C113132STPL100020 | U13 - 542-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-V-141) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL100030 | U13 - 542-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL100090 | U13 - 542-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5450 | 0.014481 | 10610.ST.PL.TN | 68.13 | 0.029721
C113132STPL100110 | U13 - 542-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5227 | 0.41333 | 10610.ST.PL.TN | 65.34 | 0.74726
C113132STPL100120 | U13 - 542-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3290 | 0 | 10610.ST.PL.TN | 41.12 | 0
C113132STPL100130 | U13 - 542-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5590 | 0 | 10610.ST.PL.TN | 69.87 | 0
C113132STPL100170 | U13 - 542-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL100180 | U13 - 542-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL100220 | U13 - 542-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5377 | 0 | 10610.ST.PL.TN | 67.22 | 0
C113132STPL100240 | U13 - 542-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 507 | 0 | 10610.ST.PL.TN | 6.34 | 0
C113132CIVE100170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 1) 542-V-128 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1382 | 2.8211 | 10610.CI.CO.M3 | 23.03 | 23.03
C113132CIVE100180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 1) 542-V-120 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2686 | 10.5179 | 10610.CI.CO.M3 | 44.76 | 44.76
C113132CIVE100200 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 1) 542-V-110 A/B/C/D | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42578 | 2678.1624 | 10610.CI.CO.M3 | 851.56 | 851.56
C113132CIVE100200 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 1) 542-V-110 A/B/C/D | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42578 | 2678.1624 | 10610.CI.CO.M3 | 851.56 | 851.56
C113132CIVE200010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 2) 543-V-125 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2225 | 6.6401 | 10610.CI.CO.M3 | 37.08 | 37.0799
C113132CIVE200040 | U13 - Vertical Vessel (Cold Closed Drain Drum) Foundation Execution (Train 2) 543-V-132 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1796 | 2.3831 | 10610.CI.CO.M3 | 29.94 | 21.39
C113132CIVE200040 | U13 - Vertical Vessel (Cold Closed Drain Drum) Foundation Execution (Train 2) 543-V-132 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1796 | 2.3831 | 10610.CI.CO.M3 | 29.94 | 21.39
C113132CIVE200070 | U13 - Vertical Vessel (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 2) 543-V-124 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2901 | 9.8717 | 10610.CI.CO.M3 | 48.35 | 34.5398
C113132CIVE200100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 2) 543-V-118 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7804 | 80.9757 | 10610.CI.CO.M3 | 130.07 | 130.0704
C113132CIVE200150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116A | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 22.2812 | 10610.CI.CO.M3 | 73.09 | 52.21
C113132CIVE200180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 2) 543-V-120 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2474 | 7.9809 | 10610.CI.CO.M3 | 41.24 | 41.24
C113132CIVE200190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 2) 543-V-129 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1168 | 1.0073 | 10610.CI.CO.M3 | 16.68 | 11.9143
C113132CIVE300070 | U13 - Vertical Vessel (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 3) 544-V-124 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2901 | 12.4326 | 10610.CI.CO.M3 | 48.35 | 48.35
C113132CIVE300150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116A | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132CIVE300160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116B | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132CIVE300170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 3) 544-V-128 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1382 | 2.8211 | 10610.CI.CO.M3 | 23.03 | 23.03
C113132CIUG300030 | U13 - UG Civil Works (Train 3) | CI | CIUG2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 99457 | 8357.4181 | 10610.CI.UG.LM | 4972.85 | 3926.5484
C113132CIVE100100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 1) 542-V-118 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 114.6523 | 10610.CI.CO.M3 | 148.43 | 148.43
C113132CIVE100110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 1) 542-V-119 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25828 | 985.4803 | 10610.CI.CO.M3 | 516.56 | 516.56
C113132CIVE100140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 1) 542-V-117 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2823 | 11.773 | 10610.CI.CO.M3 | 47.05 | 47.05
C113132CIVE100170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 1) 542-V-128 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1382 | 2.8211 | 10610.CI.CO.M3 | 23.03 | 23.03
C113132CIVE100190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 1) 542-V-129 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1168 | 2.0147 | 10610.CI.CO.M3 | 16.68 | 16.68
C113132CIVE200020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 2) 543-V-123 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2451 | 5.0142 | 10610.CI.CO.M3 | 40.85 | 29.1801
C113132CIVE200020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 2) 543-V-123 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2451 | 5.0142 | 10610.CI.CO.M3 | 40.85 | 29.1801
C113132CIVE200050 | U13 - Vertical Vessel (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 2) 543-V-127 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2225 | 6.6401 | 10610.CI.CO.M3 | 37.08 | 37.0801
C113132CIVE200110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 2) 543-V-119 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25242 | 941.2694 | 10610.CI.CO.M3 | 504.84 | 504.84
C113132CIVE200140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 2) 543-V-117 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2823 | 8.9475 | 10610.CI.CO.M3 | 47.05 | 33.6101
C113132CIVE200170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 2) 543-V-128 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1382 | 1.4106 | 10610.CI.CO.M3 | 23.03 | 16.4501
C113132CIVE200180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 2) 543-V-120 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2474 | 7.9809 | 10610.CI.CO.M3 | 41.24 | 41.24
C113132CIVE300010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 3) 544-V-125 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE300010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 3) 544-V-125 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE300020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 3) 544-V-123 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2451 | 8.8747 | 10610.CI.CO.M3 | 40.85 | 40.85
C113132CIVE100090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 1) 542-V-115 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1522 | 3.4212 | 10610.CI.CO.M3 | 25.36 | 25.36
C113132CIVE100110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 1) 542-V-119 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25828 | 985.4803 | 10610.CI.CO.M3 | 516.56 | 516.56
C113132CIVE100150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116A | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE100150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116A | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE100160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116B | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE100180 | U13 - Vertical Vessel (Reflux Separator) Foundation Execution (Train 1) 542-V-120 | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2686 | 10.5179 | 10610.CI.CO.M3 | 44.76 | 44.76
C113132CIVE100210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 1) 542-V-116C | CI | CIVE | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4117 | 25.0372 | 10610.CI.CO.M3 | 68.61 | 68.61
C113132CIVE200010 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 2) 543-V-125 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2225 | 6.6401 | 10610.CI.CO.M3 | 37.08 | 37.0799
C113132CIVE200030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 2) 543-V-134 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6224 | 51.5032 | 10610.CI.CO.M3 | 103.73 | 103.7297
C113132CIVE200030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 2) 543-V-134 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6224 | 51.5032 | 10610.CI.CO.M3 | 103.73 | 103.7297
C113132CIVE200050 | U13 - Vertical Vessel (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 2) 543-V-127 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2225 | 6.6401 | 10610.CI.CO.M3 | 37.08 | 37.0801
C113132CIVE200070 | U13 - Vertical Vessel (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 2) 543-V-124 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2901 | 9.8717 | 10610.CI.CO.M3 | 48.35 | 34.5398
C113132CIVE200090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 2) 543-V-115 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1522 | 1.7106 | 10610.CI.CO.M3 | 25.36 | 18.1144
C113132CIVE200100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 2) 543-V-118 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7804 | 80.9757 | 10610.CI.CO.M3 | 130.07 | 130.0704
C113132CIVE200110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 2) 543-V-119 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25242 | 941.2694 | 10610.CI.CO.M3 | 504.84 | 504.84
C113132CIVE200140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 2) 543-V-117 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2823 | 8.9475 | 10610.CI.CO.M3 | 47.05 | 33.6101
C113132STPL100320 | U13 - 542-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-F-114A/B) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL100350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41597 | 164.4882 | 10610.ST.PL.TN | 519.96 | 37.3879
C113132STPL100360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 1) (542-SU-101; 542-SU-502) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132STPL200010 | U13 - 543-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL200020 | U13 - 543-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-V-141) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL200060 | U13 - 543-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3197 | 0.20625 | 10610.ST.PL.TN | 39.96 | 0.60839
C113132STPL200070 | U13 - 543-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4041 | 0 | 10610.ST.PL.TN | 50.51 | 0
C113132STPL200080 | U13 - 543-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4581 | 0 | 10610.ST.PL.TN | 57.26 | 0
C113132STPL200100 | U13 - 543-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5969 | 0 | 10610.ST.PL.TN | 74.61 | 0
C113132STPL200120 | U13 - 543-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3290 | 0 | 10610.ST.PL.TN | 41.12 | 0
C113132STPL200160 | U13 - 543-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4149 | 0 | 10610.ST.PL.TN | 51.86 | 0
C113132STPL200170 | U13 - 543-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL200190 | U13 - 543-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.ST.PL.TN | 19.96 | 0
C113132STPL200190 | U13 - 543-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.ST.PL.TN | 19.96 | 0
C113132STPL200200 | U13 - 543-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1165 | 0 | 10610.ST.PL.TN | 14.56 | 0
C113132STPL200220 | U13 - 543-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5377 | 0 | 10610.ST.PL.TN | 67.22 | 0
C113132STPL200270 | U13 - Lube Oil Cooler for 543-SH-001 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132CIVE300030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 3) 544-V-134 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6224 | 56.503 | 10610.CI.CO.M3 | 103.73 | 103.73
C113132CIVE300030 | U13 - Vertical Vessel (Warm Feed Gas Separator) Foundation Execution (Train 3) 544-V-134 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6224 | 56.503 | 10610.CI.CO.M3 | 103.73 | 103.73
C113132CIVE300040 | U13 - Vertical Vessel (Cold Closed Drain Drum) Foundation Execution (Train 3) 544-V-132 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1758 | 4.5657 | 10610.CI.CO.M3 | 29.3 | 29.3
C113132CIVE300140 | U13 - Vertical Vessel (Sales Gas Compressor Suction Scrubber) Foundation Execution (Train 3) 544-V-117 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2823 | 11.773 | 10610.CI.CO.M3 | 47.05 | 47.05
C113132CIVE300150 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116A | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132CIVE300190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 3) 544-V-129 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1168 | 2.0147 | 10610.CI.CO.M3 | 16.68 | 16.68
C113132CIVE300190 | U13 - Vertical Vessel (Regeneration Gas Compressor Discharge Drum) Foundation Execution (Train 3) 544-V-129 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1168 | 2.0147 | 10610.CI.CO.M3 | 16.68 | 16.68
C113132STEQ100070 | U13 - 542-STR-007 Structure Erection (Train 1) (542-F-114A/B) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2386 | 0 | 10610.ST.ER.TN | 45.02 | 0
C113132STEQ100080 | U13 - 542-STR-005 Structure Erection (Train 1) (542-E-128; 542-E-129) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2755 | 0 | 10610.ST.ER.TN | 51.97 | 0
C113132STEQ100140 | U13 - Structure Erection around Vessels 542-V-110A; 542-V-110B; 542-V-110C; 542-V-110D | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4643 | 0 | 10610.ST.ER.TN | 87.6 | 0
C113132STEQ100170 | U13 - 542-STR-006 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 515 | 0 | 10610.ST.ER.TN | 9.72 | 0
C113132STEQ200010 | U13 - 543-STR-001 Structure Erection (Train 2) (543-V-141) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 44838 | 0 | 10610.ST.ER.TN | 846 | 0
C113132STEQ200070 | U13 - 543-STR-007 Structure Erection (Train 2) (543-E-114A/B) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2386 | 0 | 10610.ST.ER.TN | 45.02 | 0
C113132STEQ200110 | U13 - Structure Erection for Lube Oil Cooler (close to 543-SH-002) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2226 | 0 | 10780.ST.ST.MH
C113132STEQ300010 | U13 - 544-STR-001 Structure Erection (Train 3) (544-V-141) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44838 | 433.7709 | 10610.ST.ER.TN | 846 | 158.6098
C113132STEQ300070 | U13 - 544-STR-007 Structure Erection (Train 3) (544-E-114A/B) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2386 | 0.71367 | 10610.ST.ER.TN | 45.02 | 5.0066
C113132STEQ300080 | U13 - 544-STR-005 Structure Erection (Train 3) (544-E-128; 544-E-129) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3102 | 0 | 10610.ST.ER.TN | 58.54 | 0
C113132STPL200330 | U13 - 543-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-E-128; 543-E-129) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 462 | 0 | 10610.ST.PL.TN | 5.77 | 0
C113132STPL200350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37950 | 140.0387 | 10610.ST.PL.TN | 474.38 | 34.8999
C113132STPL200360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 2) (543-SU-101; 543-SU-502) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132STPL200370 | U13 - 543-V-110A/B/C/D Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1279 | 0 | 10610.ST.PL.TN | 15.99 | 0
C113132STPL300010 | U13 - 544-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL300030 | U13 - 544-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL300050 | U13 - 544-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5218 | 0 | 10610.ST.PL.TN | 65.23 | 0
C113132STPL300060 | U13 - 544-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3232 | 0 | 10610.ST.PL.TN | 40.41 | 0
C113132STPL300080 | U13 - 544-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4630 | 1.6466 | 10610.ST.PL.TN | 57.88 | 29.7913
C113132STPL300100 | U13 - 544-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5971 | 0.72944 | 10610.ST.PL.TN | 74.63 | 12.9846
C113132STPL300110 | U13 - 544-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5193 | 1.8217 | 10610.ST.PL.TN | 64.91 | 8.3276
C113132STPL300130 | U13 - 544-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5940 | 0 | 10610.ST.PL.TN | 74.25 | 0
C113132STPL300200 | U13 - 544-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1159 | 0 | 10610.ST.PL.TN | 14.49 | 0
C113132STPL300220 | U13 - 544-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4948 | 0 | 10610.ST.PL.TN | 61.85 | 0
C113132STPL300240 | U13 - 544-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1652 | 0 | 10610.ST.PL.TN | 20.65 | 0
C113132STPL300260 | U13 - Lube Oil Cooler for 544-SH-004 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL300360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 3) (544-SU-101; 544-SU-502) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132CIVE200160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116B | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 25.7947 | 10610.CI.CO.M3 | 73.09 | 73.0904
C113132CIVE200170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 2) 543-V-128 | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1382 | 1.4106 | 10610.CI.CO.M3 | 23.03 | 16.4501
C113132CIVE200210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116C | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 25.5675 | 10610.CI.CO.M3 | 73.09 | 73.0904
C113132CIVE200210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 2) 543-V-116C | CI | CIVE | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4385 | 25.5675 | 10610.CI.CO.M3 | 73.09 | 73.0904
C113132CIVE300020 | U13 - Vertical Vessel (Second Stage Refrigerant Flash Drum) Foundation Execution (Train 3) 544-V-123 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2451 | 8.8747 | 10610.CI.CO.M3 | 40.85 | 40.85
C113132CIVE300040 | U13 - Vertical Vessel (Cold Closed Drain Drum) Foundation Execution (Train 3) 544-V-132 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1758 | 4.5657 | 10610.CI.CO.M3 | 29.3 | 29.3
C113132CIVE300050 | U13 - Vertical Vessel (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 3) 544-V-127 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE300050 | U13 - Vertical Vessel (Propane Compressor First Stage Suction Drum) Foundation Execution (Train 3) 544-V-127 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2225 | 7.3129 | 10610.CI.CO.M3 | 37.08 | 37.08
C113132CIVE300070 | U13 - Vertical Vessel (Propane Compressor Second Stage Suction Drum) Foundation Execution (Train 3) 544-V-124 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2901 | 12.4326 | 10610.CI.CO.M3 | 48.35 | 48.35
C113132CIVE300090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 3) 544-V-115 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1660 | 4.0713 | 10610.CI.CO.M3 | 27.67 | 27.67
C113132CIVE300090 | U13 - Vertical Vessel (Regeneration Gas Separator) Foundation Execution (Train 3) 544-V-115 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1660 | 4.0713 | 10610.CI.CO.M3 | 27.67 | 27.67
C113132CIVE300100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 3) 544-V-118 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7804 | 89.5906 | 10610.CI.CO.M3 | 130.07 | 130.07
C113132CIVE300100 | U13 - Vertical Vessel (Cold Separator) Foundation Execution (Train 3) 544-V-118 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7804 | 89.5906 | 10610.CI.CO.M3 | 130.07 | 130.07
C113132CIVE300110 | U13 - Vertical Vessel (Demethanizer) Foundation Execution (Train 3) 544-V-119 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25057 | 927.5042 | 10610.CI.CO.M3 | 501.13 | 501.13
C113132CIVE300160 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116B | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132STEQ100010 | U13 - 542-STR-001 Structure Erection (Train 1) (542-V-141) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 44838 | 0 | 10610.ST.ER.TN | 846 | 0
C113132STEQ300100 | U13 - Auxiliary Structure Erection for Pumps 544-P-109A/B/C | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10610.ST.ER.TN | 57.07 | 0
C113132STEQ300170 | U13 - 543-STR-006 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 468 | 0 | 10610.ST.ER.TN | 8.83 | 0
C113132STEQ300190 | U13 - 544-STR-010 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STEQ300200 | U13 - 543-STR-010 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STMS200010 | U13 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Train 2) | ST | STMS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 114 | 0 | 10610.ST.PL.TN | 1.9 | 0
C113132STMS300010 | U13 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Train 3) | ST | STMS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 114 | 0 | 10610.ST.PL.TN | 1.9 | 0
C113132STPL100010 | U13 - 542-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL100040 | U13 - 542-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4385 | 0 | 10610.ST.PL.TN | 54.82 | 0
C113132STPL100070 | U13 - 542-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4070 | 0 | 10610.ST.PL.TN | 50.88 | 0
C113132STPL100110 | U13 - 542-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5227 | 0.41333 | 10610.ST.PL.TN | 65.34 | 0.74726
C113132STPL100160 | U13 - 542-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4152 | 0 | 10610.ST.PL.TN | 51.9 | 0
C113132STPL100190 | U13 - 542-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.ST.PL.TN | 19.96 | 0
C113132STPL100200 | U13 - 542-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1159 | 0 | 10610.ST.PL.TN | 14.49 | 0
C113132STPL100210 | U13 - 542-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2394 | 0 | 10610.ST.PL.TN | 29.93 | 0
C113132STPL100220 | U13 - 542-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5377 | 0 | 10610.ST.PL.TN | 67.22 | 0
C113132STPL100260 | U13 - Lube Oil Cooler for 542-SH-004 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL100280 | U13 - 542-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL100350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41597 | 164.4882 | 10610.ST.PL.TN | 519.96 | 37.3879
C113132CIVE300170 | U13 - Vertical Vessel (Regeneration Gas Compressor Suction Drum) Foundation Execution (Train 3) 544-V-128 | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1382 | 2.8211 | 10610.CI.CO.M3 | 23.03 | 23.03
C113132CIVE300200 | U13 - Vertical Vessel (Molecular Sieve Adsorber) Foundation Execution (Train 3) 544-V-110 A/B/C/D | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 42578 | 2678.1624 | 10610.CI.CO.M3 | 851.56 | 851.56
C113132CIVE300210 | U13 - Vertical Vessel (Mercury Adsorber) Foundation Execution (Train 3) 544-V-116C | CI | CIVE | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4376 | 28.2918 | 10610.CI.CO.M3 | 72.94 | 72.94
C113132STEQ100120 | U13 - Structure Erection for Lube Oil Cooler (close to 542-SH-004) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2915 | 0 | 10780.ST.ST.MH
C113132STEQ100140 | U13 - Structure Erection around Vessels 542-V-110A; 542-V-110B; 542-V-110C; 542-V-110D | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4643 | 0 | 10610.ST.ER.TN | 87.6 | 0
C113132STEQ100160 | U13 - 542-STR-010 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STEQ100170 | U13 - 542-STR-006 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 515 | 0 | 10610.ST.ER.TN | 9.72 | 0
C113132STEQ200140 | U13 - Structure Erection around Vessels 543-V-110A; 543-V-110B; 543-V-110C; 543-V-110D | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7628 | 0 | 10610.ST.ER.TN | 143.92 | 0
C113132STEQ300080 | U13 - 544-STR-005 Structure Erection (Train 3) (544-E-128; 544-E-129) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3102 | 0 | 10610.ST.ER.TN | 58.54 | 0
C113132STEQ300110 | U13 - Structure Erection for Lube Oil Cooler (close to 544-SH-002) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2226 | 0 | 10780.ST.ST.MH
C113132STEQ300150 | U13 - 544-STR-006 Structure Erection (Train 3) (544-V-132) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 421 | 0 | 10610.ST.ER.TN | 7.95 | 0
C113132STEQ300160 | U13 - 544-STR-011 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4612 | 9.2513 | 10610.ST.ER.TN | 87.01 | 39.4052
C113132STEQ300180 | U13 - 543-STR-011 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4612 | 0 | 10610.ST.ER.TN | 87.01 | 0
C113132STEQ300190 | U13 - 544-STR-010 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STPL100020 | U13 - 542-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-V-141) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL100050 | U13 - 542-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5260 | 0 | 10610.ST.PL.TN | 65.75 | 0
C113132STPL100060 | U13 - 542-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3203 | 0 | 10610.ST.PL.TN | 40.04 | 0
C113132STPL100070 | U13 - 542-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4070 | 0 | 10610.ST.PL.TN | 50.88 | 0
C113132STPL300370 | U13 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 916 | 0 | 10610.ST.PL.TN | 11.46 | 0
C113132STPL300400 | U13 - 544-STR-006 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 71 | 0 | 10610.ST.PL.TN | 0.88 | 0
C113132STPR100010 | U13 - 542-PR-101 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24754 | 421.8243 | 10610.ST.PR.TN | 467.06 | 277.4663
C113132STPR100050 | U13 - 542-PR-104 Main Piperack Erection (Train 1) (542-E-106) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26147 | 791.7839 | 10610.ST.PR.TN | 493.34 | 440.004
C113132STPR100060 | U13 - 542-PR-105 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19100 | 447.7178 | 10610.ST.PR.TN | 360.37 | 330.8173
C113132STPR100080 | U13 - 542-PR-107 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26648 | 692.1492 | 10610.ST.PR.TN | 502.8 | 371.0646
C113132STPR100100 | U13 - 542-PR-109 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35600 | 1155.9341 | 10610.ST.PR.TN | 671.7 | 547.5827
C113132STPR100110 | U13 - 542-PR-110 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31168 | 1174.968 | 10610.ST.PR.TN | 588.07 | 558.0862
C113132STPR100130 | U13 - 542-PR-112 Main Piperack Erection (Train 1) (542-E-112) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33329 | 736.5726 | 10610.ST.PR.TN | 628.84 | 349.6361
C113132STPR100150 | U13 - 542-PR-201 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22320 | 498.6679 | 10610.ST.PR.TN | 421.13 | 302.3694
C113132STPR100160 | U13 - 542-PR-301 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32063 | 0 | 10610.ST.PR.TN | 604.95 | 0
C113132STPR100190 | U13 - 542-PR-601 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6910 | 55.0528 | 10610.ST.PR.TN | 130.38 | 116.5575
C113132STPR100220 | U13 - 542-PR-901 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3628 | 16.6339 | 10610.ST.PR.TN | 68.45 | 68.4456
C113132STPR200010 | U13 - 543-PR-101 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24736 | 0 | 10610.ST.PR.TN | 466.72 | 0
C113132STPR200030 | U13 - 543-PR-102 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22410 | 481.7799 | 10610.ST.PR.TN | 422.82 | 377.1573
C113132STPR200040 | U13 - 543-PR-103 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31262 | 886.0871 | 10610.ST.PR.TN | 589.85 | 477.1876
C113132STPR200060 | U13 - 543-PR-105 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19062 | 491.7347 | 10610.ST.PR.TN | 359.66 | 338.4426
C113132STPR200070 | U13 - 543-PR-106 Main Piperack Erection (Train 2) (543-E-120) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24092 | 755.5078 | 10610.ST.PR.TN | 454.56 | 425.0141
C113132STPR200080 | U13 - 543-PR-107 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27311 | 571.6969 | 10610.ST.PR.TN | 515.31 | 333.9218
C113132STPL200020 | U13 - 543-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-V-141) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL200030 | U13 - 543-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL200040 | U13 - 543-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4358 | 0 | 10610.ST.PL.TN | 54.47 | 0
C113132STPL200040 | U13 - 543-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4358 | 0 | 10610.ST.PL.TN | 54.47 | 0
C113132STPL200050 | U13 - 543-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5243 | 0 | 10610.ST.PL.TN | 65.54 | 0
C113132STPL200060 | U13 - 543-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3197 | 0.20625 | 10610.ST.PL.TN | 39.96 | 0.60839
C113132STPL200100 | U13 - 543-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5969 | 0 | 10610.ST.PL.TN | 74.61 | 0
C113132STPL200110 | U13 - 543-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5226 | 0 | 10610.ST.PL.TN | 65.32 | 0
C113132STPL200130 | U13 - 543-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5044 | 0 | 10610.ST.PL.TN | 63.05 | 0
C113132STPL200150 | U13 - 543-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3758 | 0 | 10610.ST.PL.TN | 46.98 | 0
C113132STPL200160 | U13 - 543-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4149 | 0 | 10610.ST.PL.TN | 51.86 | 0
C113132STPL200220 | U13 - 543-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5377 | 0 | 10610.ST.PL.TN | 67.22 | 0
C113132STPL200240 | U13 - 543-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10610.ST.PL.TN | 5.2 | 0
C113132STPL200250 | U13 - Lube Oil Cooler for 543-SH-002 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL200280 | U13 - 543-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10610.ST.PL.TN | 42.55 | 0
C113132STPL300020 | U13 - 544-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-V-141) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL300040 | U13 - 544-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4392 | 12.8648 | 10610.ST.PL.TN | 54.9 | 27.7021
C113132STEQ100020 | U13 - 542-STR-002 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14787 | 0 | 10610.ST.ER.TN | 279 | 0
C113132STEQ100080 | U13 - 542-STR-005 Structure Erection (Train 1) (542-E-128; 542-E-129) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2755 | 0 | 10610.ST.ER.TN | 51.97 | 0
C113132STEQ100100 | U13 - Auxiliary Structure Erection for Pumps 542-P-109A/B/C | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10610.ST.ER.TN | 57.07 | 0
C113132STEQ100130 | U13 - Structure Erection for Lube Oil Cooler (close to 542-SH-001) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1855 | 0 | 10780.ST.ST.MH
C113132STEQ100150 | U13 - 542-STR-011 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4612 | 0 | 10610.ST.ER.TN | 87.01 | 0
C113132STEQ100160 | U13 - 542-STR-010 Structure Erection (Train 1) | ST | STEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STEQ200020 | U13 - 543-STR-002 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14787 | 0 | 10610.ST.ER.TN | 279 | 0
C113132STEQ200080 | U13 - 543-STR-005 Structure Erection (Train 2) (543-E-128; 543-E-129) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2755 | 0 | 10610.ST.ER.TN | 51.97 | 0
C113132STEQ200100 | U13 - Auxiliary Structure Erection for Pumps 543-P-109A/B/C | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3085 | 0 | 10610.ST.ER.TN | 58.21 | 0
C113132STEQ300010 | U13 - 544-STR-001 Structure Erection (Train 3) (544-V-141) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44838 | 433.7709 | 10610.ST.ER.TN | 846 | 158.6098
C113132STEQ300020 | U13 - 544-STR-002 Structure Erection (Train 3) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14787 | 93.378 | 10610.ST.ER.TN | 279 | 123.9853
C113132STEQ300100 | U13 - Auxiliary Structure Erection for Pumps 544-P-109A/B/C | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10610.ST.ER.TN | 57.07 | 0
C113132STEQ300120 | U13 - Structure Erection for Lube Oil Cooler (close to 544-SH-004) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2120 | 0 | 10780.ST.ST.MH
C113132STEQ300130 | U13 - Structure Erection for Lube Oil Cooler (close to 544-SH-001) | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2703 | 0 | 10780.ST.ST.MH
C113132STEQ300140 | U13 - Structure Erection around Vessels 544-V-110A; 544-V-110B; 544-V-110C; 544-V-110D | ST | STEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5464 | 9.3159 | 10610.ST.ER.TN | 103.1 | 43.6187
C113132STEQ300170 | U13 - 543-STR-006 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 468 | 0 | 10610.ST.ER.TN | 8.83 | 0
C113132STEQ300180 | U13 - 543-STR-011 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4612 | 0 | 10610.ST.ER.TN | 87.01 | 0
C113132STEQ300200 | U13 - 543-STR-010 Structure Erection (Train 2) | ST | STEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10610.ST.ER.TN | 7 | 0
C113132STMS100010 | U13 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (Train 1) | ST | STMS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 114 | 0 | 10610.ST.PL.TN | 1.9 | 0
C113132STPL300070 | U13 - 544-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4042 | 0 | 10610.ST.PL.TN | 50.52 | 0
C113132STPL300090 | U13 - 544-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5430 | 15.9635 | 10610.ST.PL.TN | 67.88 | 37.8283
C113132STPL300120 | U13 - 544-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3290 | 0.19396 | 10610.ST.PL.TN | 41.12 | 0.55882
C113132STPL300150 | U13 - 544-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3894 | 0 | 10610.ST.PL.TN | 48.68 | 0
C113132STPL300160 | U13 - 544-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3916 | 0 | 10610.ST.PL.TN | 48.95 | 0
C113132STPL300170 | U13 - 544-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL300190 | U13 - 544-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1599 | 0 | 10610.ST.PL.TN | 19.99 | 0
C113132STPL300210 | U13 - 544-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ST.PL.TN | 30 | 0
C113132STPL300240 | U13 - 544-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1652 | 0 | 10610.ST.PL.TN | 20.65 | 0
C113132STPL300280 | U13 - 544-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL300320 | U13 - 544-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-E-114A/B) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL300330 | U13 - 544-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-E-128; 544-E-129) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ST.PL.TN | 6.5 | 0
C113132STPL300350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43498 | 234.3992 | 10610.ST.PL.TN | 543.72 | 50.9619
C113132STPR100030 | U13 - 542-PR-102 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22464 | 418.0497 | 10610.ST.PR.TN | 423.84 | 312.7951
C113132STPR100040 | U13 - 542-PR-103 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31362 | 760.929 | 10610.ST.PR.TN | 591.74 | 386.4035
C113132STPR100060 | U13 - 542-PR-105 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19100 | 447.7178 | 10610.ST.PR.TN | 360.37 | 330.8173
C113132STPR100090 | U13 - 542-PR-108 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32498 | 1228.2205 | 10610.ST.PR.TN | 613.18 | 581.8493
C113132STPR100100 | U13 - 542-PR-109 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35600 | 1155.9341 | 10610.ST.PR.TN | 671.7 | 547.5827
C113132STPL100080 | U13 - 542-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4469 | 0 | 10610.ST.PL.TN | 55.87 | 0
C113132STPL100090 | U13 - 542-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5450 | 0.014481 | 10610.ST.PL.TN | 68.13 | 0.029721
C113132STPL100100 | U13 - 542-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5971 | 0 | 10610.ST.PL.TN | 74.63 | 0
C113132STPL100150 | U13 - 542-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3768 | 0 | 10610.ST.PL.TN | 47.09 | 0
C113132STPL100160 | U13 - 542-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4152 | 0 | 10610.ST.PL.TN | 51.9 | 0
C113132STPL100180 | U13 - 542-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL100190 | U13 - 542-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.ST.PL.TN | 19.96 | 0
C113132STPL100210 | U13 - 542-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2394 | 0 | 10610.ST.PL.TN | 29.93 | 0
C113132STPL100230 | U13 - 542-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL100250 | U13 - Lube Oil Cooler for 542-SH-002 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL100330 | U13 - 542-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-E-128; 542-E-129) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 462 | 0 | 10610.ST.PL.TN | 5.77 | 0
C113132STPL100330 | U13 - 542-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-E-128; 542-E-129) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 462 | 0 | 10610.ST.PL.TN | 5.77 | 0
C113132STPL100370 | U13 - 542-V-110A/B/C/D Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 779 | 0 | 10610.ST.PL.TN | 9.73 | 0
C113132STPL200090 | U13 - 543-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5461 | 0 | 10610.ST.PL.TN | 68.27 | 0
C113132STPL200090 | U13 - 543-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5461 | 0 | 10610.ST.PL.TN | 68.27 | 0
C113132STPL200110 | U13 - 543-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5226 | 0 | 10610.ST.PL.TN | 65.32 | 0
C113132STPL200120 | U13 - 543-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3290 | 0 | 10610.ST.PL.TN | 41.12 | 0
C113132STPR200100 | U13 - 543-PR-109 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 35589 | 1110.8389 | 10610.ST.PR.TN | 671.49 | 520.4013
C113132STPR200130 | U13 - 543-PR-112 Main Piperack Erection (Train 2) (543-E-112) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30074 | 283.4374 | 10610.ST.PR.TN | 567.44 | 123.1327
C113132STPR200150 | U13 - 543-PR-201 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22320 | 162.4693 | 10610.ST.PR.TN | 421.13 | 101.9142
C113132STPR200160 | U13 - 543-PR-301 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32063 | 339.6694 | 10610.ST.PR.TN | 604.95 | 130.0785
C113132STPR200200 | U13 - 543-PR-701 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9520 | 0 | 10610.ST.PR.TN | 179.62 | 0
C113132STPR300010 | U13 - 544-PR-101 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23348 | 111.8191 | 10610.ST.PR.TN | 440.53 | 13.3054
C113132STPR300060 | U13 - 544-PR-105 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19274 | 524.3394 | 10610.ST.PR.TN | 363.65 | 346.7386
C113132STPR300080 | U13 - 544-PR-107 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27608 | 1028.6239 | 10610.ST.PR.TN | 520.91 | 499.5535
C113132STPR300100 | U13 - 544-PR-109 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35600 | 1738.0165 | 10610.ST.PR.TN | 671.7 | 671.7005
C113132STPR300110 | U13 - 544-PR-110 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30960 | 1314.8488 | 10610.ST.PR.TN | 584.16 | 584.1572
C113132STPR300110 | U13 - 544-PR-110 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30960 | 1314.8488 | 10610.ST.PR.TN | 584.16 | 584.1572
C113132STPR300130 | U13 - 544-PR-112 Main Piperack Erection (Train 3) (544-E-112) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35416 | 870.9326 | 10610.ST.PR.TN | 668.23 | 378.8834
C113132STPR300150 | U13 - 544-PR-201 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22320 | 313.0308 | 10610.ST.PR.TN | 421.13 | 182.7745
C113132STPR300170 | U13 - 544-PR-401 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9117 | 99.0732 | 10610.ST.PR.TN | 172.01 | 169.601
C113132STPR300190 | U13 - 544-PR-601 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6910 | 60.495 | 10610.ST.PR.TN | 130.38 | 124.8777
C113132STPR300220 | U13 - 544-PR-901 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3628 | 18.4228 | 10610.ST.PR.TN | 68.45 | 68.4485
C113132STPR300220 | U13 - 544-PR-901 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3628 | 18.4228 | 10610.ST.PR.TN | 68.45 | 68.4485
C113132STSH100010 | U13 - 542-SH-001 Compressor Shelter Structure Erection (Train 1) for 542-C-101 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20776 | 0 | 10610.ST.ER.TN | 392.01 | 0
C113132STSH100030 | U13 - 542-SH-001 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-101 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10610.ST.ER.TN | 43.56 | 0
C113132STPR100160 | U13 - 542-PR-301 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32063 | 0 | 10610.ST.PR.TN | 604.95 | 0
C113132STPR100180 | U13 - 542-PR-501 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14275 | 167.178 | 10610.ST.PR.TN | 269.34 | 185.5754
C113132STPR100190 | U13 - 542-PR-601 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6910 | 55.0528 | 10610.ST.PR.TN | 130.38 | 116.5575
C113132STPR100200 | U13 - 542-PR-701 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9520 | 0 | 10610.ST.PR.TN | 179.62 | 0
C113132STPR100210 | U13 - 542-PR-801 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20825 | 122.5927 | 10610.ST.PR.TN | 392.92 | 91.5462
C113132STPR200020 | U13 - 543-PR-401 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9117 | 74.411 | 10610.ST.PR.TN | 172.01 | 136.9011
C113132STPR200030 | U13 - 543-PR-102 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22410 | 481.7799 | 10610.ST.PR.TN | 422.82 | 377.1573
C113132STPR200070 | U13 - 543-PR-106 Main Piperack Erection (Train 2) (543-E-120) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24092 | 755.5078 | 10610.ST.PR.TN | 454.56 | 425.0141
C113132STPR200110 | U13 - 543-PR-110 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31159 | 737.3843 | 10610.ST.PR.TN | 587.91 | 376.2632
C113132STPR200180 | U13 - 543-PR-501 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14275 | 0 | 10610.ST.PR.TN | 269.34 | 0
C113132STPR200190 | U13 - 543-PR-601 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6944 | 0 | 10610.ST.PR.TN | 131.03 | 0
C113132STPR200210 | U13 - 543-PR-801 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20825 | 166.0624 | 10610.ST.PR.TN | 392.92 | 109.6213
C113132STPR300030 | U13 - 544-PR-102 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23219 | 715.9906 | 10610.ST.PR.TN | 438.09 | 413.1163
C113132STPR300040 | U13 - 544-PR-103 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31115 | 1301.3931 | 10610.ST.PR.TN | 587.07 | 567.6945
C113132STPR300070 | U13 - 544-PR-106 Main Piperack Erection (Train 3) (544-E-120) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24099 | 832.5881 | 10610.ST.PR.TN | 454.7 | 442.7899
C113132STPR300090 | U13 - 544-PR-108 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32379 | 1439.0747 | 10610.ST.PR.TN | 610.92 | 609.093
C113132STPR300100 | U13 - 544-PR-109 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35600 | 1738.0165 | 10610.ST.PR.TN | 671.7 | 671.7005
C113132STPR300120 | U13 - 544-PR-111 Main Piperack Erection (Train 3) (544-E-112) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19616 | 512.6801 | 10610.ST.PR.TN | 370.11 | 351.4154
C113132STPR300130 | U13 - 544-PR-112 Main Piperack Erection (Train 3) (544-E-112) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35416 | 870.9326 | 10610.ST.PR.TN | 668.23 | 378.8834
C113132STPL100010 | U13 - 542-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL100030 | U13 - 542-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL100040 | U13 - 542-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4385 | 0 | 10610.ST.PL.TN | 54.82 | 0
C113132STPL100050 | U13 - 542-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5260 | 0 | 10610.ST.PL.TN | 65.75 | 0
C113132STPL100060 | U13 - 542-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3203 | 0 | 10610.ST.PL.TN | 40.04 | 0
C113132STPL100080 | U13 - 542-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4469 | 0 | 10610.ST.PL.TN | 55.87 | 0
C113132STPL100100 | U13 - 542-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5971 | 0 | 10610.ST.PL.TN | 74.63 | 0
C113132STPL100120 | U13 - 542-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3290 | 0 | 10610.ST.PL.TN | 41.12 | 0
C113132STPL100130 | U13 - 542-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5590 | 0 | 10610.ST.PL.TN | 69.87 | 0
C113132STPL100150 | U13 - 542-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3768 | 0 | 10610.ST.PL.TN | 47.09 | 0
C113132STPL100170 | U13 - 542-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL100200 | U13 - 542-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1159 | 0 | 10610.ST.PL.TN | 14.49 | 0
C113132STPL100230 | U13 - 542-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL100240 | U13 - 542-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 507 | 0 | 10610.ST.PL.TN | 6.34 | 0
C113132STPL100270 | U13 - Lube Oil Cooler for 542-SH-001 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL100280 | U13 - 542-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL100320 | U13 - 542-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 1) (542-F-114A/B) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL200130 | U13 - 543-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5044 | 0 | 10610.ST.PL.TN | 63.05 | 0
C113132STPL200150 | U13 - 543-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3758 | 0 | 10610.ST.PL.TN | 46.98 | 0
C113132STPL200170 | U13 - 543-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL200180 | U13 - 543-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL200180 | U13 - 543-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL200210 | U13 - 543-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2394 | 0 | 10610.ST.PL.TN | 29.93 | 0
C113132STPL200230 | U13 - 543-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL200240 | U13 - 543-P-109A/B/C Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10610.ST.PL.TN | 5.2 | 0
C113132STPL200280 | U13 - 543-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10610.ST.PL.TN | 42.55 | 0
C113132STPL200320 | U13 - 543-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-E-114A/B) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL200350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37950 | 140.0387 | 10610.ST.PL.TN | 474.38 | 34.8999
C113132STPL200360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 2) (543-SU-101; 543-SU-502) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132STPL200370 | U13 - 543-V-110A/B/C/D Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1279 | 0 | 10610.ST.PL.TN | 15.99 | 0
C113132STPL300040 | U13 - 544-PR-104 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4392 | 12.8648 | 10610.ST.PL.TN | 54.9 | 27.7021
C113132STPL300050 | U13 - 544-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5218 | 0 | 10610.ST.PL.TN | 65.23 | 0
C113132STPL300060 | U13 - 544-PR-105 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3232 | 0 | 10610.ST.PL.TN | 40.41 | 0
C113132STPL300070 | U13 - 544-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4042 | 0 | 10610.ST.PL.TN | 50.52 | 0
C113132STSH100060 | U13 - 542-SH-002 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-102 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.ST.ER.TN | 38.72 | 0
C113132STSH100070 | U13 - 542-SH-004 Compressor Shelter Structure Erection (Train 1) for 542-C-103 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13161 | 0 | 10610.ST.ER.TN | 248.31 | 0
C113132STSH100090 | U13 - 542-SH-004 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-103 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66 | 0 | 10610.ST.ER.TN | 27.59 | 0
C113132STSH100100 | U13 - 542-SH-003 Compressor Shelter Structure Erection (Train 1) for 542-EC-101 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7179 | 0 | 10610.ST.ER.TN | 135.45 | 0
C113132STSH100110 | U13 - 542-SH-003 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-EC-101 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113132STSH200030 | U13 - 543-SH-001 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-101 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10610.ST.ER.TN | 43.56 | 0
C113132STSH200040 | U13 - 543-SH-002 Compressor Shelter Structure Erection (Train 2) for 543-C-102 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 18164 | 5.7318 | 10610.ST.ER.TN | 342.71 | 5.1036
C113132STSH200070 | U13 - 543-SH-004 Compressor Shelter Structure Erection (Train 2) for 543-C-103 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12983 | 0 | 10610.ST.ER.TN | 244.96 | 0
C113132STSH200090 | U13 - 543-SH-004 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-103 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 65 | 0 | 10610.ST.ER.TN | 27.22 | 0
C113132STSH200100 | U13 - 543-SH-003 Compressor Shelter Structure Erection (Train 2) for 543-EC-101 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7179 | 0 | 10610.ST.ER.TN | 135.45 | 0
C113132STSH300010 | U13 - 544-SH-001 Compressor Shelter Structure Erection (Train 3) for 544-C-101 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6470 | 10.6027 | 10610.ST.ER.TN | 122.08 | 24.5585
C113132STSH300030 | U13 - 544-SH-001 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-101 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10610.ST.ER.TN | 13.56 | 0
C113132STSH300060 | U13 - 544-SH-002 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-102 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.ST.ER.TN | 38.72 | 0
C113132STSH300070 | U13 - 544-SH-004 Compressor Shelter Structure Erection (Train 3) for 544-C-103 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12983 | 22.7123 | 10610.ST.ER.TN | 244.96 | 24.3805
C113132STSH300090 | U13 - 544-SH-004 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-103 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65 | 0 | 10610.ST.ER.TN | 27.22 | 0
C113132STSH300100 | U13 - 544-SH-003 Compressor Shelter Structure Erection (Train 3) for 544-EC-101 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7179 | 25.2021 | 10610.ST.ER.TN | 135.45 | 54.0827
C113133PAPP100010 | U13 - Piping SandBl. & Priming (Train 1) | PA | PAPP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 176282 | 17208.8336 | 10610.PA.PP.M2 | 0 | 0
C113132STPR300160 | U13 - 544-PR-301 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29503 | 225.5463 | 10610.ST.PR.TN | 556.67 | 114.3512
C113132STPR300180 | U13 - 544-PR-501 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14310 | 205.6595 | 10610.ST.PR.TN | 270.01 | 228.695
C113132STPR300200 | U13 - 544-PR-701 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9535 | 0 | 10610.ST.PR.TN | 179.9 | 0
C113132STPR300210 | U13 - 544-PR-801 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20825 | 421.8572 | 10610.ST.PR.TN | 392.92 | 371.7021
C113132STSH100030 | U13 - 542-SH-001 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-101 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10610.ST.ER.TN | 43.56 | 0
C113132STSH100040 | U13 - 542-SH-002 Compressor Shelter Structure Erection (Train 1) for 542-C-102 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18468 | 0 | 10610.ST.ER.TN | 348.46 | 0
C113132STSH100070 | U13 - 542-SH-004 Compressor Shelter Structure Erection (Train 1) for 542-C-103 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13161 | 0 | 10610.ST.ER.TN | 248.31 | 0
C113132STSH200060 | U13 - 543-SH-002 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-102 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 91 | 0 | 10610.ST.ER.TN | 38.08 | 0
C113132STSH200070 | U13 - 543-SH-004 Compressor Shelter Structure Erection (Train 2) for 543-C-103 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12983 | 0 | 10610.ST.ER.TN | 244.96 | 0
C113132STSH200110 | U13 - 543-SH-003 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-EC-101 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113132STSH300010 | U13 - 544-SH-001 Compressor Shelter Structure Erection (Train 3) for 544-C-101 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6470 | 10.6027 | 10610.ST.ER.TN | 122.08 | 24.5585
C113132STSH300030 | U13 - 544-SH-001 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-101 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10610.ST.ER.TN | 13.56 | 0
C113132STSH300070 | U13 - 544-SH-004 Compressor Shelter Structure Erection (Train 3) for 544-C-103 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12983 | 22.7123 | 10610.ST.ER.TN | 244.96 | 24.3805
C113133PAEQ200010 | U13 - Equipment Painting (Train 2) | PA | PAEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6198 | 0 | 10610.PA.EQ.M2 | 2479 | 0
C113133PAFP300010 | U13 - Piping Final Coat & Touch-Up Painting (Train 3) | PA | PAFP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21154 | 0 | 10780.PA.PA.MH
C113133PAPP100010 | U13 - Piping SandBl. & Priming (Train 1) | PA | PAPP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 176282 | 17208.8336 | 10610.PA.PP.M2 | 0 | 0
C113133PAPP200010 | U13 - Piping SandBl. & Priming (Train 2) | PA | PAPP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 176284 | 13692.6404 | 10610.PA.PP.M2 | 88142 | 30990.3403
C113133PASP100010 | U13 - Piping Supports SandBl. & Priming (Train 1) | PA | PASP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23339 | 26.0882 | 10610.PA.SU.TN | 0 | 0
C113132STPL300090 | U13 - 544-PR-108 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5430 | 15.9635 | 10610.ST.PL.TN | 67.88 | 37.8283
C113132STPL300100 | U13 - 544-PR-109 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5971 | 0.72944 | 10610.ST.PL.TN | 74.63 | 12.9846
C113132STPL300110 | U13 - 544-PR-110 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5193 | 1.8217 | 10610.ST.PL.TN | 64.91 | 8.3276
C113132STPL300120 | U13 - 544-PR-111 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3290 | 0.19396 | 10610.ST.PL.TN | 41.12 | 0.55882
C113132STPL300150 | U13 - 544-PR-102 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3894 | 0 | 10610.ST.PL.TN | 48.68 | 0
C113132STPL300160 | U13 - 544-PR-101 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3916 | 0 | 10610.ST.PL.TN | 48.95 | 0
C113132STPL300180 | U13 - 544-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL300190 | U13 - 544-PR-701 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1599 | 0 | 10610.ST.PL.TN | 19.99 | 0
C113132STPL300210 | U13 - 544-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ST.PL.TN | 30 | 0
C113132STPL300230 | U13 - 544-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL300250 | U13 - Lube Oil Cooler for 544-SH-002 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.ST.ST.MH
C113132STPL300320 | U13 - 544-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-E-114A/B) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL300330 | U13 - 544-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-E-128; 544-E-129) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ST.PL.TN | 6.5 | 0
C113132STPL300350 | U13- Rest of Equipment Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43498 | 234.3992 | 10610.ST.PL.TN | 543.72 | 50.9619
C113132STPL300370 | U13 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 916 | 0 | 10610.ST.PL.TN | 11.46 | 0
C113132STPR100020 | U13 - 542-PR-401 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9117 | 84.298 | 10610.ST.PR.TN | 172.01 | 166.8489
C113132STPR100030 | U13 - 542-PR-102 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22464 | 418.0497 | 10610.ST.PR.TN | 423.84 | 312.7951
C113132STPR100040 | U13 - 542-PR-103 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31362 | 760.929 | 10610.ST.PR.TN | 591.74 | 386.4035
C113132STPL100360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 1) (542-SU-101; 542-SU-502) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132STPL100370 | U13 - 542-V-110A/B/C/D Structure Platforms, Ladders & Handrails Erection (Train 1) | ST | STPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 779 | 0 | 10610.ST.PL.TN | 9.73 | 0
C113132STPL200010 | U13 - 543-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL200030 | U13 - 543-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL200050 | U13 - 543-PR-103 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5243 | 0 | 10610.ST.PL.TN | 65.54 | 0
C113132STPL200070 | U13 - 543-PR-106 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4041 | 0 | 10610.ST.PL.TN | 50.51 | 0
C113132STPL200080 | U13 - 543-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4581 | 0 | 10610.ST.PL.TN | 57.26 | 0
C113132STPL200200 | U13 - 543-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1165 | 0 | 10610.ST.PL.TN | 14.56 | 0
C113132STPL200210 | U13 - 543-PR-501 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2394 | 0 | 10610.ST.PL.TN | 29.93 | 0
C113132STPL200230 | U13 - 543-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL200260 | U13 - Lube Oil Cooler for 543-SH-004 Structure Platforms, Ladders & Handrails Erection (Train 2) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10780.ST.ST.MH
C113132STPL200320 | U13 - 543-STR-007 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-E-114A/B) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ST.PL.TN | 5 | 0
C113132STPL200330 | U13 - 543-STR-005 Structure Platforms, Ladders & Handrails Erection (Train 2) (543-E-128; 543-E-129) | ST | STPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 462 | 0 | 10610.ST.PL.TN | 5.77 | 0
C113132STPL300010 | U13 - 544-PR-401 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1529 | 0 | 10610.ST.PL.TN | 19.11 | 0
C113132STPL300020 | U13 - 544-STR-001 Structure Platforms, Ladders & Handrails Erection (Train 3) (544-V-141) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7520 | 0 | 10610.ST.PL.TN | 94 | 0
C113132STPL300030 | U13 - 544-STR-002 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL300080 | U13 - 544-PR-107 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4630 | 1.6466 | 10610.ST.PL.TN | 57.88 | 29.7913
C113133PAPP300010 | U13 - Piping SandBl. & Priming (Train 3) | PA | PAPP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 176283 | 30081.5992 | 10610.PA.PP.M2 | 0 | 0
C113133PAPP300010 | U13 - Piping SandBl. & Priming (Train 3) | PA | PAPP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 176283 | 30081.5992 | 10610.PA.PP.M2 | 0 | 0
C113133PASP100010 | U13 - Piping Supports SandBl. & Priming (Train 1) | PA | PASP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23339 | 26.0882 | 10610.PA.SU.TN | 0 | 0
C113133PASP200010 | U13 - Piping Supports SandBl. & Priming (Train 2) | PA | PASP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23339 | 27.9953 | 10610.PA.SU.TN | 0 | 0
C113133PASP300010 | U13 - Piping Supports SandBl. & Priming (Train 3) | PA | PASP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23339 | 140.9502 | 10610.PA.SU.TN | 0 | 0
C113133PAST100010 | U13 - Steel Structure Painting Touch Up (Train 1) | PA | PAST | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 50012 | 0 | 10780.PA.PA.MH
C113134ELCL100020 | U13 - Electrical Cable Laying (Train 1) | EL | ELCL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 169127 | 0 | 10610.EL.PL.LM | 270058.45 | 0
C113134ELCL200020 | U13 - Electrical Cable Laying (Train 2) | EL | ELCL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 182804 | 0 | 10610.EL.PL.LM | 291897.52 | 0
C113134ELCL300020 | U13 - Electrical Cable Laying (Train 3) | EL | ELCL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160595 | 10145.3878 | 10610.EL.PL.LM | 256434.64 | 71958.1243
C113134ELCO100010 | U13 - Lighting Cable Gland & Conn./Testing (Train 1) | EL | ELCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23063 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELCO200010 | U13 - Lighting Cable Gland & Conn./Testing (Train 2) | EL | ELCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24928 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELCO300010 | U13 - Lighting Cable Gland & Conn./Testing (Train 3) | EL | ELCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21899 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELEL100015 | U13 - Earthing Works (Train 1) | EL | ELEL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30750 | 128.877 | 10610.EL.ES.LM | 28109.94 | 2593.4231
C113134ELEL200015 | U13 - Earthing Works (Train 2) | EL | ELEL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33237 | 0 | 10610.EL.ES.LM | 28109.94 | 0
C113134ELEL200025 | U13 - Lightning Works (Train 2) | EL | ELEL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33237 | 0 | 10780.EL.EL.MH
C113134ELEL300015 | U13 - Earthing Works (Train 3) | EL | ELEL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29199 | 239.3079 | 10610.EL.ES.LM | 28109.94 | 5340.8886
C113134ELEL300025 | U13 - Lightning Works (Train 3) | EL | ELEL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29199 | 0 | 10780.EL.EL.MH
C113134ELEQ100010 | U13 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Train 1) | EL | ELEQ3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23063 | 0 | 10780.EL.EL.MH
C113134ELEQ200010 | U13 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Train 2) | EL | ELEQ3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24928 | 0 | 10780.EL.EL.MH
C113134ELEQ300010 | U13 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (Train 3) | EL | ELEQ3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21899 | 0 | 10780.EL.EL.MH
C113134ELCI100010 | U13 - Conduits Installation (Train 1) | EL | ELCI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19219 | 0 | 10780.EL.EL.MH
C113134ELCI200010 | U13 - Conduits Installation (Train 2) | EL | ELCI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20773 | 0 | 10780.EL.EL.MH
C113134ELCL200010 | U13 - Lighting Cable Laying (Train 2) | EL | ELCL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37392 | 0 | 10610.EL.LC.LM | 159573.63 | 0
C113134ELCL300010 | U13 - Lighting Cable Laying (Train 3) | EL | ELCL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32849 | 0 | 10610.EL.LC.LM | 140186.04 | 0
C113134ELCO100020 | U13 - Electrical Cable Gland & Conn./Testing (Train 1) | EL | ELCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 92251 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELCO300020 | U13 - Electrical Cable Gland & Conn./Testing (Train 3) | EL | ELCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 87597 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELCP100010 | U13 - Cathodic Protection Piping (Train 1) | EL | ELCP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15375 | 0 | 10780.EL.EL.MH
C113134ELCP300010 | U13 - Cathodic Protection Piping (Train 3) | EL | ELCP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14600 | 0 | 10780.EL.EL.MH
C113134ELEL100025 | U13 - Lightning Works (Train 1) | EL | ELEL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30750 | 0 | 10780.EL.EL.MH
C113134ELHT200010 | U13 - Electrical Heat Tracing (Train 2) | EL | ELHT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29082 | 0 | 10610.EL.ET.LM | 660 | 0
C113134ELHT300010 | U13 - Electrical Heat Tracing (Train 3) | EL | ELHT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25549 | 0 | 10610.EL.ET.LM | 680 | 0
C113134ELTI100020 | U13 - Electrical Cable Trays Installation (Train 1) | EL | ELTI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 76876 | 0 | 10610.EL.CT.LM | 15257.2 | 0
C113134ELTI200010 | U13 - Lighting Cable Trays Installation (Train 2) | EL | ELTI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24928 | 0 | 10610.EL.CT.LM | 7640.19 | 0
C113134ELTI200020 | U13 - Electrical Cable Trays Installation (Train 2) | EL | ELTI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 83093 | 0 | 10610.EL.CT.LM | 14188.92 | 0
C113134ELTI300010 | U13 - Lighting Cable Trays Installation (Train 3) | EL | ELTI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21899 | 0 | 10610.EL.CT.LM | 7542.76 | 0
C113134ELTI300020 | U13 - Electrical Cable Trays Installation (Train 3) | EL | ELTI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72998 | 0 | 10610.EL.CT.LM | 14007.99 | 0
C113134FPEQ100012 | U13 - Equipment Fireproofing (Train 1) 542-E-118 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100014 | U13 - Equipment Fireproofing (Train 1) 542-E-113 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100018 | U13 - Equipment Fireproofing (Train 1) 542-V-119 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 48.3416 | 10780.FP.FP.MH
C113134FPEQ100019 | U13 - Equipment Fireproofing (Train 1) 542-V-122 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100020 | U13 - Equipment Fireproofing (Train 1) 542-F-117A/B | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113132STPR100070 | U13 - 542-PR-106 Main Piperack Erection (Train 1) (542-E-120) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24268 | 684.6813 | 10610.ST.PR.TN | 457.89 | 434.0366
C113132STPR100090 | U13 - 542-PR-108 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32498 | 1228.2205 | 10610.ST.PR.TN | 613.18 | 581.8493
C113132STPR100110 | U13 - 542-PR-110 Main Piperack Erection (Train 1) (542-E-119) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31168 | 1174.968 | 10610.ST.PR.TN | 588.07 | 558.0862
C113132STPR100120 | U13 - 542-PR-111 Main Piperack Erection (Train 1) (542-E-112) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19616 | 409.4502 | 10610.ST.PR.TN | 370.11 | 309.839
C113132STPR100180 | U13 - 542-PR-501 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14275 | 167.178 | 10610.ST.PR.TN | 269.34 | 185.5754
C113132STPR100200 | U13 - 542-PR-701 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9520 | 0 | 10610.ST.PR.TN | 179.62 | 0
C113132STPR100210 | U13 - 542-PR-801 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20825 | 122.5927 | 10610.ST.PR.TN | 392.92 | 91.5462
C113132STPR100220 | U13 - 542-PR-901 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3628 | 16.6339 | 10610.ST.PR.TN | 68.45 | 68.4456
C113132STPR200020 | U13 - 543-PR-401 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9117 | 74.411 | 10610.ST.PR.TN | 172.01 | 136.9011
C113132STPR200040 | U13 - 543-PR-103 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31262 | 886.0871 | 10610.ST.PR.TN | 589.85 | 477.1876
C113132STPR200050 | U13 - 543-PR-104 Main Piperack Erection (Train 2) (543-E-106) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25983 | 735.9486 | 10610.ST.PR.TN | 490.24 | 454.4527
C113132STPR200060 | U13 - 543-PR-105 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19062 | 491.7347 | 10610.ST.PR.TN | 359.66 | 338.4426
C113132STPR200090 | U13 - 543-PR-108 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32563 | 1050.9749 | 10610.ST.PR.TN | 614.4 | 560.9498
C113132STPR200120 | U13 - 543-PR-111 Main Piperack Erection (Train 2) (543-E-112) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19616 | 359.3817 | 10610.ST.PR.TN | 370.11 | 320.943
C113132STPR200130 | U13 - 543-PR-112 Main Piperack Erection (Train 2) (543-E-112) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30074 | 283.4374 | 10610.ST.PR.TN | 567.44 | 123.1327
C113132STPR200180 | U13 - 543-PR-501 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14275 | 0 | 10610.ST.PR.TN | 269.34 | 0
C113132STPR200210 | U13 - 543-PR-801 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20825 | 166.0624 | 10610.ST.PR.TN | 392.92 | 109.6213
C113132STPR300010 | U13 - 544-PR-101 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23348 | 111.8191 | 10610.ST.PR.TN | 440.53 | 13.3054
C113132STPR300030 | U13 - 544-PR-102 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23219 | 715.9906 | 10610.ST.PR.TN | 438.09 | 413.1163
C113132STPL300130 | U13 - 544-PR-112 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5940 | 0 | 10610.ST.PL.TN | 74.25 | 0
C113132STPL300170 | U13 - 544-PR-901 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 608 | 0 | 10610.ST.PL.TN | 7.61 | 0
C113132STPL300180 | U13 - 544-PR-801 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3493 | 0 | 10610.ST.PL.TN | 43.66 | 0
C113132STPL300200 | U13 - 544-PR-601 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1159 | 0 | 10610.ST.PL.TN | 14.49 | 0
C113132STPL300220 | U13 - 544-PR-301 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4948 | 0 | 10610.ST.PL.TN | 61.85 | 0
C113132STPL300230 | U13 - 544-PR-201 Piperack Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3743 | 0 | 10610.ST.PL.TN | 46.79 | 0
C113132STPL300270 | U13 - Lube Oil Cooler for 544-SH-001 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10780.ST.ST.MH
C113132STPL300280 | U13 - 544-V-123/124/125/126/127 Structure Platforms, Ladders & Handrails Erection (Train 3) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10610.ST.PL.TN | 31 | 0
C113132STPL300360 | U13 - Pits Platforms, Ladders & Handrails Erection (Train 3) (544-SU-101; 544-SU-502) | ST | STPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 413 | 0 | 10610.ST.PL.TN | 5.16 | 0
C113132STPR100010 | U13 - 542-PR-101 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24754 | 421.8243 | 10610.ST.PR.TN | 467.06 | 277.4663
C113132STPR100020 | U13 - 542-PR-401 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9117 | 84.298 | 10610.ST.PR.TN | 172.01 | 166.8489
C113132STPR100050 | U13 - 542-PR-104 Main Piperack Erection (Train 1) (542-E-106) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26147 | 791.7839 | 10610.ST.PR.TN | 493.34 | 440.004
C113132STPR100070 | U13 - 542-PR-106 Main Piperack Erection (Train 1) (542-E-120) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24268 | 684.6813 | 10610.ST.PR.TN | 457.89 | 434.0366
C113132STPR100080 | U13 - 542-PR-107 Main Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26648 | 692.1492 | 10610.ST.PR.TN | 502.8 | 371.0646
C113132STPR100120 | U13 - 542-PR-111 Main Piperack Erection (Train 1) (542-E-112) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19616 | 409.4502 | 10610.ST.PR.TN | 370.11 | 309.839
C113132STPR100130 | U13 - 542-PR-112 Main Piperack Erection (Train 1) (542-E-112) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33329 | 736.5726 | 10610.ST.PR.TN | 628.84 | 349.6361
C113132STPR100150 | U13 - 542-PR-201 Secondary Piperack Erection (Train 1) | ST | STPR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22320 | 498.6679 | 10610.ST.PR.TN | 421.13 | 302.3694
C113132STPR200010 | U13 - 543-PR-101 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24736 | 0 | 10610.ST.PR.TN | 466.72 | 0
C113134ELHT100010 | U13 - Electrical Heat Tracing (Train 1) | EL | ELHT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26907 | 0 | 10610.EL.ET.LM | 630 | 0
C113134ELHT200010 | U13 - Electrical Heat Tracing (Train 2) | EL | ELHT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29082 | 0 | 10610.EL.ET.LM | 660 | 0
C113134ELPL100010 | U13 - Plant Lighting - (Lighting poles and fixtures) Installation (Train 1) | EL | ELPL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 49969 | 0 | 10780.EL.EL.MH
C113134ELTI100010 | U13 - Lighting Cable Trays Installation (Train 1) | EL | ELTI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23063 | 0 | 10610.EL.CT.LM | 8483.03 | 0
C113134ELTI300020 | U13 - Electrical Cable Trays Installation (Train 3) | EL | ELTI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72998 | 0 | 10610.EL.CT.LM | 14007.99 | 0
C113134FPEQ100013 | U13 - Equipment Fireproofing (Train 1) 542-E-119 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100016 | U13 - Equipment Fireproofing (Train 1) 542-P-112 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ200015 | U13 - Equipment Fireproofing (Train 2) 543-P-109A/B/C | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200016 | U13 - Equipment Fireproofing (Train 2) 543-P-112 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200018 | U13 - Equipment Fireproofing (Train 2) 543-V-119 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 43.3302 | 10610.FP.EQ.M2 | 152 | 76
C113134FPEQ300012 | U13 - Equipment Fireproofing (Train 3) 544-E-118 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300015 | U13 - Equipment Fireproofing (Train 3) 544-P-109A/B/C | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300020 | U13 - Equipment Fireproofing (Train 3) 544-F-117A/B | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPSS100140 | U13 - Secondary PR Steel Structure Fireproofing (Train 1) | FP | FPSS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 86835 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134FPSS200010 | U13 - Main PR Steel Structure Fireproofing (Train 2) (543-PR-101 TO 543-PR-112) | FP | FPSS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 101361 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134FPSS200140 | U13 - Secondary PR Steel Structure Fireproofing (Train 2) | FP | FPSS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 101361 | 0 | 10780.FP.FP.MH
C113134FPSS300010 | U13 - Main PR Steel Structure Fireproofing (Train 3) (544-PR-101 TO 544-PR-112) | FP | FPSS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105981 | 0 | 10780.FP.FP.MH
C113134FPSS300140 | U13 - Secondary PR Steel Structure Fireproofing (Train 3) | FP | FPSS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105981 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134FPSS300240 | U13 - Steel Structures Fireproofing (Train 3) (544-STR-001 TO 544-STR-009) | FP | FPSS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 95383 | 0 | 10780.FP.FP.MH
C113134MEMC300020 | 544 - Miscellaneous Electrical | EL | ELEQ2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10950 | 0 | 10780.EL.EL.MH
C113134FPEQ200011 | U13 - Equipment Fireproofing (Train 2) 543-EC-101 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200012 | U13 - Equipment Fireproofing (Train 2) 543-E-118 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200014 | U13 - Equipment Fireproofing (Train 2) 543-E-113 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200017 | U13 - Equipment Fireproofing (Train 2) 543-V-118 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200018 | U13 - Equipment Fireproofing (Train 2) 543-V-119 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 43.3302 | 10610.FP.EQ.M2 | 152 | 76
C113134FPEQ200019 | U13 - Equipment Fireproofing (Train 2) 543-V-122 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200020 | U13 - Equipment Fireproofing (Train 2) 543-F-117A/B | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ300019 | U13 - Equipment Fireproofing (Train 3) 544-V-122 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPSS200240 | U13 - Steel Structures Fireproofing (Train 2) (543-STR-001 TO 543-STR-011) | FP | FPSS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 101361 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134MEMC100020 | 542 - Miscellaneous Electrical | EL | ELEQ2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11531 | 0 | 10780.EL.EL.MH
C113134PRMR100010 | U13 - Motor Run (Train 1) | PR | PRMR | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15986 | 0 | 10780.PR.PR.MH
C113136MEAC100010 | U13 - Air Coolers (Regeneration Gas Cooler) Pre-Assembly 542-E-106 (Train 1) | ME | MEAC1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8144 | 97.981 | 10780.ME.ME.MH
C113136MEAC100020 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Pre-Assembly 542-E-112 (Train 1) | ME | MEAC1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20683 | 31.5351 | 10780.ME.ME.MH
C113136MEAC100040 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Pre-Assembly 542-E-120 (Train 1) | ME | MEAC1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4530 | 3.81 | 10780.ME.ME.MH
C113136MEAC100050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 542-E-106 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 66 | 0
C113136MEAC200010 | U13 - Air Coolers (Regeneration Gas Cooler) Pre-Assembly 543-E-106 (Train 2) | ME | MEAC1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8144 | 9.0966 | 10780.ME.ME.MH
C113136MEAC200060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 543-E-112 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MEAC200070 | U13 - Air Coolers (Refrigerant Condenser) Erection 543-E-119 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 54 | 0
C113136MEAC200080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 543-E-120 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113132STPR300050 | U13 - 544-PR-104 Main Piperack Erection (Train 3) (544-E-106) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26186 | 1009.0032 | 10610.ST.PR.TN | 494.07 | 492.7428
C113132STPR300060 | U13 - 544-PR-105 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19274 | 524.3394 | 10610.ST.PR.TN | 363.65 | 346.7386
C113132STPR300090 | U13 - 544-PR-108 Main Piperack Erection (Train 3) (544-E-119) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32379 | 1439.0747 | 10610.ST.PR.TN | 610.92 | 609.093
C113132STPR300120 | U13 - 544-PR-111 Main Piperack Erection (Train 3) (544-E-112) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19616 | 512.6801 | 10610.ST.PR.TN | 370.11 | 351.4154
C113132STPR300160 | U13 - 544-PR-301 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29503 | 225.5463 | 10610.ST.PR.TN | 556.67 | 114.3512
C113132STPR300170 | U13 - 544-PR-401 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9117 | 99.0732 | 10610.ST.PR.TN | 172.01 | 169.601
C113132STPR300210 | U13 - 544-PR-801 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20825 | 421.8572 | 10610.ST.PR.TN | 392.92 | 371.7021
C113132STSH100040 | U13 - 542-SH-002 Compressor Shelter Structure Erection (Train 1) for 542-C-102 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18468 | 0 | 10610.ST.ER.TN | 348.46 | 0
C113132STSH200010 | U13 - 543-SH-001 Compressor Shelter Structure Erection (Train 2) for 543-C-101 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20776 | 0 | 10610.ST.ER.TN | 392.01 | 0
C113132STSH200030 | U13 - 543-SH-001 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-101 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10610.ST.ER.TN | 43.56 | 0
C113132STSH200090 | U13 - 543-SH-004 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-103 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 65 | 0 | 10610.ST.ER.TN | 27.22 | 0
C113132STSH200110 | U13 - 543-SH-003 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-EC-101 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113132STSH300040 | U13 - 544-SH-002 Compressor Shelter Structure Erection (Train 3) for 544-C-102 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18468 | 189.1267 | 10610.ST.ER.TN | 348.46 | 132.2556
C113132STSH300100 | U13 - 544-SH-003 Compressor Shelter Structure Erection (Train 3) for 544-EC-101 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7179 | 25.2021 | 10610.ST.ER.TN | 135.45 | 54.0827
C113132STSH300110 | U13 - 544-SH-003 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-EC-101 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113133PAEQ100010 | U13 - Equipment Painting (Train 1) | PA | PAEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6198 | 0 | 10780.PA.PA.MH
C113133PAEQ300010 | U13 - Equipment Painting (Train 3) | PA | PAEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6198 | 0 | 10780.PA.PA.MH
C113133PASP300010 | U13 - Piping Supports SandBl. & Priming (Train 3) | PA | PASP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23339 | 140.9502 | 10610.PA.SU.TN | 0 | 0
C113132STPR200050 | U13 - 543-PR-104 Main Piperack Erection (Train 2) (543-E-106) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25983 | 735.9486 | 10610.ST.PR.TN | 490.24 | 454.4527
C113132STPR200080 | U13 - 543-PR-107 Main Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27311 | 571.6969 | 10610.ST.PR.TN | 515.31 | 333.9218
C113132STPR200090 | U13 - 543-PR-108 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32563 | 1050.9749 | 10610.ST.PR.TN | 614.4 | 560.9498
C113132STPR200100 | U13 - 543-PR-109 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 35589 | 1110.8389 | 10610.ST.PR.TN | 671.49 | 520.4013
C113132STPR200110 | U13 - 543-PR-110 Main Piperack Erection (Train 2) (543-E-119) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31159 | 737.3843 | 10610.ST.PR.TN | 587.91 | 376.2632
C113132STPR200120 | U13 - 543-PR-111 Main Piperack Erection (Train 2) (543-E-112) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19616 | 359.3817 | 10610.ST.PR.TN | 370.11 | 320.943
C113132STPR200150 | U13 - 543-PR-201 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 22320 | 162.4693 | 10610.ST.PR.TN | 421.13 | 101.9142
C113132STPR200160 | U13 - 543-PR-301 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32063 | 339.6694 | 10610.ST.PR.TN | 604.95 | 130.0785
C113132STPR200190 | U13 - 543-PR-601 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6944 | 0 | 10610.ST.PR.TN | 131.03 | 0
C113132STPR200200 | U13 - 543-PR-701 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9520 | 0 | 10610.ST.PR.TN | 179.62 | 0
C113132STPR200220 | U13 - 543-PR-901 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3628 | 13.5082 | 10610.ST.PR.TN | 68.45 | 68.4488
C113132STPR200220 | U13 - 543-PR-901 Secondary Piperack Erection (Train 2) | ST | STPR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3628 | 13.5082 | 10610.ST.PR.TN | 68.45 | 68.4488
C113132STPR300040 | U13 - 544-PR-103 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31115 | 1301.3931 | 10610.ST.PR.TN | 587.07 | 567.6945
C113132STPR300050 | U13 - 544-PR-104 Main Piperack Erection (Train 3) (544-E-106) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26186 | 1009.0032 | 10610.ST.PR.TN | 494.07 | 492.7428
C113132STPR300070 | U13 - 544-PR-106 Main Piperack Erection (Train 3) (544-E-120) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24099 | 832.5881 | 10610.ST.PR.TN | 454.7 | 442.7899
C113132STPR300080 | U13 - 544-PR-107 Main Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27608 | 1028.6239 | 10610.ST.PR.TN | 520.91 | 499.5535
C113132STPR300150 | U13 - 544-PR-201 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22320 | 313.0308 | 10610.ST.PR.TN | 421.13 | 182.7745
C113132STPR300180 | U13 - 544-PR-501 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14310 | 205.6595 | 10610.ST.PR.TN | 270.01 | 228.695
C113132STPR300190 | U13 - 544-PR-601 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6910 | 60.495 | 10610.ST.PR.TN | 130.38 | 124.8777
C113136MEAC100060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 542-E-112 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MEAC100070 | U13 - Air Coolers (Refrigerant Condenser) Erection 542-E-119 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102100 | 0 | 10610.ME.ER.TN | 1021 | 0
C113136MEAC100080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 542-E-120 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113136MEAC200050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 543-E-106 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 66 | 0
C113136MEAC200070 | U13 - Air Coolers (Refrigerant Condenser) Erection 543-E-119 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 54 | 0
C113136MEAC300020 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Pre-Assembly 544-E-112 (Train 3) | ME | MEAC1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20683 | 33.6206 | 10780.ME.ME.MH
C113136MEAC300050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 544-E-106 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6600 | 59.5245 | 10610.ME.ER.TN | 66 | 66
C113136MEAC300060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 544-E-112 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MECO100010 | U13 - Expander / compressor Erection 542-EC-101 (Train 1) | ME | MECO1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO100030 | U13 - Propane compressor Erection 542-C-102 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5080 | 30.0223 | 10610.ME.ER.TN | 127 | 127
C113136MECO100030 | U13 - Propane compressor Erection 542-C-102 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5080 | 30.0223 | 10610.ME.ER.TN | 127 | 127
C113136MECO100070 | U13 - Regeneration Gas compressor motor Erection 542-CM-103 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C113136MECO200020 | U13 - Sales Gas Compressor Erection 543-C-101 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5880 | 38.3074 | 10610.ME.ER.TN | 147 | 147
C113136MECO200030 | U13 - Propane compressor Erection 543-C-102 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5080 | 0 | 10610.ME.ER.TN | 127 | 0
C113136MECO200060 | U13 - Propane compressor motor Erection 543-CM-102 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19200 | 0 | 10610.ME.ER.TN | 480 | 0
C113136MECO300020 | U13 - Sales Gas Compressor Erection 544-C-101 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5880 | 40.2227 | 10610.ME.ER.TN | 147 | 147
C113136MECO300030 | U13 - Propane compressor Erection 544-C-102 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5080 | 30.0223 | 10610.ME.ER.TN | 127 | 127
C113136MECO300040 | U13 - Regeneration Gas compressor Erection 544-C-103 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2800 | 0.46328 | 10610.ME.ER.TN | 70 | 0
C113136MEAC300010 | U13 - Air Coolers (Regeneration Gas Cooler) Pre-Assembly 544-E-106 (Train 3) | ME | MEAC1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8144 | 97.981 | 10780.ME.ME.MH
C113136MEAC300070 | U13 - Air Coolers (Refrigerant Condenser) Erection 544-E-119 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 54 | 0
C113136MEAC300080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 544-E-120 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113136MECO100010 | U13 - Expander / compressor Erection 542-EC-101 (Train 1) | ME | MECO1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO100020 | U13 - Sales gas compressor Erection 542-C-101 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5880 | 40.2227 | 10610.ME.ER.TN | 147 | 147
C113136MECO100040 | U13 - Regeneration Gas compressor Erection 542-C-103 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.ME.ER.TN | 70 | 0
C113136MECO100060 | U13 - Propane compressor motor Erection 542-CM-102 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18000 | 376.9311 | 10610.ME.ER.TN | 450 | 450
C113136MECO200010 | U13 - Expander / compressor Erection 543-EC-101 (Train 2) | ME | MECO1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO200070 | U13 - Regeneration Gas compressor motor Erection 543-CM-103 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C113136MEFU300010 | U13 - Regeneration Gas Heater Erection 544-ME-101 (Train 3) | ME | MEFU | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15780 | 89.2424 | 10610.ME.ER.TN | 263 | 54.3489
C113136MEHE100010 | U13 - Heat Exchangers (Gas/Gas Exchanger) Erection 542-E-113 (Train 1) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE100040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 542-E-114A (Train 1) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE100100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 542-E-114B (Train 1) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE200010 | U13 - Heat Exchangers (Gas/Gas Exchanger) Erection 543-E-113 (Train 2) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE200030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 543-E-109 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE200040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 543-E-114A (Train 2) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE200060 | U13 - Heat Exchangers (Residue Gas Recycle Cooler) 543-E-126 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE200080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 543-E-129 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113133PAST200010 | U13 - Steel Structure Painting Touch Up (Train 2) | PA | PAST | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 50012 | 0 | 10780.PA.PA.MH
C113133PAST300010 | U13 - Steel Structure Painting Touch Up (Train 3) | PA | PAST | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50012 | 0 | 10780.PA.PA.MH
C113134ELCI300010 | U13 - Conduits Installation (Train 3) | EL | ELCI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18249 | 0 | 10780.EL.EL.MH
C113134ELCL100010 | U13 - Lighting Cable Laying (Train 1) | EL | ELCL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34594 | 0 | 10610.EL.LC.LM | 147634.29 | 0
C113134ELCL200010 | U13 - Lighting Cable Laying (Train 2) | EL | ELCL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37392 | 0 | 10610.EL.LC.LM | 159573.63 | 0
C113134ELCO100010 | U13 - Lighting Cable Gland & Conn./Testing (Train 1) | EL | ELCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23063 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELCO100020 | U13 - Electrical Cable Gland & Conn./Testing (Train 1) | EL | ELCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 92251 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELCO200020 | U13 - Electrical Cable Gland & Conn./Testing (Train 2) | EL | ELCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 99711 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELCP200010 | U13 - Cathodic Protection Piping (Train 2) | EL | ELCP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16619 | 0 | 10780.EL.EL.MH
C113134ELHT100010 | U13 - Electrical Heat Tracing (Train 1) | EL | ELHT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26907 | 0 | 10610.EL.ET.LM | 630 | 0
C113134ELHT300010 | U13 - Electrical Heat Tracing (Train 3) | EL | ELHT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25549 | 0 | 10610.EL.ET.LM | 680 | 0
C113134ELPL200010 | U13 - Plant Lighting - (Lighting poles and fixtures) Installation (Train 2) | EL | ELPL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54010 | 0 | 10780.EL.EL.MH
C113134ELPL300010 | U13 - Plant Lighting - (Lighting poles and fixtures) Installation (Train 3) | EL | ELPL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47448 | 0 | 10780.EL.EL.MH
C113134ELTI100010 | U13 - Lighting Cable Trays Installation (Train 1) | EL | ELTI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23063 | 0 | 10610.EL.CT.LM | 8483.03 | 0
C113134ELTI100020 | U13 - Electrical Cable Trays Installation (Train 1) | EL | ELTI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 76876 | 0 | 10610.EL.CT.LM | 15257.2 | 0
C113134ELTI300010 | U13 - Lighting Cable Trays Installation (Train 3) | EL | ELTI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21899 | 0 | 10610.EL.CT.LM | 7542.76 | 0
C113134FPEQ100011 | U13 - Equipment Fireproofing (Train 1) 542-EC-101 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100015 | U13 - Equipment Fireproofing (Train 1) 542-P-109A/B/C | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ100017 | U13 - Equipment Fireproofing (Train 1) 542-V-118 | FP | FPEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5948 | 0 | 10780.FP.FP.MH
C113134FPEQ200012 | U13 - Equipment Fireproofing (Train 2) 543-E-118 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113132STPR300200 | U13 - 544-PR-701 Secondary Piperack Erection (Train 3) | ST | STPR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9535 | 0 | 10610.ST.PR.TN | 179.9 | 0
C113132STSH100010 | U13 - 542-SH-001 Compressor Shelter Structure Erection (Train 1) for 542-C-101 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20776 | 0 | 10610.ST.ER.TN | 392.01 | 0
C113132STSH100060 | U13 - 542-SH-002 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-102 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.ST.ER.TN | 38.72 | 0
C113132STSH100090 | U13 - 542-SH-004 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-C-103 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66 | 0 | 10610.ST.ER.TN | 27.59 | 0
C113132STSH100100 | U13 - 542-SH-003 Compressor Shelter Structure Erection (Train 1) for 542-EC-101 | ST | STSH1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7179 | 0 | 10610.ST.ER.TN | 135.45 | 0
C113132STSH100110 | U13 - 542-SH-003 Compressor Shelter Roofing & Wall Erection (Train 1) for 542-EC-101 | ST | STSH2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113132STSH200010 | U13 - 543-SH-001 Compressor Shelter Structure Erection (Train 2) for 543-C-101 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20776 | 0 | 10610.ST.ER.TN | 392.01 | 0
C113132STSH200040 | U13 - 543-SH-002 Compressor Shelter Structure Erection (Train 2) for 543-C-102 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 18164 | 5.7318 | 10610.ST.ER.TN | 342.71 | 5.1036
C113132STSH200060 | U13 - 543-SH-002 Compressor Shelter Roofing & Wall Erection (Train 2) for 543-C-102 | ST | STSH2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 91 | 0 | 10610.ST.ER.TN | 38.08 | 0
C113132STSH200100 | U13 - 543-SH-003 Compressor Shelter Structure Erection (Train 2) for 543-EC-101 | ST | STSH1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7179 | 0 | 10610.ST.ER.TN | 135.45 | 0
C113132STSH300040 | U13 - 544-SH-002 Compressor Shelter Structure Erection (Train 3) for 544-C-102 | ST | STSH1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18468 | 189.1267 | 10610.ST.ER.TN | 348.46 | 132.2556
C113132STSH300060 | U13 - 544-SH-002 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-102 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.ST.ER.TN | 38.72 | 0
C113132STSH300090 | U13 - 544-SH-004 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-C-103 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65 | 0 | 10610.ST.ER.TN | 27.22 | 0
C113132STSH300110 | U13 - 544-SH-003 Compressor Shelter Roofing & Wall Erection (Train 3) for 544-EC-101 | ST | STSH2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36 | 0 | 10610.ST.ER.TN | 15.05 | 0
C113133PAEQ200010 | U13 - Equipment Painting (Train 2) | PA | PAEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6198 | 0 | 10610.PA.EQ.M2 | 2479 | 0
C113133PAFP100010 | U13 - Piping Final Coat & Touch-Up Painting (Train 1) | PA | PAFP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21154 | 0 | 10780.PA.PA.MH
C113133PAFP200010 | U13 - Piping Final Coat & Touch-Up Painting (Train 2) | PA | PAFP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21154 | 0 | 10780.PA.PA.MH
C113133PAPP200010 | U13 - Piping SandBl. & Priming (Train 2) | PA | PAPP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 176284 | 13692.6404 | 10610.PA.PP.M2 | 88142 | 30990.3403
C113136MECO300050 | U13 - Sales gas compressor motor Erection 544-CM-101 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16800 | 328.3489 | 10610.ME.ER.TN | 420 | 420
C113136MECO300050 | U13 - Sales gas compressor motor Erection 544-CM-101 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16800 | 328.3489 | 10610.ME.ER.TN | 420 | 420
C113136MECO300070 | U13 - Regeneration Gas compressor motor Erection 544-CM-103 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 3.7819 | 10610.ME.ER.TN | 200 | 0
C113136MEHE100010 | U13 - Heat Exchangers (Gas/Gas Exchanger) Erection 542-E-113 (Train 1) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE100020 | U13 - Demethanizer Reboiler Erection 542-E-118 (Train 1) (HL) (400 + 250 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE100030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 542-E-109 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE100050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 542-E-125 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE100060 | U13 - Heat Exchangers (Residue Gas Recycle Cooler) 542-E-126 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE100070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 542-E-128 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C113136MEHE100080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 542-E-129 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113136MEHE100100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 542-E-114B (Train 1) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE200020 | U13 - Demethanizer Reboiler Erection 543-E-118 (Train 2) (HL) (400 + 250 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE200050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 543-E-125 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE200060 | U13 - Heat Exchangers (Residue Gas Recycle Cooler) 543-E-126 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE200090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 543-E-141 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE300020 | U13 - Demethanizer Reboiler Erection 544-E-118 (Train 3) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE300030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 544-E-109 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE300060 | U13 - Heat Exchangers (Residue Gas Recycle Chiller) 544-E-126 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE200100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 543-E-114B (Train 2) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE300010 | U13 - Gas/Gas Exchanger Erection 544-E-113 (Train 3) (HL) (1600 + 800 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE300020 | U13 - Demethanizer Reboiler Erection 544-E-118 (Train 3) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE300030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 544-E-109 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE300070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 544-E-128 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 560 | 0.46212 | 10610.ME.ER.TN | 14 | 14
C113136MEHE300090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 544-E-141 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE300100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 544-E-114B (Train 3) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHM100010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 542-P-110B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 542-P-112 (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 542-P-501A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 542-P-501B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 543-P-110B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 543-P-112 (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 543-P-501A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109C (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113134FPEQ200013 | U13 - Equipment Fireproofing (Train 2) 543-E-119 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200016 | U13 - Equipment Fireproofing (Train 2) 543-P-112 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200017 | U13 - Equipment Fireproofing (Train 2) 543-V-118 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ300011 | U13 - Equipment Fireproofing (Train 3) 544-EC-101 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300013 | U13 - Equipment Fireproofing (Train 3) 544-E-119 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300014 | U13 - Equipment Fireproofing (Train 3) 544-E-113 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300018 | U13 - Equipment Fireproofing (Train 3) 544-V-119 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 41.4818 | 10780.FP.FP.MH
C113134FPSS100010 | U13 - Main PR Steel Structure Fireproofing (Train 1) (542-PR-101 TO 542-PR-112) | FP | FPSS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 107057 | 0 | 10780.FP.FP.MH
C113134FPSS100240 | U13 - Steel Structures Fireproofing (Train 1) (542-STR-001 TO 542-STR-011) | FP | FPSS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 107057 | 0 | 10780.FP.FP.MH
C113134FPSS200240 | U13 - Steel Structures Fireproofing (Train 2) (543-STR-001 TO 543-STR-011) | FP | FPSS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 101361 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134MEMC200020 | 543 - Miscellaneous Electrical | EL | ELEQ2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12464 | 0 | 10780.EL.EL.MH
C113136MEAC100030 | U13 - Air Coolers (Refrigerant Condenser) Pre-Assembly 542-E-119 (Train 1) | ME | MEAC1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 77604 | 929.0055 | 10780.ME.ME.MH
C113136MEAC100050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 542-E-106 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 66 | 0
C113136MEAC100060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 542-E-112 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MEAC100070 | U13 - Air Coolers (Refrigerant Condenser) Erection 542-E-119 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 102100 | 0 | 10610.ME.ER.TN | 1021 | 0
C113136MEAC100080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 542-E-120 (Train 1) | ME | MEAC2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113136MEAC200020 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Pre-Assembly 543-E-112 (Train 2) | ME | MEAC1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20683 | 0 | 10780.ME.ME.MH
C113136MEAC200030 | U13 - Air Coolers (Refrigerant Condenser) Pre-Assembly 543-E-119 (Train 2) | ME | MEAC1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 77604 | 0 | 10780.ME.ME.MH
C113136MEAC200080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 543-E-120 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113133PASP200010 | U13 - Piping Supports SandBl. & Priming (Train 2) | PA | PASP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23339 | 27.9953 | 10610.PA.SU.TN | 0 | 0
C113134ELCL100010 | U13 - Lighting Cable Laying (Train 1) | EL | ELCL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34594 | 0 | 10610.EL.LC.LM | 147634.29 | 0
C113134ELCL100020 | U13 - Electrical Cable Laying (Train 1) | EL | ELCL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 169127 | 0 | 10610.EL.PL.LM | 270058.45 | 0
C113134ELCL200020 | U13 - Electrical Cable Laying (Train 2) | EL | ELCL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 182804 | 0 | 10610.EL.PL.LM | 291897.52 | 0
C113134ELCL300010 | U13 - Lighting Cable Laying (Train 3) | EL | ELCL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32849 | 0 | 10610.EL.LC.LM | 140186.04 | 0
C113134ELCL300020 | U13 - Electrical Cable Laying (Train 3) | EL | ELCL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160595 | 10145.3878 | 10610.EL.PL.LM | 256434.64 | 71958.1243
C113134ELCO200010 | U13 - Lighting Cable Gland & Conn./Testing (Train 2) | EL | ELCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24928 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELCO200020 | U13 - Electrical Cable Gland & Conn./Testing (Train 2) | EL | ELCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 99711 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELCO300010 | U13 - Lighting Cable Gland & Conn./Testing (Train 3) | EL | ELCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21899 | 0 | 10610.EL.CO.UN | 1336 | 0
C113134ELCO300020 | U13 - Electrical Cable Gland & Conn./Testing (Train 3) | EL | ELCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 87597 | 0 | 10610.EL.CO.UN | 4156 | 0
C113134ELEL100015 | U13 - Earthing Works (Train 1) | EL | ELEL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 30750 | 128.877 | 10610.EL.ES.LM | 28109.94 | 2593.4231
C113134ELEL200015 | U13 - Earthing Works (Train 2) | EL | ELEL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 33237 | 0 | 10610.EL.ES.LM | 28109.94 | 0
C113134ELEL300015 | U13 - Earthing Works (Train 3) | EL | ELEL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29199 | 239.3079 | 10610.EL.ES.LM | 28109.94 | 5340.8886
C113134ELTI200010 | U13 - Lighting Cable Trays Installation (Train 2) | EL | ELTI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24928 | 0 | 10610.EL.CT.LM | 7640.19 | 0
C113134ELTI200020 | U13 - Electrical Cable Trays Installation (Train 2) | EL | ELTI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 83093 | 0 | 10610.EL.CT.LM | 14188.92 | 0
C113134FPEQ200011 | U13 - Equipment Fireproofing (Train 2) 543-EC-101 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200013 | U13 - Equipment Fireproofing (Train 2) 543-E-119 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200014 | U13 - Equipment Fireproofing (Train 2) 543-E-113 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200015 | U13 - Equipment Fireproofing (Train 2) 543-P-109A/B/C | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ200019 | U13 - Equipment Fireproofing (Train 2) 543-V-122 | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113136MEHE300090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 544-E-141 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE300100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 544-E-114B (Train 3) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHM100020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109C (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 542-P-110A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 542-P-112 (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109C (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 543-P-110A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM300020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM300030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109C (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM300050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 544-P-110B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHV100020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 1) 542-F-108A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV100030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 1) 542-F-110A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 2) 543-F-107A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV200040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 2) 543-F-117A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHM300040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 544-P-110A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 544-P-112 (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 544-P-501A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 544-P-501B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHV100020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 1) 542-F-108A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV100040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 1) 542-F-117A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV100100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 1) 542-F-108B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 2) 543-F-108A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 2) 543-F-110A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 2) 543-F-117A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV200050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 2) 543-F-117B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV200060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 2) 543-F-107B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV300010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 3) 544-F-107A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV300020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 3) 544-F-108A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEMC100010 | U13 - Miscellaneous Erection (Train 1) | ME | MEMC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEMC200010 | U13 - Miscellaneous Erection (Train 2) | ME | MEMC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEMC300010 | U13 - Miscellaneous Erection (Train 3) | ME | MEMC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEAC300040 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Pre-Assembly 544-E-120 (Train 3) | ME | MEAC1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4530 | 4.8559 | 10780.ME.ME.MH
C113136MEAC300050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 544-E-106 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6600 | 59.5245 | 10610.ME.ER.TN | 66 | 66
C113136MEAC300060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 544-E-112 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MECO100020 | U13 - Sales gas compressor Erection 542-C-101 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5880 | 40.2227 | 10610.ME.ER.TN | 147 | 147
C113136MECO100050 | U13 - Sales gas compressor Motor Erection 542-CM-101 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18000 | 376.9311 | 10610.ME.ER.TN | 450 | 450
C113136MECO100050 | U13 - Sales gas compressor Motor Erection 542-CM-101 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18000 | 376.9311 | 10610.ME.ER.TN | 450 | 450
C113136MECO100060 | U13 - Propane compressor motor Erection 542-CM-102 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18000 | 376.9311 | 10610.ME.ER.TN | 450 | 450
C113136MECO100070 | U13 - Regeneration Gas compressor motor Erection 542-CM-103 (Train 1) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C113136MECO200010 | U13 - Expander / compressor Erection 543-EC-101 (Train 2) | ME | MECO1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO200020 | U13 - Sales Gas Compressor Erection 543-C-101 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5880 | 38.3074 | 10610.ME.ER.TN | 147 | 147
C113136MECO200040 | U13 - Regeneration Gas compressor Erection 543-C-103 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.ME.ER.TN | 70 | 0
C113136MECO200050 | U13 - Sales gas compressor motor Erection 543-CM-101 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19200 | 408.4417 | 10610.ME.ER.TN | 480 | 480
C113136MECO300010 | U13 - Expander / compressor Erection 544-EC-101 (Train 3) | ME | MECO1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO300060 | U13 - Propane compressor motor Erection 544-CM-102 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16800 | 328.3489 | 10610.ME.ER.TN | 420 | 420
C113136MEFU100010 | U13 - Regeneration Gas Heater Erection 542-ME-101 (Train 1) | ME | MEFU | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15780 | 65.6995 | 10610.ME.ER.TN | 263 | 26.3
C113136MEFU200010 | U13 - Regeneration Gas Heater Erection 543-ME-101 (Train 2) | ME | MEFU | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15780 | 56.9003 | 10610.ME.ER.TN | 263 | 23.9698
C113136MEHE100030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 542-E-109 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE100040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 542-E-114A (Train 1) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHV200050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 2) 543-F-117B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV200100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 2) 543-F-108B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 2) 543-F-110B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV300020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 3) 544-F-108A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEHV300050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 3) 544-F-117B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0.5305 | 10610.ME.ER.TN | 15 | 15
C113136MEIN100010 | U13 - Internals Erection (Train 1) | ME | MEIN | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10441 | 0 | 10780.ME.ME.MH
C113136MEIN300010 | U13 - Internals Erection (Train 3) | ME | MEIN | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10441 | 0 | 10780.ME.ME.MH
C113136MEMC200020 | U13 - Equipment Pre-Dressing before erection (Train 2) | IS | ISEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6687 | 66.0621 | 10610.IS.EQ.M2 | 172 | 172
C113136METC100020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 542-EOT-102 (Train 1) in 542-SH-002 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC100030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 542-EOT-103 (Train 1) in 542-SH-003 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METC100040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 542-EOT-104 (Train 1) in 542-SH-004 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METC200010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 543-EOT-101 (Train 2) in 543-SH-001 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC200020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 543-EOT-102 (Train 2) in 543-SH-002 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC200040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 543-EOT-104 (Train 2) in 543-SH-004 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METC300020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 544-EOT-102 (Train 3) in 544-SH-002 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC300030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 544-EOT-103 (Train 3) in 544-SH-003 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METO300010 | U13 - Columns (Demethanizer) Erection 544-V-119 (Train 3) (HL) (1600 + 650 TON) | ME | METO1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113134FPEQ200020 | U13 - Equipment Fireproofing (Train 2) 543-F-117A/B | FP | FPEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5631 | 0 | 10610.FP.EQ.M2 | 152 | 0
C113134FPEQ300016 | U13 - Equipment Fireproofing (Train 3) 544-P-112 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPEQ300017 | U13 - Equipment Fireproofing (Train 3) 544-V-118 | FP | FPEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5299 | 0 | 10780.FP.FP.MH
C113134FPSS100140 | U13 - Secondary PR Steel Structure Fireproofing (Train 1) | FP | FPSS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 86835 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134FPSS200010 | U13 - Main PR Steel Structure Fireproofing (Train 2) (543-PR-101 TO 543-PR-112) | FP | FPSS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 101361 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134FPSS300140 | U13 - Secondary PR Steel Structure Fireproofing (Train 3) | FP | FPSS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105981 | 0 | 10610.FP.ST.M2 | 29294.66 | 0
C113134PRMR200010 | U13 - Motor Run (Train 2) | PR | PRMR | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11271 | 0 | 10780.PR.PR.MH
C113134PRMR300010 | U13 - Motor Run (Train 3) | PR | PRMR | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11031 | 0 | 10780.PR.PR.MH
C113136MEAC200040 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Pre-Assembly 543-E-120 (Train 2) | ME | MEAC1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4530 | 4.1168 | 10780.ME.ME.MH
C113136MEAC200050 | U13 - Air Coolers (Regeneration Gas Cooler) Erection 543-E-106 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 66 | 0
C113136MEAC200060 | U13 - Air Coolers (Sales Gas Compressor Aftercooler) Erection 543-E-112 (Train 2) | ME | MEAC2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27100 | 0 | 10610.ME.ER.TN | 271 | 0
C113136MEAC300030 | U13 - Air Coolers (Refrigerant Condenser) Pre-Assembly 544-E-119 (Train 3) | ME | MEAC1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 77604 | 1320.3765 | 10780.ME.ME.MH
C113136MEAC300070 | U13 - Air Coolers (Refrigerant Condenser) Erection 544-E-119 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 54 | 0
C113136MEAC300080 | U13 - Air Coolers (Regeneration Gas Compressor Discharge Cooler) Erection 544-E-120 (Train 3) | ME | MEAC2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 80 | 0
C113136MECO100040 | U13 - Regeneration Gas compressor Erection 542-C-103 (Train 1) (400 TON) | ME | MECO2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.ME.ER.TN | 70 | 0
C113136MECO200030 | U13 - Propane compressor Erection 543-C-102 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5080 | 0 | 10610.ME.ER.TN | 127 | 0
C113136MECO200040 | U13 - Regeneration Gas compressor Erection 543-C-103 (Train 2) (400 TON) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.ME.ER.TN | 70 | 0
C113136MECO200050 | U13 - Sales gas compressor motor Erection 543-CM-101 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19200 | 408.4417 | 10610.ME.ER.TN | 480 | 480
C113136MECO200060 | U13 - Propane compressor motor Erection 543-CM-102 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19200 | 0 | 10610.ME.ER.TN | 480 | 0
C113136MEHE100080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 542-E-129 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113136MEHE100090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 542-E-141 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE200020 | U13 - Demethanizer Reboiler Erection 543-E-118 (Train 2) (HL) (400 + 250 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE200030 | U13 - Heat Exchangers (Demethanizer Trim Reboiler) 543-E-109 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHE200050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 543-E-125 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE200070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 543-E-128 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C113136MEHE200100 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 543-E-114B (Train 2) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE300010 | U13 - Gas/Gas Exchanger Erection 544-E-113 (Train 3) (HL) (1600 + 800 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE300040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 544-E-114A (Train 3) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE300050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 544-E-125 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE300070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 544-E-128 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 560 | 0.46212 | 10610.ME.ER.TN | 14 | 14
C113136MEHE300080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 544-E-129 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113136MEHM100050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 542-P-110B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 542-P-501B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 543-P-110A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 543-P-110B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEVV100020 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110B (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100040 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110D (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100070 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116B (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100080 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116C (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100090 | U13 - Vertical (Sales Gas Compressor Suction Scrubber) Vessels Erection 542-V-117 (Train 1) (HL) (400 + 250) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEVV100110 | U13 - Vertical (Cold Separator) Vessels Erection 542-V-118 (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15840 | 0 | 10610.ME.ER.TN | 396 | 0
C113136MEVV100115 | U13 - Vertical (Reflux Separator) Vessels Erection 542-V-120 (Train 1) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4360 | 28.0827 | 10610.ME.ER.TN | 109 | 109
C113136MEVV100120 | U13 - Vertical (Refrigerant Surge Drum) Vessels Erection 542-V-122 (Train 1) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV100150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 542-V-125 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1600 | 3.7819 | 10610.ME.ER.TN | 40 | 40
C113136MEVV100160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 542-V-127 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1760 | 4.5761 | 10610.ME.ER.TN | 44 | 44
C113136MEVV100190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 542-V-132 (Train 1) | ME | MEHV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113136MEVV100210 | U13 - Vertical (Warm Feed Gas Separator) Vessels Erection 542-V-134 (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6800 | 0 | 10610.ME.ER.TN | 170 | 0
C113136MEVV200020 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110B (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200030 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110C (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200060 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116A (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV200090 | U13 - Vertical Vessels (Sales Gas Compressor Suction Scrubber) Erection 543-V-117 (Train 2) (HL) (400 + 250) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3240 | 0 | 10610.ME.ER.TN | 81 | 0
C113136MEMC300020 | U13 - Equipment Pre-Dressing before erection (Train 3) | IS | ISEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6104 | 55.0421 | 10610.IS.EQ.M2 | 171 | 171
C113136MEPA200020 | U13 - Methanol Injection Package Installation 543-ME-104 (Train 2) | ME | MEPA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136METC100040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 542-EOT-104 (Train 1) in 542-SH-004 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METC200030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 543-EOT-103 (Train 2) in 543-SH-003 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METC200040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 543-EOT-104 (Train 2) in 543-SH-004 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METC300030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 544-EOT-103 (Train 3) in 544-SH-003 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METO200010 | U13 - Columns (Demethanizer) Erection 543-V-119 (Train 2) (HL) (1600 + 800 TON) | ME | METO1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113136METO300010 | U13 - Columns (Demethanizer) Erection 544-V-119 (Train 3) (HL) (1600 + 650 TON) | ME | METO1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113136MEVV100010 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110A (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100060 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116A (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100070 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116B (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100115 | U13 - Vertical (Reflux Separator) Vessels Erection 542-V-120 (Train 1) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4360 | 28.0827 | 10610.ME.ER.TN | 109 | 109
C113136MEVV100130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 542-V-123 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2200 | 7.1501 | 10610.ME.ER.TN | 55 | 55
C113136MEVV100140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 542-V-124 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2240 | 7.4125 | 10610.ME.ER.TN | 56 | 56
C113136MEVV100200 | U13 - Vertical (Refrigerant Head Drum) Vessels Erection 542-V-141 (Train 1) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV100210 | U13 - Vertical (Warm Feed Gas Separator) Vessels Erection 542-V-134 (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6800 | 0 | 10610.ME.ER.TN | 170 | 0
C113136MEVV100220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 542-V-133 (Train 1) | ME | MEHV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MECO200070 | U13 - Regeneration Gas compressor motor Erection 543-CM-103 (Train 2) | ME | MECO2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C113136MECO300010 | U13 - Expander / compressor Erection 544-EC-101 (Train 3) | ME | MECO1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C113136MECO300020 | U13 - Sales Gas Compressor Erection 544-C-101 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5880 | 40.2227 | 10610.ME.ER.TN | 147 | 147
C113136MECO300030 | U13 - Propane compressor Erection 544-C-102 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5080 | 30.0223 | 10610.ME.ER.TN | 127 | 127
C113136MECO300040 | U13 - Regeneration Gas compressor Erection 544-C-103 (Train 3) (400 TON) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2800 | 0.46328 | 10610.ME.ER.TN | 70 | 0
C113136MECO300060 | U13 - Propane compressor motor Erection 544-CM-102 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16800 | 328.3489 | 10610.ME.ER.TN | 420 | 420
C113136MECO300070 | U13 - Regeneration Gas compressor motor Erection 544-CM-103 (Train 3) | ME | MECO2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 3.7819 | 10610.ME.ER.TN | 200 | 0
C113136MEFU100010 | U13 - Regeneration Gas Heater Erection 542-ME-101 (Train 1) | ME | MEFU | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15780 | 65.6995 | 10610.ME.ER.TN | 263 | 26.3
C113136MEFU200010 | U13 - Regeneration Gas Heater Erection 543-ME-101 (Train 2) | ME | MEFU | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15780 | 56.9003 | 10610.ME.ER.TN | 263 | 23.9698
C113136MEFU300010 | U13 - Regeneration Gas Heater Erection 544-ME-101 (Train 3) | ME | MEFU | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15780 | 89.2424 | 10610.ME.ER.TN | 263 | 54.3489
C113136MEHE100020 | U13 - Demethanizer Reboiler Erection 542-E-118 (Train 1) (HL) (400 + 250 TON) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEHE100050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 542-E-125 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE100060 | U13 - Heat Exchangers (Residue Gas Recycle Cooler) 542-E-126 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE100070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 542-E-128 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C113136MEHE100090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 542-E-141 (Train 1) | ME | MEHE1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE200010 | U13 - Heat Exchangers (Gas/Gas Exchanger) Erection 543-E-113 (Train 2) (HL) (800 + 400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13400 | 0 | 10610.ME.ER.TN | 335 | 0
C113136MEHE200040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 543-E-114A (Train 2) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE200070 | U13 - Heat Exchangers (Regeneration Gas Superheater) 543-E-128 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C113136MEHM200080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 543-P-501B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM300050 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 544-P-110B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 544-P-501B (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHV100010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 1) 542-F-107A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV100050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 1) 542-F-117B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV100060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 1) 542-F-107B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV100230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 1) 542-F-110B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200020 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 2) 543-F-108A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 2) 543-F-110A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV300010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 3) 544-F-107A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV300030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 3) 544-F-110A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEHV300040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 3) 544-F-117A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0.5305 | 10610.ME.ER.TN | 15 | 15
C113136MEHV300040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 3) 544-F-117A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0.5305 | 10610.ME.ER.TN | 15 | 15
C113136MEHV300060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 3) 544-F-107B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEIN200010 | U13 - Internals Erection (Train 2) | ME | MEIN | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10441 | 0 | 10780.ME.ME.MH
C113136MEMC100010 | U13 - Miscellaneous Erection (Train 1) | ME | MEMC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEVV200010 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110A (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200040 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110D (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 543-V-115 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1280 | 0 | 10610.ME.ER.TN | 32 | 0
C113136MEVV200070 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116B (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV200115 | U13 - Vertical Vessels (Reflux Separator) Erection 543-V-120 (Train 2) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4360 | 0 | 10610.ME.ER.TN | 109 | 0
C113136MEVV200120 | U13 - Vertical Vessels (Refrigerant Surge Drum) Erection 543-V-122 (Train 2) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV200140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 543-V-124 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2240 | 0 | 10610.ME.ER.TN | 56 | 0
C113136MEVV200180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 543-V-129 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10610.ME.ER.TN | 26 | 0
C113136MEVV200190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 543-V-132 (Train 2) | ME | MEHV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113136MEVV200200 | U13 - Vertical Vessels (Refrigerant Head Drum) Erection 543-V-141 (Train 2) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV300070 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116B (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 3) 544-F-108B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEVV300110 | U13 - Vertical Vessels (Cold Separator) Erection 544-V-118 (Train 3) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15840 | 370.6609 | 10610.ME.ER.TN | 396 | 396
C113136MEVV300115 | U13 - Vertical Vessels (Reflux Separator) Erection 544-V-120 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4360 | 28.0827 | 10610.ME.ER.TN | 109 | 109
C113136MEVV300130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 544-V-123 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2200 | 7.1501 | 10610.ME.ER.TN | 55 | 55
C113136MEVV300180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 544-V-129 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 1.5978 | 10610.ME.ER.TN | 26 | 26
C113136MEVV200110 | U13 - Vertical Vessels (Cold Separator) Erection 543-V-118 (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15840 | 0 | 10610.ME.ER.TN | 396 | 0
C113136MEVV200115 | U13 - Vertical Vessels (Reflux Separator) Erection 543-V-120 (Train 2) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4360 | 0 | 10610.ME.ER.TN | 109 | 0
C113136MEVV200130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 543-V-123 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2200 | 0 | 10610.ME.ER.TN | 55 | 0
C113136MEVV200160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 543-V-127 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1760 | 0 | 10610.ME.ER.TN | 44 | 0
C113136MEVV200190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 543-V-132 (Train 2) | ME | MEHV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113136MEVV200210 | U13 - Vertical Vessels (Warm Feed Gas Separator) Erection 543-V-134 (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6800 | 0 | 10610.ME.ER.TN | 170 | 0
C113136MEVV200220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 543-V-133 (Train 2) | ME | MEHV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C113136MEVV300010 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110A (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300030 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110C (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300040 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110D (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300060 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116A (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300080 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116C (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 3) 544-F-108B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEVV300115 | U13 - Vertical Vessels (Reflux Separator) Erection 544-V-120 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4360 | 28.0827 | 10610.ME.ER.TN | 109 | 109
C113136MEVV300120 | U13 - Vertical Vessels (Refrigerant Surge Drum) Erection 544-V-122 (Train 3) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV300130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 544-V-123 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2200 | 7.1501 | 10610.ME.ER.TN | 55 | 55
C113136MEVV300230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 3) 544-F-110B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113137INCO100020 | U13 - Communication System Installation (Comp. Shelter 542-SH-001) (Train 1) | IN | INCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4030 | 0 | 10780.IN.IN.MH
C113137INCO200020 | U13 - Communication System Installation (Comp. Shelter 543-SH-001) (Train 2) | IN | INCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3259 | 0 | 10780.IN.IN.MH
C113137INCO200040 | U13 - Communication System Installation (Comp. Shelter 543-SH-003) (Train 2) | IN | INCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3259 | 0 | 10780.IN.IN.MH
C113137INCO200050 | U13 - Communication System Installation (Comp. Shelter 543-SH-004) (Train 2) | IN | INCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3259 | 0 | 10780.IN.IN.MH
C113137INCO300010 | U13 - Communication System Installation (Train 3) | IN | INCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3421 | 0 | 10780.IN.IN.MH
C113137INFC100010 | U13 - Fiber Optic Gland & Conn./Testing (Train 1) | IN | INFC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10990 | 0 | 10610.IN.CO.UN | 510 | 0
C113137INFG100040 | U13 - Fire & Gas System Installation (Comp. Shelter 542-SH-003) (Train 1) | IN | INFG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2381 | 0 | 10780.IN.IN.MH
C113137INFG200030 | U13 - Fire & Gas System Installation (Comp. Shelter 543-SH-002) (Train 2) | IN | INFG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1926 | 0 | 10780.IN.IN.MH
C113137INFG300040 | U13 - Fire & Gas System Installation (Comp. Shelter 544-SH-003) (Train 3) | IN | INFG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2022 | 0 | 10780.IN.IN.MH
C113137INGC200010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 2) | IN | INGC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 57770 | 0 | 10610.IN.CO.UN | 890 | 0
C113137INHU100020 | U13 - Process Hook Up´s Erection (Train 1) | IN | INHU1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 50372 | 0 | 10780.IN.IN.MH
C113137INHU200020 | U13 - Process Hook Up´s Erection (Train 2) | IN | INHU1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40735 | 0 | 10780.IN.IN.MH
C113137ININ100010 | U13 - Instruments Installation (Train 1) | IN | ININ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36634 | 0 | 10610.IN.IN.UN | 1160 | 0
C113137ININ300010 | U13 - Instruments Installation (Train 3) | IN | ININ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31103 | 0 | 10610.IN.IN.UN | 690 | 0
C113137ININ300012 | U13 - Valve Installation (Train 2) | IN | ININ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29626 | 0 | 10610.IN.IN.UN | 740 | 0
C113137INIP100010 | U13 - Instruments Calibration (Train 1) | IN | INIP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11906 | 0 | 10780.IN.IN.MH
C113137INIP300013 | U13 - Valve Calibration (Train 3) | IN | INIP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10109 | 0 | 10780.IN.IN.MH
C113137INJB300010 | U13 - Junction Boxes & Local Panels Install. (Train 3) | IN | INJB | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40434 | 0 | 10780.IN.IN.MH
C113137INML200010 | U13- Multi Pair Cable Pulling (Train 2) | IN | INML | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 115540 | 0 | 10610.IN.MC.LM | 393921.03 | 0
C113137INML300010 | U13- Multi Pair Cable Pulling (Train 3) | IN | INML | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 121302 | 0 | 10610.IN.MC.LM | 413566.93 | 0
C115131PIRA000020 | U15 - Piping Erection on Rack (577-PR-112 / 577-PR-113 ) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 549.0704 | 10610.PI.PR.DI | 7417.92 | 486.0963
C115131PISU000030 | U15 - Piping Supports Prefabrication | PI | PISU1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156138 | 11994.4574 | 10610.PI.PU.TN | 600.53 | 63.0985
C115131PRHT000020 | U15 - Piping Hydrotesting | PR | PRHT | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 246523 | 0 | 10610.PR.HT.DI | 339273 | 0
C115131PRRE000000 | U15 - Piping Reinstatement | PR | PRRE | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 197218 | 0 | 10610.PR.RE.DI | 339273 | 0
C115132CIGT000030 | U15 - Steel Structure Grouting Execution | CI | CIGT | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4260 | 3.2707 | 10780.CI.CI.MH
C115132CIPR000130 | U15 - Main Piperack Foundations Execution/Modification 577 | CI | CIPR2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2971 | 13.0381 | 10610.CI.CO.M3 | 49.51 | 49.51
C115132STPL000040 | U15 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67415 | 0 | 10610.ST.PL.TN | 842.68 | 0
C115132STPR30 | U15 - Main Piperack Erection (577-PR-121) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22228 | 206.2004 | 10610.ST.PR.TN | 419.4 | 137.3919
C115132STSP000080 | U15 - Miscellaneous Platforms and Crossover | ST | STMS | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.ST.ST.MH
C115133PAFP000020 | U15 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13385 | 0 | 10780.PA.PA.MH
C115133PAST000020 | U15 - Steel Structure Painting Touch Up | PA | PAST | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9630 | 0 | 10780.PA.PA.MH
C115134ELCO000020 | U15 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2587 | 0 | 10610.EL.CO.UN | 985 | 0
C115134ELEL000025 | U15 - Earthing Works | EL | ELEL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2299 | 0 | 10610.EL.ES.LM | 7726.12 | 0
C115134ELPL000020 | U15 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5605 | 0 | 10780.EL.EL.MH
C115134ELTI000020 | U15 - Lighting Cable Trays Installation | EL | ELTI | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2587 | 0 | 10780.EL.EL.MH
C116131ISEQ000020 | U16 - Equipment Insulation | IS | ISEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4150 | 0 | 10610.IS.EQ.M2 | 14070 | 0
C116131ISPI000030 | U16 - Piping Insulation | IS | ISPI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32082 | 0 | 10610.IS.PI.M2 | 70350 | 0
C116131PIBB000040 | U16 - Big Bore Piping A/Equip. Erection - North of racks area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIBB000050 | U16 - Big Bore Piping A/Equip. Erection - Scraper launcher area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIPR000030 | U16 - Piping Prefabrication | PI | PIPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179568 | 36850.2045 | 10610.PI.FB.DI | 44891.91 | 29764.9561
C113136MEHE200080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 543-E-129 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113136MEHE200090 | U13 - Heat Exchangers (Habshan 1 Train 3 Feed Gas Chiller) 543-E-141 (Train 2) | ME | MEHE1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10610.ME.ER.TN | 34 | 0
C113136MEHE300040 | U13 - Heat Exchangers (Dehydration Feed Gas Chiller) 544-E-114A (Train 3) (HL) (400 TON) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3280 | 0 | 10610.ME.ER.TN | 82 | 0
C113136MEHE300050 | U13 - Heat Exchangers (Regeneration Gas Chiller) 544-E-125 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10610.ME.ER.TN | 19 | 0
C113136MEHE300060 | U13 - Heat Exchangers (Residue Gas Recycle Chiller) 544-E-126 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.ME.ER.TN | 20 | 0
C113136MEHE300080 | U13 - Heat Exchangers (Regeneration Gas Pipeline Chiller) 544-E-129 (Train 3) | ME | MEHE1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.ME.ER.TN | 10 | 0
C113136MEHM100010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109B (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 542-P-109C (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM100040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 542-P-110A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM100070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 542-P-501A (Train 1) | ME | MEHM1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200020 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200030 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 543-P-109C (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM200060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 543-P-112 (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM200070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 543-P-501A (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEMC100020 | U13 - Equipment Pre-Dressing before erection (Train 1) | IS | ISEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7185 | 76.2679 | 10610.IS.EQ.M2 | 172 | 172
C113136MEMC100020 | U13 - Equipment Pre-Dressing before erection (Train 1) | IS | ISEQ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7185 | 76.2679 | 10610.IS.EQ.M2 | 172 | 172
C113136MEMC200020 | U13 - Equipment Pre-Dressing before erection (Train 2) | IS | ISEQ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6687 | 66.0621 | 10610.IS.EQ.M2 | 172 | 172
C113136MEMC300020 | U13 - Equipment Pre-Dressing before erection (Train 3) | IS | ISEQ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6104 | 55.0421 | 10610.IS.EQ.M2 | 171 | 171
C113136MEPA100020 | U13 - Package (Methanol Injection Package) Installation 542-ME-104 (Train 1) | ME | MEPA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEPA200020 | U13 - Methanol Injection Package Installation 543-ME-104 (Train 2) | ME | MEPA | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEPA300020 | U13 - Methanol Injection Package Installation 544-ME-104 (Train 3) | ME | MEPA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136METC100010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 542-EOT-101 (Train 1) in 542-SH-001 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC200010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 543-EOT-101 (Train 2) in 543-SH-001 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC300010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 544-EOT-101 (Train 3) in 544-SH-001 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC300020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 544-EOT-102 (Train 3) in 544-SH-002 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC300040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 544-EOT-104 (Train 3) in 544-SH-004 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METO100010 | U13 - Columns (Demethanizer) Erection 542-V-119 (Train 1) (HL) (1600 + 800 TON) | ME | METO1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113136METO200010 | U13 - Columns (Demethanizer) Erection 543-V-119 (Train 2) (HL) (1600 + 800 TON) | ME | METO1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113136MEVV100010 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110A (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100030 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110C (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100040 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110D (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEHM200080 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 543-P-501B (Train 2) | ME | MEHM1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300010 | U13 - Horizontal Pump (Demethanizer Bottoms Pump) with Electrical Motor Erection 544-P-109A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136MEHM300040 | U13 - Horizontal Pump (Warm Closed Drain Drum Pump) with Electrical Motor Erection 544-P-110A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300060 | U13 - Horizontal Pump (Propane Return Pump) with Electrical Motor Erection 544-P-112 (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHM300070 | U13 - Horizontal Pump (Oily Water Sump Pump) with Electrical Motor Erection 544-P-501A (Train 3) | ME | MEHM1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C113136MEHV100010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 1) 542-F-107A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV100030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 1) 542-F-110A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV100040 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 1) 542-F-117A | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV100050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 1) 542-F-117B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEHV100060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 1) 542-F-107B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV100100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 1) 542-F-108B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV100230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 1) 542-F-110B | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200010 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 2) 543-F-107A | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV200060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 2) 543-F-107B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEHV200100 | U13 - Vertical Vessels (Dehydration Outlet Gas Filter) Erection (Train 2) 543-F-108B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV200230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 2) 543-F-110B | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEHV300030 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 3) 544-F-110A | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113136MEVV300140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 544-V-124 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2240 | 7.4125 | 10610.ME.ER.TN | 56 | 56
C113136MEVV300150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 544-V-125 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1600 | 3.7819 | 10610.ME.ER.TN | 40 | 40
C113136MEVV300170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 544-V-128 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C113136MEVV300200 | U13 - Vertical Vessels (Refrigerant Head Drum) Erection 544-V-141 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV300210 | U13 - Vertical Vessels (Warm Feed Gas Separator) Erection 544-V-134 (Train 3) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6800 | 68.1392 | 10610.ME.ER.TN | 170 | 170
C113136MEVV300220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 544-V-133 (Train 3) | ME | MEHV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C113137INAI100010 | U13 - Analyzers Equipment Installation (Train 1) | IN | INAI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24728 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INAI200010 | U13 - Analyzers Equipment Installation (Train 2) | IN | INAI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19997 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INAI300010 | U13 - Analyzers Equipment Installation (Train 3) | IN | INAI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20995 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INCI100010 | U13 - Conduits Installation (Train 1) | IN | INCT3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11870 | 0 | 10780.IN.IN.MH
C113137INCT300010 | U13 - Primary Cable Trays Installation (Train 3) | IN | INCT1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 97197 | 0 | 10610.IN.CT.LM | 860 | 0
C113137INCT300020 | U13 - Secondary Cable Trays Installation (Train 3) | IN | INCT2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54430 | 0 | 10610.IN.CT.LM | 960 | 0
C113137INFC300010 | U13 - Fiber Optic Gland & Conn./Testing (Train 3) | IN | INFC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9331 | 0 | 10610.IN.CO.UN | 590 | 0
C113137INFG100010 | U13 - Fire & Gas System Installation (Train 1) | IN | INFG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2381 | 0 | 10780.IN.IN.MH
C113137INFG200040 | U13 - Fire & Gas System Installation (Comp. Shelter 543-SH-003) (Train 2) | IN | INFG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1926 | 0 | 10780.IN.IN.MH
C113137INFG300030 | U13 - Fire & Gas System Installation (Comp. Shelter 544-SH-002) (Train 3) | IN | INFG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2022 | 0 | 10780.IN.IN.MH
C113137INFG300050 | U13 - Fire & Gas System Installation (Comp. Shelter 544-SH-004) (Train 3) | IN | INFG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2022 | 0 | 10780.IN.IN.MH
C113137INFO100010 | U13 - Fiber Optic Cable Pulling (Train 1) | IN | INFO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15570 | 0 | 10610.IN.FO.LM | 56818 | 0
C116131PIRA000040 | U16 - Piping Erection on Rack 545-PR-103 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000050 | U16 - Piping Erection on Rack 545-PR-102 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000080 | U16 - Piping Erection on Rack 545-PR-105/106/107/108 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PISB000030 | U16 - Small Bore Piping A/Equip. Erection - South of racks area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PISB000040 | U16 - Small Bore Piping A/Equip. Erection - North of racks area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PISB000050 | U16 - Small Bore Piping A/Equip. Erection - Scraper launcher area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PISU000050 | U16 - Piping Supports Prefabrication | PI | PISU1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15108 | 205.1352 | 10610.PI.PU.TN | 58.11 | 31.6534
C116131PISU000050 | U16 - Piping Supports Prefabrication | PI | PISU1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15108 | 205.1352 | 10610.PI.PU.TN | 58.11 | 31.6534
C116131PRFL000030 | U16 - Piping Flushing/Blowing | PR | PRFL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5927 | 0 | 10610.PR.FL.DI | 72907 | 0
C116132CICT000020 | U16 - Instrument earth Trenches Execution | CI | CICT3 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37730 | 21.03 | 10780.CI.CI.MH
C116132CIHE000120 | U16 - Foundation execution 30" PL-952 Scrapper Launcher 545-V-503 | CI | CIHE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12047 | 214.3908 | 10610.CI.CO.M3 | 240.93 | 240.93
C116132CIHE000130 | U16 - Foundation execution NGL Surge Sphere 545-V-201A | CI | CIHE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14538 | 312.23 | 10610.CI.CO.M3 | 290.76 | 290.76
C116132CIPE000020 | U16 - Packaged Equipment (NGL Shipping Meter) Foundation Execution - Metering Skid (545-ME-201) | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6410 | 60.6972 | 10610.CI.CO.M3 | 106.83 | 106.8297
C116132CIPE000030 | U16 - Packaged Equipment Foundation Execution 545-ME-301 | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2171 | 0.22629 | 10780.CI.CI.MH
C116132CIPE000090 | U16 - Packaged Equipment Foundation Execution Pig Trolley Foundation | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1006 | 1.4949 | 10610.CI.CO.M3 | 14.37 | 14.37
C116132CIPR000150 | U16 - Trestle Support Foundations Execution | CI | CIPR2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5877 | 51.0218 | 10610.CI.CO.M3 | 97.95 | 97.95
C116132CIPR000150 | U16 - Trestle Support Foundations Execution | CI | CIPR2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5877 | 51.0218 | 10610.CI.CO.M3 | 97.95 | 97.95
C116132CIPR000190 | U16 - 545-PR-103 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12317 | 224.1087 | 10610.CI.CO.M3 | 246.33 | 246.33
C116132CIPR000200 | U16 - 545-PR-105 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25382 | 951.7207 | 10610.CI.CO.M3 | 507.63 | 507.63
C113136MEVV100050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 542-V-115 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1280 | 2.4143 | 10610.ME.ER.TN | 32 | 32
C113136MEVV100120 | U13 - Vertical (Refrigerant Surge Drum) Vessels Erection 542-V-122 (Train 1) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV100140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 542-V-124 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2240 | 7.4125 | 10610.ME.ER.TN | 56 | 56
C113136MEVV100170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 542-V-128 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 3.0557 | 10610.ME.ER.TN | 36 | 36
C113136MEVV100180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 542-V-129 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10610.ME.ER.TN | 26 | 0
C113136MEVV100200 | U13 - Vertical (Refrigerant Head Drum) Vessels Erection 542-V-141 (Train 1) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV100220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 542-V-133 (Train 1) | ME | MEHV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C113136MEVV200020 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110B (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200040 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110D (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200060 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116A (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV200070 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116B (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV200080 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116C (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV200110 | U13 - Vertical Vessels (Cold Separator) Erection 543-V-118 (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15840 | 0 | 10610.ME.ER.TN | 396 | 0
C113136MEVV200120 | U13 - Vertical Vessels (Refrigerant Surge Drum) Erection 543-V-122 (Train 2) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV200130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 543-V-123 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2200 | 0 | 10610.ME.ER.TN | 55 | 0
C113136MEVV200140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 543-V-124 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2240 | 0 | 10610.ME.ER.TN | 56 | 0
C113137INGC100010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 1) | IN | INGC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 71437 | 0 | 10610.IN.CO.UN | 830 | 0
C113137INGC100020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 1) | IN | INGC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47625 | 0 | 10610.IN.CO.UN | 640 | 0
C113137INGC200010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 2) | IN | INGC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 57770 | 0 | 10610.IN.CO.UN | 890 | 0
C113137INGC200020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 2) | IN | INGC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 38513 | 0 | 10610.IN.CO.UN | 720 | 0
C113137INGC300010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 3) | IN | INGC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60651 | 0 | 10610.IN.CO.UN | 1000 | 0
C113137INGC300020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 3) | IN | INGC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40434 | 0 | 10610.IN.CO.UN | 1000 | 0
C113137INHU300010 | U13 - Pneumatic Hook Up´s Erection (Train 3) | IN | INHU3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9812 | 0 | 10780.IN.IN.MH
C113137INHU300020 | U13 - Process Hook Up´s Erection (Train 3) | IN | INHU1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 42767 | 0 | 10780.IN.IN.MH
C113137ININ300011 | U13 - Valve Installation (Train 1) | IN | ININ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36634 | 0 | 10610.IN.IN.UN | 580 | 0
C113137ININ300013 | U13 -Valve Installation (Train 3) | IN | ININ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31103 | 0 | 10610.IN.IN.UN | 600 | 0
C113137INIP200010 | U13 - Instruments Calibration (Train 2) | IN | INIP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9628 | 0 | 10780.IN.IN.MH
C113137INJB200010 | U13 - Junction Boxes & Local Panels Install. (Train 2) | IN | INJB | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 38513 | 0 | 10780.IN.IN.MH
C113137INML100010 | U13- Multi Pair Cable Pulling (Train 1) | IN | INML | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 142874 | 0 | 10610.IN.MC.LM | 487114.08 | 0
C113137INML300010 | U13- Multi Pair Cable Pulling (Train 3) | IN | INML | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 121302 | 0 | 10610.IN.MC.LM | 413566.93 | 0
C113137INSL100010 | U13 - Single Pair Cable Pulling (Train 1) | IN | INSL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 114482 | 0 | 10610.IN.SC.LM | 257754.59 | 0
C113137INSL300010 | U13 - Single Pair Cable Pulling (Train 3) | IN | INSL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 97197 | 0 | 10610.IN.SC.LM | 218836.86 | 0
C113137PRLT100010 | U13 - Loops Testing (Train 1) | PR | PRLT | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 135548 | 0 | 10780.PR.PR.MH
C113137PRLT300010 | U13 - Loops Testing (Train 3) | PR | PRLT | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 115304 | 0 | 10780.PR.PR.MH
C115131PIST000040 | U15 - Manifolds Installation | PI | PIST1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5590 | 0 | 10780.PI.PI.MH
C115131PISU000040 | U15 - Piping Supports Erection | PI | PISU2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 270239 | 0 | 10610.PI.SU.TN | 600.53 | 0
C115131PRHT000020 | U15 - Piping Hydrotesting | PR | PRHT | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 246523 | 0 | 10610.PR.HT.DI | 339273 | 0
C113136MEHV300050 | U13 - Vertical Vessels (Regeneration Gas Inlet Filter) Erection (Train 3) 544-F-117B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0.5305 | 10610.ME.ER.TN | 15 | 15
C113136MEHV300060 | U13 - Vertical Vessels (Dehydration Inlet Gas Filter) Erection (Train 3) 544-F-107B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1240 | 0 | 10610.ME.ER.TN | 31 | 0
C113136MEMC200010 | U13 - Miscellaneous Erection (Train 2) | ME | MEMC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEMC300010 | U13 - Miscellaneous Erection (Train 3) | ME | MEMC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14760 | 0 | 10610.ME.ER.TN | 246 | 0
C113136MEPA100010 | U11 - Sales Gas Custody Meter Package Installation 542-ME-001 (Loop 3 - Unit 518) | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21600 | 20.6774 | 10610.ME.ER.TN | 360 | 0
C113136MEPA100010 | U11 - Sales Gas Custody Meter Package Installation 542-ME-001 (Loop 3 - Unit 518) | ME | MEPA | 11 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21600 | 20.6774 | 10610.ME.ER.TN | 360 | 0
C113136MEPA100020 | U13 - Package (Methanol Injection Package) Installation 542-ME-104 (Train 1) | ME | MEPA | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136MEPA300020 | U13 - Methanol Injection Package Installation 544-ME-104 (Train 3) | ME | MEPA | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C113136METC100010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 542-EOT-101 (Train 1) in 542-SH-001 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC100020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 542-EOT-102 (Train 1) in 542-SH-002 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC100030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 542-EOT-103 (Train 1) in 542-SH-003 | ME | METC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METC200020 | U13 - Cranes (EOT Crane For Sales Gas Compressor) Erection 543-EOT-102 (Train 2) in 543-SH-002 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1800 | 0 | 10610.ME.ER.TN | 30 | 0
C113136METC200030 | U13 - Cranes (EOT Crane For Regeneration Gas Compressor) Erection 543-EOT-103 (Train 2) in 543-SH-003 | ME | METC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C113136METC300010 | U13 - Cranes (EOT Crane For Expander / Compressor) Erection 544-EOT-101 (Train 3) in 544-SH-001 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C113136METC300040 | U13 - Cranes (EOT Crane For Propane Compressor) Erection 544-EOT-104 (Train 3) in 544-SH-004 | ME | METC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 25 | 0
C113136METO100010 | U13 - Columns (Demethanizer) Erection 542-V-119 (Train 1) (HL) (1600 + 800 TON) | ME | METO1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34860 | 1795.2344 | 10610.ME.ER.TN | 581 | 581
C113136MEVV100020 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110B (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 543-V-125 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1600 | 0 | 10610.ME.ER.TN | 40 | 0
C113136MEVV200170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 543-V-128 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C113136MEVV200180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 543-V-129 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10610.ME.ER.TN | 26 | 0
C113136MEVV200200 | U13 - Vertical Vessels (Refrigerant Head Drum) Erection 543-V-141 (Train 2) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV200210 | U13 - Vertical Vessels (Warm Feed Gas Separator) Erection 543-V-134 (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6800 | 0 | 10610.ME.ER.TN | 170 | 0
C113136MEVV300020 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110B (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 544-V-115 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1280 | 0 | 10610.ME.ER.TN | 32 | 0
C113136MEVV300080 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116C (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300090 | U13 - Vertical Vessels (Sales Gas Compressor Suction Scrubber) Erection 544-V-117 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEVV300160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 544-V-127 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1760 | 4.5761 | 10610.ME.ER.TN | 44 | 44
C113136MEVV300190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 544-V-132 (Train 3) | ME | MEHV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113136MEVV300200 | U13 - Vertical Vessels (Refrigerant Head Drum) Erection 544-V-141 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3400 | 0 | 10610.ME.ER.TN | 85 | 0
C113136MEVV300210 | U13 - Vertical Vessels (Warm Feed Gas Separator) Erection 544-V-134 (Train 3) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6800 | 68.1392 | 10610.ME.ER.TN | 170 | 170
C113136MEVV300220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 544-V-133 (Train 3) | ME | MEHV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C113136MEVV300230 | U13 - Vertical Vessels (Feed Gas Dust Filter) Erection (Train 3) 544-F-110B | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0.76391 | 10610.ME.ER.TN | 18 | 18
C113137INAI100010 | U13 - Analyzers Equipment Installation (Train 1) | IN | INAI | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24728 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INCI300010 | U13 - Conduits Installation (Train 3) | IN | INCT3 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10077 | 0 | 10780.IN.IN.MH
C113136MEVV100030 | U13 - Vertical (Molecular Sieve Adsorber) Vessels Erection 542-V-110C (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV100050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 542-V-115 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1280 | 2.4143 | 10610.ME.ER.TN | 32 | 32
C113136MEVV100060 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116A (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100080 | U13 - Vertical (Mercury Adsorber) Vessels Erection 542-V-116C (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113136MEVV100090 | U13 - Vertical (Sales Gas Compressor Suction Scrubber) Vessels Erection 542-V-117 (Train 1) (HL) (400 + 250) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEVV100110 | U13 - Vertical (Cold Separator) Vessels Erection 542-V-118 (Train 1) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15840 | 0 | 10610.ME.ER.TN | 396 | 0
C113136MEVV100130 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 542-V-123 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2200 | 7.1501 | 10610.ME.ER.TN | 55 | 55
C113136MEVV100150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 542-V-125 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1600 | 3.7819 | 10610.ME.ER.TN | 40 | 40
C113136MEVV100160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 542-V-127 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1760 | 4.5761 | 10610.ME.ER.TN | 44 | 44
C113136MEVV100170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 542-V-128 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1440 | 3.0557 | 10610.ME.ER.TN | 36 | 36
C113136MEVV100180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 542-V-129 (Train 1) | ME | MEVV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10610.ME.ER.TN | 26 | 0
C113136MEVV100190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 542-V-132 (Train 1) | ME | MEHV | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113136MEVV200010 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110A (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200030 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 543-V-110C (Train 2) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17000 | 0 | 10610.ME.ER.TN | 425 | 0
C113136MEVV200050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 543-V-115 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1280 | 0 | 10610.ME.ER.TN | 32 | 0
C113136MEVV200080 | U13 - Vertical Vessels (Mercury Adsorber) Erection 543-V-116C (Train 2) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8120 | 0 | 10610.ME.ER.TN | 203 | 0
C113137INCO100010 | U13 - Communication System Installation (Train 1) | IN | INCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4030 | 0 | 10780.IN.IN.MH
C113137INCO100050 | U13 - Communication System Installation (Comp. Shelter 542-SH-004) (Train 1) | IN | INCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4030 | 0 | 10780.IN.IN.MH
C113137INCO200030 | U13 - Communication System Installation (Comp. Shelter 543-SH-002) (Train 2) | IN | INCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3259 | 0 | 10780.IN.IN.MH
C113137INCO300020 | U13 - Communication System Installation (Comp. Shelter 544-SH-001) (Train 3) | IN | INCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3421 | 0 | 10780.IN.IN.MH
C113137INCO300030 | U13 - Communication System Installation (Comp. Shelter 544-SH-002) (Train 3) | IN | INCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3421 | 0 | 10780.IN.IN.MH
C113137INCO300040 | U13 - Communication System Installation (Comp. Shelter 544-SH-003) (Train 3) | IN | INCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3421 | 0 | 10780.IN.IN.MH
C113137INCT100010 | U13 - Primary Cable Trays Installation (Train 1) | IN | INCT1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 114482 | 0 | 10610.IN.CT.LM | 970 | 0
C113137INCT100020 | U13 - Secondary Cable Trays Installation (Train 1) | IN | INCT2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 64110 | 0 | 10610.IN.CT.LM | 920 | 0
C113137INCT200010 | U13 - Primary Cable Trays Installation (Train 2) | IN | INCT1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 92580 | 0 | 10610.IN.CT.LM | 930 | 0
C113137INCT200020 | U13 - Secondary Cable Trays Installation (Train 2) | IN | INCT2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 51845 | 0 | 10610.IN.CT.LM | 960 | 0
C113137INCT300020 | U13 - Secondary Cable Trays Installation (Train 3) | IN | INCT2 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54430 | 0 | 10610.IN.CT.LM | 960 | 0
C113137INFC100010 | U13 - Fiber Optic Gland & Conn./Testing (Train 1) | IN | INFC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10990 | 0 | 10610.IN.CO.UN | 510 | 0
C113137INFC200010 | U13 - Fiber Optic Gland & Conn./Testing (Train 2) | IN | INFC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8888 | 0 | 10610.IN.CO.UN | 590 | 0
C113137INFC300010 | U13 - Fiber Optic Gland & Conn./Testing (Train 3) | IN | INFC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9331 | 0 | 10610.IN.CO.UN | 590 | 0
C113137INFG100020 | U13 - Fire & Gas System Installation (Comp. Shelter 542-SH-001) (Train 1) | IN | INFG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2381 | 0 | 10780.IN.IN.MH
C113137INFG200010 | U13 - Fire & Gas System Installation (Train 2) | IN | INFG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1926 | 0 | 10780.IN.IN.MH
C113137INFG200050 | U13 - Fire & Gas System Installation (Comp. Shelter 543-SH-004) (Train 2) | IN | INFG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1926 | 0 | 10780.IN.IN.MH
C113137INFG300020 | U13 - Fire & Gas System Installation (Comp. Shelter 544-SH-001) (Train 3) | IN | INFG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2022 | 0 | 10780.IN.IN.MH
C113137INFO200010 | U13 - Fiber Optic Cable Pulling (Train 2) | IN | INFO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12591 | 0 | 10610.IN.FO.LM | 45948 | 0
C115132CIPR000120 | U15 - Main Piperack Foundations (577-PR-112 / 577-PR-113) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 75657 | 8455.9933 | 10610.CI.CO.M3 | 1513.14 | 1513.14
C115132STPL000040 | U15 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67415 | 0 | 10610.ST.PL.TN | 842.68 | 0
C115132STSP000020 | U15 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18529 | 0 | 10610.ST.PL.TN | 308.82 | 0
C115133PASP000020 | U15 - Piping Supports SandBl. & Priming | PA | PASP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9632 | 18.5739 | 10610.PA.SU.TN | 0 | 0
C115134ELCL000020 | U15 - Lighting Cable Laying | EL | ELCL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3880 | 0 | 10610.EL.LC.LM | 16383.24 | 0
C115134ELCP000020 | U15 - Cathodic Protection Piping | EL | ELCP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1725 | 0 | 10780.EL.EL.MH
C115134ELGR000020 | U15 - Grounding Installation | EL | ELEL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2299 | 0 | 10780.EL.EL.MH
C115134MEMC000020 | U15 - Miscellaneous Electrical | EL | ELEQ2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1293 | 0 | 10780.EL.EL.MH
C115137PRLT000020 | U15 - Loops Testing | PR | PRLT | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2905 | 0 | 10780.PR.PR.MH
C116131NIPR000020 | U16 - Nitrogen Purging & Inerting (Unit 545) | PR | PRFL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1270 | 0 | 10780.PR.PR.MH
C116131PIBB000030 | U16 - Big Bore Piping A/Equip. Erection - South of racks area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIBB000050 | U16 - Big Bore Piping A/Equip. Erection - Scraper launcher area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIPR000030 | U16 - Piping Prefabrication | PI | PIPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179568 | 36850.2045 | 10610.PI.FB.DI | 44891.91 | 29764.9561
C116131PIRA000030 | U16 - Piping Erection on Rack 545-PR-104 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000040 | U16 - Piping Erection on Rack 545-PR-103 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000060 | U16 - Piping Erection on Rack 545-PR-101B | PI | PIRA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000070 | U16 - Piping Erection on Rack 545-PR-101A | PI | PIRA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000080 | U16 - Piping Erection on Rack 545-PR-105/106/107/108 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PISU000060 | U16 - Piping Supports Erection | PI | PISU2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26148 | 0 | 10610.PI.SU.TN | 58.11 | 0
C116131PIUG000030 | U16 - Piping Erection UG | PI | PIUG | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 282 | 0.073642 | 10610.PI.UG.DI | 188 | 112.8
C116131PRFL000030 | U16 - Piping Flushing/Blowing | PR | PRFL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5927 | 0 | 10610.PR.FL.DI | 72907 | 0
C113136MEVV200090 | U13 - Vertical Vessels (Sales Gas Compressor Suction Scrubber) Erection 543-V-117 (Train 2) (HL) (400 + 250) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3240 | 0 | 10610.ME.ER.TN | 81 | 0
C113136MEVV200150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 543-V-125 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1600 | 0 | 10610.ME.ER.TN | 40 | 0
C113136MEVV200160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 543-V-127 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1760 | 0 | 10610.ME.ER.TN | 44 | 0
C113136MEVV200170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 543-V-128 (Train 2) | ME | MEVV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C113136MEVV200220 | U13 - Horizontal Vessels (Warm Closed Drain Drum) Erection 543-V-133 (Train 2) | ME | MEHV | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C113136MEVV300010 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110A (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300020 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110B (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300030 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110C (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300040 | U13 - Vertical Vessels (Molecular Sieve Adsorber) Erection 544-V-110D (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17000 | 426.9374 | 10610.ME.ER.TN | 425 | 425
C113136MEVV300050 | U13 - Vertical Vessels (Regeneration Gas Separator) Erection 544-V-115 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1280 | 0 | 10610.ME.ER.TN | 32 | 0
C113136MEVV300060 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116A (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300070 | U13 - Vertical Vessels (Mercury Adsorber) Erection 544-V-116B (Train 3) (HL) (800 + 650 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4044 | 10610.ME.ER.TN | 203 | 203
C113136MEVV300090 | U13 - Vertical Vessels (Sales Gas Compressor Suction Scrubber) Erection 544-V-117 (Train 3) (HL) (400 + 250 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 15.508 | 10610.ME.ER.TN | 81 | 81
C113136MEVV300110 | U13 - Vertical Vessels (Cold Separator) Erection 544-V-118 (Train 3) (HL) (800 + 400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15840 | 370.6609 | 10610.ME.ER.TN | 396 | 396
C113136MEVV300120 | U13 - Vertical Vessels (Refrigerant Surge Drum) Erection 544-V-122 (Train 3) (HL) (400 TON) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5200 | 0 | 10610.ME.ER.TN | 130 | 0
C113136MEVV300140 | U13 - Vertical Vessels (Propane Compressor Second Stage Suction Drum) Erection 544-V-124 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2240 | 7.4125 | 10610.ME.ER.TN | 56 | 56
C113137INFO300010 | U13 - Fiber Optic Cable Pulling (Train 3) | IN | INFO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13219 | 0 | 10610.IN.FO.LM | 48239 | 0
C113137INFS100010 | U13 - Fire Fighting Equipments Installation (Train 1) | IN | INFS | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11906 | 0 | 10780.IN.IN.MH
C113137INFS300010 | U13 - Fire Fighting Equipments Installation (Train 3) | IN | INFS | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10109 | 0 | 10780.IN.IN.MH
C113137ININ100010 | U13 - Instruments Installation (Train 1) | IN | ININ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36634 | 0 | 10610.IN.IN.UN | 1160 | 0
C113137ININ200010 | U13 - Instruments Installation (Train 2) | IN | ININ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29626 | 0 | 10610.IN.IN.UN | 870 | 0
C113137ININ300010 | U13 - Instruments Installation (Train 3) | IN | ININ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31103 | 0 | 10610.IN.IN.UN | 690 | 0
C113137ININ300011 | U13 - Valve Installation (Train 1) | IN | ININ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36634 | 0 | 10610.IN.IN.UN | 580 | 0
C113137ININ300012 | U13 - Valve Installation (Train 2) | IN | ININ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29626 | 0 | 10610.IN.IN.UN | 740 | 0
C113137INIP300011 | U13 - Valve Calibration (Train 1) | IN | INIP | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11906 | 0 | 10780.IN.IN.MH
C113137INML100010 | U13- Multi Pair Cable Pulling (Train 1) | IN | INML | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 142874 | 0 | 10610.IN.MC.LM | 487114.08 | 0
C113137INSL100010 | U13 - Single Pair Cable Pulling (Train 1) | IN | INSL | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 114482 | 0 | 10610.IN.SC.LM | 257754.59 | 0
C113137INSL200010 | U13 - Single Pair Cable Pulling (Train 2) | IN | INSL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 92580 | 0 | 10610.IN.SC.LM | 208442.24 | 0
C113137MEMC200010 | 543 - Miscellaneous Instrumetation | IN | ININ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29626 | 0 | 10780.IN.IN.MH
C113137PRLT200010 | U13 - Loops Testing (Train 2) | PR | PRLT | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 109897 | 0 | 10780.PR.PR.MH
C115131PIRA000020 | U15 - Piping Erection on Rack (577-PR-112 / 577-PR-113 ) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 549.0704 | 10610.PI.PR.DI | 7417.92 | 486.0963
C115131PIST000030 | U15 - Piping Steam Tracing Installation | PI | PIST2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11180 | 0 | 10780.PI.PI.MH
C115131PRFL000020 | U15 - Piping Flushing/Steam Blowing | PR | PRFL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 49305 | 0 | 10610.PR.FL.DI | 339273 | 0
C115131PRRE000000 | U15 - Piping Reinstatement | PR | PRRE | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 197218 | 0 | 10610.PR.RE.DI | 339273 | 0
C115132CIGR000020 | U15 - Grounding Network Execution | CI | CIGR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4260 | 0 | 10780.CI.CI.MH
C115132STSP000020 | U15 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18529 | 0 | 10610.ST.PL.TN | 308.82 | 0
C115133PAPP000020 | U15 - Piping SandBl. & Priming | PA | PAPP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24190 | 603.2627 | 10610.PA.PP.M2 | 0 | 0
C116131PRHT000030 | U16 - Piping Hydrotesting | PR | PRHT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28019 | 0 | 10610.PR.HT.DI | 72907 | 0
C116132CIHE000120 | U16 - Foundation execution 30" PL-952 Scrapper Launcher 545-V-503 | CI | CIHE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12047 | 214.3908 | 10610.CI.CO.M3 | 240.93 | 240.93
C116132CIHE000140 | U16 - Foundation execution NGL Surge Sphere 545-V-201B | CI | CIHE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14538 | 312.23 | 10610.CI.CO.M3 | 290.76 | 290.76
C116132CIPD000010 | U16 - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15352 | 300.3453 | 10780.CI.CI.MH
C116132CIPE000040 | U16 - Packaged Equipment Foundation Execution 545-ME-302 | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1296 | 2.4813 | 10780.CI.CI.MH
C116132CIPE000080 | U16 - Packaged Equipment Foundation Execution Jib Crane Foundation 545-Y-001 | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 774 | 0.88444 | 10610.CI.CO.M3 | 11.05 | 11.05
C116132CIPR000140 | U16 - 545-PR-104 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18153 | 486.8142 | 10610.CI.CO.M3 | 363.06 | 363.06
C116132CIPR000180 | U16 - 545-PR-102 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12539 | 232.2602 | 10610.CI.CO.M3 | 250.77 | 250.77
C116132CIPR000200 | U16 - 545-PR-105 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25382 | 951.7207 | 10610.CI.CO.M3 | 507.63 | 507.63
C116132CIPR000210 | U16 - 545-PR-106 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23906 | 844.2678 | 10610.CI.CO.M3 | 478.12 | 478.12
C116132CIPR000220 | U16 - 545-PR-107 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11462 | 194.0744 | 10610.CI.CO.M3 | 229.23 | 229.23
C116132CIPR000235 | U16 - 545-PR-108 A Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18227 | 490.7912 | 10610.CI.CO.M3 | 364.54 | 364.54
C116132CIPR000240 | U16 - 545-PR-109 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15755 | 366.6935 | 10610.CI.CO.M3 | 315.1 | 315.1
C116132CIPS000020 | U16 - Liquid Collection New Pit - Testing | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 980 | 1.4188 | 10780.CI.CI.MH
C116132CIPS000040 | U16 - Liquid Collection New Pit - Backfill | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4270 | 26.9353 | 10780.CI.CI.MH
C116132CIPS000130 | U16 - NLCP Pit: Base Concrete : First Part | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38553 | 2195.7208 | 10610.CI.CO.M3 | 771.05 | 771.05
C116132CIPS000150 | U16 - NLCP Pit:Wall Concrete: First Part , First Stage | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3782 | 21.1305 | 10780.CI.CI.MH
C116132CIRE000070 | U16 - NGL Booster Pump Foundation Execution 545-P-201C | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116132CIRE000250 | U16 - NGL Shipping Pump Foundation Execution 545-P-202B | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CISF000020 | U16 - Stairs & Small Foundations Execution | CI | CISF | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 17.4872 | 10610.CI.CO.M3 | 66.21 | 49.6601
C113136MEVV300150 | U13 - Vertical Vessels (Second Stage Refrigerant Flash Drum) Erection 544-V-125 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1600 | 3.7819 | 10610.ME.ER.TN | 40 | 40
C113136MEVV300160 | U13 - Vertical Vessels (Propane Compressor First Stage Suction Drum) Erection 544-V-127 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1760 | 4.5761 | 10610.ME.ER.TN | 44 | 44
C113136MEVV300170 | U13 - Vertical Vessels (Regeneration Gas Compressor Suction Drum) Erection 544-V-128 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ME.ER.TN | 36 | 0
C113136MEVV300180 | U13 - Vertical Vessels (Regeneration Gas Compressor Discharge Drum) Erection 544-V-129 (Train 3) | ME | MEVV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 1.5978 | 10610.ME.ER.TN | 26 | 26
C113136MEVV300190 | U13 - Horizontal Vessels (Cold Closed Drain Drum) Erection 544-V-132 (Train 3) | ME | MEHV | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 640 | 0 | 10610.ME.ER.TN | 16 | 0
C113137INAI200010 | U13 - Analyzers Equipment Installation (Train 2) | IN | INAI | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19997 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INAI300010 | U13 - Analyzers Equipment Installation (Train 3) | IN | INAI | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20995 | 0 | 10610.IN.AI.UN | 17 | 0
C113137INCI200010 | U13 - Conduits Installation (Train 2) | IN | INCT3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9599 | 0 | 10780.IN.IN.MH
C113137INCO100030 | U13 - Communication System Installation (Comp. Shelter 542-SH-002) (Train 1) | IN | INCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4030 | 0 | 10780.IN.IN.MH
C113137INCO100040 | U13 - Communication System Installation (Comp. Shelter 542-SH-003) (Train 1) | IN | INCO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4030 | 0 | 10780.IN.IN.MH
C113137INCO200010 | U13 - Communication System Installation (Train 2) | IN | INCO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3259 | 0 | 10780.IN.IN.MH
C113137INCO300050 | U13 - Communication System Installation (Comp. Shelter 544-SH-004) (Train 3) | IN | INCO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3421 | 0 | 10780.IN.IN.MH
C113137INCT100010 | U13 - Primary Cable Trays Installation (Train 1) | IN | INCT1 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 114482 | 0 | 10610.IN.CT.LM | 970 | 0
C113137INCT100020 | U13 - Secondary Cable Trays Installation (Train 1) | IN | INCT2 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 64110 | 0 | 10610.IN.CT.LM | 920 | 0
C113137INCT200010 | U13 - Primary Cable Trays Installation (Train 2) | IN | INCT1 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 92580 | 0 | 10610.IN.CT.LM | 930 | 0
C113137INCT200020 | U13 - Secondary Cable Trays Installation (Train 2) | IN | INCT2 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 51845 | 0 | 10610.IN.CT.LM | 960 | 0
C113137INCT300010 | U13 - Primary Cable Trays Installation (Train 3) | IN | INCT1 | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 97197 | 0 | 10610.IN.CT.LM | 860 | 0
C113137INFC200010 | U13 - Fiber Optic Gland & Conn./Testing (Train 2) | IN | INFC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8888 | 0 | 10610.IN.CO.UN | 590 | 0
C113137INFG100030 | U13 - Fire & Gas System Installation (Comp. Shelter 542-SH-002) (Train 1) | IN | INFG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2381 | 0 | 10780.IN.IN.MH
C116132CISF000021 | U16 - Access Structure foundation for 545-PLTF-001 | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10920 | 176.1618 | 10610.CI.CO.M3 | 218.4 | 218.3998
C116132CIUG000050 | U16 - UG Civil Works - Part A | CI | CIUG1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4040 | 16.5609 | 10780.CI.CI.MH
C116132FPEQ000021 | U16 - Equipment Fireproofing 545-ME-201 | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPEQ000022 | U16 - Equipment Fireproofing 545-P-201A/B/C | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPSS000030 | U16 - Main PR Steel Structure Fireproofing (545-PR-111A TO 545-PR-109) | FP | FPSS | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 48285 | 0 | 10610.FP.ST.M2 | 5519.48 | 0
C116132PLIN000020 | U16 - Piling works NGL Surge Sphere 545-V-201A | PL | PLIN | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1361 | 2.7364 | 10610.PL.PL.UN | 30 | 30
C116132PLIN000040 | U16 - Paving Demolition , Dewatering, Existing Pit partial demolition, and other preparatory work for piling | SP | SPDE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21320 | 671.4919 | 10780.SP.SP.MH
C116132SPDE001150 | U16 - Demolition and Relocation of UG Utilities: Earthing Grid, AOC Manholes, Pipe, Fire Trap, V-Ditch, Fire Point etc | SP | SPDE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2160 | 6.8925 | 10610.SP.SP.M3 | 200 | 200
C116132STMS000020 | U16 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ST.PL.TN | 25 | 0
C116132STPL000050 | U16 - 545-PR-104 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1805 | 0 | 10610.ST.PL.TN | 22.57 | 0
C116132STPL000060 | U16 - Liquid Collection Pits Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.ST.PL.TN | 0 | 0
C116132STPL000090 | U16 - NGL Surge Sphere 545-V-201A Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2080 | 0 | 10780.ST.ST.MH
C116132STPL000100 | U16 - Aux. Structure for Pumps Platforms, Ladders & Handrails Erection (545-P-202A/B/C) | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10780.ST.ST.MH
C116132STPL000110 | U16 - 545-PR-101A Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4104 | 0 | 10610.ST.PL.TN | 51.3 | 0
C116132STPL000130 | U16 - 545-PR-102 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1224 | 0 | 10610.ST.PL.TN | 15.3 | 0
C116132STPL000190 | U16 - 545-PR-109 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1004 | 0 | 10610.ST.PL.TN | 12.55 | 0
C116132STPR000040 | U16 - 545-PR-104 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10764 | 61.6782 | 10610.ST.PR.TN | 203.1 | 84.0821
C116132STPR000050 | U16 - Trestle Support Erection | ST | STMS | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6196 | 17.6124 | 10610.ST.PL.TN | 103.27 | 37.4192
C116132STPR000060 | U16 - 545-PR-101A Piperack Erection | ST | STPR | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24470 | 0 | 10610.ST.PR.TN | 461.7 | 0
C115133PAPP000020 | U15 - Piping SandBl. & Priming | PA | PAPP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24190 | 603.2627 | 10610.PA.PP.M2 | 0 | 0
C115133PASP000020 | U15 - Piping Supports SandBl. & Priming | PA | PASP | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9632 | 18.5739 | 10610.PA.SU.TN | 0 | 0
C115134ELCO000020 | U15 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2587 | 0 | 10610.EL.CO.UN | 985 | 0
C115134ELEL000025 | U15 - Earthing Works | EL | ELEL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2299 | 0 | 10610.EL.ES.LM | 7726.12 | 0
C115134ELEL000035 | U15 - Lightning Works | EL | ELEL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2299 | 0 | 10780.EL.EL.MH
C1160PRPRPL000030 | U16 - Punch List | PR | PRPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8516 | 0 | 10780.PR.PR.MH
C1160PRPRWT000030 | U16 - Walkthrough | PR | PRWT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3650 | 0 | 10780.PR.PR.MH
C116131ISEQ000020 | U16 - Equipment Insulation | IS | ISEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4150 | 0 | 10610.IS.EQ.M2 | 14070 | 0
C116131MEMC000030 | U16 - Miscellaneous Piping | PI | PISU2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1010 | 0 | 10780.PI.PI.MH
C116131NITR000010 | U16 - Nitrogen Leak Test (Unit 545) | PR | PRFL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1270 | 0 | 10780.PR.PR.MH
C116131PIBB000030 | U16 - Big Bore Piping A/Equip. Erection - South of racks area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIBB000040 | U16 - Big Bore Piping A/Equip. Erection - North of racks area | PI | PIBB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26192 | 0 | 10610.PI.BB.DI | 2619.17 | 0
C116131PIPR000040 | U16 - UG Piping Prefabrication | PI | PIPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9662 | 54.0177 | 10610.PI.FB.DI | 2415.4 | 837.0669
C116131PIRA000050 | U16 - Piping Erection on Rack 545-PR-102 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000060 | U16 - Piping Erection on Rack 545-PR-101B | PI | PIRA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000090 | U16 - Piping Erection on Rack 545-PR-109 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PISB000030 | U16 - Small Bore Piping A/Equip. Erection - South of racks area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PISB000040 | U16 - Small Bore Piping A/Equip. Erection - North of racks area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PISB000050 | U16 - Small Bore Piping A/Equip. Erection - Scraper launcher area | PI | PISB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4496 | 0 | 10610.PI.SB.DI | 408.72 | 0
C116131PIUG000030 | U16 - Piping Erection UG | PI | PIUG | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 282 | 0.073642 | 10610.PI.UG.DI | 188 | 112.8
C116131PRBO000040 | U16 - Static Box Up | PR | PRBO1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 75034 | 0 | 10780.PR.PR.MH
C113137INFG100050 | U13 - Fire & Gas System Installation (Comp. Shelter 542-SH-004) (Train 1) | IN | INFG | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2381 | 0 | 10780.IN.IN.MH
C113137INFG200020 | U13 - Fire & Gas System Installation (Comp. Shelter 543-SH-001) (Train 2) | IN | INFG | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1926 | 0 | 10780.IN.IN.MH
C113137INFG300010 | U13 - Fire & Gas System Installation (Train 3) | IN | INFG | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2022 | 0 | 10780.IN.IN.MH
C113137INFO100010 | U13 - Fiber Optic Cable Pulling (Train 1) | IN | INFO | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15570 | 0 | 10610.IN.FO.LM | 56818 | 0
C113137INFO200010 | U13 - Fiber Optic Cable Pulling (Train 2) | IN | INFO | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12591 | 0 | 10610.IN.FO.LM | 45948 | 0
C113137INFO300010 | U13 - Fiber Optic Cable Pulling (Train 3) | IN | INFO | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13219 | 0 | 10610.IN.FO.LM | 48239 | 0
C113137INFS200010 | U13 - Fire Fighting Equipments Installation (Train 2) | IN | INFS | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9628 | 0 | 10780.IN.IN.MH
C113137INGC100010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 1) | IN | INGC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 71437 | 0 | 10610.IN.CO.UN | 830 | 0
C113137INGC100020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 1) | IN | INGC | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47625 | 0 | 10610.IN.CO.UN | 640 | 0
C113137INGC200020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 2) | IN | INGC | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 38513 | 0 | 10610.IN.CO.UN | 720 | 0
C113137INGC300010 | U13 - Multi Pair Cable Gland & Conn./Testing (Train 3) | IN | INGC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60651 | 0 | 10610.IN.CO.UN | 1000 | 0
C113137INGC300020 | U13 - Single Pair Cable Gland & Conn./Testing (Train 3) | IN | INGC | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40434 | 0 | 10610.IN.CO.UN | 1000 | 0
C113137INHU100010 | U13 - Pneumatic Hook Up´s Erection (Train 1) | IN | INHU3 | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9812 | 0 | 10780.IN.IN.MH
C113137INHU200010 | U13 - Pneumatic Hook Up´s Erection (Train 2) | IN | INHU3 | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9812 | 0 | 10780.IN.IN.MH
C113137ININ200010 | U13 - Instruments Installation (Train 2) | IN | ININ | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 29626 | 0 | 10610.IN.IN.UN | 870 | 0
C113137ININ300013 | U13 -Valve Installation (Train 3) | IN | ININ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31103 | 0 | 10610.IN.IN.UN | 600 | 0
C113137INIP300010 | U13 - Instruments Calibration (Train 3) | IN | INIP | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10109 | 0 | 10780.IN.IN.MH
C113137INIP300012 | U13 - Valve Calibration (Train 2) | IN | INIP | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9628 | 0 | 10780.IN.IN.MH
C113137INJB100010 | U13 - Junction Boxes & Local Panels Install. (Train 1) | IN | INJB | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47625 | 0 | 10780.IN.IN.MH
C113137INML200010 | U13- Multi Pair Cable Pulling (Train 2) | IN | INML | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 115540 | 0 | 10610.IN.MC.LM | 393921.03 | 0
C116132STPR000080 | U16 - 545-PR-102 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7298 | 0 | 10610.ST.PR.TN | 137.7 | 0
C116132STPR000090 | U16 - 545-PR-103 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6031 | 0 | 10610.ST.PR.TN | 113.79 | 0
C116132STPR000100 | U16 - 545-PR-105 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10067 | 137.2579 | 10610.ST.PR.TN | 189.95 | 183.5882
C116132STPR000100 | U16 - 545-PR-105 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10067 | 137.2579 | 10610.ST.PR.TN | 189.95 | 183.5882
C116132STPR000130 | U16 - 545-PR-108 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9481 | 89.0925 | 10610.ST.PR.TN | 178.88 | 168.5025
C116132STSP000030 | U16 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8283 | 0 | 10610.ST.PL.TN | 138.05 | 0
C116133PAEQ000020 | U16 - Equipment Painting | PA | PAEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5630 | 0 | 10780.PA.PA.MH
C116133PAFP000030 | U16 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1419 | 0 | 10780.PA.PA.MH
C116134ELCI300010 | U16 - Conduits Installation | EL | ELCI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1920 | 0.53367 | 10610.EL.CD.LM | 48 | 4.32
C116134ELCL000040 | U16 - Lighting Cable Laying | EL | ELCL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3456 | 0 | 10610.EL.LC.LM | 16332.41 | 0
C116134ELCO000040 | U16 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.CO.UN | 81 | 0
C116134ELCO000050 | U16 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9215 | 0 | 10610.EL.CO.UN | 702 | 0
C116134ELCT000020 | U16 - Cathodic Protection Spheres | EL | ELCT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1536 | 0 | 10780.EL.EL.MH
C116134ELEL000035 | U16 - Earthing Works | EL | ELEL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2048 | 0 | 10610.EL.ES.LM | 1167.14 | 0
C116134ELEQ300010 | U16 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.EQ.UN | 38 | 0
C116134ELGR000030 | U16 - Grounding Installation | EL | ELEL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2048 | 0 | 10780.EL.EL.MH
C116134ELTI000040 | U16 - Lighting Cable Trays Installation | EL | ELTI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.CT.LM | 564.87 | 0
C116134ELTI000050 | U16 - Electrical Cable Trays Installation | EL | ELTI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7680 | 0 | 10610.EL.CT.LM | 1049.04 | 0
C116136MEHM000030 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201A | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHM000060 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202B | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116136MEHM000070 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202C | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116131PRRE000020 | U16 - Piping Reinstatement | PR | PRRE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19355 | 0 | 10610.PR.RE.DI | 72907 | 0
C116132CICT000030 | U16 - Covered Concrete Trenches Execution | CI | CICT1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18649 | 273.3311 | 10780.CI.CI.MH
C116132CIDM000010 | U16 - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12050 | 176.5839 | 10610.CI.CO.M3 | 241 | 200.0001
C116132CIDM000010 | U16 - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12050 | 176.5839 | 10610.CI.CO.M3 | 241 | 200.0001
C116132CIGT000040 | U16 - Equipment Grouting Execution | CI | CIGT | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5500 | 0 | 10780.CI.CI.MH
C116132CIMF000020 | U16 - Miscellaneous Foundations Execution | CI | CIMF | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22655 | 650.7033 | 10610.CI.CO.M3 | 453.1 | 453.0998
C116132CIPE000070 | U16 - Packaged Equipment Foundation Execution Deluge Valve Skid | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11132 | 183.0747 | 10610.CI.CO.M3 | 185.54 | 185.54
C116132CIPE000080 | U16 - Packaged Equipment Foundation Execution Jib Crane Foundation 545-Y-001 | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 774 | 0.88444 | 10610.CI.CO.M3 | 11.05 | 11.05
C116132CIPR000140 | U16 - 545-PR-104 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18153 | 486.8142 | 10610.CI.CO.M3 | 363.06 | 363.06
C116132CIPR000160 | U16 - 545-PR-101A Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38601 | 2201.2203 | 10610.CI.CO.M3 | 772.02 | 772.02
C116132CIPR000160 | U16 - 545-PR-101A Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38601 | 2201.2203 | 10610.CI.CO.M3 | 772.02 | 772.02
C116132CIPR000170 | U16 - 545-PR-101B Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40772 | 2455.7554 | 10610.CI.CO.M3 | 815.43 | 815.43
C116132CIPR000170 | U16 - 545-PR-101B Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40772 | 2455.7554 | 10610.CI.CO.M3 | 815.43 | 815.43
C116132CIPR000180 | U16 - 545-PR-102 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12539 | 232.2602 | 10610.CI.CO.M3 | 250.77 | 250.77
C116132CIPR000230 | U16 - 545-PR-108 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13136 | 254.9037 | 10610.CI.CO.M3 | 262.71 | 262.71
C116132CIPS000110 | U16 - NLCP Pit:Excavation & Dewatering | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3886 | 22.3086 | 10780.CI.CI.MH
C116132CIPS000130 | U16 - NLCP Pit: Base Concrete : First Part | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38553 | 2195.7208 | 10610.CI.CO.M3 | 771.05 | 771.05
C116132CIPS000140 | U16 - NLCP Pit:Base concrete : Second Part | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38553 | 2195.7208 | 10610.CI.CO.M3 | 771.05 | 771.05
C116132CIPS000180 | U16 - NLCP Pit:Wall Concrete: Second Part , Second Stage | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2031 | 6.0938 | 10780.CI.CI.MH
C116132CIRE000050 | U16 - NGL Booster Pump Foundation Execution 545-P-201A | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116136MEHV000010 | U16 - NGL Surge Sphere Erection 545-V-201A (up to HT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 74934 | 2578.1334 | 10610.ME.ER.TN | 1222 | 383.6958
C116136MEHV000090 | U16 - 30" PL-952 Scrapper Launcher 545-V-503 (L) Erection | ME | MEHV | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C116136MEMC000020 | U16 - Miscellaneous Erection | ME | MEMC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4500 | 0 | 10610.ME.ER.TN | 75 | 0
C116136MEPA000030 | U16 - Package Installation 545-ME-301 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13200 | 0 | 10610.ME.ER.TN | 220 | 0
C116136MEPA000040 | U16 - Package Installation 545-ME-302 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13200 | 0 | 10610.ME.ER.TN | 220 | 0
C116137INCI000030 | U16 - Conduits Installation | IN | INCT3 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1379 | 0 | 10780.IN.IN.MH
C116137INCO000030 | U16 - Communication System Installation | IN | INCO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2341 | 0 | 10780.IN.IN.MH
C116137INFO000010 | U16 - Fiber Optic Cable Pulling | IN | INFO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1809 | 0 | 10610.IN.FO.LM | 107612 | 0
C116137INGC000050 | U16 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8300 | 0 | 10610.IN.CO.UN | 530 | 0
C116137INGC000065 | U16 - Termination at JB end and Instrument End | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1844 | 0 | 10610.IN.CO.UN | 390 | 0
C116FPSS000000700 | U16 - NGL Surge Sphere 545-V-201B - Fire Proofing | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116PAEQ000000710 | U16 - NGL Surge Sphere 545-V-201A - External Blasting & Painting | PA | PAEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1720 | 0 | 10780.PA.PA.MH
C116PRHT000000700 | U16 - NGL Surge Sphere 545-V-201B - Hydrotesting | PR | PRHT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6849 | 0 | 10780.PR.PR.MH
C116PRRE000000700 | U16 - NGL Surge Sphere 545-V-201A - Erection of connecting spool and Instruments Installation | PR | PRRE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7258 | 0 | 10780.PR.PR.MH
C117131ISPI000040 | U17 - Piping Insulation | IS | ISPI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 901 | 0 | 10780.IS.IS.MH
C117131PIPR000040 | U17 - Piping Prefabrication | PI | PIPR | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2376 | 6.561 | 10610.PI.FB.DI | 594 | 382.6649
C117131PIRA000030 | U17 - Piping Erection on Rack (500-PR-101 & 500-PR-102) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0 | 10610.PI.PR.DI | 156 | 0
C117131PIRA000160 | U17 - Piping Erection on Rack (577-PR-101) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 1.4983 | 10610.PI.PR.DI | 156 | 78
C117131PISU000070 | U17 - Piping Supports Prefabrication | PI | PISU1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 208000 | 1320.4543 | 10610.PI.PU.TN | 0 | 0
C117131PISU000080 | U17 - Piping Supports Erection | PI | PISU2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 450 | 0 | 10780.PI.PI.MH
C117131PRRE000030 | U17 - Piping Reinstatement | PR | PRRE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17574 | 0 | 10610.PR.RE.DI | 2296 | 0
C113137INSL200010 | U13 - Single Pair Cable Pulling (Train 2) | IN | INSL | 13 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 92580 | 0 | 10610.IN.SC.LM | 208442.24 | 0
C113137INSL300010 | U13 - Single Pair Cable Pulling (Train 3) | IN | INSL | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 97197 | 0 | 10610.IN.SC.LM | 218836.86 | 0
C113137MEMC100010 | 542 - Miscellaneous Instrumetation | IN | ININ | 13 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 36634 | 0 | 10780.IN.IN.MH
C113137MEMC300010 | 544 - Miscellaneous Instrumetation | IN | ININ | 13 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31103 | 0 | 10780.IN.IN.MH
C1150PRPRPL000020 | U15 - Punch List | PR | PRPL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.PR.PR.MH
C1150PRPRWT000020 | U15 - Walkthrough | PR | PRWT | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 783 | 0 | 10780.PR.PR.MH
C115131ISPI000020 | U15 - Piping Insulation | IS | ISPI | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 225745 | 0 | 10780.IS.IS.MH
C115131PIPR000020 | U15 - Piping Prefabrication | PI | PIPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 617869 | 456762.661 | 10610.PI.FB.DI | 154467.25 | 113109.1225
C115131PIPR000020 | U15 - Piping Prefabrication | PI | PIPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 617869 | 456762.661 | 10610.PI.FB.DI | 154467.25 | 113109.1225
C115131PISU000030 | U15 - Piping Supports Prefabrication | PI | PISU1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156138 | 11994.4574 | 10610.PI.PU.TN | 600.53 | 63.0985
C115131PISU000040 | U15 - Piping Supports Erection | PI | PISU2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 270239 | 0 | 10610.PI.SU.TN | 600.53 | 0
C115131PRFL000020 | U15 - Piping Flushing/Steam Blowing | PR | PRFL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 49305 | 0 | 10610.PR.FL.DI | 339273 | 0
C115132CIPR000120 | U15 - Main Piperack Foundations (577-PR-112 / 577-PR-113) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 75657 | 8455.9933 | 10610.CI.CO.M3 | 1513.14 | 1513.14
C115132CIPR000130 | U15 - Main Piperack Foundations Execution/Modification 577 | CI | CIPR2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2971 | 13.0381 | 10610.CI.CO.M3 | 49.51 | 49.51
C115132STPR30 | U15 - Main Piperack Erection (577-PR-121) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22228 | 206.2004 | 10610.ST.PR.TN | 419.4 | 137.3919
C115134ELCL000020 | U15 - Lighting Cable Laying | EL | ELCL | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3880 | 0 | 10610.EL.LC.LM | 16383.24 | 0
C116131ISPI000030 | U16 - Piping Insulation | IS | ISPI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32082 | 0 | 10610.IS.PI.M2 | 70350 | 0
C116131PIPR000040 | U16 - UG Piping Prefabrication | PI | PIPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9662 | 54.0177 | 10610.PI.FB.DI | 2415.4 | 837.0669
C116131PIRA000030 | U16 - Piping Erection on Rack 545-PR-104 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000070 | U16 - Piping Erection on Rack 545-PR-101A | PI | PIRA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C116131PIRA000090 | U16 - Piping Erection on Rack 545-PR-109 | PI | PIRA | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14222 | 0 | 10610.PI.PR.DI | 1580.21 | 0
C117132CIGR000040 | U17 - Grounding Network Execution | CI | CIGR | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2005 | 0.64139 | 10780.CI.CI.MH
C117132CIPR000200 | U17 - SL & Receiver - Piperack 577-PR-101 Foundations Execution | CI | CIPR2 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29643 | 1298.0857 | 10610.CI.CO.M3 | 592.85 | 592.85
C117132CIPR000210 | U17 - SL & Receiver - Trestle Support Foundations Execution | CI | CIPR2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5877 | 51.0218 | 10610.CI.CO.M3 | 97.95 | 97.95
C117132CIPT000010 | U17 - Anchor Block Pipe Tracks Execution | CI | CIPT1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17393 | 48.2651 | 10610.CI.CO.M3 | 347.86 | 0
C117132CIPT000010 | U17 - Anchor Block Pipe Tracks Execution | CI | CIPT1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17393 | 48.2651 | 10610.CI.CO.M3 | 347.86 | 0
C117132CIPV000070 | U17 - Concrete Paving Execution | CI | CIPV1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1345 | 0.34598 | 10610.CI.PV.M2 | 747 | 14.94
C117132CIPV000080 | U17 - Gravel Paving Execution | CI | CIPV2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5264 | 0 | 10780.CI.CI.MH
C117132CISF000090 | U17 - Stairs & Small Foundations Execution (516/517/518-STR-V501) | CI | CISF | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1292 | 0.28355 | 10610.CI.CO.M3 | 21.53 | 0
C117132CIUG000100 | U17 - UG Pipe Installation (OD) | CI | CIUG2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 98359 | 12980.0852 | 10610.CI.UG.LM | 4917.97 | 4917.9464
C117132CIUG000150 | U17 - UG GRE Pipe Installation (FW) | CI | CIUG2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6552 | 16.6917 | 10780.CI.CI.MH
C117132CIVE000030 | U17 - Foundation Execution 56" PL-628 Pipeline Scrapper Launcher 542-V-503(L) | CI | CIVE | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11542 | 195.3801 | 10610.CI.CO.M3 | 230.83 | 230.8301
C117132CIVE000040 | U17 - Jib Crane Foundation Execution | CI | CIVE | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4829 | 34.1517 | 10610.CI.CO.M3 | 80.48 | 80.48
C117132CIVE000070 | U17 - Pig Trolley Foundation Execution | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1292 | 2.3658 | 10610.CI.CO.M3 | 21.53 | 21.53
C117132STPL000080 | U17 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5495 | 0 | 10610.ST.PL.TN | 68.69 | 0
C117132STPR000060 | U17 - Main Piperack Erection (577-PR-103) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31823 | 1496.0691 | 10610.ST.PR.TN | 600.44 | 600.4473
C117132STSP000040 | U17 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 305 | 0 | 10610.ST.PL.TN | 5.09 | 0
C117133PAPP000040 | U17 - Piping SandBl. & Priming | PA | PAPP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3262 | 6.4908 | 10610.PA.PP.M2 | 1631 | 8597.131
C117134ELCL000060 | U17 - Lighting Cable Laying | EL | ELCL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 265 | 0 | 10610.EL.LC.LM | 1169.06 | 0
C117134ELCO000070 | U17 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 707 | 0 | 10610.EL.CO.UN | 675 | 0
C117134ELEL000056 | U17 - Lightning Works | EL | ELEL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 157 | 0 | 10780.EL.EL.MH
C116132CIRE000050 | U16 - NGL Booster Pump Foundation Execution 545-P-201A | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116132CIRE000060 | U16 - NGL Booster Pump Foundation Execution 545-P-201B | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116132CIRE000240 | U16 - NGL Shipping Pump Foundation Execution 545-P-202A | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CIRE000250 | U16 - NGL Shipping Pump Foundation Execution 545-P-202B | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CISF000021 | U16 - Access Structure foundation for 545-PLTF-001 | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10920 | 176.1618 | 10610.CI.CO.M3 | 218.4 | 218.3998
C116132CISF000022 | U16 - Access Structure foundation for 545-PLTF-007 | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4511 | 30.0603 | 10610.CI.CO.M3 | 75.18 | 75.18
C116132CIUG000070 | U16 - UG Pipe Installation (OD) - Part A | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21039 | 455.9436 | 10610.CI.UG.LM | 1051.95 | 820.521
C116132CIUG000140 | U16 - UG Pipe Installation (CD) - Part B | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3600 | 12.5334 | 10780.CI.CI.MH
C116132CIUG000150 | U16 - UG Civil Works - Part B | CI | CIUG1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4040 | 0 | 10780.CI.CI.MH
C116132CIUG000180 | U16 - UG GRE Pipe Installation (FW) - Part B | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10780.CI.CI.MH
C116132FPEQ000021 | U16 - Equipment Fireproofing 545-ME-201 | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPEQ000023 | U16 - Equipment Fireproofing 545-P-202A/B/C | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPEQ000024 | U16 - Equipment Fireproofing 545-V-201A/B | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPSS000030 | U16 - Main PR Steel Structure Fireproofing (545-PR-111A TO 545-PR-109) | FP | FPSS | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 48285 | 0 | 10610.FP.ST.M2 | 5519.48 | 0
C116132STEQ000030 | U16 - Auxiliary Structure Erection for Pumps 545-P-202A/B/C | ST | STEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5830 | 0 | 10780.ST.ST.MH
C116132STMS000020 | U16 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ST.PL.TN | 25 | 0
C116132STPL000051 | U16 - 545-PLTF-007 Valve Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6160 | 0 | 10610.ST.PL.TN | 77 | 0
C116132STPL000070 | U16 - Rest of Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2870 | 0 | 10610.ST.PL.TN | 35.87 | 0
C116132STPL000080 | U16 - NGL Surge Sphere 545-V-201B Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10780.ST.ST.MH
C116132STPL000130 | U16 - 545-PR-102 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1224 | 0 | 10610.ST.PL.TN | 15.3 | 0
C117134ELTI000060 | U17 - Lighting Cable Trays Installation | EL | ELTI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10610.EL.CT.LM | 842.84 | 0
C117134ELTI000070 | U17 - Electrical Cable Trays Installation | EL | ELTI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 589 | 0 | 10610.EL.CT.LM | 1565.28 | 0
C117134MEMC000070 | U17 - Miscellaneous Electrical | EL | ELEQ2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 88 | 0 | 10780.EL.EL.MH
C117136MEVV000020 | U17 - Pig Trolley (518-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 14 | 0
C117136MEVV000030 | U17 - 48" PL-627 Scraper Receiver 518-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C117136MEVV000070 | U17 - Pig Trolley (516-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C117136MEVV000080 | U17 - Pig Trolley (517-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C117136MEVV000100 | U17 - Jib Crane (516-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000110 | U17 - Jib Crane (517-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000120 | U17 - Jib Crane (542-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000130 | U17 - Fire Hydrants Erection FH-03-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C117136MEVV000140 | U17 - Fire Hydrants Erection FH-04-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000150 | U17 - Fire Hydrants Erection FH-05-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000170 | U17 - Fire Hydrants Erection FH-YY-YYY | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000180 | U17 - Jib Crane (518-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000430 | U17 - 36" PL-626 Scraper Receiver 517-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C117137ELCO000050 | U17 - Multi Pair Cable Pulling | IN | INML | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7539 | 18.0531 | 10610.IN.MC.LM | 26894.41 | 6723.6025
C117137INCI000020 | U17- Conduits Installation | IN | INCT3 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 626 | 0 | 10780.IN.IN.MH
C117137INFG000020 | U17 - Fire & Gas Detection System Installation | IN | INFG | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 628 | 0 | 10780.IN.IN.MH
C117137INGC000050 | U17 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3770 | 0 | 10610.IN.CO.UN | 530 | 0
C117137INHU000040 | U17 - Pneumatic Hook Up´s Erection | IN | INHU3 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10780.IN.IN.MH
C116131PISU000060 | U16 - Piping Supports Erection | PI | PISU2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 26148 | 0 | 10610.PI.SU.TN | 58.11 | 0
C116131PRHT000030 | U16 - Piping Hydrotesting | PR | PRHT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28019 | 0 | 10610.PR.HT.DI | 72907 | 0
C116131PRRE000020 | U16 - Piping Reinstatement | PR | PRRE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19355 | 0 | 10610.PR.RE.DI | 72907 | 0
C116132CICT000010 | U16 - Electrical earth Trenches Execution | CI | CICT2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47988 | 0 | 10780.CI.CI.MH
C116132CIGR000030 | U16 - Grounding Network Execution | CI | CIGR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4690 | 0 | 10780.CI.CI.MH
C116132CIGT000050 | U16 - Steel Structure Grouting Execution | CI | CIGT | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5500 | 1.1172 | 10780.CI.CI.MH
C116132CIHE000130 | U16 - Foundation execution NGL Surge Sphere 545-V-201A | CI | CIHE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14538 | 312.23 | 10610.CI.CO.M3 | 290.76 | 290.76
C116132CIHE000140 | U16 - Foundation execution NGL Surge Sphere 545-V-201B | CI | CIHE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14538 | 312.23 | 10610.CI.CO.M3 | 290.76 | 290.76
C116132CIMF000020 | U16 - Miscellaneous Foundations Execution | CI | CIMF | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22655 | 650.7033 | 10610.CI.CO.M3 | 453.1 | 453.0998
C116132CIPE000020 | U16 - Packaged Equipment (NGL Shipping Meter) Foundation Execution - Metering Skid (545-ME-201) | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6410 | 60.6972 | 10610.CI.CO.M3 | 106.83 | 106.8297
C116132CIPE000070 | U16 - Packaged Equipment Foundation Execution Deluge Valve Skid | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11132 | 183.0747 | 10610.CI.CO.M3 | 185.54 | 185.54
C116132CIPE000090 | U16 - Packaged Equipment Foundation Execution Pig Trolley Foundation | CI | CIPE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1006 | 1.4949 | 10610.CI.CO.M3 | 14.37 | 14.37
C116132CIPR000190 | U16 - 545-PR-103 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12317 | 224.1087 | 10610.CI.CO.M3 | 246.33 | 246.33
C116132CIPR000210 | U16 - 545-PR-106 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23906 | 844.2678 | 10610.CI.CO.M3 | 478.12 | 478.12
C116132CIPR000220 | U16 - 545-PR-107 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11462 | 194.0744 | 10610.CI.CO.M3 | 229.23 | 229.23
C116132CIPR000230 | U16 - 545-PR-108 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13136 | 254.9037 | 10610.CI.CO.M3 | 262.71 | 262.71
C116132CIPS000100 | U16 - Valve Pit | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1308 | 2.5274 | 10780.CI.CI.MH
C116132CIPS000170 | U16 - NLCP Pit:Wall Concrete: First Part , Second Stage | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2031 | 6.0938 | 10780.CI.CI.MH
C116132CIPV000040 | U16 - Concrete Paving Execution | CI | CIPV1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12069 | 37.0563 | 10610.CI.PV.M2 | 6704.92 | 1206.8856
C116132CIPV000050 | U16 - Gravel Paving Execution | CI | CIPV2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4023 | 0 | 10610.CI.GV.M2 | 6705.25 | 0
C116132CIPR000235 | U16 - 545-PR-108 A Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18227 | 490.7912 | 10610.CI.CO.M3 | 364.54 | 364.54
C116132CIPR000240 | U16 - 545-PR-109 Piperack Foundations Execution | CI | CIPR1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15755 | 366.6935 | 10610.CI.CO.M3 | 315.1 | 315.1
C116132CIPS000030 | U16 - Liquid Collection New Pit - Coating Water proffing | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2370 | 8.2978 | 10780.CI.CI.MH
C116132CIPS000120 | U16 - NLCP Pit:Blinding | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3886 | 22.3086 | 10780.CI.CI.MH
C116132CIPS000140 | U16 - NLCP Pit:Base concrete : Second Part | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38553 | 2195.7208 | 10610.CI.CO.M3 | 771.05 | 771.05
C116132CIPS000160 | U16 - NLCP Pit:Wall Concrete: Second Part , First Stage | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3782 | 21.1305 | 10780.CI.CI.MH
C116132CIPS000190 | U16 - NLCP Pit:Completion | CI | CIPS1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3886 | 22.3086 | 10780.CI.CI.MH
C116132CIPV000040 | U16 - Concrete Paving Execution | CI | CIPV1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12069 | 37.0563 | 10610.CI.PV.M2 | 6704.92 | 1206.8856
C116132CIRE000060 | U16 - NGL Booster Pump Foundation Execution 545-P-201B | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116132CIRE000260 | U16 - NGL Shipping Pump Foundation Execution 545-P-202C | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CISF000020 | U16 - Stairs & Small Foundations Execution | CI | CISF | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 17.4872 | 10610.CI.CO.M3 | 66.21 | 49.6601
C116132CIST000010 | U16 - Auxiliary Structure foundation for Pumps 545-P-202A/B/C | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4028 | 23.9711 | 10610.CI.CO.M3 | 67.14 | 67.14
C116132CIST000010 | U16 - Auxiliary Structure foundation for Pumps 545-P-202A/B/C | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4028 | 23.9711 | 10610.CI.CO.M3 | 67.14 | 67.14
C116132CIUG000040 | U16 - UG GRE Pipe Installation (FW) - Part A | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3600 | 2.1437 | 10780.CI.CI.MH
C116132CIUG000070 | U16 - UG Pipe Installation (OD) - Part A | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21039 | 455.9436 | 10610.CI.UG.LM | 1051.95 | 820.521
C116132CIUG000170 | U16 - UG Pipe Installation (OD) - Part B | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3600 | 13.3495 | 10780.CI.CI.MH
C116132FPEQ000022 | U16 - Equipment Fireproofing 545-P-201A/B/C | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132PLIN000030 | U16 - Piling works NGL Surge Sphere 545-V-201B | PL | PLIN | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1361 | 2.7364 | 10610.PL.PL.UN | 30 | 30
C116132STPL000070 | U16 - Rest of Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2870 | 0 | 10610.ST.PL.TN | 35.87 | 0
C116132STPL000110 | U16 - 545-PR-101A Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4104 | 0 | 10610.ST.PL.TN | 51.3 | 0
C116132STPL000120 | U16 - 545-PR-101B Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4264 | 0 | 10610.ST.PL.TN | 53.3 | 0
C116132STPL000140 | U16 - 545-PR-103 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1011 | 0 | 10610.ST.PL.TN | 12.64 | 0
C116132STPL000150 | U16 - 545-PR-105 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1688 | 0 | 10610.ST.PL.TN | 21.11 | 0
C116132STPL000190 | U16 - 545-PR-109 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1004 | 0 | 10610.ST.PL.TN | 12.55 | 0
C116132STPR000050 | U16 - Trestle Support Erection | ST | STMS | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6196 | 17.6124 | 10610.ST.PL.TN | 103.27 | 37.4192
C116132STPR000070 | U16 - 545-PR-101B Piperack Erection | ST | STPR | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25424 | 0 | 10610.ST.PR.TN | 479.7 | 0
C116132STPR000110 | U16 - 545-PR-106 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6178 | 56.3848 | 10610.ST.PR.TN | 116.57 | 116.5725
C116132STPR000120 | U16 - 545-PR-107 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4165 | 25.6251 | 10610.ST.PR.TN | 78.58 | 78.579
C116132STPR000120 | U16 - 545-PR-107 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4165 | 25.6251 | 10610.ST.PR.TN | 78.58 | 78.579
C116133PASP000030 | U16 - Piping Supports SandBl. & Priming | PA | PASP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2478 | 0.64279 | 10610.PA.SU.TN | 0 | 0
C116134ELCO000040 | U16 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.CO.UN | 81 | 0
C116134ELEL000035 | U16 - Earthing Works | EL | ELEL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2048 | 0 | 10610.EL.ES.LM | 1167.14 | 0
C116134PRMR000030 | U16 - Motor Run | PR | PRMR | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 333 | 0 | 10780.PR.PR.MH
C116136MEHM000040 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201B | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHM000040 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201B | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHM000050 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201C | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHV000010 | U16 - NGL Surge Sphere Erection 545-V-201A (up to HT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 74934 | 2578.1334 | 10610.ME.ER.TN | 1222 | 383.6958
C116136MEHV000100 | U16 - Jib Crane Equipment Erection 545-Y-001 | ME | METC | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8400 | 0 | 10610.ME.ER.TN | 140 | 0
C116136MEPA000020 | U16 - NGL Shipping Meter Package Installation 545-ME-201 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.ME.ER.TN | 8 | 0
C116136MEPA000020 | U16 - NGL Shipping Meter Package Installation 545-ME-201 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.ME.ER.TN | 8 | 0
C116132STPL000160 | U16 - 545-PR-106 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1036 | 0 | 10610.ST.PL.TN | 12.95 | 0
C116132STPL000170 | U16 - 545-PR-107 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 698 | 0.067861 | 10610.ST.PL.TN | 8.73 | 0.64017
C116132STPL000170 | U16 - 545-PR-107 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 698 | 0.067861 | 10610.ST.PL.TN | 8.73 | 0.64017
C116132STPL000180 | U16 - 545-PR-108 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1590 | 0 | 10610.ST.PL.TN | 19.88 | 0
C116132STPL190 | U16 - 545-PLTF-001 Valve Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12 | 0 | 10610.ST.PL.TN | 0.15 | 0
C116132STPR000040 | U16 - 545-PR-104 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10764 | 61.6782 | 10610.ST.PR.TN | 203.1 | 84.0821
C116132STPR000070 | U16 - 545-PR-101B Piperack Erection | ST | STPR | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25424 | 0 | 10610.ST.PR.TN | 479.7 | 0
C116132STPR000080 | U16 - 545-PR-102 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7298 | 0 | 10610.ST.PR.TN | 137.7 | 0
C116132STPR000110 | U16 - 545-PR-106 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6178 | 56.3848 | 10610.ST.PR.TN | 116.57 | 116.5725
C116132STPR000130 | U16 - 545-PR-108 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9481 | 89.0925 | 10610.ST.PR.TN | 178.88 | 168.5025
C116132STPR000135 | U16 - 545-PR-108A Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9211 | 46.5118 | 10610.ST.PR.TN | 173.8 | 59.4609
C116132STPR000135 | U16 - 545-PR-108A Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9211 | 46.5118 | 10610.ST.PR.TN | 173.8 | 59.4609
C116132STPR000140 | U16 - 545-PR-109 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5985 | 24.3631 | 10610.ST.PR.TN | 112.93 | 62.0912
C116133PAPP000030 | U16 - Piping SandBl. & Priming | PA | PAPP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11828 | 196.813 | 10610.PA.PP.M2 | 0 | 0
C116133PASP000030 | U16 - Piping Supports SandBl. & Priming | PA | PASP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2478 | 0.64279 | 10610.PA.SU.TN | 0 | 0
C116133PAST000030 | U16 - Steel Structure Painting Touch Up | PA | PAST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21285 | 0 | 10780.PA.PA.MH
C116134ELCL000040 | U16 - Lighting Cable Laying | EL | ELCL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3456 | 0 | 10610.EL.LC.LM | 16332.41 | 0
C116134ELCL000050 | U16 - Electrical Cable Laying | EL | ELCL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16895 | 0 | 10610.EL.PL.LM | 26417.22 | 0
C116134ELCO000050 | U16 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9215 | 0 | 10610.EL.CO.UN | 702 | 0
C116134ELEL000045 | U16 - Lightning Works | EL | ELEL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2048 | 0 | 10610.EL.ES.LM | 1167.14 | 0
C116132CIPV000050 | U16 - Gravel Paving Execution | CI | CIPV2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4023 | 0 | 10610.CI.GV.M2 | 6705.25 | 0
C116132CIRD000040 | U16 - Road Early Base & Sub Base Execution | CI | CIRD1 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3500 | 0 | 10780.CI.CI.MH
C116132CIRE000070 | U16 - NGL Booster Pump Foundation Execution 545-P-201C | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1739 | 4.467 | 10610.CI.CO.M3 | 28.98 | 28.98
C116132CIRE000240 | U16 - NGL Shipping Pump Foundation Execution 545-P-202A | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CIRE000260 | U16 - NGL Shipping Pump Foundation Execution 545-P-202C | CI | CIRE1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3951 | 23.0635 | 10610.CI.CO.M3 | 65.86 | 65.86
C116132CISF000022 | U16 - Access Structure foundation for 545-PLTF-007 | CI | CIST | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4511 | 30.0603 | 10610.CI.CO.M3 | 75.18 | 75.18
C116132CIUG000060 | U16 - UG Pipe Installation (CD) - Part A | CI | CIUG2 | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3600 | 12.5334 | 10780.CI.CI.MH
C116132FPEQ000023 | U16 - Equipment Fireproofing 545-P-202A/B/C | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132FPEQ000024 | U16 - Equipment Fireproofing 545-V-201A/B | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116132PLIN000000 | U16 - Test Pile (Non-Working pile) | PL | PLIN | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 45 | 0.0029915 | 10780.PL.PL.MH
C116132PLIN000020 | U16 - Piling works NGL Surge Sphere 545-V-201A | PL | PLIN | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1361 | 2.7364 | 10610.PL.PL.UN | 30 | 30
C116132PLIN000030 | U16 - Piling works NGL Surge Sphere 545-V-201B | PL | PLIN | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1361 | 2.7364 | 10610.PL.PL.UN | 30 | 30
C116132SPDE001150 | U16 - Demolition and Relocation of UG Utilities: Earthing Grid, AOC Manholes, Pipe, Fire Trap, V-Ditch, Fire Point etc | SP | SPDE | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2160 | 6.8925 | 10610.SP.SP.M3 | 200 | 200
C116132STPL000050 | U16 - 545-PR-104 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1805 | 0 | 10610.ST.PL.TN | 22.57 | 0
C116132STPL000120 | U16 - 545-PR-101B Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4264 | 0 | 10610.ST.PL.TN | 53.3 | 0
C116132STPL000140 | U16 - 545-PR-103 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1011 | 0 | 10610.ST.PL.TN | 12.64 | 0
C116132STPL000150 | U16 - 545-PR-105 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1688 | 0 | 10610.ST.PL.TN | 21.11 | 0
C116132STPL000160 | U16 - 545-PR-106 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1036 | 0 | 10610.ST.PL.TN | 12.95 | 0
C116132STPL000180 | U16 - 545-PR-108 Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1590 | 0 | 10610.ST.PL.TN | 19.88 | 0
C117137INSL000030 | U17 - Single Pair Cable Pulling | IN | INSL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6041 | 0 | 10610.IN.SC.LM | 11525.7 | 0
C117CIMF000000010 | U17 - Fire Hydrants Foundation Execution (06 Nos) | CI | CIMF | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7985 | 10.5496 | 10780.CI.CI.MH
C118131PIRA000110 | U18 - Piping Erection on Rack | PI | PIRA | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9900 | 0 | 10780.PI.PI.MH
C118131PRHT000160 | U18 - Piping Hydrotesting | PR | PRHT | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54273 | 0 | 10610.PR.HT.DI | 6842 | 0
C118131PRRE000070 | U18 - Piping Reinstatement | PR | PRRE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43419 | 0 | 10610.PR.RE.DI | 6842 | 0
C118132CIGR000100 | U18 - Grounding Network Execution | CI | CIGR | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26511 | 0 | 10610.CI.GR.LM | 44185 | 0
C118132CIGT000180 | U18 - Steel Structure Grouting Execution | CI | CIGT | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10780.CI.CI.MH
C118132CIHE000150 | U18 - Vent Stack Foundation execution | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 392 | 0.024744 | 10610.CI.CO.M3 | 5.6 | 0
C118132CIHE000160 | U18 - Pig Trolley Foundation execution (628-Y-502) | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 733 | 0.086505 | 10610.CI.CO.M3 | 10.47 | 0
C118132CIPS000070 | U18 - Valve PIT-2 Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4703 | 0 | 10610.CI.CO.M3 | 78.39 | 0
C118132STMS000020 | U18 - Miscellaneous Steel Structures Erection - Safety Bollards | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.ST.ST.MH
C118132STMS000040 | U18 - Miscellaneous Steel Structures Erection | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1110 | 0 | 10610.ST.PL.TN | 18.5 | 0
C118132STMS000060 | U18 - Pipe Towers Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10780.ST.ST.MH
C118132STMS000100 | U18 - Passive Cooled Shelter Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2520 | 0 | 10780.ST.ST.MH
C118133PAFP000110 | U18 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 189 | 0 | 10780.PA.PA.MH
C118134ELCO000070 | U18 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0 | 10610.EL.CO.UN | 432 | 0
C118134ELEL000035 | U18 - Lightning Works | EL | ELEL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 311 | 0 | 10780.EL.EL.MH
C118134ELPL000020 | U18 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10780.EL.EL.MH
C118134MEMC000060 | U18 - Miscellaneous Electrical | EL | ELEQ2 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 175 | 0 | 10780.EL.EL.MH
C118136MEHV000020 | U18 - Jib Crane (628-Y-101) Erection | ME | METC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C118136MEHV000230 | U18 - Pig Trolley Erection (628-Y-502) | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C116137INCT000010 | U16 - Secondary Cable Trays Installation | IN | INCT2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7449 | 0 | 10610.IN.CT.LM | 740 | 0
C116137INFC000010 | U16 - Fiber Optic Gland & Conn./Testing | IN | INFC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1277 | 0 | 10610.IN.CO.UN | 490 | 0
C116137INFG000030 | U16 - Fire & Gas System Installation | IN | INFG | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1383 | 0 | 10780.IN.IN.MH
C116137INFS000030 | U16 - Fire Fighting Equipments Installation | IN | INFS | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1383 | 0 | 10610.IN.FG.UN | 1007 | 0
C116137INGC000055 | U16 - Termination at JB end and Marshalling | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1844 | 0 | 10780.IN.IN.MH
C116137INGC000060 | U16 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1844 | 0 | 10610.IN.CO.UN | 390 | 0
C116137INIP000030 | U16 - Instruments Calibration | IN | INIP | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1383 | 0 | 10780.IN.IN.MH
C116137INJB000030 | U16 - Junction Boxes & Local Panels Install | IN | INJB | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5533 | 0 | 10780.IN.IN.MH
C116137INML000030 | U16- Multi Pair Cable Pulling | IN | INML | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16600 | 0 | 10610.IN.MC.LM | 62894.26 | 0
C116137INSL000030 | U16 - Single Pair Cable Pulling | IN | INSL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13301 | 0 | 10610.IN.SC.LM | 21255.69 | 0
C116137PRLT000030 | U16 - Loops Testing | PR | PRLT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15553 | 0 | 10780.PR.PR.MH
C116FPSS000000710 | U16 - NGL Surge Sphere 545-V-201A - Fire Proofing | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116ISEQ000000710 | U16 - NGL Surge Sphere 545-V-201A - External Insulation & Cladding | IS | ISEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1795 | 0 | 10780.IS.IS.MH
C116PAEQ000000700 | U16 - NGL Surge Sphere 545-V-201B - External Blasting & Painting | PA | PAEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1720 | 0 | 10780.PA.PA.MH
C116PRBO200000010 | U16 - NGL Surge Sphere 545-V-201B - Sphere Final Inspection & Box up | PR | PRBO2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 34136 | 0 | 10780.PR.PR.MH
C116PRBO200000020 | U16 - NGL Surge Sphere 545-V-201A - Sphere Final Inspection & Box up | PR | PRBO2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33587 | 0 | 10780.PR.PR.MH
C1170PRPRWT000040 | U17 - Walkthrough | PR | PRWT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 414 | 0 | 10780.PR.PR.MH
C117131PIBB000040 | U17 - Big Bore Piping Around Equipment Erection | PI | PIBB | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.PI.BB.DI | 60 | 0
C117131PIRA000030 | U17 - Piping Erection on Rack (500-PR-101 & 500-PR-102) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0 | 10610.PI.PR.DI | 156 | 0
C117131PIRA000050 | U17 - Piping Erection on Rack (577-PR-102) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0.51179 | 10610.PI.PR.DI | 156 | 49.1197
C117131PISB000040 | U17 - Small Bore Piping Around Equipment Erection | PI | PISB | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1133 | 0 | 10780.PI.PI.MH
C116134ELHT300010 | U16 - Electrical Heat Tracing | EL | ELHT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2688 | 0 | 10780.EL.EL.MH
C116134ELPL300010 | U16 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4992 | 0 | 10780.EL.EL.MH
C116134MEMC000050 | U16 - Miscellaneous Electrical | EL | ELEQ2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1152 | 0 | 10780.EL.EL.MH
C116136MEHM000020 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202A | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116136MEHM000030 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201A | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHM000050 | U16 - NGL Booster Pump with Electrical Motor Erection 545-P-201C | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C116136MEHM000060 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202B | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116136MEHV000090 | U16 - 30" PL-952 Scrapper Launcher 545-V-503 (L) Erection | ME | MEHV | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 560 | 0 | 10610.ME.ER.TN | 14 | 0
C116136MEHV000110 | U16 - Pig Trolley Erection | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8400 | 0 | 10610.ME.ER.TN | 140 | 0
C116136MEMC000020 | U16 - Miscellaneous Erection | ME | MEMC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4500 | 0 | 10610.ME.ER.TN | 75 | 0
C116137INCT000010 | U16 - Secondary Cable Trays Installation | IN | INCT2 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7449 | 0 | 10610.IN.CT.LM | 740 | 0
C116137INCT000050 | U16 - Primary Cable Trays Installation | IN | INCT1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13301 | 0 | 10610.IN.CT.LM | 880 | 0
C116137INFC000010 | U16 - Fiber Optic Gland & Conn./Testing | IN | INFC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1277 | 0 | 10610.IN.CO.UN | 490 | 0
C116137INGC000050 | U16 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8300 | 0 | 10610.IN.CO.UN | 530 | 0
C116137INGC000065 | U16 - Termination at JB end and Instrument End | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1844 | 0 | 10610.IN.CO.UN | 390 | 0
C116137INHU000050 | U16 - Pneumatic Hook Up´s Erection | IN | INHU3 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2708 | 0 | 10780.IN.IN.MH
C116137ININ000030 | U16 - Instruments Installation | IN | ININ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4256 | 0 | 10610.IN.IN.UN | 920 | 0
C116137ININ000031 | U16 - Valve Installation | IN | ININ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4256 | 0 | 10610.IN.IN.UN | 750 | 0
C116137INIP000031 | U16 - Valve Calibration | IN | INIP | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1383 | 0 | 10780.IN.IN.MH
C116137INSL000030 | U16 - Single Pair Cable Pulling | IN | INSL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13301 | 0 | 10610.IN.SC.LM | 21255.69 | 0
C116137MEMC000050 | U16 - Miscellaneous Instrumetation | IN | ININ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4256 | 0 | 10780.IN.IN.MH
C118137ELCO000100 | U18 - Cable Glanding and Terminations | IN | INGC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3012 | 0 | 10610.IN.CO.UN | 480 | 0
C118137ELCO000110 | U18 - Installation of Field Instruments | IN | ININ | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 471 | 0 | 10780.IN.IN.MH
C118137MEMCO00090 | U18 - Miscellaneous Instrumetation | IN | ININ | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3150 | 0 | 10780.IN.IN.MH
C118CIMF000000020 | U18 - Stairways Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 832 | 0.16138 | 10610.CI.CO.M3 | 11.88 | 0
C118CIMF000000070 | U18 - Pipe Tracks Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17393 | 25.871 | 10610.CI.CO.M3 | 347.86 | 0
C118PRBO200000020 | U18 - Static Box Up | PR | PRBO1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1275 | 0 | 10780.PR.PR.MH
C119131PRHT000000 | U17 - Precommissioning | PR | PRFL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11837 | 0 | 10780.PR.PR.MH
C122131PIRA000320 | U15 - Piping Erection on Rack (577-PR-130) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000330 | U15 - Piping Erection on Rack (577-PR-135) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000340 | U15 - Piping Erection on Rack (577-PR-131) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000350 | U15 - Piping Erection on Rack (577-PR-132) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000360 | U15 - Piping Erection on Rack (577-PR-133) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000390 | U15 - Piping Erection on Rack (577-PR-137) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000420 | U15 - Piping Erection on Rack (577-PR-140) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000440 | U15 - Piping Erection on Rack (577-PR-143) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 90.9301 | 10610.PI.PR.DI | 7417.92 | 112.0106
C122131PIRA000490 | U15 - Piping Erection on Rack (577-PR-148) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122132CIPR000540 | U15 - Main Piperack Foundations Execution (577-PB-130) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4092 | 10610.CI.CO.M3 | 135.34 | 135.3407
C122132CIPR000550 | U15 - Main Piperack Foundations Execution (577-PR-135) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19410 | 556.2887 | 10610.CI.CO.M3 | 388.2 | 388.2003
C122132CIPR000585 | U15 - Main Piperack Foundations Execution (577-PB-122/577-PR-122A) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 587.1823 | 10780.CI.CI.MH
C122132CIPR000600 | U15 - Main Piperack Foundations Execution (577-PR-136) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18863 | 410.1193 | 10610.CI.CO.M3 | 377.25 | 316.89
C122132CIPR000610 | U15 - Main Piperack Foundations Execution (577-PR-137) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40805 | 2459.7624 | 10610.CI.CO.M3 | 816.1 | 816.1004
C116132STPR000060 | U16 - 545-PR-101A Piperack Erection | ST | STPR | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 24470 | 0 | 10610.ST.PR.TN | 461.7 | 0
C116132STPR000090 | U16 - 545-PR-103 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6031 | 0 | 10610.ST.PR.TN | 113.79 | 0
C116132STPR000140 | U16 - 545-PR-109 Piperack Erection | ST | STPR | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5985 | 24.3631 | 10610.ST.PR.TN | 112.93 | 62.0912
C116132STSP000030 | U16 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8283 | 0 | 10610.ST.PL.TN | 138.05 | 0
C116133PAPP000030 | U16 - Piping SandBl. & Priming | PA | PAPP | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11828 | 196.813 | 10610.PA.PP.M2 | 0 | 0
C116134ELCI300010 | U16 - Conduits Installation | EL | ELCI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1920 | 0.53367 | 10610.EL.CD.LM | 48 | 4.32
C116134ELCL000050 | U16 - Electrical Cable Laying | EL | ELCL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16895 | 0 | 10610.EL.PL.LM | 26417.22 | 0
C116134ELCP000030 | U16 - Cathodic Protection Piping | EL | ELCP | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1536 | 0 | 10780.EL.EL.MH
C116134ELEL000045 | U16 - Lightning Works | EL | ELEL | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2048 | 0 | 10610.EL.ES.LM | 1167.14 | 0
C116134ELEQ300010 | U16 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.EQ.UN | 38 | 0
C116134ELTI000040 | U16 - Lighting Cable Trays Installation | EL | ELTI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2304 | 0 | 10610.EL.CT.LM | 564.87 | 0
C116134ELTI000050 | U16 - Electrical Cable Trays Installation | EL | ELTI | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7680 | 0 | 10610.EL.CT.LM | 1049.04 | 0
C116136MEHM000020 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202A | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116136MEHM000070 | U16 - NGL Shipping Pump with Electrical Motor Erection 545-P-202C | ME | MEHM1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1560 | 0 | 10610.ME.ER.TN | 26 | 0
C116136MEHV000020 | U16 - NGL Surge Sphere Erection 545-V-201B (up to HT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 73855 | 2580.966 | 10610.ME.ER.TN | 1222 | 395.928
C116136MEHV000020 | U16 - NGL Surge Sphere Erection 545-V-201B (up to HT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 73855 | 2580.966 | 10610.ME.ER.TN | 1222 | 395.928
C116136MEHV000100 | U16 - Jib Crane Equipment Erection 545-Y-001 | ME | METC | 16 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8400 | 0 | 10610.ME.ER.TN | 140 | 0
C116136MEHV000110 | U16 - Pig Trolley Erection | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8400 | 0 | 10610.ME.ER.TN | 140 | 0
C116136MEPA000030 | U16 - Package Installation 545-ME-301 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13200 | 0 | 10610.ME.ER.TN | 220 | 0
C116136MEPA000040 | U16 - Package Installation 545-ME-302 | ME | MEPA | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13200 | 0 | 10610.ME.ER.TN | 220 | 0
C122132CIPR000610 | U15 - Main Piperack Foundations Execution (577-PR-137) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40805 | 2459.7624 | 10610.CI.CO.M3 | 816.1 | 816.1004
C122132CIPR000640 | U15 - Main Piperack Foundations Execution (577-PR-140) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12681 | 237.5507 | 10610.CI.CO.M3 | 253.61 | 253.61
C122132CIPR000680 | U15 - Main Piperack Foundations Execution (577-PR-145) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21628 | 691.0335 | 10610.CI.CO.M3 | 432.56 | 432.56
C122132CIPR000700 | U15 - Main Piperack Foundations Execution (577-PR-147) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20705 | 633.2955 | 10610.CI.CO.M3 | 414.09 | 414.09
C122132METK110080 | U12 - Lean Solvent Storage Tank Erection 537-TK-101 - Roof Erection including Appurtenances | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 4.2694 | 10610.ME.TE.TN | 17 | 17
C122132METK110170 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 5 & Compression Ring Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110240 | U12 - Lean Solvent Storage Tank Erection 537-TK-101 - Roof Platform & Staircase Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132STPR000330 | U15 - Main Piperack Erection (577-PR-141) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12453 | 110.9312 | 10610.ST.PR.TN | 234.97 | 157.4305
C122132STPR000340 | U15 - Main Piperack Erection (577-PR-142 to 577-PR-147) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 83566 | 9257.8906 | 10610.ST.PR.TN | 1576.72 | 1576.7125
C122132STPR000350 | U15 - Main Piperack Erection (577-PR-148) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10929 | 76.5273 | 10610.ST.PR.TN | 206.21 | 107.2341
C122132STPR000360 | U15 - Main Piperack Erection (577-PR-136 to 577-PR-140) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64160 | 3988.7416 | 10610.ST.PR.TN | 1210.57 | 847.3943
C122132STPR000370 | U15 - Main Piperack Erection (577-PR-129 / 577-PR-130) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19980 | 224.983 | 10610.ST.PR.TN | 376.98 | 169.6417
C122132STPR000371 | U15 - Main Piperack Erection (577-PR-128) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11299 | 0 | 10610.ST.PR.TN | 213.19 | 0
C2200PRELCL100000 | U20 - SS-520 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1702 | 0 | 10780.EL.EL.MH
C2200PRELCL100040 | U20 - SS-522 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1745 | 0 | 10780.EL.EL.MH
C2200PRELCL100050 | U20 - SS-525 -Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 78 | 0 | 10780.EL.EL.MH
C2200PRELCL100120 | U20 - OMS-014 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10780.EL.EL.MH
C2200PRINFG100010 | U20 - SS-520 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1484 | 0 | 10780.IN.IN.MH
C2200PRINFG100080 | U20 - NMCB - F&G Detection Test | IN | INFG | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C117131PRHT000040 | U17 - Piping Hydrotesting | PR | PRHT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21968 | 0 | 10610.PR.HT.DI | 2296 | 0
C117132CIMF000030 | U17 - Piping Supports Foundations Execution | CI | CIMF | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6883 | 56.2368 | 10610.CI.CO.M3 | 114.72 | 101.9742
C117132CIMF000030 | U17 - Piping Supports Foundations Execution | CI | CIMF | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6883 | 56.2368 | 10610.CI.CO.M3 | 114.72 | 101.9742
C117132CIPR000160 | U17 - SL & Receiver - Piperack 577-PR-102 Foundations Execution | CI | CIPR1 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11142 | 183.4013 | 10610.CI.CO.M3 | 222.85 | 222.85
C117132CIPR000200 | U17 - SL & Receiver - Piperack 577-PR-101 Foundations Execution | CI | CIPR2 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29643 | 1298.0857 | 10610.CI.CO.M3 | 592.85 | 592.85
C117132CISF000090 | U17 - Stairs & Small Foundations Execution (516/517/518-STR-V501) | CI | CISF | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1292 | 0.28355 | 10610.CI.CO.M3 | 21.53 | 0
C117132CIUG000090 | U17 - UG Pipe Installation (CD) | CI | CIUG2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 58460 | 3276.1231 | 10610.CI.UG.LM | 2922.99 | 2046.0926
C117132CIUG000090 | U17 - UG Pipe Installation (CD) | CI | CIUG2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 58460 | 3276.1231 | 10610.CI.UG.LM | 2922.99 | 2046.0926
C117132CIUG000100 | U17 - UG Pipe Installation (OD) | CI | CIUG2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 98359 | 12980.0852 | 10610.CI.UG.LM | 4917.97 | 4917.9464
C117132CIUP000060 | U17 - UG Piping Prefabrication | PI | PIPR | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1415 | 1.2846 | 10780.PI.PI.MH
C117132CIVE000040 | U17 - Jib Crane Foundation Execution | CI | CIVE | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4829 | 34.1517 | 10610.CI.CO.M3 | 80.48 | 80.48
C117132CIVE000050 | U17 - Foundation Execution - 36" PL-625 Scraper Receiver 516-V-501(R) | CI | CIVE | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1243 | 2.2747 | 10610.CI.CO.M3 | 17.75 | 17.75
C117132CIVE000070 | U17 - Pig Trolley Foundation Execution | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1292 | 2.3658 | 10610.CI.CO.M3 | 21.53 | 21.53
C117132STMS000020 | U17 - Miscellaneous Steel Structures Erection - Drain Pit Grating | ST | STMS | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7 | 0 | 10610.ST.PL.TN | 0.11 | 0
C117132STPL000080 | U17 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5495 | 0 | 10610.ST.PL.TN | 68.69 | 0
C117132STPR000020 | U17 - Main Piperack Erection (577-PR-101) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13917 | 286.1292 | 10610.ST.PR.TN | 262.59 | 262.594
C117132STPR000030 | U17 - Secondary Piperack Erection (500-PR-101 & 500-PR-102) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4255 | 23.6532 | 10610.ST.PR.TN | 80.28 | 79.4841
C117133PASP000040 | U17 - Piping Supports SandBl. & Priming | PA | PASP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10610.PA.SU.TN | 0 | 0
C117134ELCL000060 | U17 - Lighting Cable Laying | EL | ELCL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 265 | 0 | 10610.EL.LC.LM | 1169.06 | 0
C117134ELCL000070 | U17 - Electrical Cable Laying | EL | ELCL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1296 | 0.0097255 | 10610.EL.PL.LM | 1815.31 | 8.895
C116FPSS000000700 | U16 - NGL Surge Sphere 545-V-201B - Fire Proofing | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116PRHT000000710 | U16 - NGL Surge Sphere 545-V-201A - Hydrotesting | PR | PRHT | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7472 | 0 | 10780.PR.PR.MH
C116PRRE000000710 | U16 - NGL Surge Sphere 545-V-201B - Erection of connecting spool and Instruments Installation | PR | PRRE | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7258 | 0 | 10780.PR.PR.MH
C117131MEMC000040 | U17 - Miscellaneous Piping | PI | PISU2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16 | 0 | 10780.PI.PI.MH
C117131PIBB000040 | U17 - Big Bore Piping Around Equipment Erection | PI | PIBB | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.PI.BB.DI | 60 | 0
C117131PIRA000040 | U17 - Piping Erection on Rack (577-PR-103) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0.52574 | 10610.PI.PR.DI | 156 | 26.0005
C117131PIRA000050 | U17 - Piping Erection on Rack (577-PR-102) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0.51179 | 10610.PI.PR.DI | 156 | 49.1197
C117131PIRA000160 | U17 - Piping Erection on Rack (577-PR-101) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 1.4983 | 10610.PI.PR.DI | 156 | 78
C117131PIUG000040 | U17 - Piping Erection UG | PI | PIUG | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 74 | 0.00069571 | 10780.PI.PI.MH
C117131PRBO000040 | U17 - Static Box Up | PR | PRBO1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2181 | 0 | 10780.PR.PR.MH
C117131PRFL000040 | U17 - Piping Flushing/Blowing | PR | PRFL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8038 | 0 | 10610.PR.FL.DI | 2296 | 0
C117131PRRE000020 | U17 - Loop Testing | PR | PRLT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7746 | 0 | 10780.PR.PR.MH
C117131PRRE000030 | U17 - Piping Reinstatement | PR | PRRE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 17574 | 0 | 10610.PR.RE.DI | 2296 | 0
C117132CIGT000070 | U17 - Steel Structure Grouting Execution | CI | CIGT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 800 | 0.27419 | 10780.CI.CI.MH
C117132CIPR000160 | U17 - SL & Receiver - Piperack 577-PR-102 Foundations Execution | CI | CIPR1 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11142 | 183.4013 | 10610.CI.CO.M3 | 222.85 | 222.85
C117132CIPR000180 | U17 - SL & Receiver - Piperack 577-PR-103 Foundations Execution | CI | CIPR1 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11142 | 183.4013 | 10610.CI.CO.M3 | 222.85 | 222.85
C117132CIPR000180 | U17 - SL & Receiver - Piperack 577-PR-103 Foundations Execution | CI | CIPR1 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11142 | 183.4013 | 10610.CI.CO.M3 | 222.85 | 222.85
C117132CIPR000210 | U17 - SL & Receiver - Trestle Support Foundations Execution | CI | CIPR2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5877 | 51.0218 | 10610.CI.CO.M3 | 97.95 | 97.95
C117132CIPV000070 | U17 - Concrete Paving Execution | CI | CIPV1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1345 | 0.34598 | 10610.CI.PV.M2 | 747 | 14.94
C117132CIUG000160 | U17 - UG Civil Works | CI | CIUG1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7200 | 59.7346 | 10780.CI.CI.MH
C117132CIVE000020 | U17 - Foundation Execution - (48" PL-627) Residue Gas Scrapper Receiver 518-V-501(R) | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C116137INCT000050 | U16 - Primary Cable Trays Installation | IN | INCT1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13301 | 0 | 10610.IN.CT.LM | 880 | 0
C116137INFO000010 | U16 - Fiber Optic Cable Pulling | IN | INFO | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1809 | 0 | 10610.IN.FO.LM | 107612 | 0
C116137INFS000030 | U16 - Fire Fighting Equipments Installation | IN | INFS | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1383 | 0 | 10610.IN.FG.UN | 1007 | 0
C116137INGC000060 | U16 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1844 | 0 | 10610.IN.CO.UN | 390 | 0
C116137INHU000060 | U16 - Process Hook Up´s Erection | IN | INHU1 | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5853 | 0 | 10780.IN.IN.MH
C116137ININ000030 | U16 - Instruments Installation | IN | ININ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4256 | 0 | 10610.IN.IN.UN | 920 | 0
C116137ININ000031 | U16 - Valve Installation | IN | ININ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4256 | 0 | 10610.IN.IN.UN | 750 | 0
C116137INML000030 | U16- Multi Pair Cable Pulling | IN | INML | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16600 | 0 | 10610.IN.MC.LM | 62894.26 | 0
C116FPSS000000710 | U16 - NGL Surge Sphere 545-V-201A - Fire Proofing | FP | FPEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 830 | 0 | 10610.FP.EQ.M2 | 143 | 0
C116ISEQ000000700 | U16 - NGL Surge Sphere 545-V-201B - External Insulation & Cladding | IS | ISEQ | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1683 | 0 | 10780.IS.IS.MH
C1170PRPRPL000040 | U17 - Punch List | PR | PRPL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 967 | 0 | 10780.PR.PR.MH
C117131PIPR000040 | U17 - Piping Prefabrication | PI | PIPR | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2376 | 6.561 | 10610.PI.FB.DI | 594 | 382.6649
C117131PIRA000040 | U17 - Piping Erection on Rack (577-PR-103) | PI | PIRA | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1404 | 0.52574 | 10610.PI.PR.DI | 156 | 26.0005
C117131PISU000070 | U17 - Piping Supports Prefabrication | PI | PISU1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 208000 | 1320.4543 | 10610.PI.PU.TN | 0 | 0
C117131PRFL000040 | U17 - Piping Flushing/Blowing | PR | PRFL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8038 | 0 | 10610.PR.FL.DI | 2296 | 0
C117131PRHT000040 | U17 - Piping Hydrotesting | PR | PRHT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21968 | 0 | 10610.PR.HT.DI | 2296 | 0
C117132CIGT000060 | U17 - Equipment Grouting Execution | CI | CIGT | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 160 | 0.013615 | 10780.CI.CI.MH
C117132CIPR000170 | U17 - SL & Receiver - Piperack 500-PR-101 & 500-PR-102 Foundations Execution | CI | CIPR2 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4463 | 29.4239 | 10610.CI.CO.M3 | 74.38 | 74.38
C117132CIPR000170 | U17 - SL & Receiver - Piperack 500-PR-101 & 500-PR-102 Foundations Execution | CI | CIPR2 | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4463 | 29.4239 | 10610.CI.CO.M3 | 74.38 | 74.38
C117132CIVE000020 | U17 - Foundation Execution - (48" PL-627) Residue Gas Scrapper Receiver 518-V-501(R) | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C117132CIVE000050 | U17 - Foundation Execution - 36" PL-625 Scraper Receiver 516-V-501(R) | CI | CIVE | 17 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1243 | 2.2747 | 10610.CI.CO.M3 | 17.75 | 17.75
C2200PRINFG100100 | U20 - OMS-013 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 359 | 0 | 10780.IN.IN.MH
C2200PRLT00000220 | U20 - OMS-013 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 294 | 0 | 10780.PR.PR.MH
C2200PRLT00000245 | U20 - SS-516 - Loops Testing for Transformer #B | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 449 | 0 | 10780.PR.PR.MH
C2200PRLT00000280 | U20 - SS-501 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000320 | U20 - SS-515 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000420 | U20 - IES-504 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2767 | 0 | 10780.PR.PR.MH
C2200PRLT00000430 | U20 - IES-505 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2724 | 0 | 10780.PR.PR.MH
C2200PRPRPL000150 | U20 - SS-523 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89 | 0 | 10780.PR.PR.MH
C2200PRPRPL000170 | U20 - SS-524 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 158 | 0 | 10780.PR.PR.MH
C2200PRPRPL000180 | U20 - SS-525 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12 | 0 | 10780.PR.PR.MH
C2200PRPRPL000190 | U20 - SS-520 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 245 | 0 | 10780.PR.PR.MH
C2200PRPRPL000230 | U20 - IES-513 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 864 | 0 | 10780.PR.PR.MH
C2200PRPRPL000240 | U20 - IES-514 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 865 | 0 | 10780.PR.PR.MH
C2200PRPRPL000290 | U20 - SS-516 - Punch List Clearance for Transformer #A | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10780.PR.PR.MH
C2200PRPRWT000140 | U20 - OMS-013 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10780.PR.PR.MH
C2200PRPRWT000210 | U20 - SS-523 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38 | 0 | 10780.PR.PR.MH
C2200PRPRWT000260 | U20 - SS-522 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 107 | 0 | 10780.PR.PR.MH
C2200PRPRWT000275 | U20 - SS-516- Walkthrough for Transformer #B | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41 | 0 | 10780.PR.PR.MH
C220132BUSS000545 | U20 - SS-503 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 332 | 0.16283 | 10780.BU.BU.MH
C220132BUSS000550 | U20 - SS-504 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7195 | 0 | 10780.BU.BU.MH
C220132BUSS000590 | U20 - SS-516 - Demolition of Civil Compounds related to existing Transformers | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16965 | 0 | 10780.BU.BU.MH
C220132BUSS000605 | U20 - IES-518 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C117132CIVE000060 | U17 - Foundation Execution - Residue (36" PL-626) Gas Scrapper Receiver 517-V-501(R) | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1243 | 2.272 | 10610.CI.CO.M3 | 17.75 | 17.75
C117132STPR000020 | U17 - Main Piperack Erection (577-PR-101) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13917 | 286.1292 | 10610.ST.PR.TN | 262.59 | 262.594
C117132STPR000060 | U17 - Main Piperack Erection (577-PR-103) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31823 | 1496.0691 | 10610.ST.PR.TN | 600.44 | 600.4473
C117132STPR000070 | U17 - Main Piperack Erection (577-PR-102) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13377 | 264.3569 | 10610.ST.PR.TN | 252.4 | 252.4047
C117132STSP000040 | U17 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 305 | 0 | 10610.ST.PL.TN | 5.09 | 0
C117133PAFP000040 | U17 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 408 | 0 | 10780.PA.PA.MH
C117133PAST000040 | U17 - Steel Structure Painting Touch Up | PA | PAST | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 62440 | 0 | 10780.PA.PA.MH
C117134ELCL000070 | U17 - Electrical Cable Laying | EL | ELCL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1296 | 0.0097255 | 10610.EL.PL.LM | 1815.31 | 8.895
C117134ELCO000070 | U17 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 707 | 0 | 10610.EL.CO.UN | 675 | 0
C117134ELEL000045 | U17 - Earthing Works | EL | ELEL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 157 | 0.0010929 | 10780.EL.EL.MH
C117134ELPL000030 | U17 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 383 | 0 | 10780.EL.EL.MH
C117136MEVV000020 | U17 - Pig Trolley (518-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 14 | 0
C117136MEVV000090 | U17 - Pig Trolley (542-V-503) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C117136MEVV000120 | U17 - Jib Crane (542-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000130 | U17 - Fire Hydrants Erection FH-03-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C117136MEVV000140 | U17 - Fire Hydrants Erection FH-04-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000430 | U17 - 36" PL-626 Scraper Receiver 517-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C117137ELCO000050 | U17 - Multi Pair Cable Pulling | IN | INML | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7539 | 18.0531 | 10610.IN.MC.LM | 26894.41 | 6723.6025
C117137INHU000050 | U17 - Process Hook Up´s Erection | IN | INHU1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2658 | 0 | 10780.IN.IN.MH
C117137INSL000030 | U17 - Single Pair Cable Pulling | IN | INSL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6041 | 0 | 10610.IN.SC.LM | 11525.7 | 0
C117137MEMC000050 | U17 - Miscellaneous Instrumetation | IN | ININ | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1933 | 0 | 10780.IN.IN.MH
C117134ELCO000060 | U17 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10610.EL.CO.UN | 391 | 0
C117134ELEQ000010 | U17 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10780.EL.EL.MH
C117134ELGR000040 | U17 - Grounding Installation | EL | ELEL | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 157 | 0 | 10780.EL.EL.MH
C117134ELTI000060 | U17 - Lighting Cable Trays Installation | EL | ELTI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10610.EL.CT.LM | 842.84 | 0
C117136MEVV000030 | U17 - 48" PL-627 Scraper Receiver 518-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C117136MEVV000070 | U17 - Pig Trolley (516-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C117136MEVV000160 | U17 - Fire Hydrants Erection FH-XX-XXX | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C117136MEVV000180 | U17 - Jib Crane (518-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000420 | U17 - 36" PL-625 Scraper Receiver 516-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C117136MEVV000440 | U17 - 56" PL-628 Pipeline Scrapper Launcher 542-V-503 (L) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C117137ELCO000060 | U17 - Installation of Field Instruments | IN | ININ | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1933 | 0 | 10780.IN.IN.MH
C117137ELCO000061 | U17 - Installation of valve | IN | ININ | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1933 | 0 | 10780.IN.IN.MH
C117137INAI000020 | U17- Analyzers Equipment Installation | IN | INAI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1305 | 0 | 10610.IN.AI.UN | 1 | 0
C117137INCT000050 | U17 - Primary Cable Trays Installation | IN | INCT1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6041 | 0 | 10610.IN.CT.LM | 680 | 0
C117137INCT000060 | U17- Secondary Cable Trays Installation | IN | INCT2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3383 | 0 | 10610.IN.CT.LM | 510 | 0
C117137INFC000020 | U17 - Fiber Optic Gland & Conn./Testing | IN | INFC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 580 | 0 | 10610.IN.CO.UN | 330 | 0
C117137INFS000020 | U17 - Fire Fighting Equipments Installation | IN | INFS | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 628 | 0 | 10780.IN.IN.MH
C117137INGC000020 | U17 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2513 | 0 | 10610.IN.CO.UN | 420 | 0
C117137INGC000050 | U17 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3770 | 0 | 10610.IN.CO.UN | 530 | 0
C117137INIP000020 | U17 - Instruments Calibration | IN | INIP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 628 | 0 | 10780.IN.IN.MH
C117137INIP000021 | U17 - Valve Calibration | IN | INIP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 628 | 0 | 10780.IN.IN.MH
C117132CIVE000030 | U17 - Foundation Execution 56" PL-628 Pipeline Scrapper Launcher 542-V-503(L) | CI | CIVE | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11542 | 195.3801 | 10610.CI.CO.M3 | 230.83 | 230.8301
C117132CIVE000060 | U17 - Foundation Execution - Residue (36" PL-626) Gas Scrapper Receiver 517-V-501(R) | CI | CIVE | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1243 | 2.272 | 10610.CI.CO.M3 | 17.75 | 17.75
C117132STMS000030 | U17 - Miscellaneous Steel Structures Erection - Safety Bollards | ST | STMS | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 65 | 0 | 10610.ST.PL.TN | 1.08 | 0
C117132STPR000030 | U17 - Secondary Piperack Erection (500-PR-101 & 500-PR-102) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4255 | 23.6532 | 10610.ST.PR.TN | 80.28 | 79.4841
C117132STPR000070 | U17 - Main Piperack Erection (577-PR-102) | ST | STPR | 17 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13377 | 264.3569 | 10610.ST.PR.TN | 252.4 | 252.4047
C117133PAPP000040 | U17 - Piping SandBl. & Priming | PA | PAPP | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3262 | 6.4908 | 10610.PA.PP.M2 | 1631 | 8597.131
C117134ELCI000030 | U17 - Conduits Installation | EL | ELCI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 147 | 0 | 10780.EL.EL.MH
C117134ELCO000060 | U17 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10610.EL.CO.UN | 391 | 0
C117134ELTI000070 | U17 - Electrical Cable Trays Installation | EL | ELTI | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 589 | 0 | 10610.EL.CT.LM | 1565.28 | 0
C117136MEVV000080 | U17 - Pig Trolley (517-V-501) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C117136MEVV000090 | U17 - Pig Trolley (542-V-503) Erection | ME | MEPA | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 18 | 0
C117136MEVV000100 | U17 - Jib Crane (516-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000110 | U17 - Jib Crane (517-Y-001) Erection | ME | METC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C117136MEVV000150 | U17 - Fire Hydrants Erection FH-05-001 | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000160 | U17 - Fire Hydrants Erection FH-XX-XXX | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3600 | 0 | 10610.ME.ER.TN | 60 | 0
C117136MEVV000170 | U17 - Fire Hydrants Erection FH-YY-YYY | ME | MEMC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C117136MEVV000420 | U17 - 36" PL-625 Scraper Receiver 516-V-501 (R) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C117136MEVV000440 | U17 - 56" PL-628 Pipeline Scrapper Launcher 542-V-503 (L) Erection | ME | MEHV | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C117137INCT000050 | U17 - Primary Cable Trays Installation | IN | INCT1 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6041 | 0 | 10610.IN.CT.LM | 680 | 0
C117137INCT000060 | U17- Secondary Cable Trays Installation | IN | INCT2 | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3383 | 0 | 10610.IN.CT.LM | 510 | 0
C220132BUSS000630 | U20 - IES-509 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 0 | 10780.BU.BU.MH
C220132BUSS000635 | U20 - IES-509 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSS000645 | U20 - IES-500 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 204 | 0 | 10780.BU.BU.MH
C220132BUSS000675 | U20 - OMS-008 - Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSS000680 | U20 - MB - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 60.9336 | 10780.BU.BU.MH
C220132BUSS000695 | U20 - MB - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSS000750 | U20 - SS-512 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8394 | 10.2007 | 10780.BU.BU.MH
C220132BUSS000755 | U20 - SS-512 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 441 | 0 | 10780.BU.BU.MH
C220132BUSSAR100050 | U20 - SS-521 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 0 | 10780.BU.BU.MH
C220132BUSSAR100090 | U20 - SS-521 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7933 | 0 | 10780.BU.BU.MH
C220132BUSSAR100160 | U20 - SS-524 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5017 | 37.181 | 10780.BU.BU.MH
C220132BUSSAR100170 | U20 - SS-523 - External Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR100260 | U20 - IES-514 - External Wall Finish | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5340 | 0 | 10780.BU.BU.MH
C220132BUSSAR100270 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19657 | 342.4866 | 10610.BU.CO.M3 | 50 | 30
C220132BUSSAR100300 | U20 - SS-526 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10610.BU.AR.M2 | 31 | 0
C220132BUSSAR100313 | U20 - SS-521-CFP1 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3461 | 16.2824 | 10780.BU.BU.MH
C220132BUSSAR100400 | U20 - SS-522 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11490 | 0 | 10610.BU.AR.M2 | 445 | 0
C220132BUSSAR100410 | U20 - SS-520 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 47.7692 | 10780.BU.BU.MH
C220132BUSSAR100413 | U20 - SS-522-CFP1 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4596 | 23.0911 | 10780.BU.BU.MH
C220132BUSSAR100480 | U20 - NMCB - Architectural Works for Transformer Room | BU | BUARPT | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 0 | 10780.BU.BU.MH
C117CISF000000010 | U17 - Stairs & Small Foundations Execution (542-STR-V503) | CI | CISF | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 44286 | 2653.9625 | 10610.CI.CO.M3 | 885.72 | 885.72
C118000SPVC000030 | U18 - Perimeter Fence and Gates Erection | SP | SPVC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1100 | 0 | 10780.SP.SP.MH
C1180PRPRPL000120 | U18 - Punch List | PR | PRPL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1217 | 0 | 10780.PR.PR.MH
C1180PRPRWT000110 | U18 - Walkthrough | PR | PRWT | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 522 | 0 | 10780.PR.PR.MH
C118131ISPI000110 | U18 - Piping Insulation | IS | ISPI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2993 | 0 | 10610.IS.PI.M2 | 1091 | 0
C118131MEMC000110 | U18 - Miscellaneous Piping | PI | PISU2 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32 | 0 | 10780.PI.PI.MH
C118131PIBB000130 | U18 - Big Bore Piping A/Equip. Erection | PI | PIBB | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5500 | 0 | 10780.PI.PI.MH
C118131PIPR000100 | U18 - Piping Prefabrication | PI | PIPR | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30564 | 876.4641 | 10610.PI.FB.DI | 7641.09 | 4585.3636
C118131PIPR000100 | U18 - Piping Prefabrication | PI | PIPR | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30564 | 876.4641 | 10610.PI.FB.DI | 7641.09 | 4585.3636
C118131PIUG000130 | U18 - Piping Erection UG | PI | PIUG | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2112 | 0 | 10610.PI.UG.DI | 1408 | 0
C118131PRFL000100 | U18 - Piping Flushing/Blowing | PR | PRFL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23777 | 0 | 10610.PR.FL.DI | 6842 | 0
C118131PRHT000160 | U18 - Piping Hydrotesting | PR | PRHT | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54273 | 0 | 10610.PR.HT.DI | 6842 | 0
C118132CIMF000090 | U18 - Passive Cooled Shelter Foundation Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 204 | 0.054102 | 10780.CI.CI.MH
C118132SPVC000040 | U18 - Site Preparation - Vibrocompaction | SP | SPVC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 840 | 1.0366 | 10780.SP.SP.MH
C118132STMS000040 | U18 - Miscellaneous Steel Structures Erection | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1110 | 0 | 10610.ST.PL.TN | 18.5 | 0
C118133PAPP000100 | U18 - Piping Sand Bl. & Priming | PA | PAPP | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1514 | 0.89028 | 10780.PA.PA.MH
C118133PASP000110 | U18 - Piping Supports Sand Bl. & Priming | PA | PASP | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4 | 0 | 10780.PA.PA.MH
C118134ELCL000050 | U18 - Lighting Cable Laying | EL | ELCL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 525 | 0 | 10610.EL.LC.LM | 1980.51 | 0
C118134ELCL000060 | U18 - Electrical Cable Laying | EL | ELCL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2568 | 0 | 10610.EL.PL.LM | 4284.64 | 0
C118134ELCO000070 | U18 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0 | 10610.EL.CO.UN | 432 | 0
C118134ELCO000080 | U18 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.EL.CO.UN | 999 | 0
C118134ELEL000025 | U18 - Earthing Works | EL | ELEL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 311 | 0 | 10780.EL.EL.MH
C117137INJB000020 | U17 - Junction Boxes & Local Panels Install. | IN | INJB | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2513 | 0 | 10780.IN.IN.MH
C117137INSL000020 | U17 - Fiber Optic Cable Pulling | IN | INFO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 822 | 0 | 10610.IN.FO.LM | 580 | 0
C117CISF000000010 | U17 - Stairs & Small Foundations Execution (542-STR-V503) | CI | CISF | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 44286 | 2653.9625 | 10610.CI.CO.M3 | 885.72 | 885.72
C118000SPVC000020 | U18 - Fence Poles Erection | SP | SPVC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 172 | 0 | 10780.SP.SP.MH
C118131PIUG000130 | U18 - Piping Erection UG | PI | PIUG | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2112 | 0 | 10610.PI.UG.DI | 1408 | 0
C118131PRRE000070 | U18 - Piping Reinstatement | PR | PRRE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43419 | 0 | 10610.PR.RE.DI | 6842 | 0
C118132CIGR000100 | U18 - Grounding Network Execution | CI | CIGR | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26511 | 0 | 10610.CI.GR.LM | 44185 | 0
C118132CIHE000140 | U18 - Scrapper Receiver 628-V-501 (R) Foundation execution | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2016 | 5.8461 | 10610.CI.CO.M3 | 33.6 | 33.6
C118132CIPS000090 | U18 - Drain PIT Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 403 | 0 | 10610.CI.CO.M3 | 5.76 | 0
C118132SPSP000070 | U18 - Site Preparation | SP | SPSP | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 840 | 1.0424 | 10780.SP.SP.MH
C118132STMS000030 | U18 - Stairways 542-V-502 Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.ST.ST.MH
C118132STMS000050 | U18 - Pipe Bridge Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7680 | 0 | 10610.ST.ER.TN | 128 | 0
C118132STMS000070 | U18 - Fire Point Shelter Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10780.ST.ST.MH
C118133PAST000110 | U18 - Steel Structure Painting Touch Up | PA | PAST | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20410 | 0 | 10780.PA.PA.MH
C118134ELCI000020 | U18 - Solar Panel & Battery System Installation | EL | ELEQ1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 876 | 0 | 10780.EL.EL.MH
C118134ELCI000030 | U18 - Conduits Installation | EL | ELCI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 292 | 0 | 10780.EL.EL.MH
C118134ELCL000050 | U18 - Lighting Cable Laying | EL | ELCL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 525 | 0 | 10610.EL.LC.LM | 1980.51 | 0
C118134ELCL000060 | U18 - Electrical Cable Laying | EL | ELCL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2568 | 0 | 10610.EL.PL.LM | 4284.64 | 0
C118134ELTI000060 | U18 - Electrical Cable Trays Installation | EL | ELTI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1167 | 0 | 10610.EL.CT.LM | 69.29 | 0
C118136MEHV000210 | U18 - 56" Sale Gas Scrapper Receiver 628-V-501 (R) Erection | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C118136MEHV000220 | U18 - Vent Stack Erection | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6400 | 0 | 10610.ME.ER.TN | 160 | 0
C117137INFC000020 | U17 - Fiber Optic Gland & Conn./Testing | IN | INFC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 580 | 0 | 10610.IN.CO.UN | 330 | 0
C117137INGC000020 | U17 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2513 | 0 | 10610.IN.CO.UN | 420 | 0
C117137INSL000020 | U17 - Fiber Optic Cable Pulling | IN | INFO | 17 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 822 | 0 | 10610.IN.FO.LM | 580 | 0
C118131ISPI000110 | U18 - Piping Insulation | IS | ISPI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2993 | 0 | 10610.IS.PI.M2 | 1091 | 0
C118131PISB000101 | U18 - Small Bore Piping A/Equip. Erection | PI | PISB | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10780.PI.PI.MH
C118131PISU000210 | U18 - Piping Supports Prefabrication | PI | PISU1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 158600 | 26568.1052 | 10780.PI.PI.MH
C118131PISU000220 | U18 - Piping Supports Erection | PI | PISU2 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 333000 | 0 | 10780.PI.PI.MH
C118131PRFL000100 | U18 - Piping Flushing/Blowing | PR | PRFL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23777 | 0 | 10610.PR.FL.DI | 6842 | 0
C118131PRRE000020 | U18 - Loop Testing | PR | PRLT | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10999 | 0 | 10780.PR.PR.MH
C118132CIHE000140 | U18 - Scrapper Receiver 628-V-501 (R) Foundation execution | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2016 | 5.8461 | 10610.CI.CO.M3 | 33.6 | 33.6
C118132CIHE000150 | U18 - Vent Stack Foundation execution | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 392 | 0.024744 | 10610.CI.CO.M3 | 5.6 | 0
C118132CIHE000160 | U18 - Pig Trolley Foundation execution (628-Y-502) | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 733 | 0.086505 | 10610.CI.CO.M3 | 10.47 | 0
C118132CIPS000070 | U18 - Valve PIT-2 Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4703 | 0 | 10610.CI.CO.M3 | 78.39 | 0
C118132CIPS000080 | U18 - Valve PIT-1 Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11521 | 0 | 10610.CI.CO.M3 | 192.02 | 0
C118132CIPS000080 | U18 - Valve PIT-1 Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11521 | 0 | 10610.CI.CO.M3 | 192.02 | 0
C118132CIPS000090 | U18 - Drain PIT Construction | CI | CIPS1 | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 403 | 0 | 10610.CI.CO.M3 | 5.76 | 0
C118132STMS000050 | U18 - Pipe Bridge Installation | ST | STMS | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7680 | 0 | 10610.ST.ER.TN | 128 | 0
C118134ELCO000080 | U18 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.EL.CO.UN | 999 | 0
C118134ELGR000020 | U18 - Grounding Installation | EL | ELEL | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 311 | 0 | 10780.EL.EL.MH
C118134ELTI000050 | U18 - Lighting Cable Trays Installation | EL | ELTI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0 | 10610.EL.CT.LM | 37.31 | 0
C118134ELTI000060 | U18 - Electrical Cable Trays Installation | EL | ELTI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1167 | 0 | 10610.EL.CT.LM | 69.29 | 0
C220132BUSSAR100510 | U20 - SS-522 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11490 | 0 | 10780.BU.BU.MH
C220132BUSSAR100512 | U20 - SS-524-CFP1 - Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2394 | 8.4677 | 10780.BU.BU.MH
C220132BUSSAR100620 | U20 - SS-526 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR100660 | U20 - SS-521 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 0 | 10780.BU.BU.MH
C220132BUSSAR100690 | U20 - SS-525 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 586 | 0 | 10780.BU.BU.MH
C220132BUSSAR100710 | U20 - SS-525 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100770 | U20 - NMCB - Concrete Cast-in Situ & Precast for Parapet Wall | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7446 | 0 | 10610.BU.CO.M3 | 29 | 0
C220132BUSSAR100780 | U20 - NMCB - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0.038291 | 10610.CI.ET.M3 | 180 | 63
C220132BUSSAR100810 | U20 - IES-514 - Internal Wall Finish | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6866 | 0 | 10780.BU.BU.MH
C220132BUSSAR100820 | U20 - SS-526 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10780.BU.BU.MH
C220132BUSSAR100850 | U20 - SS-524 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 0 | 10780.BU.BU.MH
C220132BUSSAR100880 | U20 - SS-524 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 0 | 10780.BU.BU.MH
C220132BUSSAR100890 | U20 - IES-514 - Raised Floor Installation | BU | BUARRA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6866 | 0 | 10780.BU.BU.MH
C220132BUSSAR100900 | U20 - SS-523 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR100940 | U20 - OMS-013 - External Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR100970 | U20 - SS-520 - Roof Waterproofing (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 25.8212 | 10780.BU.BU.MH
C220132BUSSAR101030 | U20 - NMCB - External Painting | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101040 | U20 - SS-520 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR101100 | U20 - SS-526 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR101110 | U20 - OMS-014 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.AR.M2 | 24 | 0
C220132BUSSAR101200 | U20 - IES-514 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2746 | 0 | 10780.BU.BU.MH
C220132BUSSAR101210 | U20 - IES-514 - Install False Ceiling | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5340 | 0 | 10780.BU.BU.MH
C220132BUSSAR101240 | U20 - NMCB - Internal Painting | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101320 | U20 - SS-523 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101330 | U20 - OMS-014 - Internal Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101370 | U20 - IES-514 - Internal Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6866 | 0 | 10780.BU.BU.MH
C220132BUSSAR101390 | U20 - OMS-015 - External Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101410 | U20 - NMCB - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 13.2678 | 10780.BU.BU.MH
C220132BUSSAR101480 | U20 - OMS-014 - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101490 | U20 - OMS-013 - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10780.BU.BU.MH
C220132BUSSAR101510 | U20 - OMS-015 - Install False Ceiling | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101550 | U20 - IES-514 - Install Rockwool Insulation | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 0 | 10780.BU.BU.MH
C220132BUSSAR101600 | U20 - OMS-015 - Install Rockwool Insulation | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101710 | U20 - OMS-015 - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101790 | U20 - IES-513 - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2226 | 0 | 10780.BU.BU.MH
C220132BUSSAR101810 | U20 - OMS-015 - Install Hand Railing | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSAR101830 | U20 - OMS-015 - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101890 | U20 - OMS-014 - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSSAR101900 | U20 - OMS-014 - Waterproofing Works | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0 | 10780.BU.BU.MH
C220132BUSSCS100030 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27139 | 1088.08 | 10610.BU.CO.M3 | 329.33 | 329.33
C220132BUSSCS100070 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Internal Columns (Elect. Subst.) GF to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 110.6335 | 10610.BU.CO.M3 | 65 | 65
C118137ELCO000011 | U18 - Installation of Valves | IN | ININ | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 470 | 0 | 10780.IN.IN.MH
C118137ELCO000090 | U18 - Multi Pair Cable Pulling | IN | INML | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5647 | 0 | 10780.IN.IN.MH
C118CIHE000000010 | U18 - Jib Crane Foundation Execution (628-Y-101) | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.0023 | 10610.CI.CO.M3 | 20.13 | 20.13
C118CIMF000000020 | U18 - Stairways Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 832 | 0.16138 | 10610.CI.CO.M3 | 11.88 | 0
C118CIMF000000040 | U18 - Pipe Towers Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40086 | 1399.2913 | 10610.CI.CO.M3 | 801.71 | 400.863
C118CIMF000000050 | U18 - Pipe Supports Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1319 | 1.734 | 10610.CI.CO.M3 | 21.98 | 13.19
C118CIMF000000050 | U18 - Pipe Supports Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1319 | 1.734 | 10610.CI.CO.M3 | 21.98 | 13.19
C118CIMF000000070 | U18 - Pipe Tracks Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17393 | 25.871 | 10610.CI.CO.M3 | 347.86 | 0
C122131PIRA000310 | U15 - Piping Erection on Rack (577-PR-128 & 129) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000330 | U15 - Piping Erection on Rack (577-PR-135) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000340 | U15 - Piping Erection on Rack (577-PR-131) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000350 | U15 - Piping Erection on Rack (577-PR-132) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000360 | U15 - Piping Erection on Rack (577-PR-133) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000400 | U15 - Piping Erection on Rack (577-PR-138) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000410 | U15 - Piping Erection on Rack (577-PR-139) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000430 | U15 - Piping Erection on Rack (577-PR-141) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 90.9301 | 10610.PI.PR.DI | 7417.92 | 112.0106
C122131PIRA000450 | U15 - Piping Erection on Rack (577-PR-144) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 172.1154 | 10610.PI.PR.DI | 7417.92 | 212.0042
C122131PIRA000460 | U15 - Piping Erection on Rack (577-PR-145) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 30.0247 | 10610.PI.PR.DI | 7417.92 | 37.0154
C122131PIRA000470 | U15 - Piping Erection on Rack (577-PR-146) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000480 | U15 - Piping Erection on Rack (577-PR-147) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000490 | U15 - Piping Erection on Rack (577-PR-148) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C118137ELCO000100 | U18 - Cable Glanding and Terminations | IN | INGC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3012 | 0 | 10610.IN.CO.UN | 480 | 0
C118CIMF000000030 | U18 - Pipe Bridge Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44103 | 928.5245 | 10610.CI.CO.M3 | 882.06 | 215.3108
C118CIMF000000030 | U18 - Pipe Bridge Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44103 | 928.5245 | 10610.CI.CO.M3 | 882.06 | 215.3108
C118CIMF000000040 | U18 - Pipe Towers Foundations Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40086 | 1399.2913 | 10610.CI.CO.M3 | 801.71 | 400.863
C118CIMF000000060 | U18 - Wind Sock Mast Foundation Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82 | 0.0010456 | 10780.CI.CI.MH
C118CIMF000000080 | U18 - Solar Panel System Foundation | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2942 | 12.3662 | 10610.CI.CO.M3 | 49.04 | 49.04
C118CIMF000000080 | U18 - Solar Panel System Foundation | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2942 | 12.3662 | 10610.CI.CO.M3 | 49.04 | 49.04
C122131PIRA000310 | U15 - Piping Erection on Rack (577-PR-128 & 129) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000370 | U15 - Piping Erection on Rack (577-PR-134) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000380 | U15 - Piping Erection on Rack (577-PR-136) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000410 | U15 - Piping Erection on Rack (577-PR-139) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000450 | U15 - Piping Erection on Rack (577-PR-144) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 172.1154 | 10610.PI.PR.DI | 7417.92 | 212.0042
C122131PIRA000480 | U15 - Piping Erection on Rack (577-PR-147) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122132CIPR000530 | U15 - Main Piperack Foundations Execution (577-PB-129) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38449 | 1917.721 | 10610.CI.CO.M3 | 768.98 | 713.6122
C122132CIPR000530 | U15 - Main Piperack Foundations Execution (577-PB-129) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38449 | 1917.721 | 10610.CI.CO.M3 | 768.98 | 713.6122
C122132CIPR000570 | U15 - Main Piperack Foundations Execution (577-PB-132) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15518 | 355.7443 | 10610.CI.CO.M3 | 310.36 | 310.3599
C122132CIPR000580 | U15 - Main Piperack Foundations Execution (577-PR-133) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22457 | 745.0233 | 10610.CI.CO.M3 | 449.14 | 449.14
C122132CIPR000590 | U15 - Main Piperack Foundations Execution (577-PR-134) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37366 | 2062.6219 | 10610.CI.CO.M3 | 747.32 | 747.3202
C122132CIPR000620 | U15 - Main Piperack Foundations Execution (577-PR-138) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13740 | 278.8944 | 10610.CI.CO.M3 | 274.8 | 274.8
C122132CIPR000640 | U15 - Main Piperack Foundations Execution (577-PR-140) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12681 | 237.5507 | 10610.CI.CO.M3 | 253.61 | 253.61
C118134ELTI000050 | U18 - Lighting Cable Trays Installation | EL | ELTI | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0 | 10610.EL.CT.LM | 37.31 | 0
C118136MEHV000020 | U18 - Jib Crane (628-Y-101) Erection | ME | METC | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C118136MEHV000210 | U18 - 56" Sale Gas Scrapper Receiver 628-V-501 (R) Erection | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C118136MEHV000220 | U18 - Vent Stack Erection | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6400 | 0 | 10610.ME.ER.TN | 160 | 0
C118136MEHV000230 | U18 - Pig Trolley Erection (628-Y-502) | ME | MEHV | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ME.ER.TN | 18 | 0
C118CIHE000000010 | U18 - Jib Crane Foundation Execution (628-Y-101) | CI | CIHE | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.0023 | 10610.CI.CO.M3 | 20.13 | 20.13
C118CIMF000000010 | U18 - Fire Point Shelter Foundation Execution | CI | CIMF | 18 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 204 | 0.0064713 | 10780.CI.CI.MH
C122131PIRA000320 | U15 - Piping Erection on Rack (577-PR-130) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000370 | U15 - Piping Erection on Rack (577-PR-134) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000380 | U15 - Piping Erection on Rack (577-PR-136) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000390 | U15 - Piping Erection on Rack (577-PR-137) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000400 | U15 - Piping Erection on Rack (577-PR-138) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000420 | U15 - Piping Erection on Rack (577-PR-140) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 253.2348 | 10610.PI.PR.DI | 7417.92 | 311.9977
C122131PIRA000430 | U15 - Piping Erection on Rack (577-PR-141) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 90.9301 | 10610.PI.PR.DI | 7417.92 | 112.0106
C122131PIRA000440 | U15 - Piping Erection on Rack (577-PR-143) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 90.9301 | 10610.PI.PR.DI | 7417.92 | 112.0106
C122131PIRA000460 | U15 - Piping Erection on Rack (577-PR-145) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 30.0247 | 10610.PI.PR.DI | 7417.92 | 37.0154
C122131PIRA000470 | U15 - Piping Erection on Rack (577-PR-146) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 0 | 10610.PI.PR.DI | 7417.92 | 0
C122131PIRA000500 | U15 - Piping Erection on Rack (577-PR-122/ 577-PR-122 A) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 314.3377 | 10610.PI.PR.DI | 7417.92 | 825.9854
C122132CIPR000535 | U15 - Main Piperack Foundations Execution (577-PR-128) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 590.9169 | 10780.CI.CI.MH
C122132CIPR000540 | U15 - Main Piperack Foundations Execution (577-PB-130) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 97.4092 | 10610.CI.CO.M3 | 135.34 | 135.3407
C122132CIPR000651 | U15 - Main Piperack Foundations Execution (577-PR-142) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30121 | 1340.3097 | 10610.CI.CO.M3 | 602.42 | 602.4208
C122132CIPR000660 | U15 - Main Piperack Foundations Execution (577-PR-143) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20280 | 607.5784 | 10610.CI.CO.M3 | 405.6 | 405.6
C122132CIPR000680 | U15 - Main Piperack Foundations Execution (577-PR-145) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21628 | 691.0335 | 10610.CI.CO.M3 | 432.56 | 432.56
C122132CIPR000690 | U15 - Main Piperack Foundations Execution (577-PR-146) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31554 | 1470.8499 | 10610.CI.CO.M3 | 631.07 | 631.07
C122132CIPR000690 | U15 - Main Piperack Foundations Execution (577-PR-146) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31554 | 1470.8499 | 10610.CI.CO.M3 | 631.07 | 631.07
C122132CIPR000700 | U15 - Main Piperack Foundations Execution (577-PR-147) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20705 | 633.2955 | 10610.CI.CO.M3 | 414.09 | 414.09
C122132CIPR000710 | U15 - Main Piperack Foundations Execution (577-PR-148) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11562 | 197.3598 | 10610.CI.CO.M3 | 192.7 | 192.7
C122132METK110050 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 1 Erection including Appurtenances | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110100 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 2 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110120 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 3 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110150 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 4 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132STPR000380 | U15 - Main Piperack Erection (577-PR-135) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8772 | 65.9976 | 10610.ST.PR.TN | 165.5 | 134.1016
C122132STPR000390 | U15 - Main Piperack Erection (577-PR-131) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12164 | 95.7387 | 10610.ST.PR.TN | 229.51 | 126.2313
C122132STPR000400 | U15 - Main Piperack Erection (577-PR-132) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14894 | 158.5168 | 10610.ST.PR.TN | 281.03 | 174.2367
C122132STPR000410 | U15 - Main Piperack Erection (577-PR-133) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11851 | 195.5451 | 10610.ST.PR.TN | 223.6 | 223.5972
C122132STPR000420 | U15 - Main Piperack Erection (577-PR-134) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20365 | 336.6709 | 10610.ST.PR.TN | 384.25 | 268.9791
C2200PRELCL100010 | U20 - SS - 521 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1446 | 0 | 10780.EL.EL.MH
C2200PRELCL100060 | U20 - OMS-013 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 121 | 0 | 10780.EL.EL.MH
C2200PRELCL100100 | U20 - OMS-015 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 312 | 0 | 10780.EL.EL.MH
C122131PIRA000500 | U15 - Piping Erection on Rack (577-PR-122/ 577-PR-122 A) | PI | PIRA | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 66761 | 314.3377 | 10610.PI.PR.DI | 7417.92 | 825.9854
C122132CIPR000550 | U15 - Main Piperack Foundations Execution (577-PR-135) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19410 | 556.2887 | 10610.CI.CO.M3 | 388.2 | 388.2003
C122132CIPR000560 | U15 - Main Piperack Foundations Execution (577-PB-131) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14672 | 318.0023 | 10610.CI.CO.M3 | 293.43 | 293.43
C122132CIPR000580 | U15 - Main Piperack Foundations Execution (577-PR-133) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22457 | 745.0233 | 10610.CI.CO.M3 | 449.14 | 449.14
C122132CIPR000620 | U15 - Main Piperack Foundations Execution (577-PR-138) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13740 | 278.8944 | 10610.CI.CO.M3 | 274.8 | 274.8
C122132CIPR000630 | U15 - Main Piperack Foundations Execution (577-PR-139) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36635 | 1982.7081 | 10610.CI.CO.M3 | 732.7 | 732.7002
C122132CIPR000651 | U15 - Main Piperack Foundations Execution (577-PR-142) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30121 | 1340.3097 | 10610.CI.CO.M3 | 602.42 | 602.4208
C122132CIPR000660 | U15 - Main Piperack Foundations Execution (577-PR-143) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20280 | 607.5784 | 10610.CI.CO.M3 | 405.6 | 405.6
C122132CIPR000670 | U15 - Main Piperack Foundations Execution (577-PR-144) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31085 | 1427.4508 | 10610.CI.CO.M3 | 621.69 | 621.69
C122132METK110030 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Annular Plate and Bottom Plate Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 4.2694 | 10610.ME.TE.TN | 17 | 17
C122132METK110080 | U12 - Lean Solvent Storage Tank Erection 537-TK-101 - Roof Erection including Appurtenances | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 4.2694 | 10610.ME.TE.TN | 17 | 17
C122132METK110150 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 4 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132PAEQ100020 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Internal Painting for Shell and Bottom | PA | PAEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2260 | 0 | 10780.PA.PA.MH
C122132STPR000340 | U15 - Main Piperack Erection (577-PR-142 to 577-PR-147) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 83566 | 9257.8906 | 10610.ST.PR.TN | 1576.72 | 1576.7125
C122132STPR000350 | U15 - Main Piperack Erection (577-PR-148) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10929 | 76.5273 | 10610.ST.PR.TN | 206.21 | 107.2341
C122132STPR000360 | U15 - Main Piperack Erection (577-PR-136 to 577-PR-140) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64160 | 3988.7416 | 10610.ST.PR.TN | 1210.57 | 847.3943
C122132STPR000370 | U15 - Main Piperack Erection (577-PR-129 / 577-PR-130) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19980 | 224.983 | 10610.ST.PR.TN | 376.98 | 169.6417
C122132STPR000420 | U15 - Main Piperack Erection (577-PR-134) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20365 | 336.6709 | 10610.ST.PR.TN | 384.25 | 268.9791
C2200PRELCL100070 | U20 - SS-523 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 436 | 0 | 10780.EL.EL.MH
C122132CIPR000560 | U15 - Main Piperack Foundations Execution (577-PB-131) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14672 | 318.0023 | 10610.CI.CO.M3 | 293.43 | 293.43
C122132CIPR000570 | U15 - Main Piperack Foundations Execution (577-PB-132) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15518 | 355.7443 | 10610.CI.CO.M3 | 310.36 | 310.3599
C122132CIPR000590 | U15 - Main Piperack Foundations Execution (577-PR-134) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37366 | 2062.6219 | 10610.CI.CO.M3 | 747.32 | 747.3202
C122132CIPR000600 | U15 - Main Piperack Foundations Execution (577-PR-136) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18863 | 410.1193 | 10610.CI.CO.M3 | 377.25 | 316.89
C122132CIPR000630 | U15 - Main Piperack Foundations Execution (577-PR-139) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36635 | 1982.7081 | 10610.CI.CO.M3 | 732.7 | 732.7002
C122132CIPR000650 | U15 - Main Piperack Foundations Execution (577-PB-141) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23903 | 844.0383 | 10610.CI.CO.M3 | 478.05 | 478.0496
C122132CIPR000650 | U15 - Main Piperack Foundations Execution (577-PB-141) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23903 | 844.0383 | 10610.CI.CO.M3 | 478.05 | 478.0496
C122132CIPR000670 | U15 - Main Piperack Foundations Execution (577-PR-144) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31085 | 1427.4508 | 10610.CI.CO.M3 | 621.69 | 621.69
C122132CIPR000710 | U15 - Main Piperack Foundations Execution (577-PR-148) | CI | CIPR1 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11562 | 197.3598 | 10610.CI.CO.M3 | 192.7 | 192.7
C122132METK110030 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Annular Plate and Bottom Plate Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 4.2694 | 10610.ME.TE.TN | 17 | 17
C122132METK110050 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 1 Erection including Appurtenances | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110100 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 2 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110120 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 3 Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110170 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Shell 5 & Compression Ring Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110240 | U12 - Lean Solvent Storage Tank Erection 537-TK-101 - Roof Platform & Staircase Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0.53183 | 10610.ME.TE.TN | 6 | 6
C122132METK110250 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Internal Piping Erection | ME | METK1 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0.13296 | 10780.ME.ME.MH
C122132PAEQ100010 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- External Painting for Roof and Shell | PA | PAEQ | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2260 | 0 | 10780.PA.PA.MH
C122132PRHT100010 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Hydrotesting and Settlement Check | PR | PRHT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 18288 | 82.7599 | 10780.PR.PR.MH
C2200PRINFG100000 | U20 - SS-521 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1178 | 0 | 10780.IN.IN.MH
C2200PRINFG100020 | U20 - SS-526 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21 | 0 | 10780.IN.IN.MH
C2200PRINFG100040 | U20 - SS-522 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1375 | 0 | 10780.IN.IN.MH
C2200PRINFG100110 | U20 - OMS-015 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1172 | 0 | 10780.IN.IN.MH
C2200PRLT00000200 | U20 - IES-514 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22211 | 0 | 10780.PR.PR.MH
C2200PRLT00000250 | U20 - SS-500 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000260 | U20 - SS-503 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000290 | U20 - SS-012 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000300 | U20 - SS-521 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 965 | 0 | 10780.PR.PR.MH
C2200PRLT00000340 | U20 - IES-015 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000360 | U20 - IES-1A - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4073 | 0 | 10780.PR.PR.MH
C2200PRLT00000370 | U20 - IES-304 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4427 | 0 | 10780.PR.PR.MH
C2200PRLT00000400 | U20 - IES-502 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4427 | 0 | 10780.PR.PR.MH
C2200PRLT00000530 | U20 - SS-526 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18 | 0 | 10780.PR.PR.MH
C2200PRPRPL000200 | U20 - SS-521 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 207 | 0 | 10780.PR.PR.MH
C2200PRPRPL000250 | U20 - OMS-013 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23 | 0 | 10780.PR.PR.MH
C2200PRPRPL000295 | U20 - SS-516 - Punch List Clearance for Transformer #B | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10780.PR.PR.MH
C2200PRPRWT000220 | U20 - SS-524 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 68 | 0 | 10780.PR.PR.MH
C2200PRPRWT000250 | U20 - SS-521 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89 | 0 | 10780.PR.PR.MH
C220132BUSS000535 | U20 - SS-500 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 332 | 0 | 10780.BU.BU.MH
C220132BUSS000555 | U20 - SS-504 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 379 | 0 | 10780.BU.BU.MH
C220132BUSS000560 | U20 - SS-501 - Modifications (Doors/Windows/Glazing) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8394 | 0 | 10780.BU.BU.MH
C122132PRHT100020 | U12 - Lean Solvent Storage Tank Erection 537-TK-101- Dewatering and Cleaning | PR | PRHT | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9144 | 0 | 10780.PR.PR.MH
C122132STPR000330 | U15 - Main Piperack Erection (577-PR-141) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12453 | 110.9312 | 10610.ST.PR.TN | 234.97 | 157.4305
C122132STPR000380 | U15 - Main Piperack Erection (577-PR-135) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8772 | 65.9976 | 10610.ST.PR.TN | 165.5 | 134.1016
C122132STPR000390 | U15 - Main Piperack Erection (577-PR-131) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12164 | 95.7387 | 10610.ST.PR.TN | 229.51 | 126.2313
C122132STPR000400 | U15 - Main Piperack Erection (577-PR-132) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14894 | 158.5168 | 10610.ST.PR.TN | 281.03 | 174.2367
C122132STPR000410 | U15 - Main Piperack Erection (577-PR-133) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11851 | 195.5451 | 10610.ST.PR.TN | 223.6 | 223.5972
C2200PRELCL100020 | U20 - SS-526 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 77 | 0 | 10780.EL.EL.MH
C2200PRELCL100030 | U20 - SS-524 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 972 | 0 | 10780.EL.EL.MH
C2200PRELCL100080 | U20 - IES-514 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 829 | 0 | 10780.EL.EL.MH
C2200PRELCL100090 | U20 - NMCB - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3770 | 0 | 10780.EL.EL.MH
C2200PRELCL100110 | U20 - IES-513 - Resistance and Continuity Test | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 822 | 0 | 10780.EL.EL.MH
C2200PRINFG100030 | U20 - SS-524 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1444 | 0 | 10780.IN.IN.MH
C2200PRINFG100060 | U20 - SS-523 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1338 | 0 | 10780.IN.IN.MH
C2200PRINFG100120 | U20 - OMS-014 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 124 | 0 | 10780.IN.IN.MH
C2200PRLT00000190 | U20 - SS-520 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1178 | 0 | 10780.PR.PR.MH
C2200PRLT00000210 | U20 - OMS-014 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 109 | 0 | 10780.PR.PR.MH
C2200PRLT00000230 | U20 - OMS-015 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 960 | 0 | 10780.PR.PR.MH
C2200PRLT00000270 | U20 - SS-504 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000330 | U20 - IES-012 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000350 | U20 - IES-016 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000380 | U20 - IES-500 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3995 | 0 | 10780.PR.PR.MH
C2200PRLT00000390 | U20 - IES-501 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4648 | 0 | 10780.PR.PR.MH
C2200PRINFG100050 | U20 - SS-525 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 124 | 0 | 10780.IN.IN.MH
C2200PRINFG100070 | U20 - IES-514 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C2200PRINFG100090 | U20 - IES-513 - F&G Detection Test | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C2200PRLT00000240 | U20 - SS-516 - Loops Testing for Transformer #A | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2245 | 0 | 10780.PR.PR.MH
C2200PRLT00000310 | U20 - SS-502 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000440 | U20 - IES-507 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4427 | 0 | 10780.PR.PR.MH
C2200PRLT00000450 | U20 - IES-508-504 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4427 | 0 | 10780.PR.PR.MH
C2200PRLT00000460 | U20 - Ruwais - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000470 | U20 - CR-541 & MAQTA - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2767 | 0 | 10780.PR.PR.MH
C2200PRLT00000500 | U20 - SS-523 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1097 | 0 | 10780.PR.PR.MH
C2200PRLT00000540 | U20 - IES-513 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22210 | 0 | 10780.PR.PR.MH
C2200PRPRPL000270 | U20 - OMS-015 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67 | 0 | 10780.PR.PR.MH
C2200PRPRWT000150 | U20 - NMCB - Walkthrough | PR | PRWT | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 345 | 0 | 10780.PR.PR.MH
C2200PRPRWT000160 | U20 - OMS-014 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8 | 0 | 10780.PR.PR.MH
C2200PRPRWT000170 | U20 - OMS-015 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.PR.PR.MH
C2200PRPRWT000230 | U20 - SS-525 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5 | 0 | 10780.PR.PR.MH
C220132BUSS000530 | U20 - SS-500 - Modifications (Structure/Architecure/Doors/Windows) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6295 | 0 | 10780.BU.BU.MH
C220132BUSS000580 | U20 - SS-515 - Modifications (Structure/Doors/Windows) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5596 | 4.5336 | 10780.BU.BU.MH
C220132BUSS000650 | U20 - OMS-007 - Modifications (Structure/Doors/Windows) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 0 | 10780.BU.BU.MH
C220132BUSS000655 | U20 - OMS-007 - Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSS000670 | U20 - OMS-008 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 0 | 10780.BU.BU.MH
C220132BUSS000730 | U20 - SS-502 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8394 | 0 | 10780.BU.BU.MH
C220132BUSSCS100080 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 106.5 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9086 | 121.9641 | 10610.BU.CO.M3 | 803 | 802.9993
C220132BUSSCS100090 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Footings | BU | BUCTFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12211 | 220.2755 | 10610.BU.CO.M3 | 1320 | 1320
C220132BUSSCS100100 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 102.0 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10831 | 173.3071 | 10610.BU.CO.M3 | 31.8 | 31.8
C220132BUSSCS100110 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) GF To RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11449 | 193.6504 | 10610.BU.CO.M3 | 123.73 | 123.7301
C220132BUSSCS100130 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 66.3366 | 10610.BU.CO.M3 | 504 | 504
C220132BUSSCS100140 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev.106.50 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11661 | 200.8887 | 10610.BU.CO.M3 | 1093 | 1093
C220132BUSSCS100150 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns -by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17596 | 457.396 | 10610.BU.CO.M3 | 125.5 | 125.5
C220132BUSSCS100150 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns -by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17596 | 457.396 | 10610.BU.CO.M3 | 125.5 | 125.5
C220132BUSSCS100151 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns- by OQC | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 62.2266 | 10610.BU.CO.M3 | 215.5 | 215.5
C220132BUSSCS100170 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5131 | 38.8901 | 10610.BU.CO.M3 | 57.27 | 57.2702
C220132BUSSCS100180 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns CF To GF - by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7277 | 78.2271 | 10610.BU.CO.M3 | 38 | 38
C220132BUSSCS100230 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 17.28 | 17.28
C220132BUSSCS100250 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 101- by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7468 | 82.393 | 10610.BU.CO.M3 | 51 | 51
C220132BUSSCS100280 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 100.00 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 6.1428 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSCS100320 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 184.2794 | 10610.BU.CO.M3 | 755 | 755
C220132BUSSCS100350 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls CF To GF - by TARGET | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8617 | 109.6958 | 10610.BU.CO.M3 | 50 | 0
C220132BUSSCS100351 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls CF To GF - by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16851 | 419.498 | 10610.BU.CO.M3 | 465 | 464.9991
C220132BUSSCS100360 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 206 | 205.9998
C220132BUSSCS100380 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Grade Beams (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 18 | 18
C220132BUSSCS100390 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7933 | 92.9648 | 10610.BU.CO.M3 | 53 | 53
C220132BUSSCS100410 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Curb Walls (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 3 | 0
C220132BUSSCS100410 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Curb Walls (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 3 | 0
C220132BUSSCS100420 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5017 | 37.181 | 10610.BU.CO.M3 | 400 | 399.9987
C220132BUSSCS100420 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5017 | 37.181 | 10610.BU.CO.M3 | 400 | 399.9987
C220132BUSSCS100430 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls Elev 116.1 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3876 | 22.1966 | 10610.BU.CO.M3 | 243.52 | 243.5191
C220132BUSSCS100440 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 46.98 | 0
C220132BUSSCS100450 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Grade Slab-by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 41.5137 | 10610.BU.CO.M3 | 570 | 570
C220132BUSSCS100451 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Grade Slab - by OQC | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 40.8909 | 10610.BU.CO.M3 | 50 | 50
C220132BUSSCS100480 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 105.45 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12064 | 215.0074 | 10610.BU.CO.M3 | 685 | 684.9992
C220132BUSSCS100510 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 55.0235 | 10610.BU.CO.M3 | 308 | 307.9997
C220132BUSSCS100510 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 55.0235 | 10610.BU.CO.M3 | 308 | 307.9997
C220132BUSSCS100520 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 64 | 63.9999
C220132BUSSCS100550 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 112.3 & 116.9 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6841 | 69.1345 | 10610.BU.CO.M3 | 824.6 | 824.5994
C220132BUSSCS100571 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns (Internal) up to RF | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 41.5137 | 10610.BU.CO.M3 | 77 | 77
C220132BUSSAR100040 | U20 - SS-522 - External Plastering/Surface Preparation (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8043 | 0 | 10780.BU.BU.MH
C220132BUSSAR100070 | U20 - SS-521 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 66.3801 | 10610.BU.AR.M2 | 1215 | 0
C220132BUSSAR100070 | U20 - SS-521 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 66.3801 | 10610.BU.AR.M2 | 1215 | 0
C220132BUSSAR100100 | U20 - SS-520 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9541 | 119.6888 | 10780.BU.BU.MH
C220132BUSSAR100190 | U20 - SS-520 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100300 | U20 - SS-526 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10610.BU.AR.M2 | 31 | 0
C220132BUSSAR100340 | U20 - SS-521 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 0 | 10780.BU.BU.MH
C220132BUSSAR100350 | U20 - SS-523 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.AR.M2 | 170 | 0
C220132BUSSAR100360 | U20 - SS-525 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 586 | 0 | 10610.BU.AR.M2 | 21 | 0
C220132BUSSAR100420 | U20 - SS-521 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 0 | 10780.BU.BU.MH
C220132BUSSAR100423 | U20 - SS-522-CFP2 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4596 | 11.5455 | 10780.BU.BU.MH
C220132BUSSAR100440 | U20 - NMCB - Internal Walls and Partitions | BU | BUARPT | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR100490 | U20 - SS-520 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 38.7318 | 10780.BU.BU.MH
C220132BUSSAR100513 | U20 - SS-524-CFP1 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2736 | 11.0599 | 10780.BU.BU.MH
C220132BUSSAR100523 | U20 - SS-524-CFP2 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2736 | 11.0599 | 10780.BU.BU.MH
C220132BUSSAR100560 | U20 - IES-513 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 18.9193 | 10610.BU.AR.M2 | 431 | 0
C220132BUSSAR100580 | U20 - SS-520 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100650 | U20 - OMS-013 - Internal Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR100670 | U20 - SS-525 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100790 | U20 - SS-524 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 21.4046 | 10780.BU.BU.MH
C2200PRLT00000410 | U20 - SS-522 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1127 | 0 | 10780.PR.PR.MH
C2200PRLT00000480 | U20 - SS-512 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 898 | 0 | 10780.PR.PR.MH
C2200PRLT00000490 | U20 - TLC - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2803 | 0 | 10780.PR.PR.MH
C2200PRLT00000510 | U20 - SS-524 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1183 | 0 | 10780.PR.PR.MH
C2200PRLT00000520 | U20 - SS-525 - Loops Testing | PR | PRLT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 109 | 0 | 10780.PR.PR.MH
C2200PRLT00000550 | U20 - NMCB - Loops Testing | PR | PRLT | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21981 | 0 | 10780.PR.PR.MH
C2200PRPRPL000160 | U20 - NMCB- Punch List Clearance | PR | PRPL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 804 | 0 | 10780.PR.PR.MH
C2200PRPRPL000210 | U20 - SS-522 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 249 | 0 | 10780.PR.PR.MH
C2200PRPRPL000220 | U20 - SS-526 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9 | 0 | 10780.PR.PR.MH
C2200PRPRPL000260 | U20 - OMS-014 - Punch List Clearance | PR | PRPL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18 | 0 | 10780.PR.PR.MH
C2200PRPRWT000180 | U20 - IES-514 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0 | 10780.PR.PR.MH
C2200PRPRWT000190 | U20 - IES-513 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 370 | 0 | 10780.PR.PR.MH
C2200PRPRWT000200 | U20 - SS-526 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4 | 0 | 10780.PR.PR.MH
C2200PRPRWT000240 | U20 - SS-520 - Walkthrough | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10780.PR.PR.MH
C2200PRPRWT000270 | U20 - SS-516- Walkthrough for Transformer #A | PR | PRWT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41 | 0 | 10780.PR.PR.MH
C220132BUSS000540 | U20 - SS-503 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6295 | 0 | 10780.BU.BU.MH
C220132BUSS000570 | U20 - SS-514 - Modifications (Doors/Windows/Glazing) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 0 | 10780.BU.BU.MH
C220132BUSS000575 | U20 - IES-514 - UG Survey and Relocation of Existing Services | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3051 | 0 | 10780.BU.BU.MH
C220132BUSS000600 | U20 - SS-518 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 0 | 10780.BU.BU.MH
C220132BUSS000610 | U20 - IES-501 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3357 | 0 | 10780.BU.BU.MH
C220132BUSS000685 | U20 - MB - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0 | 10780.BU.BU.MH
C220132BUSS000735 | U20 - SS-502 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 441 | 0 | 10780.BU.BU.MH
C220132BUSS000565 | U20 - SS-501 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 441 | 0 | 10780.BU.BU.MH
C220132BUSS000585 | U20 - SS-515 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 295 | 0 | 10780.BU.BU.MH
C220132BUSS000615 | U20 - IES-501 - UG Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 177 | 0 | 10780.BU.BU.MH
C220132BUSS000640 | U20 - IES-500 - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3874 | 0 | 10780.BU.BU.MH
C220132BUSS000690 | U20 - MCB - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8223 | 60.9336 | 10780.BU.BU.MH
C220132BUSS000740 | U20 - TLC - Modifications | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3874 | 0 | 10780.BU.BU.MH
C220132BUSSAR100010 | U20 - SS-520 - External Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100020 | U20 - SS-521 - External Plastering/Surface Preparation (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9086 | 34.1499 | 10780.BU.BU.MH
C220132BUSSAR100030 | U20 - SS-520 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100080 | U20 - SS-522 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8043 | 0 | 10780.BU.BU.MH
C220132BUSSAR100120 | U20 - SS-520 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9541 | 130.4473 | 10610.BU.AR.M2 | 1215 | 0
C220132BUSSAR100130 | U20 - SS-520 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12722 | 55.7083 | 10780.BU.BU.MH
C220132BUSSAR100140 | U20 - SS-521 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7933 | 0 | 10780.BU.BU.MH
C220132BUSSAR100150 | U20 - NMCB - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 49.5343 | 10610.BU.CO.M3 | 371 | 0
C220132BUSSAR100150 | U20 - NMCB - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 49.5343 | 10610.BU.CO.M3 | 371 | 0
C220132BUSSAR100200 | U20 - SS-520 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100213 | U20 - SS-520 -CFP1- Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5089 | 29.8398 | 10780.BU.BU.MH
C220132BUSSAR100223 | U20 - SS-520-CFP2 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5089 | 28.6921 | 10780.BU.BU.MH
C220132BUSSAR100280 | U20 - SS-524 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 10.373 | 10780.BU.BU.MH
C220132BUSSAR100310 | U20 - SS-524 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 0 | 10780.BU.BU.MH
C220132BUSSCS100620 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132BUSSCS100630 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls GF To RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 517 | 0
C220132BUSSCS100650 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Beams and Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 20.3433 | 10610.BU.CO.M3 | 862 | 861.9981
C220132BUSSCS100660 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2508 | 9.2934 | 10610.BU.CO.M3 | 53.84 | 53.8403
C220132BUSSCS100660 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2508 | 9.2934 | 10610.BU.CO.M3 | 53.84 | 53.8403
C220132BUSSCS100690 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Walls | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2126 | 0.46345 | 10610.BU.CO.M3 | 36.83 | 0
C220132BUSSCS100730 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 110.25 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 109.35 | 0
C220132BUSSCS100770 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Roof Beams & Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 25.5254 | 10610.BU.CO.M3 | 674 | 307.3777
C220132BUSSCS100820 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Parapet Wall | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 254 | 0 | 10610.BU.CO.M3 | 10.85 | 0
C220132BUSSCS100840 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Parapet Walls up to Elev 111.65 (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 18.5 | 0
C220132BUSSCS100850 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0.31867 | 10610.BU.CO.M3 | 9 | 3.6
C220132BUSSCS100900 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Walls & Columns (External) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14737 | 320.8389 | 10610.BU.CO.M3 | 98 | 98
C220132BUSSCS100900 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Walls & Columns (External) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14737 | 320.8389 | 10610.BU.CO.M3 | 98 | 98
C220132BUSSCS100910 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Parapet Wall | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 14.9468 | 10610.BU.CO.M3 | 42 | 42.0001
C220132BUSSCS100910 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Parapet Wall | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 14.9468 | 10610.BU.CO.M3 | 42 | 42.0001
C220132BUSSCS100950 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Dome | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7446 | 0 | 10610.BU.CO.M3 | 438 | 0
C220132BUSSCS100970 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 111.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 1037 | 1037
C220132BUSSAR100860 | U20 - OMS-015 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.AR.M2 | 24 | 0
C220132BUSSAR100920 | U20 - SS-525 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100930 | U20 - SS-526 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR100950 | U20 - SS-524 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 15.8986 | 10780.BU.BU.MH
C220132BUSSAR100960 | U20 - SS-522 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11490 | 25.3534 | 10780.BU.BU.MH
C220132BUSSAR100980 | U20 - SS-521 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10780.BU.BU.MH
C220132BUSSAR101010 | U20 - SS-525 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR101020 | U20 - SS-525 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR101080 | U20 - IES-513 - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 0 | 10780.BU.BU.MH
C220132BUSSAR101120 | U20 - NMCB - Install False Ceiling | BU | BUARCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101130 | U20 - IES-513 - External Plastering/Surface Preparation | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 19.3262 | 10780.BU.BU.MH
C220132BUSSAR101140 | U20 - OMS-013 - Install False Ceiling | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101170 | U20 - SS-522 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5745 | 0 | 10780.BU.BU.MH
C220132BUSSAR101270 | U20 - OMS-013 - Internal Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101300 | U20 - SS-523 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 853 | 0 | 10780.BU.BU.MH
C220132BUSSAR101350 | U20 - SS-522 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4787 | 0 | 10780.BU.BU.MH
C220132BUSSAR101400 | U20 - NMCB - Install Canopy Roofings | BU | BUARCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 0 | 10780.BU.BU.MH
C220132BUSSAR101420 | U20 - SS-523 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101440 | U20 - OMS-013 - Install Rockwool Insulation | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101450 | U20 - SS-523 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSS000745 | U20 - TLC - Survey and Relocation of Existing Services | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 204 | 0 | 10780.BU.BU.MH
C220132BUSSAR100060 | U20 - SS-524 - External Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 23.5215 | 10780.BU.BU.MH
C220132BUSSAR100110 | U20 - SS-524 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 1.4701 | 10780.BU.BU.MH
C220132BUSSAR100120 | U20 - SS-520 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9541 | 130.4473 | 10610.BU.AR.M2 | 1215 | 0
C220132BUSSAR100180 | U20 - SS-526 - External Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10780.BU.BU.MH
C220132BUSSAR100210 | U20 - SS-525 - External Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100212 | U20 - SS-520-CFP1 - Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4453 | 28.119 | 10780.BU.BU.MH
C220132BUSSAR100220 | U20 - SS-524 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5131 | 38.8901 | 10780.BU.BU.MH
C220132BUSSAR100222 | U20 - SS-520-CFP2 - Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4453 | 28.119 | 10780.BU.BU.MH
C220132BUSSAR100230 | U20 - SS-526 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10780.BU.BU.MH
C220132BUSSAR100240 | U20 - SS-521 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5192 | 0 | 10780.BU.BU.MH
C220132BUSSAR100250 | U20 - SS-525 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100270 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19657 | 342.4866 | 10610.BU.CO.M3 | 50 | 30
C220132BUSSAR100290 | U20 - SS-520 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR100312 | U20 - SS-521-CFP1 - Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3029 | 13.5531 | 10780.BU.BU.MH
C220132BUSSAR100323 | U20 - SS-521-CFP2 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5048 | 30.1159 | 10780.BU.BU.MH
C220132BUSSAR100422 | U20 - SS-522-CFP2 - Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4021 | 23.41 | 10780.BU.BU.MH
C220132BUSSAR100430 | U20 - SS-526 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10780.BU.BU.MH
C220132BUSSAR100520 | U20 - SS-525 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100530 | U20 - SS-524 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2052 | 0 | 10780.BU.BU.MH
C220132BUSSAR100320 | U20 - SS-521 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 7.4605 | 10780.BU.BU.MH
C220132BUSSAR100322 | U20 - SS-521 -CFP2- Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4327 | 27.6584 | 10780.BU.BU.MH
C220132BUSSAR100330 | U20 - OMS-013 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR100350 | U20 - SS-523 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.AR.M2 | 170 | 0
C220132BUSSAR100360 | U20 - SS-525 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 586 | 0 | 10610.BU.AR.M2 | 21 | 0
C220132BUSSAR100370 | U20 - SS-523 - External Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR100390 | U20 - SS-522 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12064 | 12.9004 | 10780.BU.BU.MH
C220132BUSSAR100400 | U20 - SS-522 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11490 | 0 | 10610.BU.AR.M2 | 445 | 0
C220132BUSSAR100412 | U20 - SS-522 -CFP1- Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4021 | 23.41 | 10780.BU.BU.MH
C220132BUSSAR100450 | U20 - IES-514 - External Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5340 | 0 | 10780.BU.BU.MH
C220132BUSSAR100460 | U20 - SS-523 - Internal Plastering (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR100470 | U20 - SS-522 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4021 | 0 | 10780.BU.BU.MH
C220132BUSSAR100500 | U20 - SS-526 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR100522 | U20 - SS-524-CFP2- Surface Preparation/Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2394 | 8.4677 | 10780.BU.BU.MH
C220132BUSSAR100540 | U20 - SS-521 - Install Cable Cellar Doors(Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 0 | 10780.BU.BU.MH
C220132BUSSAR100560 | U20 - IES-513 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 18.9193 | 10610.BU.AR.M2 | 431 | 0
C220132BUSSAR100570 | U20 - SS-525 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR100590 | U20 - SS-522 - Install Hand Railing (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3447 | 0 | 10780.BU.BU.MH
C220132BUSSAR100610 | U20 - SS-523 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR100630 | U20 - IES-514 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6866 | 0 | 10780.BU.BU.MH
C220132BUSSCS101040 | U20 - OMS-014 - Concrete Precast Slab Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS101060 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7851 | 33.146 | 10610.BU.CO.M3 | 80 | 0
C220132BUSSCS101070 | U20 - OMS-014 - Concrete Precast Walls Installation for Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 14 | 0
C220132BUSSFO100050 | U20 - SS-522 - Excavation and Compaction (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27575 | 1123.3097 | 10780.BU.BU.MH
C220132BUSSFO100070 | U20 - OMS-013 - Excavation and Compaction | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 854 | 1.0776 | 10780.BU.BU.MH
C220132BUSSFO100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19268 | 548.4632 | 10610.BU.CO.M3 | 800.83 | 800.83
C220132BUSSFO100110 | U20 - OMS-014 - Excavation and Compaction | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3392 | 16.9964 | 10780.BU.BU.MH
C220132BUSSFO100120 | U20 - IES-514 - Excavation and Compaction | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3204 | 15.1655 | 10780.BU.BU.MH
C220132BUSSFO100150 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16298 | 392.4021 | 10610.BU.CO.M3 | 1030 | 1030
C220132BUSSFO100181 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11250 | 186.9673 | 10610.BU.CO.M3 | 206 | 206
C220132BUSSFO100190 | U20 - SS-522 - Excavation (Dewatering Area) (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12256 | 221.8964 | 10780.BU.BU.MH
C220132BUSSFO100210 | U20 - SS-522 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16277 | 391.3946 | 10780.BU.BU.MH
C220132BUSSFO100220 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13796 | 281.1659 | 10610.BU.CO.M3 | 160.17 | 160.17
C220132BUSSFO100230 | U20 - SS-525 - UG Survey and Relocation of Existing Services (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 313 | 0.1445 | 10780.BU.BU.MH
C220132BUSSFO100260 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7660 | 86.6783 | 10610.BU.CO.M3 | 2677 | 2677
C220132BUSSFO100310 | U20 - NMCB - Excavation and Compaction | BU | BUCTFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20550 | 623.8671 | 10780.BU.BU.MH
C220132BUSSFO100370 | U20 - SS-522 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5745 | 42.4182 | 10780.BU.BU.MH
C220132BUSSFO100400 | U20 - SS-525 - Blinding and Water Proofing (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 78 | 0.0069399 | 10780.BU.BU.MH
C220132BUSSFO100410 | U20 - SS-526 - Blinding and Water Proofing (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 489 | 0.35356 | 10780.BU.BU.MH
C220132BUSSAR100550 | U20 - SS-521 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 1.0658 | 10780.BU.BU.MH
C220132BUSSAR100600 | U20 - SS-526 - Flooring Works (Finishing) (Elect. Subst.) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1631 | 0 | 10780.BU.BU.MH
C220132BUSSAR100680 | U20 - NMCB - Raised Floor Installation | BU | BUARRA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR100720 | U20 - SS-524 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 0 | 10780.BU.BU.MH
C220132BUSSAR100740 | U20 - SS-522 - Install False Ceiling (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6702 | 0 | 10780.BU.BU.MH
C220132BUSSAR100760 | U20 - OMS-013 - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR100770 | U20 - NMCB - Concrete Cast-in Situ & Precast for Parapet Wall | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7446 | 0 | 10610.BU.CO.M3 | 29 | 0
C220132BUSSAR100870 | U20 - SS-526 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1468 | 0 | 10780.BU.BU.MH
C220132BUSSAR100910 | U20 - IES-513 - Raised Floor Installation | BU | BUARRA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4453 | 0 | 10780.BU.BU.MH
C220132BUSSAR101000 | U20 - SS-520 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10780.BU.BU.MH
C220132BUSSAR101060 | U20 - SS-525 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR101070 | U20 - SS-526 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR101110 | U20 - OMS-014 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.AR.M2 | 24 | 0
C220132BUSSAR101150 | U20 - OMS-013 - External Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101160 | U20 - OMS-015 - Internal Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 969 | 0 | 10780.BU.BU.MH
C220132BUSSAR101180 | U20 - SS-522 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7660 | 0 | 10780.BU.BU.MH
C220132BUSSAR101190 | U20 - IES-514 - Install Hand Railing | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3662 | 0 | 10780.BU.BU.MH
C220132BUSSAR101220 | U20 - SS-523 - Install Ladder and Cage (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101230 | U20 - SS-523 - Install Rockwool Insulation (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101280 | U20 - NMCB - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101460 | U20 - IES-513 - Internal Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4453 | 6.2248 | 10780.BU.BU.MH
C220132BUSSAR101500 | U20 - SS-523 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101520 | U20 - SS-526 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1958 | 0 | 10780.BU.BU.MH
C220132BUSSAR101530 | U20 - OMS-015 - External Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101540 | U20 - OMS-014 - External Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101590 | U20 - OMS-013 - Maintenance Shed | BU | BUARFU | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 636 | 0 | 10780.BU.BU.MH
C220132BUSSAR101610 | U20 - OMS-015 - Internal Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101650 | U20 - OMS-013 - Install Hand Railing | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 436 | 0 | 10780.BU.BU.MH
C220132BUSSAR101660 | U20 - OMS-013 - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101680 | U20 - OMS-014 - External Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101700 | U20 - IES-514 - Waterproofing Works | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 0 | 10780.BU.BU.MH
C220132BUSSAR101730 | U20 - OMS-014 - Install Rockwool Insulation | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101750 | U20 - OMS-013 - Waterproofing Works | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 327 | 0 | 10780.BU.BU.MH
C220132BUSSAR101760 | U20 - IES-513 - Install Hand Railing | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2545 | 0 | 10780.BU.BU.MH
C220132BUSSAR101870 | U20 - OMS-015 - Install Fence & Gates | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSCS100030 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27139 | 1088.08 | 10610.BU.CO.M3 | 329.33 | 329.33
C220132BUSSCS100040 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev. 102.40 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25019 | 924.7172 | 10610.BU.CO.M3 | 36.68 | 36.68
C220132BUSSCS100050 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 102 - by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14711 | 319.7135 | 10610.BU.CO.M3 | 29.57 | 29.57
C220132BUSSCS100050 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 102 - by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14711 | 319.7135 | 10610.BU.CO.M3 | 29.57 | 29.57
C220132BUSSCS100051 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 102 - by OQC | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 62.2266 | 10610.BU.CO.M3 | 3.73 | 3.73
C220132BUSSFO100430 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14843 | 325.4714 | 10610.BU.CO.M3 | 701 | 701
C220132BUSSFO100440 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1705 | 4.2953 | 10610.BU.CO.M3 | 205 | 205
C220132BUSSFO100450 | U20 - NMCB - Blinding and Water Proofing | BU | BUCTFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12360 | 225.6824 | 10780.BU.BU.MH
C220132BUSSFO100500 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8697 | 111.7349 | 10610.BU.CO.M3 | 844 | 844
C220132BUSSFO100520 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 24 | 24
C220132BUSSFO100540 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7476 | 82.5677 | 10610.BU.CO.M3 | 159 | 159
C220132BUSSFO100550 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 1.3449 | 10610.BU.CO.M3 | 19.44 | 18.4699
C220132BUSSFO100560 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab(Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10610.BU.CO.M3 | 131.87 | 0
C220132BUSSFO100570 | U20 - OMS-013 - Backfilling and Compaction upto Grade Slab | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1109 | 1.8162 | 10780.BU.BU.MH
C220132BUSSFO100610 | U20 - SS-526 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 489 | 0 | 10780.BU.BU.MH
C220132BUSSFO100630 | U20 - IES-514 - Backfilling and Compaction upto Grade Slab | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 30.949 | 10780.BU.BU.MH
C220132BUSSFO100650 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1468 | 3.1842 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSFO100660 | U20 - NMCB - Backfilling and Compaction | BU | BUCTFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 94.7027 | 10780.BU.BU.MH
C220132BUSSFO100670 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 12 | 11.9999
C220132BUSSFO100670 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 12 | 11.9999
C220132BUSSFO100680 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 472 | 0.15089 | 10610.BU.CO.M3 | 5.45 | 2.18
C220132BUSSFO100700 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 30.949 | 10610.BU.CO.M3 | 75 | 75
C220132BUSSFO100710 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 55 | 0
C220132BUSSCS100060 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20180 | 601.6149 | 10610.BU.CO.M3 | 46.43 | 46.43
C220132BUSSCS100100 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 102.0 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10831 | 173.3071 | 10610.BU.CO.M3 | 31.8 | 31.8
C220132BUSSCS100130 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 66.3366 | 10610.BU.CO.M3 | 504 | 504
C220132BUSSCS100140 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev.106.50 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11661 | 200.8887 | 10610.BU.CO.M3 | 1093 | 1093
C220132BUSSCS100151 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns- by OQC | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 62.2266 | 10610.BU.CO.M3 | 215.5 | 215.5
C220132BUSSCS100170 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5131 | 38.8901 | 10610.BU.CO.M3 | 57.27 | 57.2702
C220132BUSSCS100181 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns CF To GF - by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12447 | 228.8756 | 10610.BU.CO.M3 | 173 | 173
C220132BUSSCS100200 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10375 | 159.0207 | 10610.BU.CO.M3 | 273.69 | 273.6892
C220132BUSSCS100210 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 106.45 / 112.30 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9463 | 132.2912 | 10610.BU.CO.M3 | 610.82 | 610.82
C220132BUSSCS100240 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 6.1428 | 10610.BU.CO.M3 | 36.04 | 36.04
C220132BUSSCS100250 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 101- by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7468 | 82.393 | 10610.BU.CO.M3 | 51 | 51
C220132BUSSCS100251 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 101-by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16851 | 419.498 | 10610.BU.CO.M3 | 26 | 26
C220132BUSSCS100270 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 110.6335 | 10610.BU.CO.M3 | 500 | 499.9998
C220132BUSSCS100290 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 100.00 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 8.2 | 8.2
C220132BUSSCS100340 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Walls CF To GF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1958 | 5.6628 | 10610.BU.CO.M3 | 149 | 0
C220132BUSSCS100360 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 206 | 205.9998
C220132BUSSAR100700 | U20 - SS-526 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132BUSSAR100730 | U20 - SS-521 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5048 | 0 | 10780.BU.BU.MH
C220132BUSSAR100750 | U20 - IES-513 - Internal Plastering | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 10.782 | 10780.BU.BU.MH
C220132BUSSAR100780 | U20 - NMCB - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 720 | 0.038291 | 10610.CI.ET.M3 | 180 | 63
C220132BUSSAR100800 | U20 - SS-522 - Install Cable Cellar Fences & Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4021 | 0 | 10780.BU.BU.MH
C220132BUSSAR100830 | U20 - NMCB - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 2.913 | 10780.BU.BU.MH
C220132BUSSAR100840 | U20 - NMCB - External Wall Finish | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR100860 | U20 - OMS-015 - Internal Block Walls, Partitions (Elect. Subst.) | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.AR.M2 | 24 | 0
C220132BUSSAR100990 | U20 - SS-523 - Internal Painting (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10780.BU.BU.MH
C220132BUSSAR101050 | U20 - IES-514 - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5340 | 0 | 10780.BU.BU.MH
C220132BUSSAR101090 | U20 - SS-525 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR101250 | U20 - SS-524 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 18.8172 | 10780.BU.BU.MH
C220132BUSSAR101260 | U20 - SS-522 - Waterproofing Works (Elect. Subst.) | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11490 | 0 | 10780.BU.BU.MH
C220132BUSSAR101310 | U20 - IES-513 - Install False Ceiling | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 0 | 10780.BU.BU.MH
C220132BUSSAR101340 | U20 - SS-524 - Install Doors (Elect. Subst.) | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3990 | 4.4691 | 10780.BU.BU.MH
C220132BUSSAR101470 | U20 - NMCB - Furnitures | BU | BUARFU | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101570 | U20 - OMS-014 - Install False Ceiling | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101670 | U20 - OMS-014 - Internal Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101690 | U20 - IES-514 - Install Doors & Windows | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 0 | 10780.BU.BU.MH
C220132BUSSAR101720 | U20 - OMS-014 - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10780.BU.BU.MH
C220132BUSSAR101740 | U20 - OMS-013 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 327 | 0 | 10780.BU.BU.MH
C220132BUSSAR101290 | U20 - OMS-015 - Flooring Works (Finishing) | BU | BUARFL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.BU.BU.MH
C220132BUSSAR101360 | U20 - IES-513 - External Painting | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 0 | 10780.BU.BU.MH
C220132BUSSAR101380 | U20 - NMCB - Install Hand Railing | BU | BUARCP | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 6.8327 | 10780.BU.BU.MH
C220132BUSSAR101430 | U20 - IES-514 - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 0 | 10780.BU.BU.MH
C220132BUSSAR101560 | U-20 - NMCB - Waterproofing Works | BU | BUARRF | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8935 | 0 | 10780.BU.BU.MH
C220132BUSSAR101580 | U20 - IES-513 - Install Rockwool Insulation | BU | BUARPT | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 0 | 10780.BU.BU.MH
C220132BUSSAR101620 | U20 - IES-513 - Interlocking Block Paving Works | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 0 | 10780.BU.BU.MH
C220132BUSSAR101630 | U20 - SS-525 - Interlocking Block Paving Works (Elect. Subst.) | BU | BUARIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSAR101640 | U20 - NMCB - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10780.BU.BU.MH
C220132BUSSAR101800 | U20 - IES-513 - Waterproofing Works | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 4.484 | 10780.BU.BU.MH
C220132BUSSAR101840 | U20 - OMS-015 - Waterproofing Works | BU | BUARRF | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSAR101880 | U20 - OMS-014 - Install Fence & Gates | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0 | 10780.BU.BU.MH
C220132BUSSAR101910 | U20 - OMS-014 - Install Hand Railing | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0 | 10780.BU.BU.MH
C220132BUSSAR101920 | U20 - OMS-014 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0 | 10780.BU.BU.MH
C220132BUSSCS100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) CF To GF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35408 | 1852.1445 | 10610.BU.CO.M3 | 89.43 | 89.43
C220132BUSSCS100020 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Internal Columns CF TO GF- by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25529 | 962.7769 | 10610.BU.CO.M3 | 47.22 | 47.22
C220132BUSSCS100070 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Internal Columns (Elect. Subst.) GF to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 110.6335 | 10610.BU.CO.M3 | 65 | 65
C220132BUSSCS100160 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14630 | 316.1917 | 10610.BU.CO.M3 | 701.59 | 701.5871
C220132BUSSCS100190 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 112.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6923 | 70.8034 | 10610.BU.CO.M3 | 973 | 972.9973
C220132BUSSCS100200 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10375 | 159.0207 | 10610.BU.CO.M3 | 273.69 | 273.6892
C220132BUSSFO100710 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 55 | 0
C220132BUSSFO100750 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132BUSSFO100750 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132BUSSFO100810 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 27 | 0
C220132BUSSFO100850 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1096 | 0 | 10610.BU.CO.M3 | 44 | 0
C220132BUSSFO100850 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1096 | 0 | 10610.BU.CO.M3 | 44 | 0
C220132BUSSFO100960 | U20 - SS-523 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1096 | 0 | 10780.BU.BU.MH
C220132BUSSGR100050 | U20 - SS-521 - Building Grounding Install. (Elect. Subst.) | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5048 | 0 | 10780.BU.BU.MH
C220132BUSSGR100080 | U20 - IES-513 - Building Grounding Install. | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4453 | 0 | 10780.BU.BU.MH
C220132BUSSGR100220 | U20 - SS-520 - Corrosion Monitoring and Protection to Sub structure (NEW) | BU | BUSSGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52222 | 4028.7926 | 10780.BU.BU.MH
C220132BUTRAR100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Firewall Foundation and Walls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19294 | 516.95 | 10610.BU.CO.M3 | 1372.16 | 1289.8282
C220132BUTRAR100040 | U20 - SS-521 - Plastering / Surface Preparation Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8510 | 0 | 10610.BU.AR.M2 | 915 | 0
C220132BUTRAR100060 | U20 - SS-521 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10610.BU.AR.M2 | 915 | 0
C220132BUTRFO100060 | U20 - SS-521 - Excavation and Compaction (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10096 | 150.5795 | 10780.BU.BU.MH
C220132BUTRFO100090 | U20 - SS-522 - Excavation and Compaction (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38682 | 2210.4556 | 10780.BU.BU.MH
C220132BUTRFO100100 | U20 - SS-522 - Blinding and Water Proofing (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18766 | 520.2586 | 10780.BU.BU.MH
C220132BUTRFO100110 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Firewall Foundations & Wallsl-by TARGET | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16731 | 413.5219 | 10610.BU.CO.M3 | 361 | 361
C220132BUTRFO100120 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Firewall Foundation & Walls -by TARGET | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26809 | 1061.7693 | 10610.BU.CO.M3 | 648 | 648
C220132BUSSAR101770 | U20 - OMS-015 - Install Maintenance Shed | BU | BUARFU | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 969 | 0 | 10780.BU.BU.MH
C220132BUSSAR101780 | U20 - OMS-013 - Install Fence & Gates | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10780.BU.BU.MH
C220132BUSSAR101820 | U20 - IES-513 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 0 | 10780.BU.BU.MH
C220132BUSSAR101850 | U20 - OMS-014 - Install Maintenance Shed | BU | BUARFU | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 842 | 0 | 10780.BU.BU.MH
C220132BUSSAR101860 | U20 - OMS-015 - Install Ladder and Cage | BU | BUARCP | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSCS100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) CF To GF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35408 | 1852.1445 | 10610.BU.CO.M3 | 89.43 | 89.43
C220132BUSSCS100020 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Internal Columns CF TO GF- by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25529 | 962.7769 | 10610.BU.CO.M3 | 47.22 | 47.22
C220132BUSSCS100040 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev. 102.40 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25019 | 924.7172 | 10610.BU.CO.M3 | 36.68 | 36.68
C220132BUSSCS100051 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 102 - by OQC | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 62.2266 | 10610.BU.CO.M3 | 3.73 | 3.73
C220132BUSSCS100060 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20180 | 601.6149 | 10610.BU.CO.M3 | 46.43 | 46.43
C220132BUSSCS100080 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 106.5 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9086 | 121.9641 | 10610.BU.CO.M3 | 803 | 802.9993
C220132BUSSCS100090 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Footings | BU | BUCTFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12211 | 220.2755 | 10610.BU.CO.M3 | 1320 | 1320
C220132BUSSCS100110 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) GF To RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11449 | 193.6504 | 10610.BU.CO.M3 | 123.73 | 123.7301
C220132BUSSCS100160 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14630 | 316.1917 | 10610.BU.CO.M3 | 701.59 | 701.5871
C220132BUSSCS100180 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns CF To GF - by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7277 | 78.2271 | 10610.BU.CO.M3 | 38 | 38
C220132BUSSCS100181 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns CF To GF - by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12447 | 228.8756 | 10610.BU.CO.M3 | 173 | 173
C220132BUSSCS100190 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 112.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6923 | 70.8034 | 10610.BU.CO.M3 | 973 | 972.9973
C220132BUSSCS100210 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 106.45 / 112.30 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9463 | 132.2912 | 10610.BU.CO.M3 | 610.82 | 610.82
C220132BUSSCS100240 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 6.1428 | 10610.BU.CO.M3 | 36.04 | 36.04
C220132BUSSCS100251 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Grade Beams at Elev 101-by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16851 | 419.498 | 10610.BU.CO.M3 | 26 | 26
C220132BUSSCS100260 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 763 | 0.27531 | 10610.BU.CO.M3 | 30 | 9.6
C220132BUSSCS100270 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & External Columns (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8654 | 110.6335 | 10610.BU.CO.M3 | 500 | 499.9998
C220132BUSSCS100280 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 100.00 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 6.1428 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSCS100290 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Grade Beams at EL 100.00 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 8.2 | 8.2
C220132BUSSCS100300 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 53 | 52.9999
C220132BUSSCS100351 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls CF To GF - by NMDC-INFRA | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16851 | 419.498 | 10610.BU.CO.M3 | 465 | 464.9991
C220132BUSSCS100390 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7933 | 92.9648 | 10610.BU.CO.M3 | 53 | 53
C220132BUSSCS100430 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Walls Elev 116.1 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3876 | 22.1966 | 10610.BU.CO.M3 | 243.52 | 243.5191
C220132BUSSCS100451 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Grade Slab - by OQC | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 40.8909 | 10610.BU.CO.M3 | 50 | 50
C220132BUSSCS100470 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns GF to RF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 21.9 | 0
C220132BUSSCS100530 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 70 | 0
C220132BUSSCS100530 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 70 | 0
C220132BUSSCS100560 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 104.500 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.060083 | 10610.BU.CO.M3 | 42.1 | 4.21
C220132BUSSCS100571 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns (Internal) up to RF | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 41.5137 | 10610.BU.CO.M3 | 77 | 77
C220132BUSSCS100580 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Beams and Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10610.BU.CO.M3 | 33.19 | 0
C220132BUSSCS100230 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.32478 | 10610.BU.CO.M3 | 17.28 | 17.28
C220132BUSSCS100260 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 763 | 0.27531 | 10610.BU.CO.M3 | 30 | 9.6
C220132BUSSCS100300 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns CF To GF (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 53 | 52.9999
C220132BUSSCS100320 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 184.2794 | 10610.BU.CO.M3 | 755 | 755
C220132BUSSCS100340 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Walls CF To GF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1958 | 5.6628 | 10610.BU.CO.M3 | 149 | 0
C220132BUSSCS100350 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls CF To GF - by TARGET | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8617 | 109.6958 | 10610.BU.CO.M3 | 50 | 0
C220132BUSSCS100370 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Grade Slab & Intermediate Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 52.8225 | 10610.BU.CO.M3 | 461 | 442.5591
C220132BUSSCS100370 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Grade Slab & Intermediate Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 52.8225 | 10610.BU.CO.M3 | 461 | 442.5591
C220132BUSSCS100450 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Grade Slab-by TARGET | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5301 | 41.5137 | 10610.BU.CO.M3 | 570 | 570
C220132BUSSCS100460 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Roof Beams and Roof Slab at ELEV. 112.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15690 | 363.6735 | 10610.BU.CO.M3 | 1308 | 1307.9992
C220132BUSSCS100470 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns GF to RF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 21.9 | 0
C220132BUSSCS100540 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 104.500 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 1.2691 | 10610.BU.CO.M3 | 106 | 12.72
C220132BUSSCS100540 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 104.500 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 1.2691 | 10610.BU.CO.M3 | 106 | 12.72
C220132BUSSCS100600 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Walls GF To RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1958 | 0 | 10610.BU.CO.M3 | 166 | 0
C220132BUSSCS100600 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Walls GF To RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1958 | 0 | 10610.BU.CO.M3 | 166 | 0
C220132BUSSCS100690 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Walls | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2126 | 0.46345 | 10610.BU.CO.M3 | 36.83 | 0
C220132BUSSCS100710 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Columns - GF To RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 9 | 0
C220132BUTRFO100210 | U20 - SS-523 - Plainting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.BU.AR.M2 | 75 | 0
C220132BUTRGR100020 | U20 - SS-524 - Transf. Yard Grounding (Elect. Subst.) | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1026 | 0 | 10780.BU.BU.MH
C220132BUTRGR100050 | U20 - SS-522 - Transf. Yard Grounding (Elect. Subst.) | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2681 | 0 | 10780.BU.BU.MH
C220132CICT1100020 | U20 - SS-521 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1276 | 0 | 10610.CI.ET.M3 | 319 | 0
C220132CICT1100060 | U20 - SS-524 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1004 | 0 | 10610.CI.ET.M3 | 251 | 0
C220132CICT1100070 | U20 - SS-523 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 232 | 0 | 10610.CI.ET.M3 | 58 | 0
C220132CICT1100080 | U20 - IES-514 - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3401 | 0 | 10780.CI.CI.MH
C220132CICT1100090 | U20 - IES-513 - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3401 | 0 | 10780.CI.CI.MH
C220132CIFC1100040 | U20 - SS-520 - Install Removable Chain Link Fence and Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4241 | 0 | 10780.BU.BU.MH
C220132CISF100031 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12548 | 232.6014 | 10610.BU.CO.M3 | 12.77 | 12.77
C220132CISF100080 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11298 | 144.2569 | 10610.BU.CO.M3 | 56 | 42
C220132CISF100170 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4079 | 1.2289 | 10610.BU.CO.M3 | 61.26 | 3.0599
C220132CISF100180 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 2.3745 | 10610.BU.CO.M3 | 32 | 5.76
C220132CISF100200 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4079 | 0 | 10610.BU.CO.M3 | 39.88 | 0
C220132CISF100210 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8906 | 117.1723 | 10610.BU.CO.M3 | 27 | 27
C220132ELBD100010 | U20 - SS-520 - Bus Ducts Installation (Elect. Subst.) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10780.EL.EL.MH
C220132ELCL100020 | U20 - SS-521 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 26587.81 | 0
C220132ELCL100030 | U20 - SS-522 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.PL.LM | 1598 | 0
C220132BUSSCS100670 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Walls GF to RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 79.5 | 0
C220132BUSSCS100670 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Walls GF to RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 79.5 | 0
C220132BUSSCS100710 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Columns - GF To RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 9 | 0
C220132BUSSCS100720 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5513 | 44.8971 | 10610.BU.CO.M3 | 68.24 | 68.2397
C220132BUSSCS100740 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 103 | 0
C220132BUSSCS100770 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Roof Beams & Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 25.5254 | 10610.BU.CO.M3 | 674 | 307.3777
C220132BUSSCS100780 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 110.150 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 547 | 0 | 10610.BU.CO.M3 | 75 | 0
C220132BUSSCS100780 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 110.150 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 547 | 0 | 10610.BU.CO.M3 | 75 | 0
C220132BUSSCS100890 | U20 - SS-525 - Concrete Parapet Wall at EL 111.650 (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 13.17 | 0
C220132BUSSCS100901 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Walls & Columns (External) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6891 | 70.155 | 10610.BU.CO.M3 | 366 | 365.9998
C220132BUSSCS100930 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Roof Beams | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS100980 | U20 - OMS-015 - Concrete Precast Slab Installation - RF | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS100990 | U20 - IES-514 - Concrete Precast Walls Installationfor Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 0 | 10610.BU.CO.M3 | 65 | 0
C220132BUSSCS101040 | U20 - OMS-014 - Concrete Precast Slab Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSFO100040 | U20 - IES-513 - Excavation and Compaction | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10390 | 159.4795 | 10780.BU.BU.MH
C220132BUSSFO100080 | U20 - SS-521 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17740 | 464.919 | 10780.BU.BU.MH
C220132BUSSFO100150 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16298 | 392.4021 | 10610.BU.CO.M3 | 1030 | 1030
C220132BUSSFO100170 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14822 | 324.5445 | 10610.BU.CO.M3 | 216.3 | 216.3
C220132BUSSCS100380 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Grade Beams (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 18 | 18
C220132BUSSCS100400 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1436 | 2.7167 | 10610.BU.CO.M3 | 14 | 12.0499
C220132BUSSCS100400 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1436 | 2.7167 | 10610.BU.CO.M3 | 14 | 12.0499
C220132BUSSCS100440 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns GF To RF (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 46.98 | 0
C220132BUSSCS100460 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Roof Beams and Roof Slab at ELEV. 112.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15690 | 363.6735 | 10610.BU.CO.M3 | 1308 | 1307.9992
C220132BUSSCS100480 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 105.45 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12064 | 215.0074 | 10610.BU.CO.M3 | 685 | 684.9992
C220132BUSSCS100490 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns - GF to RF | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9530 | 134.1758 | 10610.BU.CO.M3 | 362 | 362
C220132BUSSCS100490 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns - GF to RF | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9530 | 134.1758 | 10610.BU.CO.M3 | 362 | 362
C220132BUSSCS100520 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 64 | 63.9999
C220132BUSSCS100550 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 112.3 & 116.9 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6841 | 69.1345 | 10610.BU.CO.M3 | 824.6 | 824.5994
C220132BUSSCS100560 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 104.500 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0.060083 | 10610.BU.CO.M3 | 42.1 | 4.21
C220132BUSSCS100570 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns (Internal) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8694 | 111.6597 | 10610.BU.CO.M3 | 18 | 18
C220132BUSSCS100570 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns (Internal) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8694 | 111.6597 | 10610.BU.CO.M3 | 18 | 18
C220132BUSSCS100580 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Beams and Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10610.BU.CO.M3 | 33.19 | 0
C220132BUSSCS100590 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev. 104.40 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 2.5643 | 10610.BU.CO.M3 | 108.9 | 56.6302
C220132BUSSCS100590 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev. 104.40 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 2.5643 | 10610.BU.CO.M3 | 108.9 | 56.6302
C220132BUSSCS100620 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132ELCL100040 | U20 - SS-520 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 21.3563 | 10610.EL.PL.LM | 33296.08 | 26636.864
C220132ELCL100042 | U20 - SS-520-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100050 | U20 - SS-526 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 847 | 0 | 10610.EL.PL.LM | 2327.71 | 0
C220132ELCL100060 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.8552 | 10610.EL.PL.LM | 21575.12 | 21575.12
C220132ELCL100060 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.8552 | 10610.EL.PL.LM | 21575.12 | 21575.12
C220132ELCL100070 | U20 - SS-525 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.EL.PL.LM | 2354.75 | 0
C220132ELCL100080 | U20 - SS-522 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 2.615 | 10610.EL.PL.LM | 32774.66 | 2248.3417
C220132ELCL100081 | U20 - SS-522-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 16387.33 | 0
C220132ELCL100082 | U20 - SS-522-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 16387.33 | 0
C220132ELCL100090 | U20 - NMCB - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41475 | 0 | 10610.EL.PL.LM | 129137.85 | 0
C220132ELCL100100 | U20 - SS-521 - Main Power Electrical Cable (132 KV) Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 316 | 0
C220132ELCL100101 | U20 - SS-521-CFP1- Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 4431.41 | 0
C220132ELCL100120 | U20 - SS-523 - Electrical Cable Laying from SS-501 to SS-523 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.EL.PL.LM | 14371.82 | 0
C220132ELCL100130 | U20 - OMS-013 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1332 | 0 | 10610.EL.PL.LM | 2442.3 | 0
C220132ELCL100141 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 30 | 0
C220132ELCL100142 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 601 | 0
C220132ELCL100150 | U20 - IES-514 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9120 | 0 | 10610.EL.PL.LM | 16720.14 | 0
C220132ELCL100160 | U20 - IES-513 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9041 | 0 | 10610.EL.PL.LM | 16574.65 | 0
C220132ELCL100170 | U20 - SS-525 - Main Power Electrical Cable Laying from SS-504 to SS-525 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.EL.PL.LM | 785.35 | 0
C220132BUSSCS100630 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Walls GF To RF (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 517 | 0
C220132BUSSCS100640 | U20 - IES-514 - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 33.0141 | 10610.BU.CO.M3 | 360 | 0
C220132BUSSCS100640 | U20 - IES-514 - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 33.0141 | 10610.BU.CO.M3 | 360 | 0
C220132BUSSCS100650 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Beams and Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3711 | 20.3433 | 10610.BU.CO.M3 | 862 | 861.9981
C220132BUSSCS100720 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5513 | 44.8971 | 10610.BU.CO.M3 | 68.24 | 68.2397
C220132BUSSCS100790 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132BUSSCS100840 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Parapet Walls up to Elev 111.65 (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 18.5 | 0
C220132BUSSCS100870 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Slab | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9530 | 44.5463 | 10610.BU.CO.M3 | 837 | 0
C220132BUSSCS100920 | U20 - IES-514 - Concrete Precast Slab Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 22.0094 | 10610.BU.CO.M3 | 285 | 0
C220132BUSSCS100930 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Roof Beams | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS100940 | U20 - OMS-014 - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 60 | 0
C220132BUSSCS100950 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Dome | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7446 | 0 | 10610.BU.CO.M3 | 438 | 0
C220132BUSSCS100960 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Beams and Slab At Elev 110.30 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 108.9 | 0
C220132BUSSCS101000 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Roof Beams | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS101020 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1766 | 0 | 10610.BU.CO.M3 | 17.5 | 0
C220132BUSSCS101020 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1766 | 0 | 10610.BU.CO.M3 | 17.5 | 0
C220132BUSSCS101060 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Parapet Wall (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7851 | 33.146 | 10610.BU.CO.M3 | 80 | 0
C220132BUSSCS101070 | U20 - OMS-014 - Concrete Precast Walls Installation for Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 14 | 0
C220132BUSSFO100180 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11250 | 186.9673 | 10610.BU.CO.M3 | 90 | 90
C220132BUSSFO100180 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11250 | 186.9673 | 10610.BU.CO.M3 | 90 | 90
C220132BUSSFO100220 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13796 | 281.1659 | 10610.BU.CO.M3 | 160.17 | 160.17
C220132BUSSFO100240 | U20 - SS-526 - UG Survey and Relocation of Existing Services (Elect. Subst.) | SP | SPDS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 333 | 0.16382 | 10780.SP.SP.MH
C220132BUSSFO100250 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns and Walls (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23323 | 803.5892 | 10610.BU.CO.M3 | 365.38 | 365.38
C220132BUSSFO100330 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns & Walls (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24894 | 915.5025 | 10610.BU.CO.M3 | 224 | 224
C220132BUSSFO100360 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 927 | 1.2692 | 10610.BU.CO.M3 | 53 | 53
C220132BUSSFO100380 | U20 - IES-513 - Blinding and Water Proofing | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1272 | 2.3907 | 10780.BU.BU.MH
C220132BUSSFO100430 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14843 | 325.4714 | 10610.BU.CO.M3 | 701 | 701
C220132BUSSFO100460 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22405 | 741.5703 | 10610.BU.CO.M3 | 34 | 34
C220132BUSSFO100460 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22405 | 741.5703 | 10610.BU.CO.M3 | 34 | 34
C220132BUSSFO100480 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1224 | 2.2125 | 10610.BU.CO.M3 | 171.7 | 171.6997
C220132BUSSFO100490 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3453 | 17.6134 | 10610.BU.CO.M3 | 25 | 25
C220132BUSSFO100500 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8697 | 111.7349 | 10610.BU.CO.M3 | 844 | 844
C220132BUSSFO100510 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns & Walls (Floor Beam Level) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11768 | 204.5921 | 10610.BU.CO.M3 | 240 | 240
C220132BUSSFO100620 | U20 - IES-513 - Backfilling and Compaction upto Grade Slab | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12193 | 219.6198 | 10780.BU.BU.MH
C220132BUSSFO100640 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 508 | 0.3811 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSCS100730 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Beams and Slab at EL 110.25 (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2039 | 0 | 10610.BU.CO.M3 | 109.35 | 0
C220132BUSSCS100740 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Walls (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 103 | 0
C220132BUSSCS100760 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Beams | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 90.2048 | 10610.BU.CO.M3 | 335 | 169.5904
C220132BUSSCS100760 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Beams | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11169 | 90.2048 | 10610.BU.CO.M3 | 335 | 169.5904
C220132BUSSCS100790 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Grade Slab | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 818 | 0 | 10610.BU.CO.M3 | 25 | 0
C220132BUSSCS100810 | U20 - OMS-015 - Concrete Precast Walls Installation - GF | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 60 | 0
C220132BUSSCS100810 | U20 - OMS-015 - Concrete Precast Walls Installation - GF | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 60 | 0
C220132BUSSCS100820 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Parapet Wall | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 254 | 0 | 10610.BU.CO.M3 | 10.85 | 0
C220132BUSSCS100850 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0.31867 | 10610.BU.CO.M3 | 9 | 3.6
C220132BUSSCS100870 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Slab | BU | BUPCIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9530 | 44.5463 | 10610.BU.CO.M3 | 837 | 0
C220132BUSSCS100890 | U20 - SS-525 - Concrete Parapet Wall at EL 111.650 (Elect. Subst.) | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10610.BU.CO.M3 | 13.17 | 0
C220132BUSSCS100901 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Walls & Columns (External) up to RF | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6891 | 70.155 | 10610.BU.CO.M3 | 366 | 365.9998
C220132BUSSCS100920 | U20 - IES-514 - Concrete Precast Slab Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 22.0094 | 10610.BU.CO.M3 | 285 | 0
C220132BUSSCS100940 | U20 - OMS-014 - Concrete Precast Walls Installation | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 60 | 0
C220132BUSSCS100960 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Beams and Slab At Elev 110.30 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 0 | 10610.BU.CO.M3 | 108.9 | 0
C220132BUSSCS100970 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Beams and Slab at Elev 111.3 (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9575 | 135.4348 | 10610.BU.CO.M3 | 1037 | 1037
C220132BUSSCS100980 | U20 - OMS-015 - Concrete Precast Slab Installation - RF | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS100990 | U20 - IES-514 - Concrete Precast Walls Installationfor Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6103 | 0 | 10610.BU.CO.M3 | 65 | 0
C220132ELCL100180 | U20 - SS-526 - Main Power Electrical Cable Laying from SS-503 to SS-526 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 847 | 0 | 10610.EL.PL.LM | 776.33 | 0
C220132ELCL100200 | U20 - IES-514 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9120 | 0 | 10610.EL.PL.LM | 16720.14 | 0
C220132ELCL100210 | U20 - OMS-013 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1332 | 0 | 10610.EL.PL.LM | 2442.3 | 0
C220132ELCL100220 | U20 - OMS-015 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 0 | 10610.EL.PL.LM | 6287.91 | 0
C220132ELCL100230 | U20 - OMS-015 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 0 | 10610.EL.PL.LM | 6287.91 | 0
C220132ELCL1008 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-500 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 0 | 10610.EL.LC.LM | 601 | 0
C220132ELCL1010 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-521 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.LC.LM | 316 | 0
C220132ELCL1015 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-520 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.LC.LM | 30 | 0
C220132ELCO100010 | U20 - SS-526 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 924 | 0 | 10780.EL.EL.MH
C220132ELCO100060 | U20 - SS-522 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20935 | 0 | 10780.EL.EL.MH
C220132ELCO100080 | U20 - SS-523 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5229 | 0 | 10780.EL.EL.MH
C220132ELEL100080 | U20 - SS-523 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 871 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C220132ELEL100110 | U20 - IES-514 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2211 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C220132ELEL100130 | U20 - OMS-015 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEL100140 | U20 - IES-513 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2192 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C220132ELEL100150 | U20 - OMS-014 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 363 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEQ1100030 | U20 - SS-520 - ASD Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3191 | 0 | 10780.EL.EL.MH
C220132ELEQ1100150 | U20 - SS-521 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2711 | 0 | 10780.EL.EL.MH
C220132ELEQ1100160 | U20 - SS-524 - GIS Protection Panel Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1822 | 0 | 10780.EL.EL.MH
C220132BUSSFO100650 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1468 | 3.1842 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSFO100680 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 472 | 0.15089 | 10610.BU.CO.M3 | 5.45 | 2.18
C220132BUSSFO100700 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4577 | 30.949 | 10610.BU.CO.M3 | 75 | 75
C220132BUSSFO100720 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3173 | 14.8734 | 10610.BU.CO.M3 | 108 | 107.9999
C220132BUSSFO100720 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3173 | 14.8734 | 10610.BU.CO.M3 | 108 | 107.9999
C220132BUSSFO100730 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Floor beams/Grade Beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3923 | 22.7344 | 10610.BU.CO.M3 | 78 | 78
C220132BUSSFO100740 | U20 - OMS-014 - Blinding and Water Proofing | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 601 | 0.53395 | 10780.BU.BU.MH
C220132BUSSFO100760 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 650 | 0.62368 | 10610.BU.CO.M3 | 55 | 55
C220132BUSSFO100790 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0.37687 | 10610.BU.CO.M3 | 25 | 25
C220132BUSSFO100830 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5936 | 10.9319 | 10610.BU.CO.M3 | 99 | 19.7999
C220132BUSSFO100840 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0.22424 | 10610.BU.CO.M3 | 27 | 14.85
C220132BUSSFO100880 | U20 - SS-526 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1713 | 0 | 10780.BU.BU.MH
C220132BUSSFO100890 | U20 - SS-525 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0 | 10780.BU.BU.MH
C220132BUSSFO100900 | U20 - SS-524 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 0 | 10780.BU.BU.MH
C220132BUSSFO100910 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for HVAC Room Foundations | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 5.3792 | 10610.BU.CO.M3 | 14 | 14
C220132BUSSGR100090 | U20 - IES-514 - Building Grounding Install. | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6408 | 0 | 10780.BU.BU.MH
C220132BUSSGR100100 | U20 - OMS-013 - Building Grounding Install. | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1581 | 0.4062 | 10780.BU.BU.MH
C220132BUTRAR100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Firewall Foundation and Walls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19294 | 516.95 | 10610.BU.CO.M3 | 1372.16 | 1289.8282
C220132BUSSFO100010 | U20 - SS-521 - Excavation and Compaction (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30288 | 1355.2159 | 10780.BU.BU.MH
C220132BUSSFO100030 | U20 - SS-524 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24513 | 887.6854 | 10780.BU.BU.MH
C220132BUSSFO100130 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26715 | 1054.345 | 10610.BU.CO.M3 | 1337.49 | 1337.49
C220132BUSSFO100130 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26715 | 1054.345 | 10610.BU.CO.M3 | 1337.49 | 1337.49
C220132BUSSFO100140 | U20 - OMS-013 - Blinding and Water Proofing | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 981 | 1.4222 | 10780.BU.BU.MH
C220132BUSSFO100170 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14822 | 324.5445 | 10610.BU.CO.M3 | 216.3 | 216.3
C220132BUSSFO100181 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Walls & Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11250 | 186.9673 | 10610.BU.CO.M3 | 206 | 206
C220132BUSSFO100250 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Columns and Walls (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23323 | 803.5892 | 10610.BU.CO.M3 | 365.38 | 365.38
C220132BUSSFO100270 | U20 - SS-521 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10817 | 172.8569 | 10780.BU.BU.MH
C220132BUSSFO100280 | U20 - SS-523 - Excavation and Compaction (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3045 | 13.6982 | 10780.BU.BU.MH
C220132BUSSFO100300 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23959 | 848.0162 | 10610.BU.CO.M3 | 267 | 267
C220132BUSSFO100320 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17307 | 442.5085 | 10610.BU.CO.M3 | 206 | 206
C220132BUSSFO100340 | U20 - SS-525 - Excavation and Compaction (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3398 | 17.0597 | 10780.BU.BU.MH
C220132BUSSFO100350 | U20 - SS-526 - Excavation and Compaction (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7831 | 90.5931 | 10780.BU.BU.MH
C220132BUSSFO100360 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 927 | 1.2692 | 10610.BU.CO.M3 | 53 | 53
C220132BUSSFO100390 | U20 - SS-523 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1157 | 1.9779 | 10780.BU.BU.MH
C220132BUSSFO100470 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0.69488 | 10610.BU.CO.M3 | 128.2 | 98.7096
C220132BUSSFO100470 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 781 | 0.69488 | 10610.BU.CO.M3 | 128.2 | 98.7096
C220132ELEQ1100260 | U20 - SS-522 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3271 | 0 | 10780.EL.EL.MH
C220132ELEQ1100300 | U20 - SS-526 - ASD Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 144 | 0 | 10780.EL.EL.MH
C220132ELEQ1100370 | U20 - IES-514 - Electrical Equipment Installation | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6218 | 0 | 10780.EL.EL.MH
C220132ELEQ1100410 | U20 - SS-523 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 817 | 0 | 10780.EL.EL.MH
C220132ELEQ1100430 | U20 - SS-526 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 144 | 0 | 10780.EL.EL.MH
C220132ELTI100010 | U20 - SS-521 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4819 | 2.6589 | 10780.EL.EL.MH
C220132ELTI100011 | U20 - SS-521-CFP1- Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4819 | 8.6802 | 10780.EL.EL.MH
C220132ELTI100100 | U20 - IES-514 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8291 | 0 | 10780.EL.EL.MH
C220132ELTR100040 | U20 - SS-522 - Transformer Inst. 580-EE-2214/15/16/17/21/22 A/B, 518-EE-2221/22, 516-EE-2221,517-EE-2221 (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10468 | 0 | 10780.EL.EL.MH
C220132ELTR100050 | U20 - SS-523 - Transformer Inst. (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2614 | 0 | 10780.EL.EL.MH
C220132ELTR100060 | Transformer Inst. | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22623 | 0 | 10780.EL.EL.MH
C220132ELTR100070 | U20 - SS-524 - Emergency Diesel Generators (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2916 | 0 | 10780.EL.EL.MH
C220132HVIN100030 | U20 - SS-521 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4327 | 0 | 10780.BU.BU.MH
C220132HVIN100050 | U20 - SS-520 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3816 | 0 | 10780.BU.BU.MH
C220132HVIN100180 | U20 - SS-523 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1035 | 0 | 10780.BU.BU.MH
C220132HVIN100200 | U20 - SS-525 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10780.BU.BU.MH
C220132HVIN100230 | U20 - SS-521 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1442 | 0 | 10780.BU.BU.MH
C220132HVIN100240 | U20 - SS-525 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 469 | 0 | 10780.BU.BU.MH
C220132HVIN100250 | U20 - SS-522 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3447 | 0 | 10780.BU.BU.MH
C220132HVIN100270 | U20 - SS-522 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3447 | 0 | 10780.BU.BU.MH
C220132BUSSCS101000 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Roof Beams | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 722 | 0 | 10610.BU.CO.M3 | 17 | 0
C220132BUSSCS101050 | U20 - OMS-015 - Concrete Precast Walls Installation for Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 14 | 0
C220132BUSSCS101050 | U20 - OMS-015 - Concrete Precast Walls Installation for Parapet Wall | BU | BUPCIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.BU.CO.M3 | 14 | 0
C220132BUSSFO100020 | U20 - SS-524 - Excavation and Compaction (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21207 | 664.3797 | 10780.BU.BU.MH
C220132BUSSFO100060 | U20 - SS-520 - Excavation and Compaction (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29472 | 1283.1618 | 10780.BU.BU.MH
C220132BUSSFO100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19268 | 548.4632 | 10610.BU.CO.M3 | 800.83 | 800.83
C220132BUSSFO100100 | U20 - SS-520 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27351 | 1105.1467 | 10780.BU.BU.MH
C220132BUSSFO100160 | U20 - SS-522 - Dewatering Installation (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17234 | 438.7833 | 10780.BU.BU.MH
C220132BUSSFO100200 | U20 - SS-524 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9691 | 131.806 | 10780.BU.BU.MH
C220132BUSSFO100260 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7660 | 86.6783 | 10610.BU.CO.M3 | 2677 | 2677
C220132BUSSFO100290 | U20 - SS-520 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18870 | 526.0402 | 10780.BU.BU.MH
C220132BUSSFO100300 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23959 | 848.0162 | 10610.BU.CO.M3 | 267 | 267
C220132BUSSFO100320 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17307 | 442.5085 | 10610.BU.CO.M3 | 206 | 206
C220132BUSSFO100330 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Columns & Walls (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24894 | 915.5025 | 10610.BU.CO.M3 | 224 | 224
C220132BUSSFO100420 | U20 - IES-514 - Blinding and Water Proofing | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10070 | 149.8022 | 10780.BU.BU.MH
C220132BUSSFO100440 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1705 | 4.2953 | 10610.BU.CO.M3 | 205 | 205
C220132BUSSFO100490 | U20 - OMS-013 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3453 | 17.6134 | 10610.BU.CO.M3 | 25 | 25
C220132BUSSFO100530 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0.11028 | 10610.BU.CO.M3 | 9.22 | 9.22
C220132BUTRAR100020 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Transformer Foundation (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6058 | 35.5415 | 10610.BU.CO.M3 | 932 | 559.2014
C220132BUTRAR100040 | U20 - SS-521 - Plastering / Surface Preparation Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8510 | 0 | 10610.BU.AR.M2 | 915 | 0
C220132BUTRAR100050 | U20 - SS-522 - Plastering/Surface Preparation Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9000 | 0 | 10610.BU.AR.M2 | 754 | 0
C220132BUTRAR100070 | U20 - SS-520 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15902 | 0 | 10610.BU.AR.M2 | 1830 | 0
C220132BUTRAR100080 | U20 - SS-522 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8617 | 0 | 10610.BU.AR.M2 | 754 | 0
C220132BUTRAR100100 | U20 - SS-524 - Plastering/ Surface Preparation Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4447 | 0 | 10780.BU.BU.MH
C220132BUTRAR100120 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns and Walls | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 34.495 | 10610.BU.CO.M3 | 50 | 26
C220132BUTRAR100120 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Columns and Walls | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 34.495 | 10610.BU.CO.M3 | 50 | 26
C220132BUTRAR100130 | U20 - NMCB - Plastering Works | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10610.BU.AR.M2 | 65 | 0
C220132BUTRFO100010 | U20 - SS-520 - Excavation and Compaction (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6785 | 68.0075 | 10780.BU.BU.MH
C220132BUTRFO100040 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Transformer Foundations (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26927 | 834.9583 | 10610.BU.CO.M3 | 1345.71 | 1009.2816
C220132BUTRFO100110 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Firewall Foundations & Wallsl-by TARGET | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16731 | 413.5219 | 10610.BU.CO.M3 | 361 | 361
C220132BUTRFO100120 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Firewall Foundation & Walls -by TARGET | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26809 | 1061.7693 | 10610.BU.CO.M3 | 648 | 648
C220132BUTRFO100140 | U20 - NMCB - Blinding and Water Proofing | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2680 | 10.6123 | 10780.BU.BU.MH
C220132BUTRFO100150 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Transformer Foundations | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 11.2027 | 10610.BU.CO.M3 | 130 | 49.4
C220132BUTRFO100200 | U20 - SS-523 - Plastering Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.BU.AR.M2 | 75 | 0
C220132BUTRFO100210 | U20 - SS-523 - Plainting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.BU.AR.M2 | 75 | 0
C220132BUTRGR100040 | U20 - SS-520 - Transf. Yard Grounding (Elect. Subst.) | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3392 | 0 | 10780.BU.BU.MH
C220132HVIN100320 | U20 - SS-523 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 731 | 0 | 10780.BU.BU.MH
C220132HVIN100390 | U20 - NMCB -Equipment Erection Chillers | BU | HVIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3127 | 0 | 10780.BU.BU.MH
C220132HVIN100470 | U20 - IES-513 - Install Air Handling Units | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2545 | 0 | 10780.BU.BU.MH
C220132HVIN100510 | U20 - IES-514 - Install Air Handling Units | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3204 | 0 | 10780.BU.BU.MH
C220132HVIN100540 | U20 - OMS-013 -HVAC Connections | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 254 | 0 | 10780.BU.BU.MH
C220132HVIN100570 | U20 - OMS-015 -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1163 | 0 | 10780.BU.BU.MH
C220132HVIN100630 | U20 - OMS-015 - Install Air Handling Units | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 664 | 0 | 10780.BU.BU.MH
C220132HVIN100640 | U20 - IES-514 -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2136 | 0 | 10780.BU.BU.MH
C220132INCO100050 | U20 - SS-522 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2812 | 0 | 10780.IN.IN.MH
C220132INCO100080 | U20 - IES-514 - Communication System Installation | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7705 | 0 | 10780.IN.IN.MH
C220132INCO100100 | U20 - OMS-013 - Communication System Installation | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 734 | 0 | 10780.IN.IN.MH
C220132INCO100130 | U20 - OMS-014 - Communication System Installation | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.IN.IN.MH
C220132INDC100010 | U20 - NMCB - ICSS/DCS/VMS/ESD Cabinets Installation | IN | INDC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 286 | 0 | 10780.IN.IN.MH
C220132INFG100020 | U20 - SS-521 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2278 | 0 | 10780.IN.IN.MH
C220132INFG100140 | U20 - IES-514 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C220132INFG100160 | U20 - SS-525 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10780.IN.IN.MH
C220132INFG100190 | U20 - IES-513 - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0.085086 | 10780.IN.IN.MH
C220132INFG100220 | U20 - OMS-013 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0 | 10780.IN.IN.MH
C220132INFG100240 | U20 - OMS-015 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 567 | 0 | 10780.IN.IN.MH
C220132INFO100020 | U20 - IES-513 - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132BUTRGR1011 | U20 - SS-516 - Transf. Fnds Yard Concrete Structure #B (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10265 | 155.6626 | 10610.BU.CO.M3 | 149 | 148.9994
C220132CICT1100010 | U20 - SS-520 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1820 | 0 | 10610.CI.ET.M3 | 455 | 0
C220132CICT1100020 | U20 - SS-521 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1276 | 0 | 10610.CI.ET.M3 | 319 | 0
C220132CICT1100030 | U20 - SS-522 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 708 | 0 | 10610.CI.ET.M3 | 177 | 0
C220132CICT1100040 | U20 - SS-526 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44 | 0 | 10610.CI.ET.M3 | 11 | 0
C220132CICT1100050 | U20 - SS-525 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44 | 0 | 10610.CI.ET.M3 | 11 | 0
C220132CICT1100110 | U20 - OMS-013 - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3401 | 0 | 10780.CI.CI.MH
C220132CIFC1100050 | U20 - NMCB - Install Removable Chain Link Fence and Gates | BU | BUARSG | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10780.BU.BU.MH
C220132CISF100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8057 | 95.899 | 10610.BU.CO.M3 | 69.89 | 69.8897
C220132CISF100010 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8057 | 95.899 | 10610.BU.CO.M3 | 69.89 | 69.8897
C220132CISF100031 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12548 | 232.6014 | 10610.BU.CO.M3 | 12.77 | 12.77
C220132CISF100060 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3534 | 18.4524 | 10610.BU.CO.M3 | 69 | 69
C220132CISF100070 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0.044111 | 10610.BU.CO.M3 | 61.26 | 24.4997
C220132CISF100070 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0.044111 | 10610.BU.CO.M3 | 61.26 | 24.4997
C220132CISF100100 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0 | 10610.BU.CO.M3 | 39.88 | 0
C220132CISF100140 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 4.1077 | 10610.BU.CO.M3 | 26.5 | 8.4801
C220132CISF100140 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 4.1077 | 10610.BU.CO.M3 | 26.5 | 8.4801
C220132INFO100030 | U20 - NMCB - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132INML100020 | U20 - IES-514 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121880.94 | 0
C220132INML100030 | U20 - IES-513 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121880.94 | 0
C220132MEMC100020 | U20 - SS-521 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6635 | 16.4527 | 10610.BU.CO.M3 | 1 | 0.25
C220132MEMC100070 | U20 - SS-522 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10780.EL.EL.MH
C220132MEMC100080 | U20 - NMCB - Pipes and Fittings | ME | MEMC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2513 | 0 | 10780.ME.ME.MH
C220132MEMC100100 | U20 - SS-521 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 0 | 10780.EL.EL.MH
C220132MEMC100160 | U20 - SS-522 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7851 | 18.2121 | 10610.BU.CO.M3 | 1 | 0.2
C220132MEMC100180 | U20 - SS-524 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 0 | 10780.EL.EL.MH
C220132MEMC100230 | U20 - OMS-015 - Pipes & Fittings | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0 | 10780.ME.ME.MH
C220132MEMC100270 | U20 - SS-523 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1462 | 0.78923 | 10610.BU.CO.M3 | 1 | 0.25
C220132MEMC100380 | U20 - NMCB - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10780.EL.EL.MH
C220132MEMC100430 | U20 - OMS-015 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 664 | 0 | 10610.BU.CO.M3 | 0.94 | 0
C220132MEMC100440 | U20 - IES-514 - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2211 | 0 | 10780.EL.EL.MH
C220132MEMC100450 | U20 - SS-523 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 871 | 0 | 10780.EL.EL.MH
C220132MEMC100510 | U20 - OMS-014 - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 363 | 0 | 10780.EL.EL.MH
C220132MEMC100520 | U20 - OMS-014 - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 363 | 0 | 10780.EL.EL.MH
C220132METC100010 | U20 - SS-524 - EOT Crane Erection (Elect. Subst.) | ME | METC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 762 | 0.85564 | 10780.ME.ME.MH
C220132STSH2100020 | U20 - SS-521 - Install Roof Structure and Corrugated Steel Sheeting (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6202 | 0 | 10780.BU.BU.MH
C220132STSH2100030 | U20 - SS-522 - Install Roof Structure and Corrugated Steel Sheeting (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6702 | 0 | 10780.BU.BU.MH
C220132CISF100170 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4079 | 1.2289 | 10610.BU.CO.M3 | 61.26 | 3.0599
C220132CISF100180 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 2.3745 | 10610.BU.CO.M3 | 32 | 5.76
C220132ELBD100030 | U20 - SS-524 - Bus Ducts Installation (Elect. Subst.) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1944 | 0 | 10780.EL.EL.MH
C220132ELBD100040 | U20 - SS-522 - Bus Ducts Installation (Elect. Subst.) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10780.EL.EL.MH
C220132ELBD100050 | U20 -NMCB - Bus Ducts Installation (Elect. Subst.) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7541 | 0 | 10780.EL.EL.MH
C220132ELCL100010 | U20 - SS-520 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10780.EL.EL.MH
C220132ELCL100011 | U20 - SS-520-CFP1 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 5549.24 | 0
C220132ELCL100020 | U20 - SS-521 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 26587.81 | 0
C220132ELCL100031 | U20 - SS-522-CFP1 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 3.2239 | 10610.EL.LC.LM | 5462.34 | 470.8537
C220132ELCL100032 | U20 - SS-522-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 5462.34 | 0
C220132ELCL100040 | U20 - SS-520 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 21.3563 | 10610.EL.PL.LM | 33296.08 | 26636.864
C220132ELCL100041 | U20 - SS-520-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100042 | U20 - SS-520-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100062 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.311 | 10610.EL.LC.LM | 10787.56 | 10787.56
C220132ELCL100062 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.311 | 10610.EL.LC.LM | 10787.56 | 10787.56
C220132ELCL100090 | U20 - NMCB - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41475 | 0 | 10610.EL.PL.LM | 129137.85 | 0
C220132ELCL100102 | U20 - SS-521-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 4431.41 | 0
C220132ELCL100110 | U20 - NMCB - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41475 | 0 | 10610.EL.PL.LM | 43045.95 | 0
C220132ELCL100120 | U20 - SS-523 - Electrical Cable Laying from SS-501 to SS-523 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.EL.PL.LM | 14371.82 | 0
C220134ELCL000090 | U20 - SS-515 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8099 | 0 | 10780.EL.EL.MH
C220134ELCL000410 | U20 - SS-501 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12149 | 0 | 10780.EL.EL.MH
C220134ELCO000140 | U20 - SS-515 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3378 | 0 | 10780.EL.EL.MH
C220134ELCO000331 | U20 - SS-500 - Electrical (132 KV) Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10780.EL.EL.MH
C220134ELCO000360 | U20 - SS-501 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5066 | 0 | 10780.EL.EL.MH
C220134ELCO000380 | U20 - IES-501- Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2263 | 0 | 10780.EL.EL.MH
C220134ELEQ000160 | U20 - IES-15 - AC UPS Modification | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6099 | 0 | 10780.EL.EL.MH
C220134ELEQ000260 | U20 - SS-500 - Emergency Switchgear 580-EE-0005 Modification | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10780.EL.EL.MH
C220134ELEQ000290 | U20 - SS-501 - LV Switchgear 580-EE-0105 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELEQ000670 | U20 - Ruwais - New 415V AC MOV Distribution Board / Lighting Distribution Board / Switchgear Modification | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.EL.EL.MH
C220134ELEQ000760 | U20 - SS-516 - TRANSCO BAAB & BABG Substations System Modification Transformer #B (Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000765 | U20 - SS-516 - TRANSCO BAAB & BABG Substations System Modification (Shutdown) for Transformer #A | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000790 | U20 - SS-500 - 132Kv GIS (580-EE-0001) Modification | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10780.EL.EL.MH
C220134ELEQ000810 | U20 - SS-515 - New GTG MCC in MCC Room | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELEQ000840 | U20 - SS-502 - 415V MCC 580-EE-0203 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELEQ000860 | U20 - IES-501 - New UPS Distribution Board 501-PDP-07 (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4624 | 0 | 10780.EL.EL.MH
C220134ELEQ000870 | U20 - IES-504 - New UPS Distribution Board 504-PDB-125/126 (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.EL.EL.MH
C220134ELEQ000880 | U20 - IES-505 - New UPS Distribution Board 505-PDP-XXX (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 6.8511 | 10780.EL.EL.MH
C220134ELEQ000960 | U20 - IES-505 - New UPS Distribution Board 505-PDP-XXX (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 6.8511 | 10780.EL.EL.MH
C220132ELCL100140 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.EL.PL.LM | 604 | 0
C220132ELCL100150 | U20 - IES-514 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9120 | 0 | 10610.EL.PL.LM | 16720.14 | 0
C220132ELCL100180 | U20 - SS-526 - Main Power Electrical Cable Laying from SS-503 to SS-526 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 847 | 0 | 10610.EL.PL.LM | 776.33 | 0
C220132ELCL100210 | U20 - OMS-013 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1332 | 0 | 10610.EL.PL.LM | 2442.3 | 0
C220132ELCL100220 | U20 - OMS-015 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 0 | 10610.EL.PL.LM | 6287.91 | 0
C220132ELCL100230 | U20 - OMS-015 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 0 | 10610.EL.PL.LM | 6287.91 | 0
C220132ELCL100240 | U20 - OMS-014 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1496 | 0 | 10610.EL.PL.LM | 2743.56 | 0
C220132ELCL100250 | U20 - IES-513 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9041 | 0 | 10610.EL.PL.LM | 16574.65 | 0
C220132ELCL100260 | U20 - OMS-014 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1496 | 0 | 10610.EL.PL.LM | 2743.56 | 0
C220132ELCL1005 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-522 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 1598 | 0
C220132ELCL1008 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-500 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 0 | 10610.EL.LC.LM | 601 | 0
C220132ELCL1010 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-521 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.LC.LM | 316 | 0
C220132ELCL1015 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-520 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.LC.LM | 30 | 0
C220132ELCL1018 | U20 - Electrical Cable Trench and Backfilling | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 1.6179 | 10780.EL.EL.MH
C220132ELCO100070 | U20 - NMCB - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 45245 | 0 | 10780.EL.EL.MH
C220132ELCO100090 | U20 - IES-514 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9949 | 0 | 10780.EL.EL.MH
C220132ELCO100110 | U20 - OMS-015 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3742 | 0 | 10780.EL.EL.MH
C220132ELCO100130 | U20 - OMS-014 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1633 | 0 | 10780.EL.EL.MH
C220132ELEL100040 | U20 - SS-522 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100060 | U20 - NMCB - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100070 | U20 - SS-525 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C220132ELEL100150 | U20 - OMS-014 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 363 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEQ1100060 | U20 - SS-521 - ASD Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2711 | 0 | 10780.EL.EL.MH
C220132ELEQ1100110 | U20 - SS-520 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3191 | 0 | 10780.EL.EL.MH
C220132ELEQ1100190 | U20 - SS-521 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2711 | 0 | 10780.EL.EL.MH
C220132ELEQ1100220 | U20 - SS-522 - ASD Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3271 | 0 | 10780.EL.EL.MH
C220132ELEQ1100330 | U20 - SS-525 - ASD Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 146 | 0 | 10780.EL.EL.MH
C220132ELEQ1100400 | U20 - SS-525 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 146 | 0 | 10780.EL.EL.MH
C220132ELEQ1100440 | U20 - SS-523 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 817 | 0 | 10780.EL.EL.MH
C220132ELEQ1100490 | U20 - SS-523 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 817 | 0 | 10780.EL.EL.MH
C220132ELTI100040 | U20 - SS-526 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 770 | 0 | 10780.EL.EL.MH
C220132ELTI100060 | U20 - SS-525 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 779 | 0 | 10780.EL.EL.MH
C220132HVIN100020 | U20 - SS-520 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5513 | 16.6164 | 10780.BU.BU.MH
C220132HVIN100060 | U20 - SS-521 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3029 | 0 | 10780.BU.BU.MH
C220132HVIN100070 | U20 - SS-520 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3816 | 0 | 10780.BU.BU.MH
C220132HVIN100110 | U20 - SS-521 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2019 | 0 | 10780.BU.BU.MH
C220132HVIN100160 | U20 - SS-526 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2855 | 0 | 10780.BU.BU.MH
C220132HVIN100190 | U20 - SS-526 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1224 | 0 | 10780.BU.BU.MH
C220134ELER000755 | U20 - SS-516 - Earthing/Lighting/Fire Dtection/Firefighting System Modification (Shutdown) for Transformer #A | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELTI000380 | U20 - IES-501 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2263 | 0 | 10780.EL.EL.MH
C220134ELTI000400 | U20 - Ruwais - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.EL.EL.MH
C220134PRSS0005 | U20 - SS-520 - UPS black start (4 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 250 | 0 | 10780.PR.PR.MH
C220134PRSS0120 | U20 - SS-523 - 415V switchgear precommisisoning (1 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 507 | 0 | 10780.PR.PR.MH
C220134PRSS0145 | U20 - SS-524 - 415V switchgear precommisisoning (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 393 | 0 | 10780.PR.PR.MH
C220137INCC000090 | U20 - IES-304 - System Cabinets & Consoles Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INCC000230 | U20 - IES-505 - DCS/VMS/ESD Cabinets Installation | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INCC000240 | U20 - IES-502 - System Cabinets & Consoles Installation (Pre-Shutdown) / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6050 | 0 | 10780.IN.IN.MH
C220137INCC000250 | U20 - IES-502 - DCS/VMS/ESD Cabinets Installation (Pre-Shutdown) | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INCC000260 | U20 - IES-507 - System Cabinets & Consoles Installation / Modifications (Pre-Shutdown) | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 20.941 | 10780.IN.IN.MH
C220137INCC000290 | U20 - IES-508- DCS/VMS/ESD Cabinets Installation | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INCC000320 | U20 - IES-501 - System Cabinets & Consoles Installation (Shutdown Required) + Other Works | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4624 | 0 | 10780.IN.IN.MH
C220137INCC000330 | U20 - IES-501 - DCS/VMS/ESD Cabinets Installation (Shutdown Required) + Other Works | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2263 | 0 | 10780.IN.IN.MH
C220137INCC000380 | U20 - IES-507 - DCS/VMS/ESD Cabinets Installation (Shutdown Required) + Other Works | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 0 | 10780.IN.IN.MH
C220137INCT000070 | U20 - IES-505 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INCT000090 | U20 - IES-507 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 0 | 10780.IN.IN.MH
C220137INCT000190 | U20 - IES-504 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INCT000210 | U20 - IES-16 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5016 | 0 | 10780.IN.IN.MH
C220137INCT000250 | U20 - IES-501 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 0 | 10780.IN.IN.MH
C220137INDC000040 | U20 - IES-504 - DCS/VMS/ESD Cabinets Installation (Pre-Shutdown) | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INDC000060 | U20 - IES-16 - DCS/VMS/ESD Cabinets Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9739 | 0 | 10780.IN.IN.MH
C220137INDC000070 | U20 - IES-12 - DCS/VMS/ESD Cabinets Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10919 | 0 | 10780.IN.IN.MH
C220137INDC000080 | U20 - IES-1A - DCS/VMS/ESD Cabinets Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INDC000090 | U20 - IES-304 - DCS/VMS/ESD Cabinets Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INGC000030 | U20 - IES-502 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 0 | 10780.IN.IN.MH
C220137INGC000220 | U20 - IES-15 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2558 | 0 | 10780.IN.IN.MH
C220137INGC000270 | U20 - IES-501 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2263 | 0 | 10780.IN.IN.MH
C220137INML000080 | U20 - IES-1A - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INML000090 | U20 - IES-504 - Instrument Multicable Cable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INML000120 | U20 - IES-505 - Instrument Multicable Cable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INML000170 | U20 - IES-508 - Instrument Multicable Cable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INML000180 | U20 - TLC - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INML001160 | U20 - IES-507 - Instrument Multicable Cable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 0 | 10780.IN.IN.MH
C220137PRSS000050 | U20 - IES-513 - SAT Testing | PR | PRST | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2486 | 0 | 10780.PR.PR.MH
C220BUTR000000010 | U20 - SS-516 - Transf. Yard Foundations #A (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14372 | 305.1412 | 10610.BU.CO.M3 | 175 | 175
C220ELEQ000000010 | U20 - SS-516 - Decommissionig/Dismantling of Existing 220/138 Kv 80/100 MVA Transformer (Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220ELEQ000000015 | U20 - SS-516 - Decommissionig/Dismantling of Existing 220/138 Kv 80/100 MVA Transformer (Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C321131ISEQ000020 | U21 - Equipment Insulation (562) | IS | ISEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0 | 10610.IS.EQ.M2 | 410 | 0
C321131ISEQ000030 | U21 - Equipment Insulation (580) | IS | ISEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 751 | 0 | 10610.IS.EQ.M2 | 1346 | 0
C220132HVIN100220 | U20 - SS-520 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 848 | 0 | 10780.BU.BU.MH
C220132HVIN100260 | U20 - SS-524 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1596 | 0 | 10780.BU.BU.MH
C220132HVIN100310 | U20 - SS-526 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132HVIN100370 | U20 - SS-525 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 117 | 0 | 10780.BU.BU.MH
C220132HVIN100430 | U20 - OMS-013 - Install Air Handling Units | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 436 | 0 | 10780.BU.BU.MH
C220132HVIN100440 | U20 - SS-524 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2394 | 0 | 10780.BU.BU.MH
C220132HVIN100530 | U20 - SS-523 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 305 | 0 | 10780.BU.BU.MH
C220132HVIN100600 | U20 - OMS-014 -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1010 | 0 | 10780.BU.BU.MH
C220132INCC100020 | U20 - NMCB - System Cabinets & Consoles Installation | IN | INCC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCC100060 | U20 - IES-513 - Machine Monitoring System Installation | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCO100010 | U20 - SS-526 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50 | 0 | 10780.IN.IN.MH
C220132INCO100040 | U20 - SS-521 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2410 | 0 | 10780.IN.IN.MH
C220132INCT2100010 | U20 - IES-514 - Instrument Trays Installation | IN | INCT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24516 | 0 | 10780.IN.IN.MH
C220132INCT2100030 | U20 - NMCB - Instrument Trays Installation | IN | INCT2 | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 24516 | 0 | 10780.IN.IN.MH
C220132INDC100030 | U20 - IES-513 - DCS/VMS/ESD Cabinets Installation | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1812 | 0 | 10780.IN.IN.MH
C220132INFG100080 | U20 - SS-526 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10780.IN.IN.MH
C220132INFG100110 | U20 - SS-525 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.IN.IN.MH
C220132INFG100120 | U20 - NMCB - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C220132INFG100130 | U20 - SS-522 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 665 | 0 | 10780.IN.IN.MH
C220132INFG100230 | U20 - IES-513 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0.042543 | 10780.IN.IN.MH
C321131ISPI000070 | U21 - Piping Insulation (580) | IS | ISPI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10298 | 0 | 10610.IS.PI.M2 | 1176 | 0
C321131MEMC000060 | U21 - Miscellaneous Piping (580) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 596 | 0 | 10780.PI.PI.MH
C321131PIPR000060 | U21 - Piping Prefabrication (580) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 130611 | 12693.9707 | 10610.PI.FB.DI | 32652.72 | 13410.5562
C321131PIRA000020 | U21 - Piping Erection on Rack (562) | PI | PIRA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 151125 | 0 | 10610.PI.PR.DI | 16791.66 | 0
C321131PISB000071 | U21 - Small Bore Piping A/Equip. Erection (580) | PI | PISB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9871 | 0 | 10610.PI.SB.DI | 897.35 | 0
C321131PISU000020 | U21 - Piping Supports Erection (562) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25374 | 0 | 10610.PI.SU.TN | 56.39 | 0
C321131PISU000040 | U21 - Piping Supports Prefabrication (562) | PI | PISU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14661 | 70.0371 | 10610.PI.PU.TN | 56.39 | 12.8048
C321131PISU000040 | U21 - Piping Supports Prefabrication (562) | PI | PISU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14661 | 70.0371 | 10610.PI.PU.TN | 56.39 | 12.8048
C321131PISU000130 | U21 - Piping Supports Prefabrication (580) | PI | PISU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7169 | 13.0288 | 10610.PI.PU.TN | 27.57 | 2.265
C321131PIUG000020 | U21 - Piping Erection UG (562) | PI | PIUG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 78 | 0 | 10610.PI.UG.DI | 52 | 0
C321131PRBO000080 | U21 - Static Box Up (580) | PR | PRBO1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4626 | 0 | 10780.PR.PR.MH
C321131PRFL000060 | U21 - Piping Flushing/Blowing (580) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1121 | 0 | 10610.PR.FL.DI | 18434 | 0
C321131PRHT000020 | U21 - Piping Hydrotesting (562) | PR | PRHT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14841 | 0 | 10610.PR.HT.DI | 40876 | 0
C321131PRHT000070 | U21 - Piping Hydrotesting (580) | PR | PRHT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17459 | 0 | 10610.PR.HT.DI | 18434 | 0
C321131PRLT000020 | U21 - Loops Testing (562) | PR | PRLT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4922 | 0 | 10780.PR.PR.MH
C321131PRWT000020 | U21 - Walkthrough (562) | PR | PRWT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1396 | 0 | 10780.PR.PR.MH
C321132CICT000030 | U21 - Instrument earth Trenches Execution (562) | CI | CICT3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CICT000050 | U21 - Underground earth Trenches Execution (562) | CI | CICT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CIDM000030 | U21 - Manholes & Catchbasins Installation (Precast) (562) | CI | CIDM1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9977 | 2.941 | 10610.CI.CO.M3 | 166.28 | 0
C321132CIGT000010 | U21 - Equipment Grouting Execution (562) | CI | CIGT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2895 | 0 | 10780.CI.CI.MH
C321132CIGT000130 | U21 - Steel Structure Grouting Execution (580) | CI | CIGT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 750 | 0 | 10780.CI.CI.MH
C220132INFO100010 | U20 - IES-514 - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132INGC100010 | U20 - IES-514 - Fiber Optic Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18212 | 0 | 10780.IN.IN.MH
C220132INGC100040 | U20 - IES-513 - Fiber Optic Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18212 | 0 | 10780.IN.IN.MH
C220132INML100010 | U20 - NMCB - Instrument Multicable Laying | IN | INML | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121879.83 | 0
C220132INML100020 | U20 - IES-514 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121880.94 | 0
C220132MEMC100010 | U20 - SS-524 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4561 | 24.583 | 10610.BU.CO.M3 | 1 | 0.8
C220132MEMC100030 | U20 - SS-521 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 0 | 10780.EL.EL.MH
C220132MEMC100040 | U20 - SS-526 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10780.EL.EL.MH
C220132MEMC100050 | U20 - SS-520 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10780.EL.EL.MH
C220132MEMC100110 | U20 - SS-521 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 0 | 10780.EL.EL.MH
C220132MEMC100120 | U20 - SS-525 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156 | 0 | 10780.EL.EL.MH
C220132MEMC100170 | U20 - SS-522 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10780.EL.EL.MH
C220132MEMC100190 | U20 - SS-523 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 871 | 0 | 10780.EL.EL.MH
C220132MEMC100200 | U20 - IES-514 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3662 | 0 | 10610.BU.CO.M3 | 1 | 0
C220132MEMC100250 | U20 - OMS-013 - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10780.EL.EL.MH
C220132MEMC100260 | U20 - SS-526 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10780.EL.EL.MH
C220132MEMC100270 | U20 - SS-523 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1462 | 0.78923 | 10610.BU.CO.M3 | 1 | 0.25
C220132MEMC100300 | U20 - SS-522 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10780.EL.EL.MH
C220132MEMC100310 | U20 - SS-525 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156 | 0 | 10780.EL.EL.MH
C220132MEMC100320 | U20 - SS-525 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156 | 0 | 10780.EL.EL.MH
C321132CIHE000040 | U21 - Transformer STG-GSUT Foundation Execution (562) | CI | CIHE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 13.4955 | 10610.CI.CO.M3 | 155.27 | 0
C321132CIPD000020 | U21 - Fabrication Precast Drainage Man Holes & Catchbasins (562) | CI | CIPD | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1966 | 0 | 10780.CI.CI.MH
C321132CIPE000050 | U21 - Waste Heat Boiler 562-B-101J Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.CI.CO.M3 | 230 | 0
C321132CIPE000080 | U21 - Transformer GTG-GSUT Foundation Execution (580) | CI | CIHE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9414 | 2.7559 | 10610.CI.CO.M3 | 156.9 | 0
C321132CIPE000100 | U21 - Fuel Gas Skid B Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1272 | 0 | 10610.CI.CO.M3 | 21.2 | 0
C321132CIPE000120 | U21 - Seal Air Fan Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 348 | 0 | 10610.CI.CO.M3 | 4.97 | 0
C321132CIPE000130 | U21 - Cooling Air Fan Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 348 | 0 | 10610.CI.CO.M3 | 4.97 | 0
C321132CIPE000170 | U21 - GCB Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2096 | 0 | 10610.CI.CO.M3 | 34.94 | 0
C321132CIPE000170 | U21 - GCB Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2096 | 0 | 10610.CI.CO.M3 | 34.94 | 0
C321132CIPE000180 | U21 - Steam Gland Condenser Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1611 | 0 | 10780.CI.CI.MH
C321132CIPR000030 | U21 - 562-PR-103 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5796 | 49.3139 | 10610.CI.CO.M3 | 96.6 | 96.5996
C321132CIPR000280 | U21 - 580-PR-101 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2560 | 5.7666 | 10610.CI.CO.M3 | 42.66 | 20.102
C321132CIPR000280 | U21 - 580-PR-101 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2560 | 5.7666 | 10610.CI.CO.M3 | 42.66 | 20.102
C321132CIPV000030 | U21 - Stairs & Small Foundations Execution (562) | CI | CISF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1208 | 0 | 10610.CI.CO.M3 | 20.13 | 0
C321132CIPV000160 | U21 - Concrete Paving Execution (580) | CI | CIPV1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17820 | 0 | 10610.CI.PV.M2 | 9899.84 | 0
C321132CIRE000080 | U21 - Pump 562-P-302 A/B Foundation Execution (580) | CI | CIRE1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11146 | 0 | 10610.CI.CO.M3 | 222.92 | 0
C321132CISF000030 | U21 - Stairs & Small Foundations Execution (580) | CI | CISF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 227 | 0 | 10610.CI.CO.M3 | 3.25 | 0
C321132CISF000030 | U21 - Stairs & Small Foundations Execution (580) | CI | CISF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 227 | 0 | 10610.CI.CO.M3 | 3.25 | 0
C321132CIST000030 | U21 - Shelter GTG-GSUT Transformer Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 10.7967 | 10610.CI.CO.M3 | 155.27 | 0
C321132CIST000040 | U21 - Shelter 562-SH-001 Generator Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 6.7477 | 10610.CI.CO.M3 | 155.27 | 0
C220132MEMC100330 | U20 - OMS-013 - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10780.EL.EL.MH
C220132MEMC100360 | U20 - NMCB - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10780.EL.EL.MH
C220132MEMC100500 | U20 - OMS-014 - Sanitary Wares | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0 | 10780.ME.ME.MH
C220134ELCL000070 | U20 - IES-505 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.EL.EL.MH
C220134ELCL000080 | U20 - SS-012 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10919 | 0 | 10780.EL.EL.MH
C220134ELCL000100 | U20 - SS-502 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELCL000110 | U20 - SS-512 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12149 | 0 | 10780.EL.EL.MH
C220134ELCL000375 | U20 - SS-516 - Electrical Cable Laying for Transformer #A (Pre-Shutdown) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10780.EL.EL.MH
C220134ELCL000390 | U20 - SS-503 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8816 | 0 | 10780.EL.EL.MH
C220134ELCL000420 | U20 - IES-504 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.EL.EL.MH
C220134ELCO000325 | U20 - SS-516 - Electrical Cable Gland & Conn./Testing (Shutdown) for Transformer #A | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 102 | 0 | 10780.EL.EL.MH
C220134ELCO000390 | U20 - IES-500- Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2793 | 0 | 10780.EL.EL.MH
C220134ELCO000400 | U20 - Ruwais- Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.EL.EL.MH
C220134ELEQ000255 | U20 - SS-516 - LV AC System & Lighting System Modification for Transformer #A (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000680 | U20 - SS-515 - New Battery Banks for GTG AC & DC UPS | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELEQ000900 | U20 - SS-502 - 415V MCC 580-EE-0203 Modification (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELEQ000910 | U20 - SS-503 - 580-EE-0301/580-EE-0302/580-EE-0300 Modification (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6455 | 0 | 10780.EL.EL.MH
C220134ELEQ000920 | U20 - SS-504 - 580-EE-0402/580-EE-403 Modification (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134ELEQ000930 | U20 - IES-500 - New UPS Distribution Board 500-PDB-125/126 (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4153 | 0 | 10780.EL.EL.MH
C220134ELEQ000940 | U20 - IES-501 - New UPS Distribution Board 501-PDP-07 (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4624 | 0 | 10780.EL.EL.MH
C321132CIST000050 | U21 - Platform for Steam Turbine Generator Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2398 | 0.44713 | 10610.CI.CO.M3 | 39.97 | 0
C321132CIST000050 | U21 - Platform for Steam Turbine Generator Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2398 | 0.44713 | 10610.CI.CO.M3 | 39.97 | 0
C321132CIST000180 | U21 - Platform for Gas Turbine Generator Package 580-ME-101J Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6365 | 0 | 10610.CI.CO.M3 | 106.09 | 0
C321132CIST000200 | U21 - Platform for Waste Heat Boiler 562-B-101J Structure Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.CI.CO.M3 | 230 | 0
C321132CIST000210 | U21 - Gas Turbine Lube Oil Cooler Structure Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6365 | 0 | 10610.CI.CO.M3 | 106.09 | 0
C321132CIUG000065 | U21 - UG Pipe Installation (562) (CD) | CI | CIUG2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4905 | 0 | 10610.CI.UG.LM | 245.24 | 0
C321132CIUG000070 | U21 - UG Process Channel Execution (Closed Drain System) (562) | CI | CIUG3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11497 | 0 | 10610.CI.CO.M3 | 191.61 | 0
C321132CIUG000075 | U21 - UG Pipe Installation (562) (OD) | CI | CIUG2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14666 | 0 | 10610.CI.UG.LM | 733.32 | 0
C321132CIUP000030 | U21 - UG Piping Prefabrication (562) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 480 | 0.25722 | 10610.PI.FB.DI | 120 | 26.0496
C321132FPSS000040 | U21 - Steel Structure Fireproofing (580) | FP | FPSS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 396 | 0 | 10610.FP.ST.M2 | 109.4 | 0
C321132STMS000020 | U21 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (562) | ST | STMS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1829 | 4.78 | 10610.ST.PL.TN | 30.48 | 30.4846
C321132STPL000030 | U21 - Lube oil Cooler Structure Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.ST.PL.TN | 10.7 | 0
C321132STPL000040 | U21 - Platform for Steam Turbine Generator Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2480 | 0 | 10780.ST.ST.MH
C321132STPL000140 | U21 - Equipment Platforms, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 205 | 0 | 10610.ST.PL.TN | 2.56 | 0
C321132STPR000040 | U21 - 562-PR-102 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2067 | 0 | 10610.ST.PR.TN | 39 | 0
C321132STPR000050 | U21 - 562-PR-101 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2385 | 0 | 10610.ST.PR.TN | 45 | 0
C321132STPR000060 | U21 - 562-PR-201 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22466 | 0 | 10610.ST.PR.TN | 423.89 | 0
C321132STPR000110 | U21 - 580-PR-101 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4913 | 0 | 10610.ST.PR.TN | 92.7 | 0
C321132STPR000120 | U21 - 580-PR-102 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2624 | 0 | 10610.ST.PR.TN | 49.5 | 0
C220132BUSSFO100480 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Footings (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1224 | 2.2125 | 10610.BU.CO.M3 | 171.7 | 171.6997
C220132BUSSFO100510 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Columns & Walls (Floor Beam Level) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11768 | 204.5921 | 10610.BU.CO.M3 | 240 | 240
C220132BUSSFO100520 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1827 | 4.9314 | 10610.BU.CO.M3 | 24 | 24
C220132BUSSFO100530 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0.11028 | 10610.BU.CO.M3 | 9.22 | 9.22
C220132BUSSFO100540 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7476 | 82.5677 | 10610.BU.CO.M3 | 159 | 159
C220132BUSSFO100590 | U20 - SS-523 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 670 | 0 | 10780.BU.BU.MH
C220132BUSSFO100600 | U20 - SS-525 - Backfilling and Compaction upto Cable Cellar Grade (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0 | 10780.BU.BU.MH
C220132BUSSFO100640 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Plinth beams (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 508 | 0.3811 | 10610.BU.CO.M3 | 3 | 3
C220132BUSSFO100730 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Floor beams/Grade Beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3923 | 22.7344 | 10610.BU.CO.M3 | 78 | 78
C220132BUSSFO100770 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab at EL 102.40 (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4561 | 30.7287 | 10610.BU.CO.M3 | 95.15 | 95.15
C220132BUSSFO100810 | U20 - OMS-015 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10610.BU.CO.M3 | 27 | 0
C220132BUSSFO100820 | U20 - OMS-014 - Backfilling and Compaction upto Grade Slab | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0.19334 | 10780.BU.BU.MH
C220132BUSSFO100830 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5936 | 10.9319 | 10610.BU.CO.M3 | 99 | 19.7999
C220132BUSSFO100920 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for HVAC Room Foundations | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2746 | 11.1408 | 10610.BU.CO.M3 | 123 | 123
C220132BUSSFO100930 | U20 - SS-522 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4787 | 0 | 10780.BU.BU.MH
C220132BUSSGR100010 | U20 - SS-524 - Building Grounding Install. (Elect. Subst.) | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3876 | 0 | 10780.BU.BU.MH
C220132BUSSGR100020 | U20 - SS-520 - Building Grounding Install. (Elect. Subst.) | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18446 | 105.5596 | 10780.BU.BU.MH
C220132BUSSGR100040 | U20 - SS-526 - Building Grounding Install. (Elect. Subst.) | BU | BUSSGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3100 | 0 | 10780.BU.BU.MH
C321132STSH000020 | U21 - Shelter GTG-GSUT Transformer Walls & Roofing Erection (580) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 605 | 0 | 10780.ST.ST.MH
C321132STSH000060 | U21 - Shelter 562-SH-001 Structure Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33664 | 0 | 10610.ST.ER.TN | 635.16 | 0
C321132STSH000060 | U21 - Shelter 562-SH-001 Structure Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 33664 | 0 | 10610.ST.ER.TN | 635.16 | 0
C321132STSH000080 | U21 - Shelter GTG-GSUT Roofing & Wall Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 203 | 0 | 10610.ST.ER.TN | 3.83 | 0
C321133PAPP000020 | U21 - Piping SandBl. & Priming (562) | PA | PAPP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4698 | 6.1843 | 10610.PA.PP.M2 | 2349 | 464.7693
C321134ELCI000020 | U21 - Conduits Installation (562) | EL | ELCI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4792 | 0 | 10780.EL.EL.MH
C321134ELCI000060 | U21 - Conduits Installation (580) | EL | ELCI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6787 | 0 | 10780.EL.EL.MH
C321134ELCL000040 | U21 - Electrical Cable Laying (562) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42166 | 0 | 10610.EL.PL.LM | 78875.73 | 0
C321134ELCL000140 | U21 - Electrical Cable Laying (580) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 59722 | 0 | 10610.EL.PL.LM | 122148.27 | 0
C321134ELCP000060 | U21 - Cathodic Protection Piping (580) | EL | ELCP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5429 | 0 | 10780.EL.EL.MH
C321134ELEQ000030 | U21 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 390 | 0
C321134ELEQ000040 | U21 - GTG Generator Circuit Breaker 580-EE-CB-1502J Installation (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 70 | 0
C321134ELEQ000110 | U21 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 330 | 0
C321134ELTI000030 | U21 - Lighting Cable Trays Installation (562) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5750 | 0 | 10610.EL.CT.LM | 913.63 | 0
C321134ELTI000040 | U21 - Electrical Cable Trays Installation (562) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19166 | 0 | 10610.EL.CT.LM | 1696.74 | 0
C321134ELTI000120 | U21 - Lighting Cable Trays Installation (580) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8144 | 0 | 10610.EL.CT.LM | 1495.8 | 0
C321136MEAC000050 | U21 - Air Coolers (Waste Heat Boiler Blowdown Cooler) Erection 562-E-304 Waste Heat Boiler Blowdown Cooler (580) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEAC000080 | U21 - Air Coolers Erection - Gas Turbine Lube Oil Cooler (580) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 20 | 0
C321136MEHL000700 | U21 - Package Installation (Steam Turbine Package Generator) 580-ME-101K/562-ST-301 - (HL) (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 0 | 10610.ME.ER.TN | 170 | 0
C220132BUSSFO100550 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Columns (Elect. Subst.) | BU | BUSSFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 1.3449 | 10610.BU.CO.M3 | 19.44 | 18.4699
C220132BUSSFO100560 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab(Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7633 | 0 | 10610.BU.CO.M3 | 131.87 | 0
C220132BUSSFO100580 | U20 - OMS-015 - Excavation and Compaction | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0.040735 | 10780.BU.BU.MH
C220132BUSSFO100690 | U20 - OMS-015 - Blinding and Water Proofing | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSFO100760 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Footings | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 650 | 0.62368 | 10610.BU.CO.M3 | 55 | 55
C220132BUSSFO100770 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for HVAC Room Grade Slab at EL 102.40 (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4561 | 30.7287 | 10610.BU.CO.M3 | 95.15 | 95.15
C220132BUSSFO100780 | U20 - OMS-015 - Backfilling and Compaction upto Grade Slab | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 581 | 0 | 10780.BU.BU.MH
C220132BUSSFO100790 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Columns & Walls | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0.37687 | 10610.BU.CO.M3 | 25 | 25
C220132BUSSFO100800 | U20 - SS-520 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6361 | 0 | 10780.BU.BU.MH
C220132BUSSFO100840 | U20 - OMS-014 - Rebar, Formwork & Concrete Pouring for Floor beams | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 505 | 0.22424 | 10610.BU.CO.M3 | 27 | 14.85
C220132BUSSFO100860 | U20 - SS-521 - Gravel Laying for Cellar Floor (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10780.BU.BU.MH
C220132BUSSFO100910 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for HVAC Room Foundations | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 5.3792 | 10610.BU.CO.M3 | 14 | 14
C220132BUSSFO100920 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for HVAC Room Foundations | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2746 | 11.1408 | 10610.BU.CO.M3 | 123 | 123
C220132BUSSGR100030 | U20 - SS-525 - Building Grounding Install. (Elect. Subst.) | BU | BUSSGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 430 | 0 | 10780.BU.BU.MH
C220132BUSSGR100060 | U20 - SS-522 - Building Grounding Install. (Elect. Subst.) | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7277 | 0 | 10780.BU.BU.MH
C220132BUSSGR100120 | U20 - OMS-014 - Building Grounding Install. | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1010 | 0 | 10780.BU.BU.MH
C220132BUTRAR100030 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Transformer Foundations (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18766 | 336.8675 | 10610.BU.CO.M3 | 1049 | 576.9522
C220132BUTRAR100060 | U20 - SS-521 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6490 | 0 | 10610.BU.AR.M2 | 915 | 0
C321136MEPA000030 | U21 - Waste Heat Boiler Scale Inhibitor Dosing Package Installation 562-ME-308 Boiler Scale Inhibitor Dosing (580) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 180 | 0 | 10610.ME.ER.TN | 3 | 0
C321136MEPA000050 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Gearbox (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2100 | 0 | 10610.ME.ER.TN | 35 | 0
C321136MEPA000060 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Fire Fighting Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C321136MEPA000090 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Air Refrigeration Skids (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3180 | 0 | 10610.ME.ER.TN | 53 | 0
C321136MEPA000110 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Lube oil Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEPA000120 | U21 - Package Installation (LP Steam Desuperheaters) 562-ME-310A/B Desuperheaters (562) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEPA000130 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Turbine (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 90 | 0
C321136MEPA000240 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Generator (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3480 | 0 | 10610.ME.ER.TN | 58 | 0
C321136METC000050 | U21 - Cranes Erection (EOT Crane For Steam Turbine Generator) 562-EOT-301 (562) | ME | METC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C321137INCO000020 | U21 - Communication System Installation (562) | IN | INCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1568 | 0 | 10780.IN.IN.MH
C321137INCO000050 | U21 - Communication System Installation (580) | IN | INCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 502 | 0 | 10780.IN.IN.MH
C321137INCT000040 | U21 - Secondary Cable Trays Installation (562) | IN | INCT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4988 | 0 | 10610.IN.CT.LM | 200 | 0
C321137INCT000100 | U21 - Primary Cable Trays Installation (580) | IN | INCT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2852 | 0 | 10610.IN.CT.LM | 170 | 0
C321137INCT000110 | U21 - Secondary Cable Trays Installation (580) | IN | INCT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.IN.CT.LM | 200 | 0
C321137INFC000020 | U21 - Fiber Optic Gland & Conn./Testing (562) | IN | INFC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 855 | 0 | 10610.IN.CO.UN | 180 | 0
C321137INFG000020 | U21 - Fire & Gas System Installation (562) | IN | INFG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 926 | 0 | 10780.IN.IN.MH
C321137INFS000020 | U21 - Fire Fighting Equipments Installation (562) | IN | INFS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 926 | 0 | 10780.IN.IN.MH
C321137INGC000040 | U21 - Single Pair Cable Gland & Conn./Testing (562) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3705 | 0 | 10610.IN.CO.UN | 300 | 0
C220134ELEQ000950 | U20 - IES-504 - New UPS Distribution Board 504-PDB-125/126 (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.EL.EL.MH
C220134ELTI000120 | U20 - SS-512 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELTI000330 | U20 - SS-500 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 175 | 0 | 10780.EL.EL.MH
C220134ELTI000340 | U20 - SS-503 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6455 | 0 | 10780.EL.EL.MH
C220134ELTI000360 | U20 - SS-501 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELTI000370 | U20 - IES-504 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.EL.EL.MH
C220134PRSS000020 | U20 - OMS-014 - Equip. Precommissioning | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 412 | 0 | 10780.PR.PR.MH
C220134PRSS000130 | U20 - SS-516 - Substation Equip. Precommissioning for Transformer #A | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38 | 0 | 10780.PR.PR.MH
C220134PRSS0035 | U20 - SS-520 - Capacitor Bank | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1071 | 0 | 10780.PR.PR.MH
C220134PRSS0040 | U20 - SS-521 - UPS black start (4 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 334 | 0 | 10780.PR.PR.MH
C220134PRSS0070 | U20 - SS-521 - Capacitor Bank | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1201 | 0 | 10780.PR.PR.MH
C220134PRSS0075 | U20 - SS-522 - UPS black start (4 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 326 | 0 | 10780.PR.PR.MH
C220134PRSS0080 | U20 - SS-522 - 33kV GIS precommissioning (1 unit) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 611 | 0 | 10780.PR.PR.MH
C220134PRSS0095 | U20 - SS-522 - 415V switchgear precommisisoning (5 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 951 | 0 | 10780.PR.PR.MH
C220134PRSS0100 | U20 - SS-522 - Transformers precommissioning (18 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 760 | 0 | 10780.PR.PR.MH
C220134PRSS0105 | U20 - SS-522 - Variable fecuency driver precommissioning (44 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1086 | 0 | 10780.PR.PR.MH
C220134PRSS0110 | U20 - SS-522 - Capacitor Bank | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1222 | 0 | 10780.PR.PR.MH
C220134PRSS0125 | U20 - SS-523 - Transformers precommissioning (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 507 | 0 | 10780.PR.PR.MH
C220134PRSS0135 | U20 - SS-524 - 132kV Switchgear precommissioning (1 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 632 | 0 | 10780.PR.PR.MH
C220134PRSS0140 | U20 - SS-524 - 3.3KV switchgear precommisisoning (1 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 632 | 0 | 10780.PR.PR.MH
C220134PRSS0150 | U20 - SS-524 - Emergency diesel generator (580) (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 843 | 0 | 10780.PR.PR.MH
C321137INGC000130 | U21 - Single Pair Cable Gland & Conn./Testing (580) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1186 | 0 | 10610.IN.CO.UN | 190 | 0
C321137INIP000020 | U21 - Instruments Calibration (562) | IN | INIP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 926 | 0 | 10780.IN.IN.MH
C321137INJB000060 | U21 - Junction Boxes & Local Panels Install. (580) | IN | INJB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1186 | 0 | 10780.IN.IN.MH
C321137INSL000020 | U21 - Single Pair Cable Pulling (562) | IN | INSL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 0 | 10610.IN.SC.LM | 37276.78 | 0
C322131ISEQ000040 | U22 - Equipment Insulation | IS | ISEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 301 | 0 | 10610.IS.EQ.M2 | 1591 | 0
C322131PIBB000090 | U22 - Big Bore Piping A/Equip. Erection 571-PR-157 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000100 | U22 - Big Bore Piping A/Equip. Erection 571-PR-158 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000110 | U22 - Big Bore Piping A/Equip. Erection PR-571-135 to 571-V-403B, 571-SU-103 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000120 | U22 - Big Bore Piping A/Equip. Erection PR-571-138/137 to 571-V-401 A & 401B | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000140 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-117 / 118 to 571-V-302 A / 302B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIRA000110 | U22-Piping Erection on Rack (571-PR-151) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000120 | U22-Piping Erection on Rack (571-PR-152) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000140 | U22-Piping Erection on Rack (571-PR-154) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000150 | U22-Piping Erection on Rack (571-PR-155) (Including Tower near flare) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000220 | U22-Piping Erection on Rack (571-PR-137) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000230 | U22-Piping Erection on Rack (571-PR-145) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000400 | U22 - Piping Erection on Rack ((577-PB-114) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 65.4444 | 10610.PI.PR.DI | 1119.81 | 552.3463
C322131PIRA000410 | U22 - Piping Erection on Rack (577-PR-115) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 61.6737 | 10610.PI.PR.DI | 1119.81 | 485.0009
C322131PIRA000420 | U22 - Piping Erection on Rack (577-PB-116) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 56.9503 | 10610.PI.PR.DI | 1119.81 | 462
C322131PIRA000450 | U22-Piping Erection on Rack (577-PR-119 / 119 A) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 37.3016 | 10610.PI.PR.DI | 1119.81 | 323.9946
C220132BUSSGR100070 | U20 - SS-523 - Building Grounding Install. (Elect. Subst.) | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2010 | 0 | 10780.BU.BU.MH
C220132BUSSGR100110 | U20 - OMS-015 - Building Grounding Install. | BU | BUBRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1163 | 0 | 10780.BU.BU.MH
C220132BUTRAR100020 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Transformer Foundation (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6058 | 35.5415 | 10610.BU.CO.M3 | 932 | 559.2014
C220132BUTRAR100030 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Transformer Foundations (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18766 | 336.8675 | 10610.BU.CO.M3 | 1049 | 576.9522
C220132BUTRAR100050 | U20 - SS-522 - Plastering/Surface Preparation Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9000 | 0 | 10610.BU.AR.M2 | 754 | 0
C220132BUTRAR100080 | U20 - SS-522 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8617 | 0 | 10610.BU.AR.M2 | 754 | 0
C220132BUTRAR100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Transformer Foundation and Firewalls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10945 | 162.9937 | 10610.BU.CO.M3 | 232.27 | 213.6908
C220132BUTRAR100110 | U20 - SS-524 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2280 | 0 | 10780.BU.BU.MH
C220132BUTRAR100140 | U20 - NMCB - Painting Works | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5361 | 0 | 10780.BU.BU.MH
C220132BUTRFO100020 | U20 - SS-520 - Blinding and Water Proofing (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12934 | 247.1267 | 10780.BU.BU.MH
C220132BUTRFO100040 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Transformer Foundations (Elect. Subst.) | BU | BUBRFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26927 | 834.9583 | 10610.BU.CO.M3 | 1345.71 | 1009.2816
C220132BUTRFO100070 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Firewalls Foundation (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7639 | 86.2056 | 10610.BU.CO.M3 | 146.8 | 146.8004
C220132BUTRFO100070 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Firewalls Foundation (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7639 | 86.2056 | 10610.BU.CO.M3 | 146.8 | 146.8004
C220132BUTRFO100111 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Firewall Foundations & Wallsl- by OQC-B | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17307 | 414.6305 | 10610.BU.CO.M3 | 826.8 | 768.924
C220132BUTRFO100121 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Firewall Foundation & Walls-by NMDC-INFRA | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24511 | 756.3695 | 10610.BU.CO.M3 | 915 | 759.4496
C220132BUTRFO100130 | U20 - NMCB - Excavation and Compaction | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15487 | 354.325 | 10780.BU.BU.MH
C220132BUTRFO100150 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Transformer Foundations | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 11.2027 | 10610.BU.CO.M3 | 130 | 49.4
C220132BUTRFO100160 | U20 - SS-523 - Excavation & Compaction (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4081 | 20.9229 | 10780.BU.BU.MH
C322131PIRA000470 | U22-Piping Erection on Rack (577-PB-121) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000500 | U22-Piping Erection on Main Piperack/Bridge (571-PB-126) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000540 | U22-Piping Erection on Rack (571-PR-130) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 4.7385 | 10610.PI.PR.DI | 1119.81 | 79.9992
C322131PIRA000550 | U22-Piping Erection on Rack (571-PR-131) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 10.3802 | 10610.PI.PR.DI | 1119.81 | 176.0005
C322131PIRA000580 | U22-Piping Erection on Rack (571-PR-133) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 3.3175 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000590 | U22-Piping Erection on Rack (571-PR-134) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PISB000110 | U22 - Small Bore Piping A/Equip. Erection PR-571-135 to 571-V-403B, 571-SU-103 | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISU000150 | U22 - Piping Supports Prefabrication | PI | PISU1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 103021 | 10665.8335 | 10610.PI.PU.TN | 396.24 | 140.9393
C322131PRFL000070 | U22 - Piping Flushing/Steam Blowing | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16496 | 0 | 10610.PR.FL.DI | 261183 | 0
C322131PRHT000080 | U22 - Piping Hydrotesting | PR | PRHT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 164129 | 0 | 10610.PR.HT.DI | 261183 | 0
C322132CIBW100010 | U22 - TEG Storage Tank Dike Wall (571-TK-201) | CI | CIBW1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 6.8421 | 10610.CI.CO.M3 | 35.87 | 35.87
C322132CIDB000035 | U22 - Duct Banks Precast Fabrication | CI | CIDB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16402 | 270.252 | 10780.CI.CI.MH
C322132CIHE000110 | U22 - Horizontal Vessel (HC Flare K.O Drum) Foundation Execution (571-V-401A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14248 | 280.9569 | 10610.CI.CO.M3 | 284.96 | 284.96
C322132CIHE000110 | U22 - Horizontal Vessel (HC Flare K.O Drum) Foundation Execution (571-V-401A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14248 | 280.9569 | 10610.CI.CO.M3 | 284.96 | 284.96
C322132CIHE000130 | U22 - Horizontal Vessel (LT Flare K.O Drum) Foundation Execution (571-V-402A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15530 | 322.5341 | 10610.CI.CO.M3 | 310.6 | 310.6
C322132CIHE000140 | U22 - Horizontal Vessel (LT Flare K.O Drum) Foundation Execution (571-V-402B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15530 | 322.5341 | 10610.CI.CO.M3 | 310.6 | 310.6
C322132CIHE000150 | U22 - Horizontal Exchanger (LT Flare K.O Drum Heater) Foundation Execution (571-E-402A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.CI.CO.M3 | 11.43 | 0
C322132CIHE000170 | U22 - Horizontal Intermediate HC Flare K.O Drum Foundation Execution (571-V-301A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4414 | 28.7083 | 10610.CI.CO.M3 | 73.57 | 73.57
C322132CIHE000170 | U22 - Horizontal Intermediate HC Flare K.O Drum Foundation Execution (571-V-301A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4414 | 28.7083 | 10610.CI.CO.M3 | 73.57 | 73.57
C220134PRSS0170 | U20 - SS-526 - UPS black start (3 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 140 | 0 | 10780.PR.PR.MH
C220134PRSS0175 | U20 - SS-526 - Variable fecuency driver precommissioning (3 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10780.PR.PR.MH
C220137INCC000040 | U20 - IES-504 - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3025 | 0 | 10780.IN.IN.MH
C220137INCC000070 | U20 - IES-12 - System Cabinets & Consoles Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10919 | 0 | 10780.IN.IN.MH
C220137INCC000120 | U20 - CR-541 & MAQTA - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INCC000220 | U20 - IES-505 - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 2.9498 | 10780.IN.IN.MH
C220137INCC000280 | U20 - IES-508 - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 84.0713 | 10780.IN.IN.MH
C220137INCC000350 | U20 - IES-502 - System Cabinets & Consoles Installation (Shutdown Required) + Other Works | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6050 | 0 | 10780.IN.IN.MH
C220137INCC000360 | U20 - IES-502 - DCS/VMS/ESD Cabinets Installation (Shutdown Required) + Other Works | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INCO000030 | U20 - IES-505 - Communication System Installation / Modifications | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INCO000040 | U20 - IES-501 - Communication System Installation / Modifications | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 0 | 10780.IN.IN.MH
C220137INCO000050 | U20 - IES-500 - Communication System Installation / Modifications | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INCT000220 | U20 - IES-12 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3836 | 0 | 10780.IN.IN.MH
C220137INCT000260 | U20 - IES-500 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INDC000050 | U20 - IES-15 - Installation of DCS cabinet | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6099 | 0 | 10780.IN.IN.MH
C220137INFG000090 | U20 - IES-505 - Fire & Gas System Installation / / Modifications | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INFG000120 | U20 - IES-502 - Fire & Gas System Installation / / Modifications | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INFG000130 | U20 - IES-501 - Fire & Gas System Installation / / Modifications | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 0 | 10780.IN.IN.MH
C220137INFG000250 | U20 - IES-504 - Fire & Gas System Installation / / Modifications | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C322132CIHE000180 | U22 - Horizontal Intermediate HC Flare K.O Drum Foundation Execution (571-V-301B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4414 | 28.7083 | 10610.CI.CO.M3 | 73.57 | 73.5701
C322132CIHE000180 | U22 - Horizontal Intermediate HC Flare K.O Drum Foundation Execution (571-V-301B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4414 | 28.7083 | 10610.CI.CO.M3 | 73.57 | 73.5701
C322132CIHE000200 | U22 - Horizontal Intermediate LT Flare K.O Drum Foundation Execution (571-V-302B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8276 | 98.5246 | 10610.CI.CO.M3 | 137.94 | 137.9399
C322132CIHE000210 | U22 - Horizontal Intermediate LT Flare K.O Drum Foundation Execution (571-V-302A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8276 | 100.6556 | 10610.CI.CO.M3 | 137.94 | 137.9399
C322132CIHE000240 | U22 - Horizontal Intermediate Acid Gas Flare K.O Drum Foundation Execution (571-V-303) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36035 | 1918.2952 | 10610.CI.CO.M3 | 720.7 | 720.7021
C322132CIMF000120 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-402 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8088 | 93.8952 | 10610.CI.CO.M3 | 134.81 | 134.81
C322132CIMF000130 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-301 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10636 | 146.7139 | 10610.CI.CO.M3 | 177.27 | 159.5395
C322132CIMF000140 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-301 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5485 | 41.2182 | 10610.CI.CO.M3 | 91.42 | 82.2798
C322132CIMF000160 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-302 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3395 | 16.7066 | 10610.CI.CO.M3 | 56.59 | 56.5898
C322132CIMF000190 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-505) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28481 | 1163.5796 | 10610.CI.CO.M3 | 569.62 | 569.621
C322132CIMF000230 | U22 - Miscellaneous Platform Foundations Execution (PLT-V-403 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 0.68283 | 10610.CI.CO.M3 | 58.51 | 0
C322132CIMF000240 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-403) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3899 | 13.4053 | 10610.CI.CO.M3 | 64.99 | 38.9901
C322132CIMF000250 | U22 - Miscellaneous Platform Foundations Execution (PLT-PR-135) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28389 | 1162.388 | 10610.CI.CO.M3 | 567.77 | 567.77
C322132CIPE000070 | U22 - Acid Gas Flare Package Foundation Execution (571-ME-403) | CI | CIPE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 70207 | 7276.9676 | 10610.CI.CO.M3 | 1404.13 | 1404.1314
C322132CIPR000330 | U22 - Main Piperack Foundations Execution (571-PR-151) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17392 | 443.0555 | 10610.CI.CO.M3 | 347.84 | 347.84
C322132CIPR000340 | U22 - Main Piperack Foundations Execution (571-PR-152) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15290 | 342.4206 | 10610.CI.CO.M3 | 305.79 | 305.7899
C322132CIPR000350 | U22 - Main Piperack Foundations Execution (571-PR-153) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14614 | 312.8113 | 10610.CI.CO.M3 | 292.27 | 292.2701
C322132CIPR000360 | U22 - Main Piperack Foundations Execution (571-PR-154) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13104 | 251.5071 | 10610.CI.CO.M3 | 262.07 | 262.0699
C220137INFG000260 | U20 - IES-504 Fire Fighting Equipments Installation | IN | INFS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INFG000290 | U20 - IES-505 Fire Fighting Equipments Installation | IN | INFS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INGC000240 | U20 - IES-12 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3836 | 0 | 10780.IN.IN.MH
C220137INML000060 | U20 - IES-15 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6099 | 0 | 10780.IN.IN.MH
C220137INML000130 | U20 - IES-502 - Instrument Multicable Cable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INML000150 | U20 - IES-500 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220BUTR000000015 | U20 - SS-516 - UG Survey and Relocation of Existing Services | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1455 | 3.1275 | 10780.BU.BU.MH
C220INCC000000010 | U20 - TLC - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 18.5383 | 10780.IN.IN.MH
C3210PRPRPL000070 | U21 - Punch List (580) | PR | PRPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3256 | 0 | 10780.PR.PR.MH
C3210PRPRWT000060 | U21 - Walkthrough (580) | PR | PRWT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1396 | 0 | 10780.PR.PR.MH
C321131ISEQ000030 | U21 - Equipment Insulation (580) | IS | ISEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 751 | 0 | 10610.IS.EQ.M2 | 1346 | 0
C321131ISPI000070 | U21 - Piping Insulation (580) | IS | ISPI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10298 | 0 | 10610.IS.PI.M2 | 1176 | 0
C321131PIBB000070 | U21 - Big Bore Piping A/Equip. Erection (580) | PI | PIBB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38707 | 0 | 10610.PI.BB.DI | 3870.74 | 0
C321131PIPR000060 | U21 - Piping Prefabrication (580) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 130611 | 12693.9707 | 10610.PI.FB.DI | 32652.72 | 13410.5562
C321131PIRA000070 | U21 - Piping Erection on Rack (580) | PI | PIRA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47362 | 0 | 10610.PI.PR.DI | 5262.39 | 0
C321131PISU000020 | U21 - Piping Supports Erection (562) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25374 | 0 | 10610.PI.SU.TN | 56.39 | 0
C321131PISU000130 | U21 - Piping Supports Prefabrication (580) | PI | PISU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7169 | 13.0288 | 10610.PI.PU.TN | 27.57 | 2.265
C321131PRBO000090 | U21 - Rotary Box Up (580) | PR | PRBO2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 880 | 0 | 10780.PR.PR.MH
C321131PRFL000060 | U21 - Piping Flushing/Blowing (580) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1121 | 0 | 10610.PR.FL.DI | 18434 | 0
C321131PRHT000020 | U21 - Piping Hydrotesting (562) | PR | PRHT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14841 | 0 | 10610.PR.HT.DI | 40876 | 0
C321131PRRE000020 | U21 - Piping Reinstatement (562) | PR | PRRE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25840 | 0 | 10610.PR.RE.DI | 40876 | 0
C322132CIPR000370 | U22 - Main Piperack Foundations Execution (571-PR-155) (Including Tower near flare) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18290 | 478.1287 | 10610.CI.CO.M3 | 365.8 | 365.8005
C322132CIPR000410 | U22 - Main Piperack Foundations Execution (571-PR-141) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10108 | 150.9299 | 10610.CI.CO.M3 | 202.15 | 202.1498
C322132CIPR000420 | U22 - Main Piperack Foundations Execution (571-PR-139/140) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27612 | 1119.1822 | 10610.CI.CO.M3 | 552.23 | 552.2307
C322132CIPR000440 | U22 - Main Piperack Foundations Execution (571-PR-137) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23182 | 788.8699 | 10610.CI.CO.M3 | 463.63 | 463.6302
C322132CIPR000460 | U22 - Main Piperack Foundations Execution (571-PR-136) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23547 | 819.0838 | 10610.CI.CO.M3 | 470.93 | 470.9304
C322132CIPR000740 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-128) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16544 | 5.1068 | 10610.CI.CO.M3 | 330.88 | 0
C322132CIPR000770 | U22 - Main Piperack Foundations Execution (571-PR-131) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12938 | 2.0822 | 10610.CI.CO.M3 | 258.76 | 0
C322132CIPR000790 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-132A) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9310 | 2.9654 | 10610.CI.CO.M3 | 155.16 | 0
C322132CIPR000810 | U22 - Main Piperack Foundations Execution (571-PR-134) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18124 | 473.4309 | 10610.CI.CO.M3 | 362.47 | 362.47
C322132CIPR000820 | U22 - Main Piperack Foundations Execution (571-PR-135) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27139 | 1088.0631 | 10610.CI.CO.M3 | 542.78 | 542.7805
C322132CIPR000850 | U22 - Secondary Piperack Foundations Execution (545-29/26-545 BJ-BK) | CI | CIPR2 | 22 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11220 | 0 | 10610.CI.CO.M3 | 224.4 | 0
C322132CIPR100010 | U22 - Main Piperack Foundations Execution (577-PB-114) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47780 | 3372.517 | 10610.CI.CO.M3 | 955.59 | 955.59
C322132CIPR100010 | U22 - Main Piperack Foundations Execution (577-PB-114) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47780 | 3372.517 | 10610.CI.CO.M3 | 955.59 | 955.59
C322132CIPR100030 | U22 - Main Piperack Foundations Execution (577-PR-117) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 53605 | 4244.9932 | 10610.CI.CO.M3 | 1072.1 | 1072.1
C322132CIPS000050 | U22 - Basin Construction-Evaporation Pond (571-SU-502) | CI | CIPS2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 169792 | 5877.328 | 10610.CI.CO.M3 | 3395.84 | 2699.9984
C322132CIPS000060 | U22 - Sumps Construction (571-SU-401) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 33.1604 | 10610.CI.CO.M3 | 85.85 | 85.85
C322132CIPS000060 | U22 - Sumps Construction (571-SU-401) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 33.1604 | 10610.CI.CO.M3 | 85.85 | 85.85
C322132CIPS000070 | U22 - HC Flare Drain Drum Foundation Execution inside sump (571-V-404) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 39.1967 | 10610.CI.CO.M3 | 85.85 | 85.85
C322132CIPS000120 | U22 - Sumps Construction (571-SU-402) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11593 | 124.7219 | 10610.CI.CO.M3 | 193.22 | 193.2202
C321131PRRE000040 | U21 - Piping Reinstatement (580) | PR | PRRE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20121 | 0 | 10610.PR.RE.DI | 18434 | 0
C321132CICT000020 | U21 - Electrical earth Trenches Execution (562) | CI | CICT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CIDB000035 | U21 - Duct Banks Precast Installation (562) | CI | CIDB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17134 | 0 | 10610.CI.CO.M3 | 342.68 | 0
C321132CIGR000020 | U21 - Grounding Network Execution (562) | CI | CIGR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 763 | 0 | 10610.CI.GR.LM | 1271.98 | 0
C321132CIGR000070 | U21 - Grounding Network Execution (580) | CI | CIGR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10418 | 0 | 10780.CI.CI.MH
C321132CIHE000020 | U21 - Vertical Vessels (Waste Heat Boiler Blowdown Drum) Foundation Execution 562-V-302 (580) | CI | CIVE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 729 | 0 | 10780.CI.CI.MH
C321132CIMF000020 | U21 - Miscellaneous Foundations Execution (562) | CI | CIMF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3509 | 0 | 10610.CI.CO.M3 | 58.48 | 0
C321132CIOT000010 | U21 - Open Concrete Trenches Execution (562) | CI | CIOT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9840 | 0 | 10610.CI.CO.M3 | 164 | 0
C321132CIOT000010 | U21 - Open Concrete Trenches Execution (562) | CI | CIOT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9840 | 0 | 10610.CI.CO.M3 | 164 | 0
C321132CIPE000010 | U21 - Steam Turbine Generator 562-ST-301 Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27741 | 331.4884 | 10610.CI.CO.M3 | 554.82 | 0
C321132CIPE000020 | U21 - Lube Oil Skid Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2520 | 0 | 10610.CI.CO.M3 | 42 | 0
C321132CIPE000040 | U21 - Gas Turbine Generator Package 580-ME-101J Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11146 | 7.3412 | 10610.CI.CO.M3 | 222.92 | 0
C321132CIPE000070 | U21 - Auto Tune Cabinet Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1267 | 0 | 10780.CI.CI.MH
C321132CIPE000090 | U21 - Fuel Gas Skid A Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1272 | 0 | 10610.CI.CO.M3 | 21.2 | 0
C321132CIPE000150 | U21 - CEMS Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1267 | 0 | 10780.CI.CI.MH
C321132CIPR000010 | U21 - 562-PR-101 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10214 | 154.1257 | 10610.CI.CO.M3 | 170.24 | 170.24
C321132CIPR000040 | U21 - 562-PR-201 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31665 | 23.3888 | 10610.CI.CO.M3 | 633.3 | 0
C321132CIPR000050 | U21 - 562-PR-202 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2276 | 7.6526 | 10780.CI.CI.MH
C321132CIPR000290 | U21 - 580-PR-102 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3638 | 0 | 10610.CI.CO.M3 | 60.64 | 0
C321132CIPR130 | U21 - 562-PR-104 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4140 | 25.3202 | 10610.CI.CO.M3 | 69 | 69
C322132CIPS000150 | U22 - Equipment Foundation Execution inside sump (571-P-106 A/B) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 286 | 0.012719 | 10780.CI.CI.MH
C322132CIPV000200 | U22 - Gravel Paving Execution | CI | CIPV2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8540 | 0 | 10780.CI.CI.MH
C322132CIRE000090 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701F) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000100 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701C) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.6998
C322132CIRE000110 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701B) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.7
C322132CIRE000120 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701A) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.7
C322132CIRE000200 | U22 - LT K.O Drum Pumps Foundation Execution (571-P-402 A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1885 | 0 | 10610.CI.CO.M3 | 31.42 | 0
C322132CIRE000210 | U22 - Vertical Intermediate Hydrocarbon Flare K.O Drum Pump Foundation Execution (571-P-301A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1453 | 0 | 10610.CI.CO.M3 | 24.22 | 0
C322132CIRE000240 | U22 - Blowdown Drum HydroCarbon Pump Foundation Execution (571-P-503A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 423 | 0.02781 | 10610.CI.CO.M3 | 6.04 | 0
C322132CIST000190 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701B) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10758 | 124.7938 | 10610.CI.CO.M3 | 215.16 | 180.7301
C322132CIST000190 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701B) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10758 | 124.7938 | 10610.CI.CO.M3 | 215.16 | 180.7301
C322132CIST000200 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701A) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10794 | 125.3584 | 10610.CI.CO.M3 | 215.88 | 181.3392
C322132CIUG000110 | U22 - UG Civil Works | CI | CIUG1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19910 | 74.6653 | 10780.CI.CI.MH
C322132CIUG200010 | U22 - UG Pipe Installation (CD) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6361 | 4.2161 | 10610.CI.UG.LM | 318.06 | 25.4384
C322132CIUP000040 | U22 - UG Piping Prefabrication | PI | PIPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16984 | 426.1342 | 10610.PI.FB.DI | 4246 | 4486.9543
C322132CIVE000200 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.093998 | 10610.CI.CO.M3 | 9.74 | 0
C322132CIVE000240 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.021891 | 10610.CI.CO.M3 | 2.47 | 1.76
C322132CIVE000270 | U22 - HC Flare Gas Recovery Compressor Filter Foundation Execution (571-F-701B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.015901 | 10610.CI.CO.M3 | 4.57 | 0
C322132CIVE000300 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C321132CIPV000020 | U21 - Concrete Paving Execution (562) | CI | CIPV1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6782 | 0 | 10610.CI.PV.M2 | 3767.86 | 0
C321132CIPV000170 | U21 - Gravel Paving Execution (562) | CI | CIPV2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2200 | 0 | 10780.CI.CI.MH
C321132CIRD0000120 | Common General Plant Road | CI | CIPV3 | 22 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41819 | 0 | 10780.CI.CI.MH
C321132CIRD000090 | U21 - Road Execution (562) | CI | CIRD1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2761 | 0 | 10780.CI.CI.MH
C321132CIST000010 | U21 - Lube Oil Cooler Structures Foundation (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3004 | 1.3472 | 10610.CI.CO.M3 | 50.07 | 0
C321132CIST000010 | U21 - Lube Oil Cooler Structures Foundation (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3004 | 1.3472 | 10610.CI.CO.M3 | 50.07 | 0
C321132CIST000040 | U21 - Shelter 562-SH-001 Generator Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 6.7477 | 10610.CI.CO.M3 | 155.27 | 0
C321132CIST000080 | U21 - STR-101/102/103/104/105/106 Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 891 | 0 | 10610.CI.CO.M3 | 12.73 | 0
C321132CIST000170 | U21 - Platform for Air Cooler 562-E-304 Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1275 | 0 | 10610.CI.CO.M3 | 21.25 | 0
C321132CIST000200 | U21 - Platform for Waste Heat Boiler 562-B-101J Structure Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.CI.CO.M3 | 230 | 0
C321132CIUG000070 | U21 - UG Process Channel Execution (Closed Drain System) (562) | CI | CIUG3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11497 | 0 | 10610.CI.CO.M3 | 191.61 | 0
C321132CIUP000030 | U21 - UG Piping Prefabrication (562) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 480 | 0.25722 | 10610.PI.FB.DI | 120 | 26.0496
C321132SPSP000010 | Cutting of Concrete (Paved Area) | SP | SPSP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 2.0103 | 10780.SP.SP.MH
C321132STMS000020 | U21 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (562) | ST | STMS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1829 | 4.78 | 10610.ST.PL.TN | 30.48 | 30.4846
C321132STPL000050 | U21 - Piperack Platforms, Ladders & Handrails Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8389 | 87.4817 | 10610.ST.PL.TN | 104.86 | 87.0364
C321132STPL000070 | U21 - STR-101/102/103/104/105/106 Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10780.ST.ST.MH
C321132STPL000120 | U21 - Piperack Platforms, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1819 | 0 | 10610.ST.PL.TN | 22.73 | 0
C321132STPL000130 | U21 - Equipment Structures for Air Cooler 562-E-304, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 410 | 0 | 10610.ST.PL.TN | 5.12 | 0
C321132STPL000140 | U21 - Equipment Platforms, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 205 | 0 | 10610.ST.PL.TN | 2.56 | 0
C322132MEMC000040 | U22 - Miscellaneous Piping | PI | PISU2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5828 | 0 | 10780.PI.PI.MH
C322132METK110020 | U23 - (566 CWS) - Storage Tank 566-TK-201- Annular Plate and Bottom Plate Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4300 | 27.3151 | 10610.ME.TE.TN | 43 | 43
C322132METK110040 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 1 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110140 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 4 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110140 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 4 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110180 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Platform & Staircase Erection for Shell 6 and Shell 5 | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1100 | 0.1211 | 10610.ME.TE.TN | 11 | 0.77
C322132METK110190 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 6 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110200 | U22 - TEG Storage Tank Erection 571-TK-201 - Hydraulic Test | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 260 | 0.099865 | 10610.PR.HT.DI | 6 | 6
C322132METK110280 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 3 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110300 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell/Roof Nozzle and Internal Piping Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10780.ME.ME.MH
C322132METK110320 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 1 Erection including Appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110350 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Internal Piping Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.ME.ME.MH
C322132PLIN000020 | U22 - Piling Installation | PL | PLIN | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4838 | 34.5807 | 10610.PL.PL.UN | 163 | 163
C322132STEQ000080 | U22 - Miscellaneous Platform Structure Erection (Plt-V401A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 964 | 0 | 10610.ST.PL.TN | 18.18 | 0
C322132STEQ000120 | U22 - Miscellaneous Platform Structure Erection (Plt-V402B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1059 | 0 | 10610.ST.PL.TN | 19.99 | 0
C322132STEQ000140 | U22 - HC Flare Gas Recovery Compressor Structure Execution (571-C-701C) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 901 | 0 | 10780.ST.ST.MH
C322132STEQ000160 | U22 - HC Flare Gas Recovery Compressor Structure Execution (571-C-701B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 901 | 0 | 10780.ST.ST.MH
C322132STEQ000170 | U22 - HC Flare Gas Recovery Compressor Structure Execution (571-C-701A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 901 | 0 | 10780.ST.ST.MH
C321132STPL000150 | U21 - Platform for Waste Heat Boiler 562-B-101J Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 298 | 0 | 10610.ST.PL.TN | 3.72 | 0
C321132STPR000050 | U21 - 562-PR-101 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2385 | 0 | 10610.ST.PR.TN | 45 | 0
C321132STPR000080 | U21 - 562-PR-103 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2597 | 0 | 10610.ST.PR.TN | 49 | 0
C321132STPR000110 | U21 - 580-PR-101 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4913 | 0 | 10610.ST.PR.TN | 92.7 | 0
C321132STPR150 | U21 - 562-PR-104 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2650 | 1.5043 | 10610.ST.PR.TN | 50 | 0
C321132STSH000040 | U21 - Shelter GTG-GSUT Transformer Structure Erection (580) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2173 | 0 | 10780.ST.ST.MH
C321132STSH000070 | U21 - Shelter 562-SH-001 Roofing & Wall Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3740 | 0 | 10610.ST.ER.TN | 70.57 | 0
C321133PAEQ000050 | U21 - Equipment Painting (580) | PA | PAEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 951 | 0 | 10780.PA.PA.MH
C321133PAFP000020 | U21 - Piping Final Coat & Touch-Up Painting (562) | PA | PAFP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 564 | 0 | 10780.PA.PA.MH
C321133PAPP000020 | U21 - Piping SandBl. & Priming (562) | PA | PAPP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4698 | 6.1843 | 10610.PA.PP.M2 | 2349 | 464.7693
C321133PAPP000060 | U21 - Piping SandBl. & Priming (580) | PA | PAPP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6877 | 13.2514 | 10610.PA.PP.M2 | 0 | 0
C321133PAST000070 | U21 - Steel Structure Painting Touch Up (580) | PA | PAST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2377 | 0 | 10780.PA.PA.MH
C321134ELCL000030 | U21 - Lighting Cable Laying (562) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8625 | 0 | 10610.EL.LC.LM | 23344.98 | 0
C321134ELCL000040 | U21 - Electrical Cable Laying (562) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 42166 | 0 | 10610.EL.PL.LM | 78875.73 | 0
C321134ELCO000030 | U21 - Lighting Cable Gland & Conn./Testing (562) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5750 | 0 | 10610.EL.CO.UN | 364 | 0
C321134ELCO000120 | U21 - Lighting Cable Gland & Conn./Testing (580) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8144 | 0 | 10610.EL.CO.UN | 324 | 0
C321134ELCP000020 | U21 - Cathodic Protection Piping (562) | EL | ELCP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3833 | 0 | 10780.EL.EL.MH
C321134ELEL000035 | U21 - Earthing & Lightning Works (562) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5111 | 0 | 10610.EL.ES.LM | 3287.71 | 0
C321134ELEL000075 | U21 - Earthing Works (580) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7239 | 0 | 10610.EL.ES.LM | 3287.71 | 0
C321134ELEQ000040 | U21 - GTG Generator Circuit Breaker 580-EE-CB-1502J Installation (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 70 | 0
C322132STEQ000180 | U22 - HC Flare Drain Drum platform erection inside sump (571-V-404) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1961 | 0 | 10780.ST.ST.MH
C322132STEQ000200 | U22 - Cooler Support Structure Erection (571-E-701A/702A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 689 | 0 | 10780.ST.ST.MH
C322132STEQ000230 | U22 - Flare Supporting Structure (571-ME-401/403) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1113 | 0.013487 | 10780.ST.ST.MH
C322132STEQ000320 | U22 - Cooler Support Structure Erection (571-E-702C/702C) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 689 | 0.054351 | 10780.ST.ST.MH
C322132STPL000150 | U22 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89104 | 0 | 10610.ST.PL.TN | 1113.81 | 0
C322132STPL000160 | U22 - Equipment Structures, Ladders & Handrails Erection | ST | STPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7009 | 5.8297 | 10610.ST.PL.TN | 87.61 | 6.9914
C322132STPR000160 | U22 - Main Piperack Erection (571-PR-151) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7297 | 71.1595 | 10610.ST.PR.TN | 137.68 | 137.677
C322132STPR000170 | U22 - Main Piperack Erection (571-PR-152) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6384 | 54.3246 | 10610.ST.PR.TN | 120.45 | 120.449
C322132STPR000190 | U22 - Main Piperack Erection (571-PR-154) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6195 | 47.8729 | 10610.ST.PR.TN | 116.9 | 116.5745
C322132STPR000200 | U22 - Main Piperack Erection (571-PR-155) (Including Tower near flare) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9111 | 15.2292 | 10610.ST.PR.TN | 171.9 | 9.9494
C322132STPR000220 | U22 - Main Piperack Erection (571-PR-143) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7990 | 0 | 10610.ST.PR.TN | 150.76 | 0
C322132STPR000230 | U22 - Main Piperack Erection (571-PR-142) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4978 | 16.2391 | 10610.ST.PR.TN | 93.92 | 51.6579
C322132STPR000240 | U22 - Main Piperack Erection (571-PR-141) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5765 | 31.4736 | 10610.ST.PR.TN | 108.78 | 92.4631
C322132STPR000250 | U22 - Main Piperack Erection (571-PR-139/140) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14880 | 197.7379 | 10610.ST.PR.TN | 280.76 | 210.7014
C322132STPR000290 | U22 - Main Piperack Erection (571-PR-136) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14586 | 243.4146 | 10610.ST.PR.TN | 275.2 | 247.681
C322132STPR000302 | U22 - Main Piperack Erection (571-PB-128) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16536 | 0 | 10610.ST.PR.TN | 311.99 | 0
C322132STPR000303 | U22 - Main Piperack Erection (571-PR-129) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10511 | 0 | 10610.ST.PR.TN | 198.32 | 0
C322132STPR000304 | U22 - Main Piperack Erection (571-PR-130) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8894 | 0 | 10610.ST.PR.TN | 167.8 | 0
C322132STPR000305 | U22 - Main Piperack Erection (571-PR-131) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8083 | 0 | 10610.ST.PR.TN | 152.52 | 0
C322132STPR000306 | U22 - Main Piperack Erection (571-PR-132) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8068 | 0 | 10610.ST.PR.TN | 152.22 | 0
C321134ELEQ000110 | U21 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 330 | 0
C321134ELEQ000140 | U21 - STG Step-up Transformer 580-EE-2311K Installation (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 200 | 0
C321134ELGR000020 | U21 - Grounding Installation (562) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5111 | 0 | 10780.EL.EL.MH
C321134ELPL000020 | U21 - Plant Lighting - (Lighting poles and fixtures) Installation (562) | EL | ELPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12458 | 0 | 10780.EL.EL.MH
C321134ELTI000130 | U21 - Electrical Cable Trays Installation (580) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27146 | 0 | 10610.EL.CT.LM | 2777.92 | 0
C321134MEMC000070 | U21 - Miscellaneous Electrical (580) | EL | ELEQ2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1437 | 0 | 10780.EL.EL.MH
C321136MEAC000050 | U21 - Air Coolers (Waste Heat Boiler Blowdown Cooler) Erection 562-E-304 Waste Heat Boiler Blowdown Cooler (580) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEHL000020 | U21 - Package Installation (Gas Turbine Generator Pack.) 580-ME-101J (580) - Generator (HL) (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4200 | 0 | 10610.ME.ER.TN | 70 | 0
C321136MEHM000180 | U21 - Horizontal Pump with Electrical Motor Erection 562-P-308A/B Waste Heat Boiler Blowdown Pump (580) | ME | MEHM1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEHV000070 | U21 - Vertical Vessels (Waste Heat Boiler Blowdown Drum) Erection 562-V-302 Waste Heat Boiler Blowdown Drum (580) | ME | MEVV | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEPA000060 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Fire Fighting Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C321136MEPA000070 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Autotune Cabinet Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C321136MEPA000140 | U21 - Package Installation (LP Steam Desuperheaters) 562-ME-311A/B Desuperheaters (562) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEPA000240 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Generator (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3480 | 0 | 10610.ME.ER.TN | 58 | 0
C321136MESB000020 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - Duct Burners | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C321137INAI000020 | U21 - Analyzers Equipment Installation (562) | IN | INAI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1924 | 0 | 10610.IN.AI.UN | 1 | 0
C321137INCI000020 | U21 - Conduits Installation (562) | IN | INCT3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 923 | 0 | 10780.IN.IN.MH
C321137INCT000030 | U21 - Primary Cable Trays Installation (562) | IN | INCT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 0 | 10610.IN.CT.LM | 170 | 0
C322132STPR000307 | U15 - Main Piperack Erection (577-PB-122/577-PR-122A) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21894 | 334.3155 | 10610.ST.PR.TN | 413.1 | 258.1815
C322132STPR000320 | U22 - Main Piperack Erection (571-PR-133) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14068 | 0 | 10610.ST.PR.TN | 265.44 | 0
C322132STPR000325 | U22 - Main Piperack Erection (571-PR-135) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12600 | 221.5129 | 10610.ST.PR.TN | 237.73 | 232.5881
C322132STPR000325 | U22 - Main Piperack Erection (571-PR-135) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12600 | 221.5129 | 10610.ST.PR.TN | 237.73 | 232.5881
C322132STPR000470 | U22 - Secondary Piperack Erection (PR-545_29/545_26) | ST | STPR | 22 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3286 | 0 | 10780.ST.ST.MH
C322132STPR100000 | U22 - Main Piperack Erection (577-PB-116) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24467 | 876.4594 | 10610.ST.PR.TN | 461.64 | 461.6367
C322132STPR100020 | U22 - Main Piperack Erection (577-PR-115) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24777 | 906.0013 | 10610.ST.PR.TN | 467.49 | 467.489
C322132STPR100060 | U22 - Main Piperack Erection (577-PR-120) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26395 | 954.2968 | 10610.ST.PR.TN | 498.02 | 448.496
C322132STPR100070 | U22 - Main Piperack Erection (577-PR-112 / 577-PR-113) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 87614 | 10971.5161 | 10610.ST.PR.TN | 1653.1 | 1562.3617
C322132STPR100080 | U22 - Secondary Piperack Erection (571-PR-156) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12984 | 0 | 10610.ST.PR.TN | 244.99 | 0
C322132STPR100090 | U22 - Secondary Piperack Erection (571-PR-157) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15635 | 0 | 10610.ST.PR.TN | 0 | 0
C322132STSH000030 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701C) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322132STSH000040 | U22 - Compressor Shelter Roofing & Wall Erection ( SH- 571-C-701C) | ST | STSH2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30 | 0 | 10780.ST.ST.MH
C322132STSH000080 | U22 - Compressor Shelter Architecture ( SH- 571-C-701B) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2240 | 0 | 10780.ST.ST.MH
C322132STSH000100 | U22 - Compressor Shelter Roofing & Wall Erection ( SH- 571-C-701A) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30 | 0 | 10780.ST.ST.MH
C322132STSP80 | U22 - Steel Structure 571-STR-68-72 ( Pipeline Support ) | ST | STSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2782 | 0 | 10610.ST.PL.TN | 46.37 | 0
C322133PAPP000070 | U22 - Piping SandBl. & Priming | PA | PAPP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51465 | 3013.266 | 10610.PA.PP.M2 | 0 | 0
C322133PASP000080 | U22 - Piping Supports SandBl. & Priming | PA | PASP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6814 | 4.7122 | 10610.PA.SU.TN | 0 | 0
C322134ELCL000150 | U22 - Lighting Cable Laying | EL | ELCL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18391 | 0 | 10610.EL.LC.LM | 105611.52 | 0
C322134ELCL000160 | U22 - Electrical Cable Laying | EL | ELCL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89909 | 0 | 10610.EL.PL.LM | 112350.77 | 0
C321137INCT000100 | U21 - Primary Cable Trays Installation (580) | IN | INCT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2852 | 0 | 10610.IN.CT.LM | 170 | 0
C321137INCT000110 | U21 - Secondary Cable Trays Installation (580) | IN | INCT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1597 | 0 | 10610.IN.CT.LM | 200 | 0
C321137INFC000020 | U21 - Fiber Optic Gland & Conn./Testing (562) | IN | INFC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 855 | 0 | 10610.IN.CO.UN | 180 | 0
C321137INFC000060 | U21 - Fiber Optic Gland & Conn./Testing (580) | IN | INFC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 274 | 0 | 10610.IN.CO.UN | 310 | 0
C321137INFG000060 | U21 - Fire & Gas System Installation (580) | IN | INFG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 297 | 0 | 10780.IN.IN.MH
C321137INGC000040 | U21 - Single Pair Cable Gland & Conn./Testing (562) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3705 | 0 | 10610.IN.CO.UN | 300 | 0
C321137ININ000020 | U21 - Instruments Installation (562) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2850 | 0 | 10610.IN.IN.UN | 300 | 0
C321137ININ000061 | U21 - Valve Installation (580) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 913 | 0 | 10610.IN.IN.UN | 170 | 0
C321137INML000020 | U21- Multi Pair Cable Pulling (562) | IN | INML | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11115 | 0 | 10610.IN.MC.LM | 20672.33 | 0
C321137INML000060 | U21- Multi Pair Cable Pulling (580) | IN | INML | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3559 | 0 | 10610.IN.MC.LM | 17902.52 | 0
C321137INSL000020 | U21 - Single Pair Cable Pulling (562) | IN | INSL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 0 | 10610.IN.SC.LM | 37276.78 | 0
C321137MEMC000020 | U21 - Miscellaneous Instrumentation (562) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2850 | 0 | 10780.IN.IN.MH
C321137MEMC000060 | U21 - Miscellaneous Instrumentation (580) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 913 | 0 | 10780.IN.IN.MH
C3220PRPRPL000080 | U22 - Punch List | PR | PRPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14145 | 0 | 10780.PR.PR.MH
C322131ISEQ000040 | U22 - Equipment Insulation | IS | ISEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 301 | 0 | 10610.IS.EQ.M2 | 1591 | 0
C322131NIPR000020 | U22 - Nitrogen Purging & Inerting (Unit 571) | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3333 | 0 | 10780.PR.PR.MH
C322131PIBB000120 | U22 - Big Bore Piping A/Equip. Erection PR-571-138/137 to 571-V-401 A & 401B | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000130 | U22 - Big Bore Piping A/Equip. Erection PR-571-137/136 to 571-V-402 A & 402B | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000150 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-118 / 119 to 571-V-301 A / 301B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000160 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-120 to 571-V-303 A / 303B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322134ELEQ000040 | U22 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.EQ.UN | 520 | 0
C322134ELTI000140 | U22 - Lighting Cable Trays Installation | EL | ELTI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.CT.LM | 6177.24 | 0
C322136MEAC000070 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701A | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C322136MEAC000120 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Pre-Assembly 571-E-701C | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000130 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Pre-Assembly 571-E-702B | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000170 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702B | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000190 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701C) | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEAC000200 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701A) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEAC000210 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701B) | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEHE000110 | U22 - Heat Exchangers (LT Flare K.O Drum Heater) Erection 571-E-402A | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHE000140 | U22 - Heat Exchangers (Intermediate LT Flare K.O Drum Heater) Erection 571-E-302B | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHL000060 | U22 - Heavy Equipment (Intermediate Hydrocarbon Flare K.O. Drum) Erection (571-V-301B) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEHL000100 | U22 - Heavy Equipment (Hydrocarbon Flare K.O. Drum) Erection (571-V-401A) (HL) (1600 + 650 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7400 | 2.1292 | 10610.ME.ER.TN | 185 | 0
C322136MEHM000200 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000250 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000310 | U22 - Horizontal Pump (Blowdown Drum HC Pump) with Electrical Motor Erection 571-P-503A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000320 | U22 - Horizontal Pump (Blowdown Drum Sour Water Pump) with Electrical Motor Erection 571-P-504A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322131PIPR000070 | U22 - Piping Prefabrication | PI | PIPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 438493 | 216131.8821 | 10610.PI.FB.DI | 109623.13 | 59663.4298
C322131PIRA000080 | U22-Piping Erection on Rack (571-PR-148) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 38.8006 | 10610.PI.PR.DI | 1119.81 | 680.0046
C322131PIRA000080 | U22-Piping Erection on Rack (571-PR-148) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 38.8006 | 10610.PI.PR.DI | 1119.81 | 680.0046
C322131PIRA000100 | U22-Piping Erection on Rack (571-PR-146) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0.66321 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000140 | U22-Piping Erection on Rack (571-PR-154) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000170 | U22-Piping Erection on Rack (571-PR-143) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000180 | U22-Piping Erection on Rack (571-PR-142) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000200 | U22-Piping Erection on Rack (571-PR-139/140) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000210 | U22-Piping Erection on Rack (571-PR-138) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000220 | U22-Piping Erection on Rack (571-PR-137) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000230 | U22-Piping Erection on Rack (571-PR-145) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000460 | U22-Piping Erection on Rack (577-PR-120) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 23.2212 | 10610.PI.PR.DI | 1119.81 | 218.0046
C322131PIRA000470 | U22-Piping Erection on Rack (577-PB-121) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000510 | U22-Piping Erection on Main Piperack/Bridge (571-PB-127) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000520 | U22-Piping Erection on Main Piperack/Bridge (571-PB-128) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 8.9443 | 10610.PI.PR.DI | 1119.81 | 155.9895
C322131PIRA000560 | U22-Piping Erection on Rack (571-PR-132) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000580 | U22-Piping Erection on Rack (571-PR-133) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 3.3175 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000600 | U22-Piping Erection on Rack (571-PR-135) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 5.3072 | 10610.PI.PR.DI | 1119.81 | 0
C322131PISB000081 | U22 - Small Bore Piping A/Equip. Erection PR-571-142 to 571-E701/702C cooler & 571-C701 C | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000090 | U22 - Small Bore Piping A/Equip. Erection PR-571-141 to 571-E701/702B cooler & 571-C701 B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C220132BUTRAR100070 | U20 - SS-520 - Painting Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15902 | 0 | 10610.BU.AR.M2 | 1830 | 0
C220132BUTRAR100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Transformer Foundation and Firewalls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10945 | 162.9937 | 10610.BU.CO.M3 | 232.27 | 213.6908
C220132BUTRAR100130 | U20 - NMCB - Plastering Works | BU | BUARPA | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10610.BU.AR.M2 | 65 | 0
C220132BUTRFO100030 | U20 - SS-524 - Excavation and Compaction (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17900 | 473.344 | 10780.BU.BU.MH
C220132BUTRFO100050 | U20 - SS-524 - Blinding and Water Proofing (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9577 | 135.498 | 10780.BU.BU.MH
C220132BUTRFO100080 | U20 - SS-521 - Blinding and Water Proofing (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11827 | 206.6365 | 10780.BU.BU.MH
C220132BUTRFO100111 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Firewall Foundations & Wallsl- by OQC-B | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17307 | 414.6305 | 10610.BU.CO.M3 | 826.8 | 768.924
C220132BUTRFO100121 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Firewall Foundation & Walls-by NMDC-INFRA | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24511 | 756.3695 | 10610.BU.CO.M3 | 915 | 759.4496
C220132BUTRFO100170 | U20 - SS-523 - Blinding and Water Proofing (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1462 | 0 | 10780.BU.BU.MH
C220132BUTRFO100180 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Chiller Foundations (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2193 | 0 | 10610.BU.CO.M3 | 57.5 | 0
C220132BUTRFO100200 | U20 - SS-523 - Plastering Works (Elect. Subst.) | BU | BUARPA | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1401 | 0 | 10610.BU.AR.M2 | 75 | 0
C220132BUTRFO100310 | U20 - SS-523 - Install Removable Fence and Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1462 | 0 | 10780.BU.BU.MH
C220132BUTRGR100010 | U20 - SS-516 - Transf. Yard Grounding (Pre-Shutdown)ok | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16965 | 374.1595 | 10780.BU.BU.MH
C220132BUTRGR100030 | U20 - SS-521 - Transf. Yard Grounding (Elect. Subst.) | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1587 | 0 | 10780.BU.BU.MH
C220132BUTRGR100060 | U20 - SS-523 - Transf. Yard Grounding (Elect. Subst.) | BU | BUTRGR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 548 | 0 | 10780.BU.BU.MH
C220132BUTRGR1011 | U20 - SS-516 - Transf. Fnds Yard Concrete Structure #B (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10265 | 155.6626 | 10610.BU.CO.M3 | 149 | 148.9994
C220132BUTRGR1012 | U20 - SS-516 - Transf. Fnds Yard Concrete Structure #A (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10265 | 155.6626 | 10610.BU.CO.M3 | 149 | 149.0007
C220132BUTRGR1012 | U20 - SS-516 - Transf. Fnds Yard Concrete Structure #A (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10265 | 155.6626 | 10610.BU.CO.M3 | 149 | 149.0007
C220132CICT1100040 | U20 - SS-526 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44 | 0 | 10610.CI.ET.M3 | 11 | 0
C322131PISB000110 | U22 - Small Bore Piping A/Equip. Erection PR-571-135 to 571-V-403B, 571-SU-103 | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000120 | U22 - Small Bore Piping A/Equip. Erection PR-571-138/137 to 571-V-401 A & 401B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000130 | U22 - Small Bore Piping A/Equip. Erection PR-571-137/136 to 571-V-402 A & 402B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000150 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-118 / 119 to 571-V-301 A / 301B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISU000160 | U22 - Piping Supports Erection | PI | PISU2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 178306 | 0 | 10610.PI.SU.TN | 396.24 | 0
C322131PRBO000100 | U22 - Static Box Up | PR | PRBO1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29362 | 0 | 10780.PR.PR.MH
C322131PRFL000070 | U22 - Piping Flushing/Steam Blowing | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16496 | 0 | 10610.PR.FL.DI | 261183 | 0
C322131PRFL000230 | U22 - Lube Oil Flushing for Compressors (Unit 571) | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5665 | 0 | 10780.PR.PR.MH
C322131PRHT000080 | U22 - Piping Hydrotesting | PR | PRHT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 164129 | 0 | 10610.PR.HT.DI | 261183 | 0
C322131PRRE000050 | U22 - Piping Reinstatement | PR | PRRE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 131303 | 0 | 10610.PR.RE.DI | 261183 | 0
C322132CICT000080 | U22 - Covered Concrete Trenches Execution | CI | CICT1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11997 | 65.3987 | 10610.CI.CO.M3 | 239.93 | 199.9999
C322132CIDB000045 | U22 - Duct Banks Precast Installation | CI | CIDB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 62820 | 4430.7005 | 10610.CI.CO.M3 | 1256.39 | 1256.3904
C322132CIDM000050 | U22 - Manholes & Catchbasins Installation | CI | CIDM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31773 | 666.1067 | 10610.CI.CO.M3 | 635.45 | 399.9999
C322132CIGT000150 | U22 - Steel Structure Grouting Execution | CI | CIGT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1260 | 0 | 10780.CI.CI.MH
C322132CIHE000120 | U22 - Horizontal Vessel (HC Flare K.O Drum) Foundation Execution (571-V-401B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14248 | 280.9569 | 10610.CI.CO.M3 | 284.96 | 284.96
C322132CIHE000120 | U22 - Horizontal Vessel (HC Flare K.O Drum) Foundation Execution (571-V-401B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14248 | 280.9569 | 10610.CI.CO.M3 | 284.96 | 284.96
C322132CIHE000140 | U22 - Horizontal Vessel (LT Flare K.O Drum) Foundation Execution (571-V-402B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15530 | 322.5341 | 10610.CI.CO.M3 | 310.6 | 310.6
C322132CIHE000200 | U22 - Horizontal Intermediate LT Flare K.O Drum Foundation Execution (571-V-302B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8276 | 98.5246 | 10610.CI.CO.M3 | 137.94 | 137.9399
C322132CIHE000220 | U22 - Horizontal Blowdown Drum Foundation Execution (571-V-505) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5521 | 43.2304 | 10610.CI.CO.M3 | 92.02 | 92.0202
C220132CICT1100050 | U20 - SS-525 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44 | 0 | 10610.CI.ET.M3 | 11 | 0
C220132CICT1100060 | U20 - SS-524 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1004 | 0 | 10610.CI.ET.M3 | 251 | 0
C220132CICT1100070 | U20 - SS-523 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 232 | 0 | 10610.CI.ET.M3 | 58 | 0
C220132CIFC1100010 | U20 - SS-524 - Install Removable Chain Link Fence and Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1938 | 0 | 10780.BU.BU.MH
C220132CIFC1100030 | U20 - SS-522 - Install Removable Chain Link Fence and Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5170 | 0 | 10780.BU.BU.MH
C220132CISF100020 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8693 | 89.4775 | 10610.BU.CO.M3 | 66.02 | 52.8197
C220132CISF100020 | U20 - SS-520 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8693 | 89.4775 | 10610.BU.CO.M3 | 66.02 | 52.8197
C220132CISF100030 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8221 | 99.8431 | 10610.BU.CO.M3 | 47.23 | 47.23
C220132CISF100030 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8221 | 99.8431 | 10610.BU.CO.M3 | 47.23 | 47.23
C220132CISF100040 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9766 | 128.9227 | 10610.BU.CO.M3 | 41 | 37.3098
C220132CISF100040 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9766 | 128.9227 | 10610.BU.CO.M3 | 41 | 37.3098
C220132CISF100050 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8510 | 99.2769 | 10610.BU.CO.M3 | 57 | 52.44
C220132CISF100050 | U20 - SS-521 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8510 | 99.2769 | 10610.BU.CO.M3 | 57 | 52.44
C220132CISF100060 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Footings and Columns (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3534 | 18.4524 | 10610.BU.CO.M3 | 69 | 69
C220132CISF100080 | U20 - SS-522 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11298 | 144.2569 | 10610.BU.CO.M3 | 56 | 42
C220132CISF100100 | U20 - SS-525 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 273 | 0 | 10610.BU.CO.M3 | 39.88 | 0
C220132CISF100110 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7324 | 42.4003 | 10610.BU.CO.M3 | 20 | 10.75
C322132CIHE000230 | U22 - Horizontal Acid Gas Flare K.O Drum Foundation Execution (571-V-403) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11530 | 163.8255 | 10610.CI.CO.M3 | 230.59 | 201.7709
C322132CIHE000230 | U22 - Horizontal Acid Gas Flare K.O Drum Foundation Execution (571-V-403) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11530 | 163.8255 | 10610.CI.CO.M3 | 230.59 | 201.7709
C322132CIMF000090 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-401 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5318 | 26.2777 | 10610.CI.CO.M3 | 88.64 | 48.7502
C322132CIMF000100 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-402A) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 8.1602 | 10610.CI.CO.M3 | 58.51 | 23.3999
C322132CIMF000100 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-402A) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 8.1602 | 10610.CI.CO.M3 | 58.51 | 23.3999
C322132CIMF000120 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-402 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8088 | 93.8952 | 10610.CI.CO.M3 | 134.81 | 134.81
C322132CIMF000130 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-301 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10636 | 146.7139 | 10610.CI.CO.M3 | 177.27 | 159.5395
C322132CIMF000140 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-301 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5485 | 41.2182 | 10610.CI.CO.M3 | 91.42 | 82.2798
C322132CIMF000150 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-302 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5216 | 38.5071 | 10610.CI.CO.M3 | 86.94 | 85.1999
C322132CIMF000160 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-302 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3395 | 16.7066 | 10610.CI.CO.M3 | 56.59 | 56.5898
C322132CIMF000170 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-303 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1891 | 4.9146 | 10610.CI.CO.M3 | 31.51 | 31.51
C322132CIMF000170 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-303 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1891 | 4.9146 | 10610.CI.CO.M3 | 31.51 | 31.51
C322132CIMF000180 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-303 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8088 | 96.031 | 10610.CI.CO.M3 | 134.81 | 134.8105
C322132CIMF000220 | U22 - Miscellaneous Foundations Execution (571-FM-303/308/309) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7273 | 6.8372 | 10610.CI.CO.M3 | 121.21 | 40
C322132CIMF000220 | U22 - Miscellaneous Foundations Execution (571-FM-303/308/309) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7273 | 6.8372 | 10610.CI.CO.M3 | 121.21 | 40
C322132CIMF000250 | U22 - Miscellaneous Platform Foundations Execution (PLT-PR-135) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28389 | 1162.388 | 10610.CI.CO.M3 | 567.77 | 567.77
C322132CIOT000020 | U22 - Open Concrete Trenches Execution | CI | CIOT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11997 | 156.3071 | 10610.CI.CO.M3 | 239.93 | 208.7391
C322132CIPE000050 | U22 - Hydrocarbon Flare Package Foundation Execution (571-ME-401) | CI | CIPE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13542 | 270.7437 | 10780.CI.CI.MH
C322132CIPR000290 | U22 - Main Piperack Foundations Execution (571-PR-148) (Including Tower near flare) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15502 | 337.0615 | 10610.CI.CO.M3 | 310.03 | 310.0299
C322132CIPR000290 | U22 - Main Piperack Foundations Execution (571-PR-148) (Including Tower near flare) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15502 | 337.0615 | 10610.CI.CO.M3 | 310.03 | 310.0299
C322132CIPR000330 | U22 - Main Piperack Foundations Execution (571-PR-151) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17392 | 443.0555 | 10610.CI.CO.M3 | 347.84 | 347.84
C322132CIPR000340 | U22 - Main Piperack Foundations Execution (571-PR-152) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15290 | 342.4206 | 10610.CI.CO.M3 | 305.79 | 305.7899
C322132CIPR000350 | U22 - Main Piperack Foundations Execution (571-PR-153) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14614 | 312.8113 | 10610.CI.CO.M3 | 292.27 | 292.2701
C322132CIPR000390 | U22 - Main Piperack Foundations Execution (571-PR-143) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12080 | 0 | 10610.CI.CO.M3 | 241.6 | 0
C322132CIPR000420 | U22 - Main Piperack Foundations Execution (571-PR-139/140) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27612 | 1119.1822 | 10610.CI.CO.M3 | 552.23 | 552.2307
C322132CIPR000430 | U22 - Main Piperack Foundations Execution (571-PR-138) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20224 | 600.394 | 10610.CI.CO.M3 | 404.47 | 404.47
C322132CIPR000440 | U22 - Main Piperack Foundations Execution (571-PR-137) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23182 | 788.8699 | 10610.CI.CO.M3 | 463.63 | 463.6302
C322132CIPR000450 | U22 - Main Piperack Foundations Execution (571-PR-145) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10572 | 164.0693 | 10610.CI.CO.M3 | 211.44 | 211.44
C322132CIPR000740 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-128) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16544 | 5.1068 | 10610.CI.CO.M3 | 330.88 | 0
C322132CIPR000750 | U22 - Main Piperack Foundations Execution (571-PR-129) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28149 | 18.4831 | 10610.CI.CO.M3 | 562.98 | 0
C322132CIPR000760 | U22 - Main Piperack Foundations Execution (571-PR-130) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15410 | 2.9538 | 10610.CI.CO.M3 | 308.2 | 0
C322132CIPR000790 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-132A) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9310 | 2.9654 | 10610.CI.CO.M3 | 155.16 | 0
C322132CIPR000830 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701B/702B & 571-PR-157) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28391 | 1049.2586 | 10610.CI.CO.M3 | 567.82 | 504.2185
C322132CIPR000860 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701C/702C & 571-PR-158) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17171 | 345.7029 | 10610.CI.CO.M3 | 343.42 | 304.9604
C322132CIPR000860 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701C/702C & 571-PR-158) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17171 | 345.7029 | 10610.CI.CO.M3 | 343.42 | 304.9604
C322132CIPR100000 | U22 - Main Piperack Foundations Execution (577-PR-116) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37213 | 2045.7651 | 10610.CI.CO.M3 | 744.26 | 744.2607
C220132CISF100110 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7324 | 42.4003 | 10610.BU.CO.M3 | 20 | 10.75
C220132CISF100150 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7324 | 0 | 10610.BU.CO.M3 | 28 | 0
C220132CISF100190 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13995 | 289.341 | 10610.BU.CO.M3 | 12 | 12
C220132CISF100210 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8906 | 117.1723 | 10610.BU.CO.M3 | 27 | 27
C220132ELCL100012 | U20 - SS-520-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 5549.24 | 0
C220132ELCL100021 | U20 - SS-521-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 13293.91 | 0
C220132ELCL100022 | U20 - SS-521-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100032 | U20 - SS-522-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 5462.34 | 0
C220132ELCL100041 | U20 - SS-520-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100061 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.311 | 10610.EL.LC.LM | 10787.56 | 10787.56
C220132ELCL100081 | U20 - SS-522-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 16387.33 | 0
C220132ELCL1001 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-516 to SS-524 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 604 | 0
C220132ELCL100100 | U20 - SS-521 - Main Power Electrical Cable (132 KV) Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 316 | 0
C220132ELCL100102 | U20 - SS-521-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 4431.41 | 0
C220132ELCL100130 | U20 - OMS-013 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1332 | 0 | 10610.EL.PL.LM | 2442.3 | 0
C220132ELCL100140 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10610.EL.PL.LM | 604 | 0
C220132ELCL100190 | U20 - SS-523 - Main Power Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.EL.PL.LM | 5527.03 | 0
C220132ELCL100200 | U20 - IES-514 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9120 | 0 | 10610.EL.PL.LM | 16720.14 | 0
C220132ELCL100250 | U20 - IES-513 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9041 | 0 | 10610.EL.PL.LM | 16574.65 | 0
C322132CIPR100020 | U22 - Main Piperack Foundations Execution (577-PR-115) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43473 | 2791.937 | 10610.CI.CO.M3 | 869.46 | 869.46
C322132CIPR100040 | U22 - Main Piperack Foundations Execution (577-PR-118) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47496 | 3279.1912 | 10610.CI.CO.M3 | 949.92 | 949.9202
C322132CIPR100070 | U22 - Main Piperack Foundations Execution (577-PB-121) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 94186 | 13105.0627 | 10610.CI.CO.M3 | 1883.72 | 1883.72
C322132CIPS000050 | U22 - Basin Construction-Evaporation Pond (571-SU-502) | CI | CIPS2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 169792 | 5877.328 | 10610.CI.CO.M3 | 3395.84 | 2699.9984
C322132CIPS000090 | U22 - Acid Gas Flare drain Drum Foundation Execution inside sump (571-V-406) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3018 | 8.4975 | 10610.CI.CO.M3 | 50.3 | 50.3
C322132CIPS000120 | U22 - Sumps Construction (571-SU-402) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11593 | 124.7219 | 10610.CI.CO.M3 | 193.22 | 193.2202
C322132CIPS000130 | U22 - Intermediate Acid Gas Flare Drain Drum Foundation Execution inside sump (571-V-405) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 286 | 0.012719 | 10780.CI.CI.MH
C322132CIPS000200 | U22 - First Flush Pit (571-SU-501) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4835 | 11.5504 | 10610.CI.CO.M3 | 80.58 | 80.58
C322132CIRE000090 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701F) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000100 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701C) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.6998
C322132CIRE000120 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701A) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.7
C322132CIRE000130 | U22 - Acid Gas Flare K.O Drum Pumps Foundation Execution (571-P-403 A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2834 | 0 | 10610.CI.CO.M3 | 47.24 | 0
C322132CIRE000140 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701A) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000150 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000160 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701C) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000180 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701E) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000190 | U22 - Hydrocarbon Flare K.O. Drum Pumps Foundation Execution (571-P-401 A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1403 | 0 | 10610.CI.CO.M3 | 23.38 | 0
C322132CIRE000200 | U22 - LT K.O Drum Pumps Foundation Execution (571-P-402 A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1885 | 0 | 10610.CI.CO.M3 | 31.42 | 0
C220132ELCO100020 | U20 - SS-520 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20423 | 0 | 10780.EL.EL.MH
C220132ELCO100030 | U20 - SS-525 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 934 | 0 | 10780.EL.EL.MH
C220132ELEL100010 | U20 - SS-520 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100020 | U20 - SS-521 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100030 | U20 - SS-524 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100040 | U20 - SS-522 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3489 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100050 | U20 - SS-526 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100120 | U20 - OMS-013 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEL100140 | U20 - IES-513 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2192 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C220132ELEQ1100090 | U20 - SS-520 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3191 | 0 | 10780.EL.EL.MH
C220132ELEQ1100100 | U20 - SS-521 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2711 | 0 | 10780.EL.EL.MH
C220132ELEQ1100120 | U20 - SS-520 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3191 | 0 | 10780.EL.EL.MH
C220132ELEQ1100200 | U20 - SS-524 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1822 | 0 | 10780.EL.EL.MH
C220132ELEQ1100210 | U20 - SS-524 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1822 | 0.26979 | 10780.EL.EL.MH
C220132ELEQ1100250 | U20 - SS-524 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1822 | 0 | 10780.EL.EL.MH
C220132ELEQ1100380 | U20 - SS-526 - SCADA Equipment Installation/IPCS/ECS (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 144 | 0 | 10780.EL.EL.MH
C220132ELEQ1100390 | U20 - SS-523 - MCC Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 817 | 0 | 10780.EL.EL.MH
C220132ELEQ1100450 | U20 - SS-525 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 146 | 0 | 10780.EL.EL.MH
C220132ELEQ1100460 | U20 - SS-525 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 146 | 0 | 10780.EL.EL.MH
C322136MEHM000340 | U22 - Horizontal Pump (Intermediate Acid Gas Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-303B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000350 | U22 - Horizontal Pump (Acid Gas Flare K.O Drum Pump) with Electrical Motor Erection 571-P-403B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C322136MEHM000390 | U22 - Horizontal Pump with Electrical Motor Erection 571-P-701D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000410 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000420 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000440 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000450 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000470 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401B (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000490 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401D (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000500 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402B (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000510 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402C (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000540 | U22 - Horizontal Sour Oily Water Pump (571-P-701 F) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEPA000062 | U22 - LT Flare Package stick built 571-ME-402 - Part-3 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 19.3923 | 10780.ME.ME.MH
C322136MEPA000064 | U22 - LT Flare Package stick built 571-ME-402 - Part-5 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 14.3951 | 10780.ME.ME.MH
C322136MEPA000066 | U22 - LT Flare Package stick built 571-ME-402 - Part-7 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 14.3951 | 10780.ME.ME.MH
C322136MEPA000070 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-1 (HL) (320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8358 | 84.367 | 10610.ME.ER.TN | 212 | 180.2
C322136MEPA000071 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-2 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3715 | 0.10194 | 10780.ME.ME.MH
C322132CIRE000210 | U22 - Vertical Intermediate Hydrocarbon Flare K.O Drum Pump Foundation Execution (571-P-301A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1453 | 0 | 10610.CI.CO.M3 | 24.22 | 0
C322132CIRE000240 | U22 - Blowdown Drum HydroCarbon Pump Foundation Execution (571-P-503A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 423 | 0.02781 | 10610.CI.CO.M3 | 6.04 | 0
C322132CIRE000500 | U22 - Glycol water make-up pump Foundation (571-P-801A) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 255 | 0 | 10610.CI.CO.M3 | 3.65 | 0
C322132CIRE000500 | U22 - Glycol water make-up pump Foundation (571-P-801A) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 255 | 0 | 10610.CI.CO.M3 | 3.65 | 0
C322132CIRE000501 | U22 - Glycol water make-up pump Foundation (571-P-801B) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 255 | 0 | 10610.CI.CO.M3 | 3.65 | 0
C322132CIRE000501 | U22 - Glycol water make-up pump Foundation (571-P-801B) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 255 | 0 | 10610.CI.CO.M3 | 3.65 | 0
C322132CIUP000040 | U22 - UG Piping Prefabrication | PI | PIPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16984 | 426.1342 | 10610.PI.FB.DI | 4246 | 4486.9543
C322132CIVE000150 | U22 - LT Flare Package Foundation Execution (571-ME-402) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64661 | 6176.5772 | 10610.CI.CO.M3 | 1293.21 | 1293.2092
C322132CIVE000220 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000240 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.021891 | 10610.CI.CO.M3 | 2.47 | 1.76
C322132CIVE000270 | U22 - HC Flare Gas Recovery Compressor Filter Foundation Execution (571-F-701B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.015901 | 10610.CI.CO.M3 | 4.57 | 0
C322132CIVE000280 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.33985 | 10610.CI.CO.M3 | 9.74 | 6.96
C322132CIVE000300 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132FPEQ000040 | U22 - Equipment Fireproofing | FP | FPEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31124 | 0 | 10780.FP.FP.MH
C322132FPSS000050 | U22 - Steel Structure Fireproofing | FP | FPSS | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35760 | 0 | 10780.FP.FP.MH
C322132METK110000 | U22 - TEG Storage Tank Erection 571-TK-201 | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 5.9092 | 10610.ME.TE.TN | 20 | 20
C322132METK110010 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Annular Plate and Bottom Plate Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6500 | 62.4156 | 10610.ME.TE.TN | 65 | 65
C322132METK110040 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 1 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322136MEPA000075 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-6 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2600 | 0 | 10780.ME.ME.MH
C322136MEPA000077 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-8 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2600 | 0 | 10780.ME.ME.MH
C322136MEPA000120 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-2 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 151 | 0
C322136MEPA000140 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-4 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 76 | 0
C322136MEPA000171 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-8 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10780.ME.ME.MH
C322136MEPA000180 | U22 - LT Flare Package Erection 571-ME-402 - Part-4 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 76 | 0
C322136MEPA000200 | U22 - LT Flare Package Erection 571-ME-402 - Part-6 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136METC000060 | U22 - Cranes Erection (EOT Crane For Flare Recovery Package) 571-EOT-401 | ME | METC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C322136MEVV000300 | U22 - Heavy Equipment (Intermediate Hydrocarbon Flare K.O. Drum ) Erection (571-V-301A) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEVV000310 | U22 - LT Flare K.O Drum Erection 571-V-402A (Horizontal) (HL) (1600 + 650 TON) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C322136MEVV000360 | U22 - HC Flare Drain Drum Erection 571-V-404 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 360 | 0 | 10610.ME.ER.TN | 9 | 0
C322136MEVV000370 | U22 - Vertical Vessels (Blowdown Drum) Erection 571-V-505 (Horizontal) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C322136MEVV000380 | U22 - Intermediate Acid Gas Flare Drain Drum Erection 571-V-405 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 440 | 0 | 10610.ME.ER.TN | 11 | 0
C322136MEVV000390 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000400 | U22 - Acid Gas Flare Drain Drum Erection 571-V-406 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 280 | 0 | 10610.ME.ER.TN | 7 | 0
C322136MEVV000410 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000415 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322132METK110070 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Roof Erection including Appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6500 | 35.5769 | 10610.ME.TE.TN | 65 | 37.05
C322132METK110090 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 2 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110110 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 3 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110260 | U22 - TEG Storage Tank Erection 571-TK-201 - Painting | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 260 | 0.099865 | 10780.ME.ME.MH
C322132METK110320 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 1 Erection including Appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110340 | U22 - TEG Storage Tank Erection 571-TK-201 - Insulation | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 260 | 0.099865 | 10780.ME.ME.MH
C322132PLIN000020 | U22 - Piling Installation | PL | PLIN | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4838 | 34.5807 | 10610.PL.PL.UN | 163 | 163
C322132SPSP000000 | U22 - New road and fence preparation | SP | SPSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3640 | 19.5735 | 10780.SP.SP.MH
C322132STEQ000090 | U22 - Miscellaneous Platform Structure Erection (Plt-V401B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 964 | 0 | 10610.ST.PL.TN | 18.18 | 0
C322132STEQ000110 | U22 - Miscellaneous Platform Structure Erection (Plt-V402A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1059 | 0 | 10610.ST.PL.TN | 19.99 | 0
C322132STEQ000130 | U22 - Miscellaneous Piping Tower Structure Erection (571-V402 A/B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1166 | 0 | 10780.ST.ST.MH
C322132STEQ000210 | U22 - Cooler Support Structure Erection (571-E-701B/702B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 530 | 0 | 10780.ST.ST.MH
C322132STEQ000240 | U22 - Miscellaneous Platform Structure Erection (Plt-PR135) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11243 | 0 | 10610.ST.PL.TN | 212.14 | 0
C322132STEQ000250 | U22 - Miscellaneous Platform Structure Erection (Plt-V403 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 749 | 0 | 10610.ST.PL.TN | 14.13 | 0
C322132STEQ000290 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V505) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 795 | 0 | 10610.ST.PL.TN | 0 | 0
C322132STPR000140 | U22 - Main Piperack Erection (571-PR-147) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7546 | 58.1412 | 10610.ST.PR.TN | 142.38 | 136.3372
C322132STPR000150 | U22 - Main Piperack Erection (571-PR-146) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12486 | 175.8499 | 10610.ST.PR.TN | 235.59 | 226.1715
C322132STPR000160 | U22 - Main Piperack Erection (571-PR-151) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7297 | 71.1595 | 10610.ST.PR.TN | 137.68 | 137.677
C322132STPR000170 | U22 - Main Piperack Erection (571-PR-152) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6384 | 54.3246 | 10610.ST.PR.TN | 120.45 | 120.449
C220132BUTRFO100180 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Chiller Foundations (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2193 | 0 | 10610.BU.CO.M3 | 57.5 | 0
C220132BUTRFO100190 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns and Walls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 4.3361 | 10610.BU.CO.M3 | 5.7 | 1.2825
C220132BUTRFO100190 | U20 - SS-523 - Rebar, Formwork & Concrete Pouring for Columns and Walls (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2923 | 4.3361 | 10610.BU.CO.M3 | 5.7 | 1.2825
C220132CICT1100010 | U20 - SS-520 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1820 | 0 | 10610.CI.ET.M3 | 455 | 0
C220132CICT1100030 | U20 - SS-522 - Electrical earth Trenches Execution (Elect. Subst.) | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 708 | 0 | 10610.CI.ET.M3 | 177 | 0
C220132CICT1100100 | U20 - OMS-015 - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3401 | 0 | 10780.CI.CI.MH
C220132CICT1100120 | U20 - OMS-014 - Electrical earth Trenches Execution | CI | CICT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3401 | 0 | 10780.CI.CI.MH
C220132CIFC1100020 | U20 - SS-521 - Install Removable Chain Link Fence and Gates (Elect. Subst.) | BU | BUARSG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4904 | 0 | 10780.BU.BU.MH
C220132CISF100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4789 | 33.5393 | 10610.BU.CO.M3 | 101.47 | 100.4599
C220132CISF100090 | U20 - SS-524 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4789 | 33.5393 | 10610.BU.CO.M3 | 101.47 | 100.4599
C220132CISF100120 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19657 | 0 | 10610.BU.CO.M3 | 50 | 0
C220132CISF100120 | U20 - NMCB - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUTRCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19657 | 0 | 10610.BU.CO.M3 | 50 | 0
C220132CISF100150 | U20 - IES-514 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7324 | 0 | 10610.BU.CO.M3 | 28 | 0
C220132CISF100190 | U20 - IES-513 - Rebar, Formwork & Concrete Pouring for Footings and Columns | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13995 | 289.341 | 10610.BU.CO.M3 | 12 | 12
C220132CISF100200 | U20 - SS-526 - Rebar, Formwork & Concrete Pouring for Staircase and Platforms (Elect. Subst.) | BU | BUSSCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4079 | 0 | 10610.BU.CO.M3 | 39.88 | 0
C220132ELBD100020 | U20 - SS-521 - Bus Ducts Installation (Elect. Subst.) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 3.0885 | 10780.EL.EL.MH
C220132ELCL100011 | U20 - SS-520-CFP1 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 5549.24 | 0
C220132ELCL100012 | U20 - SS-520-CFP2 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4680 | 0 | 10610.EL.PL.LM | 5549.24 | 0
C322136MEVV000420 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000425 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000430 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000440 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000445 | U22 - 571-HM-304, 305 & 317- Hydrant Monitor | ME | MEMC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10800 | 0 | 10610.ME.ER.TN | 180 | 0
C322137INCO000060 | U22 - Communication System Installation | IN | INCO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5397 | 0 | 10780.IN.IN.MH
C322137INCT000120 | U22 - Primary Cable Trays Installation | IN | INCT1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30665 | 0 | 10610.IN.CT.LM | 920 | 0
C322137INCT000130 | U22 - Secondary Cable Trays Installation | IN | INCT2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17172 | 0 | 10610.IN.CT.LM | 500 | 0
C322137INFO000060 | U22 - Fiber Optic Cable Pulling | IN | INFO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4170 | 0 | 10610.IN.FO.LM | 145180 | 0
C322137INFS000070 | U22 - Fire Fighting Equipments Installation | IN | INFS | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3189 | 0 | 10780.IN.IN.MH
C322137INHU000130 | U22 - Pneumatic Hook Up´s Erection | IN | INHU3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3042 | 0 | 10780.IN.IN.MH
C322137INHU000140 | U22 - Process Hook Up´s Erection | IN | INHU1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13493 | 0 | 10780.IN.IN.MH
C322137INML000070 | U22 - Multi Pair Cable Pulling | IN | INML | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38270 | 0 | 10610.IN.MC.LM | 116399.2 | 0
C3230PRPRWT000080 | U23 - Walkthrough | PR | PRWT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2353 | 0 | 10780.PR.PR.MH
C323131ISEQ000050 | U23 - (566 CWS) - Equipment Insulation | IS | ISEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10474 | 0 | 10610.IS.EQ.M2 | 689 | 0
C323131PIBB000090 | U23 - (566 CWS) - Big Bore Piping A/Equip. Erection including Packages | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35931 | 0 | 10610.PI.BB.DI | 3593.08 | 0
C323131PIRA000000 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-102) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000010 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-103) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000020 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-104) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000090 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-101) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C322132STPR000180 | U22 - Main Piperack Erection (571-PR-153) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5810 | 45.5697 | 10610.ST.PR.TN | 109.63 | 109.6311
C322132STPR000190 | U22 - Main Piperack Erection (571-PR-154) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6195 | 47.8729 | 10610.ST.PR.TN | 116.9 | 116.5745
C322132STPR000230 | U22 - Main Piperack Erection (571-PR-142) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4978 | 16.2391 | 10610.ST.PR.TN | 93.92 | 51.6579
C322132STPR000240 | U22 - Main Piperack Erection (571-PR-141) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5765 | 31.4736 | 10610.ST.PR.TN | 108.78 | 92.4631
C322132STPR000260 | U22 - Main Piperack Erection (571-PR-138) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10371 | 119.696 | 10610.ST.PR.TN | 195.68 | 156.5393
C322132STPR000270 | U22 - Main Piperack Erection (571-PR-137) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13793 | 191.924 | 10610.ST.PR.TN | 260.24 | 218.6005
C322132STPR000280 | U22 - Main Piperack Erection (571-PR-145) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7613 | 69.6106 | 10610.ST.PR.TN | 143.64 | 143.6362
C322132STPR000301 | U22 - Main Piperack Erection (571-PB-127) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14181 | 0 | 10610.ST.PR.TN | 267.56 | 0
C322132STPR000302 | U22 - Main Piperack Erection (571-PB-128) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16536 | 0 | 10610.ST.PR.TN | 311.99 | 0
C322132STPR000304 | U22 - Main Piperack Erection (571-PR-130) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8894 | 0 | 10610.ST.PR.TN | 167.8 | 0
C322132STPR000306 | U22 - Main Piperack Erection (571-PR-132) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8068 | 0 | 10610.ST.PR.TN | 152.22 | 0
C322132STPR000307 | U15 - Main Piperack Erection (577-PB-122/577-PR-122A) | ST | STPR | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21894 | 334.3155 | 10610.ST.PR.TN | 413.1 | 258.1815
C322132STPR000310 | U22 - Main Piperack Erection (571-PB-132A) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6955 | 0 | 10610.ST.PR.TN | 131.23 | 0
C322132STPR100000 | U22 - Main Piperack Erection (577-PB-116) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24467 | 876.4594 | 10610.ST.PR.TN | 461.64 | 461.6367
C322132STPR100010 | U22 - Main Piperack Erection (577-PB-114) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33769 | 699.3468 | 10610.ST.PR.TN | 637.16 | 262.0588
C322132STPR100030 | U22 - Main Piperack Erection (577-PR-117) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25497 | 960.3739 | 10610.ST.PR.TN | 481.07 | 480.9397
C322132STPR100040 | U22 - Main Piperack Erection (577-PR-118) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18589 | 492.8489 | 10610.ST.PR.TN | 350.74 | 297.933
C322132STPR100060 | U22 - Main Piperack Erection (577-PR-120) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26395 | 954.2968 | 10610.ST.PR.TN | 498.02 | 448.496
C322132STPR100100 | U22 - Secondary Piperack Erection (571-PR-158) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15635 | 0 | 10610.ST.PR.TN | 0 | 0
C322132STSH000050 | U22 - Compressor Shelter Architecture ( SH- 571-C-701C) | ST | STSH3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2240 | 0 | 10780.ST.ST.MH
C220132ELCL100021 | U20 - SS-521-CFP1 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 13293.91 | 0
C220132ELCL100022 | U20 - SS-521-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 16648.04 | 0
C220132ELCL100030 | U20 - SS-522 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.PL.LM | 1598 | 0
C220132ELCL100031 | U20 - SS-522-CFP1 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 3.2239 | 10610.EL.LC.LM | 5462.34 | 470.8537
C220132ELCL100050 | U20 - SS-526 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 847 | 0 | 10610.EL.PL.LM | 2327.71 | 0
C220132ELCL100061 | U20 - SS-524 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 15.311 | 10610.EL.LC.LM | 10787.56 | 10787.56
C220132ELCL100070 | U20 - SS-525 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.EL.PL.LM | 2354.75 | 0
C220132ELCL100080 | U20 - SS-522 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 2.615 | 10610.EL.PL.LM | 32774.66 | 2248.3417
C220132ELCL100082 | U20 - SS-522-CFP2 - Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 16387.33 | 0
C220132ELCL1001 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-516 to SS-524 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 604 | 0
C220132ELCL100101 | U20 - SS-521-CFP1- Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4544 | 0 | 10610.EL.PL.LM | 4431.41 | 0
C220132ELCL100110 | U20 - NMCB - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 41475 | 0 | 10610.EL.PL.LM | 43045.95 | 0
C220132ELCL100141 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 30 | 0
C220132ELCL100142 | U20 - SS-524 - Main Power Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3564 | 0 | 10610.EL.LC.LM | 601 | 0
C220132ELCL100160 | U20 - IES-513 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9041 | 0 | 10610.EL.PL.LM | 16574.65 | 0
C220132ELCL100170 | U20 - SS-525 - Main Power Electrical Cable Laying from SS-504 to SS-525 (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.EL.PL.LM | 785.35 | 0
C220132ELCL100190 | U20 - SS-523 - Main Power Electrical Cable Laying (Elect. Subst.) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.EL.PL.LM | 5527.03 | 0
C220132ELCL100240 | U20 - OMS-014 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1496 | 0 | 10610.EL.PL.LM | 2743.56 | 0
C220132ELCL100260 | U20 - OMS-014 - Main Power Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1496 | 0 | 10610.EL.PL.LM | 2743.56 | 0
C323131PISB000000 | U23 - (566 CWS) - Small Bore Piping A/Tanks 566-TK-201 | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12434 | 0 | 10610.PI.SB.DI | 1130.35 | 0
C323131PISB000091 | U23 - (566 CWS) - Small Bore Piping A/Equip. Erection including Packages | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12434 | 0 | 10610.PI.SB.DI | 1130.35 | 0
C323131PRBO000120 | U23 - Static Box Up | PR | PRBO1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21414 | 0 | 10780.PR.PR.MH
C323131PRFL000080 | U23 - Piping Flushing/Blowing | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6578 | 0 | 10610.PR.FL.DI | 151729 | 0
C323131PRFL000260 | U23 - Lube Oil Flushing for Compressors (Unit 566) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2077 | 0 | 10780.PR.PR.MH
C323131PRHT000090 | U23 - Piping Hydrotesting (573) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52603 | 0 | 10610.PR.HT.DI | 76525 | 0
C323131PRHT000100 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Hydrotesting and Settlement Check | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18787 | 0 | 10780.PR.PR.MH
C323131PRRE000010 | U23 - Piping Reinstatement (567) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12826 | 0 | 10610.PR.RE.DI | 14690 | 0
C323131PRRE000090 | U23 - Piping Reinstatement (573) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65528 | 0 | 10610.PR.RE.DI | 76525 | 0
C323131PRRE000120 | U23 - Piping Reinstatement (566) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44664 | 0 | 10610.PR.RE.DI | 60514 | 0
C323132CICT000100 | U23 - (566 CWS) - Electrical earth Trenches Execution | CI | CICT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9509 | 15.6287 | 10780.CI.CI.MH
C323132CICT100020 | U23 - (567 UPW) - Covered Concrete Trenches Execution | CI | CICT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1021 | 0.43813 | 10780.CI.CI.MH
C323132CIDB100015 | U23 - (567 UPW) - Duct Banks Precast Installation | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16628 | 295.5098 | 10610.CI.CO.M3 | 332.55 | 332.55
C323132CIDM200000 | U23 - (573 FWS) - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15 | 0.00033239 | 10780.CI.CI.MH
C323132CIGR000090 | U23 - (566 CWS) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 322 | 0.01571 | 10610.CI.GR.LM | 537 | 0
C323132CIGR000090 | U23 - (566 CWS) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 322 | 0.01571 | 10610.CI.GR.LM | 537 | 0
C323132CIGT100000 | U23 - (567 UPW) - Equipment Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.CI.CI.MH
C323132CIMF000080 | U23 - (566 CWS) - Miscellaneous Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8395 | 81.9936 | 10610.CI.CO.M3 | 139.92 | 139.92
C323132CIMF000100 | U23 - (566 CWS) - Deluge Valve Skid (DVS) foundation execution (DVS) | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6973 | 23.956 | 10610.CI.CO.M3 | 116.22 | 40
C323132CIMF100030 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101F-F01-V01/02/03 ) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.4247 | 10610.CI.CO.M3 | 37.48 | 37.4801
C322133PAFP000080 | U22 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6176 | 0 | 10780.PA.PA.MH
C322133PASP000080 | U22 - Piping Supports SandBl. & Priming | PA | PASP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6814 | 4.7122 | 10610.PA.SU.TN | 0 | 0
C322133PAST000080 | U22 - Steel Structure Painting Touch Up | PA | PAST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14601 | 0 | 10780.PA.PA.MH
C322134ELCO000150 | U22 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 49042 | 0 | 10610.EL.CO.UN | 1552 | 0
C322134ELEL000085 | U22 - Earthing Works | EL | ELEL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10898 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C322134ELEQ000040 | U22 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.EQ.UN | 520 | 0
C322134ELGR000080 | U22 - Grounding Installation | EL | ELEL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10898 | 0 | 10780.EL.EL.MH
C322134ELPL000070 | U22 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26564 | 0 | 10780.EL.EL.MH
C322134ELTI000140 | U22 - Lighting Cable Trays Installation | EL | ELTI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.CT.LM | 6177.24 | 0
C322134PRMR000060 | U22 - Motor Solo Run | PR | PRMR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2229 | 0 | 10780.PR.PR.MH
C322136MEAC000070 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701A | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C322136MEAC000110 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Pre-Assembly 571-E-701B | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000150 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701B | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000180 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702C | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000190 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701C) | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEAC000210 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701B) | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MECO000080 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701A (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MECO000100 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701C (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEHE000120 | U22 - Heat Exchangers (Intermediate LT Flare K.O Drum Heater) Erection 571-E-302A | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C220132ELCL1005 | U20 - Main Power Electrical (132 KV) Cable Laying from SS-524 to SS-522 | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5483 | 0 | 10610.EL.LC.LM | 1598 | 0
C220132ELCO100040 | U20 - SS-521 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17350 | 0 | 10780.EL.EL.MH
C220132ELCO100050 | U20 - SS-524 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11663 | 0 | 10780.EL.EL.MH
C220132ELCO100100 | U20 - OMS-013 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1453 | 0 | 10780.EL.EL.MH
C220132ELCO100120 | U20 - IES-513 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9863 | 0 | 10780.EL.EL.MH
C220132ELEL100010 | U20 - SS-520 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100020 | U20 - SS-521 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2892 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100030 | U20 - SS-524 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100050 | U20 - SS-526 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10610.EL.ES.LM | 4931.57 | 0
C220132ELEL100060 | U20 - NMCB - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10610.EL.ES.LM | 9863.14 | 0
C220132ELEL100070 | U20 - SS-525 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 156 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C220132ELEL100080 | U20 - SS-523 - Install Earthing & Lightning Distribution System (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 871 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C220132ELEL100110 | U20 - IES-514 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2211 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C220132ELEL100120 | U20 - OMS-013 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEL100130 | U20 - OMS-015 - Install Earthing & Lightning Distribution System | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10610.EL.ES.LM | 821.93 | 0
C220132ELEQ1100270 | U20 - SS-522 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3271 | 0 | 10780.EL.EL.MH
C220132ELEQ1100310 | U20 - SS-522 - UPS/Batteries/Misc. Eq. Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3271 | 0 | 10780.EL.EL.MH
C220132ELEQ1100320 | U20 - NMCB - UPS/Batteries/Misc. Eq. Installation | EL | ELEQ1 | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 28278 | 0 | 10780.EL.EL.MH
C323132CIMF100040 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101G-F01-V01/02/03 ) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.3421 | 10610.CI.CO.M3 | 37.48 | 37.48
C323132CIMF100050 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101G-F01) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.2949 | 10610.CI.CO.M3 | 37.48 | 37.4798
C323132CIOT200000 | U23 - (573 FWS) - Open Concrete Trenches Execution | CI | CIOT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 100 | 0 | 10780.CI.CI.MH
C323132CIPD100000 | U23 - (567 UPW) - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4098 | 24.8091 | 10780.CI.CI.MH
C323132CIPD200000 | U23 - (573 FWS) - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1062 | 0.42487 | 10780.CI.CI.MH
C323132CIPE000080 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201C-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000090 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201C-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000100 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201C-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.68
C323132CIPE000240 | U23 - (566 CWS) - Cooling Water Chemical Dosing Package Foundation execution (566-ME-202) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4534 | 30.3703 | 10610.CI.CO.M3 | 75.57 | 75.57
C323132CIPE100010 | U23 - (567 UPW) - Instrument Air Dryer Pck. Foundations Execution (567-ME-102D) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1710 | 4.2247 | 10610.CI.CO.M3 | 28.5 | 28.5
C323132CIPE100010 | U23 - (567 UPW) - Instrument Air Dryer Pck. Foundations Execution (567-ME-102D) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1710 | 4.2247 | 10610.CI.CO.M3 | 28.5 | 28.5
C323132CIPE100020 | U23 - (567 UPW) - Air Gas Compressor Skid Foundations Execution-(567-ME-101F-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIPR000330 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-102) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96751 | 13828.5716 | 10610.CI.CO.M3 | 1935.02 | 1935.02
C323132CIPT000060 | U23 - (566 CWS) - Pipe Tracks Execution (Sleepers) | CI | CIPT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5660 | 2.9579 | 10780.CI.CI.MH
C323132CIPT200000 | U23 - (573 FWS) - Pipe Tracks Execution | CI | CIPT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11645 | 178.3405 | 10610.CI.CO.M3 | 194.08 | 173.3092
C323132CIPV000220 | U23 - (566 CWS) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23252 | 89.856 | 10610.CI.PV.M2 | 12918 | 0
C323132CIPV000220 | U23 - (566 CWS) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23252 | 89.856 | 10610.CI.PV.M2 | 12918 | 0
C323132CIRE000130 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2655 | 1.2236 | 10610.CI.CO.M3 | 44.25 | 0
C322136MEHE000130 | U22 - Heat Exchangers (LT Flare K.O Drum Heater) Erection 571-E-402B | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHL000050 | U22 - Heavy Equipment (Hydrocarbon Flare K.O. Drum) Erection (571-V-401B) (HL) (1600 + 650 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7400 | 2.1292 | 10610.ME.ER.TN | 185 | 0
C322136MEHL000060 | U22 - Heavy Equipment (Intermediate Hydrocarbon Flare K.O. Drum) Erection (571-V-301B) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEHL000080 | U22 - Heavy Equipment (Intermediate LT K.O. Drum ) Erection (571-V-302B) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEHL000100 | U22 - Heavy Equipment (Hydrocarbon Flare K.O. Drum) Erection (571-V-401A) (HL) (1600 + 650 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7400 | 2.1292 | 10610.ME.ER.TN | 185 | 0
C322136MEHM000250 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000260 | U22 - Horizontal Pump (Intermediate Acid Gas Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-303A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000270 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401A (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000290 | U22 - Horizontal Pump (Acid Gas Flare K.O Drum Pump) with Electrical Motor Erection 571-P-403A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000310 | U22 - Horizontal Pump (Blowdown Drum HC Pump) with Electrical Motor Erection 571-P-503A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000320 | U22 - Horizontal Pump (Blowdown Drum Sour Water Pump) with Electrical Motor Erection 571-P-504A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000360 | U22 - Horizontal Pump (Blowdown Drum HC Pump) with Electrical Motor Erection 571-P-503B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000400 | U22 - Horizontal Pump with Electrical Motor Erection 571-P-701C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000410 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000430 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000450 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C220132ELEQ1100510 | U20 - IES-513 - U20 - IES-513 - Electrical Equipment Installation | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6164 | 0 | 10780.EL.EL.MH
C220132ELEQ1100550 | U20 - OMS-014 - Distribution Panel Installation | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1020 | 0 | 10780.EL.EL.MH
C220132ELGR100010 | U20 - NMCB - Building Grounding Install. | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10780.EL.EL.MH
C220132ELTI100012 | U20 - SS-521-CFP2 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4819 | 6.8961 | 10780.EL.EL.MH
C220132ELTI100020 | U20 - SS-520 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5673 | 25.3171 | 10780.EL.EL.MH
C220132ELTI100022 | U20 - SS-520-CFP2 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5673 | 2.8526 | 10780.EL.EL.MH
C220132ELTI100031 | U20 - SS-524 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 13.9176 | 10780.EL.EL.MH
C220132ELTI100050 | U20 - SS-522 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5815 | 0 | 10780.EL.EL.MH
C220132ELTI100070 | U20 - NMCB - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37704 | 0 | 10780.EL.EL.MH
C220132ELTI100080 | U20 - OMS-013 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1211 | 0.26541 | 10780.EL.EL.MH
C220132ELTI100090 | U20 - SS-523 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4357 | 0 | 10780.EL.EL.MH
C220132ELTI100110 | U20 - IES-513 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8219 | 0 | 10780.EL.EL.MH
C220132ELTR100010 | U20 - SS-524 - Transformer Inst. 580-EE-2413 A/B, 580-2422 A/B (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2916 | 0 | 10780.EL.EL.MH
C220132ELTR100020 | U20 - SS-521 - Transformer Inst. 543-EE-2123/2024 A/B, 580-EE-2114/2115/2116/2121/2122 A/B (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8675 | 0 | 10780.EL.EL.MH
C220132ELTR100030 | U20 - SS-520 - Transformer Inst. 543-EE-2021/23/24, 580-EE-2014/15/16/17/18/21/22, 542-EE-2021/22/23/24 (Elect. Subst.) | EL | ELTR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10211 | 0 | 10780.EL.EL.MH
C220132HVIN100080 | U20 - SS-521 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2308 | 0 | 10780.BU.BU.MH
C220132HVIN100100 | U20 - SS-520 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2544 | 0 | 10780.BU.BU.MH
C220132HVIN100140 | U20 - SS-522 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8617 | 0 | 10780.BU.BU.MH
C220132HVIN100210 | U20 - SS-525 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 664 | 0 | 10780.BU.BU.MH
C220132ELEQ1100420 | U20 - SS-526 - Distribution Panels Installation (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 144 | 0 | 10780.EL.EL.MH
C220132ELEQ1100480 | U20 - OMS-013 - Distribution Panels Installation | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 908 | 0 | 10780.EL.EL.MH
C220132ELEQ1100530 | U20 - OMS-015 - Distribution Panels Installation | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2338 | 0 | 10780.EL.EL.MH
C220132ELTI100021 | U20 - SS-520 -CFP1- Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5673 | 6.8226 | 10780.EL.EL.MH
C220132ELTI100030 | U20 - SS-524 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 15.5071 | 10780.EL.EL.MH
C220132ELTI100032 | U20 - SS-524 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3240 | 11.7077 | 10780.EL.EL.MH
C220132ELTI100051 | U20 - SS-522-CFP1- Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5815 | 7.8876 | 10780.EL.EL.MH
C220132ELTI100052 | U20 - SS-522-CFP2 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5815 | 0.78881 | 10780.EL.EL.MH
C220132ELTI100120 | U20 - OMS-015 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3118 | 0 | 10780.EL.EL.MH
C220132ELTI100130 | U20 - OMS-014 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1360 | 0 | 10780.EL.EL.MH
C220132HVIN100090 | U20 - SS-524 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1368 | 0 | 10780.BU.BU.MH
C220132HVIN100120 | U20 - SS-524 -HVAC Duckwork/Pipes Installation (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3420 | 6.6135 | 10780.BU.BU.MH
C220132HVIN100150 | U20 - SS-526 -Equipment Erection Chillers (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132HVIN100290 | U20 - OMS-013 -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 545 | 0 | 10780.BU.BU.MH
C220132HVIN100300 | U20 - SS-526 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 979 | 0 | 10780.BU.BU.MH
C220132HVIN100360 | U20 - SS-525 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 195 | 0 | 10780.BU.BU.MH
C220132HVIN100410 | U20 - IES-514 -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6866 | 0 | 10780.BU.BU.MH
C220132HVIN100460 | U20 - SS-522 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5745 | 0 | 10780.BU.BU.MH
C220132HVIN100480 | U20 - SS-523 -HVAC Connections (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 609 | 0 | 10780.BU.BU.MH
C220132HVIN100490 | U20 - SS-524 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 798 | 0 | 10780.BU.BU.MH
C323132CIRE000140 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2655 | 1.2236 | 10610.CI.CO.M3 | 44.25 | 0
C323132CIRE000160 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323132CIRE000170 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323132CIRE000190 | U23 - (566 CWS) - Propane transfer pump foundation execution (566-P-202A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 648 | 0.072871 | 10610.CI.CO.M3 | 9.26 | 0
C323132CIRE000200 | U23 - (566 CWS) - Propane transfer pump foundation execution (566-P-202B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 648 | 0.072871 | 10610.CI.CO.M3 | 9.26 | 0
C323132CIRE200000 | U23 - (573 FWS) - Fire Water Pump Foundation Execution (573-P-201) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1383 | 2.6791 | 10610.CI.CO.M3 | 19.76 | 19.76
C323132CISF000050 | U23 - (566 CWS) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18542 | 59.6784 | 10610.CI.CO.M3 | 370.84 | 242.47
C323132CISF000050 | U23 - (566 CWS) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18542 | 59.6784 | 10610.CI.CO.M3 | 370.84 | 242.47
C323132CITF200000 | U23 - (573 FWS) - Fire Water Tank Foundation Execution (573-TK-201) | CI | CITF1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11877 | 208.3984 | 10610.CI.CO.M3 | 197.96 | 197.9606
C323132CIUG000120 | U23 - (566 CWS) - UG GRE Pipe Installation (FW) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7680 | 46.7127 | 10780.CI.CI.MH
C323132CIUG100010 | U23 - (567 UPW) - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10962 | 177.5195 | 10610.CI.CO.M3 | 182.7 | 182.7
C323132CIUG100020 | U23 - (567 UPW) - UG Civil Works | CI | CIUG1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2873 | 3.3533 | 10780.CI.CI.MH
C323132CIUG200000 | U23 - (573 FWS) - UG GRE Pipe Installation (FW) - Part A | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 405190 | 17181.5493 | 10610.CI.UG.LM | 20259.5 | 1215.57
C323132CIUG200010 | U23 - (573 FWS) - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1092 | 0 | 10610.CI.CO.M3 | 15.6 | 0
C323132CIUG200120 | U23 - (573 FWS) - UG Civil Works (System description) - Part B | CI | CIUG1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1429 | 0 | 10780.CI.CI.MH
C323132CIVE100050 | U23 - (567 UPW) - Plant Air Receiver Foundations Execution (567-V-202) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18193 | 479.9029 | 10610.CI.CO.M3 | 363.85 | 363.85
C323132ELCI100000 | U23 - (567 UPW) - Conduits Installation | EL | ELCI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2254 | 0 | 10780.EL.EL.MH
C323132ELCL100000 | U23 - (567 UPW) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19837 | 196.3758 | 10610.EL.PL.LM | 40576.62 | 14755.2821
C323132ELCL200000 | U23 - (573 FWS) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2582 | 0 | 10610.EL.PL.LM | 5438.2 | 0
C220132HVIN100330 | U20 - SS-523 - Install Air Handling Units (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 731 | 0 | 10780.BU.BU.MH
C220132HVIN100350 | U20 - IES-513 -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3181 | 1.6119 | 10780.BU.BU.MH
C220132HVIN100420 | U20 - NMCB -HVAC Duckwork/Pipes Installation | BU | HVIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 0 | 10780.BU.BU.MH
C220132HVIN100450 | U20 - NMCB - Install Air Handling Units | BU | HVIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 0 | 10780.BU.BU.MH
C220132HVIN100550 | U20 - NMCB -HVAC Connections | BU | HVIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 0 | 10780.BU.BU.MH
C220132HVIN100560 | U20 - IES-513 -HVAC Connections | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1484 | 0 | 10780.BU.BU.MH
C220132HVIN100650 | U20 - NMCB -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10780.BU.BU.MH
C220132HVIN100670 | U20 - OMS-015 -HVAC Connections | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 388 | 0 | 10780.BU.BU.MH
C220132HVIN100700 | U20 - OMS-014 -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 337 | 0 | 10780.BU.BU.MH
C220132INCC100010 | U20 - NMCB - Machine Monitoring System Installation | IN | INCC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCC100030 | U20 - IES-514 - System Cabinets & Consoles Installation | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCO100020 | U20 - SS-520 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2781 | 0.4056 | 10780.IN.IN.MH
C220132INCO100060 | U20 - NMCB - Communication System Installation | IN | INCO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7705 | 0 | 10780.IN.IN.MH
C220132INCO100110 | U20 - OMS-015 - Communication System Installation | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2397 | 0 | 10780.IN.IN.MH
C220132INCT2100020 | U20 - IES-513 - Instrument Trays Installation | IN | INCT2 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24516 | 0 | 10780.IN.IN.MH
C220132INFG100030 | U20 - SS-524 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2793 | 5.6756 | 10780.IN.IN.MH
C220132INFG100040 | U20 - SS-526 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10780.IN.IN.MH
C220132INFG100150 | U20 - NMCB - Fire Fighting Equipment Installation | IN | INFG | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C220132INFG100180 | U20 - OMS-013 - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 694 | 0 | 10780.IN.IN.MH
C220132INFG100200 | U20 - OMS-015 - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2266 | 0 | 10780.IN.IN.MH
C220132INFG100260 | U20 - OMS-014 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10780.IN.IN.MH
C322136MEHM000460 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000490 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401D (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000510 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402C (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000530 | U22 - Horizontal Sour Oily Water Pump (571-P-701 E) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000540 | U22 - Horizontal Sour Oily Water Pump (571-P-701 F) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHV000190 | U22 - HC Flare Gas Recovery Compressor Filter 571-F-701A/B | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10610.ME.ER.TN | 4 | 0
C322136MEPA000061 | U22 - LT Flare Package stick built 571-ME-402 - Part-2 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 19.98 | 10780.ME.ME.MH
C322136MEPA000065 | U22 - LT Flare Package stick built 571-ME-402 - Part-6 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 14.3951 | 10780.ME.ME.MH
C322136MEPA000067 | U22 - LT Flare Package stick built 571-ME-402 - Part-8 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3715 | 0 | 10780.ME.ME.MH
C322136MEPA000070 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-1 (HL) (320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8358 | 84.367 | 10610.ME.ER.TN | 212 | 180.2
C322136MEPA000100 | U22 - LT Flare Package Erection 571-ME-402 - Part-2 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0.013252 | 10610.ME.ER.TN | 151 | 0
C322136MEPA000110 | U22 - LT Flare Package Erection 571-ME-402 - Part-3 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 123 | 0
C322136MEPA000160 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-6 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000190 | U22 - LT Flare Package Erection 571-ME-402 - Part-5 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000200 | U22 - LT Flare Package Erection 571-ME-402 - Part-6 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136METC000060 | U22 - Cranes Erection (EOT Crane For Flare Recovery Package) 571-EOT-401 | ME | METC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C322136MEVV000250 | U22 - Heavy Equipment (Intermediate LT K.O. Drum ) Erection (571-V-302A) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C323132ELCO100000 | U23 - (567 UPW) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10820 | 10.0125 | 10610.EL.CO.UN | 405 | 0
C323132ELEL100010 | U23 - (567 UPW) - Lighting Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3607 | 0 | 10780.EL.EL.MH
C323132ELEQ100000 | U23 - (567 UPW) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2705 | 0 | 10610.EL.EQ.UN | 300 | 0
C323132INAI100000 | U23 - (567 UPW) - Analyzers Equipment Installation | IN | INAI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 216 | 0 | 10610.IN.AI.UN | 1 | 0
C323132INAI200000 | U23 - (573 FWS) - Analyzers Equipment Installation | IN | INAI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2360 | 0 | 10610.IN.AI.UN | 1 | 0
C323132INCT100010 | U23 - (567 UPW) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 561 | 0 | 10610.IN.CT.LM | 540 | 0
C323132INFO100000 | U23 - (567 UPW) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 49622 | 0
C323132INFO200000 | U23 - (573 FWS) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1486 | 0 | 10610.IN.FO.LM | 830 | 0
C323132INGC200010 | U23 - (573 FWS) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4546 | 0 | 10610.IN.CO.UN | 380 | 0
C323132INHU200000 | U23 - (573 FWS) - Pneumatic Hook Up´s Erection | IN | INHU3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1101 | 0 | 10780.IN.IN.MH
C323132INHU200010 | U23 - (573 FWS) - Process Hook Up´s Erection | IN | INHU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4808 | 0 | 10780.IN.IN.MH
C323132ININ100000 | U23 - (567 UPW) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 321 | 0 | 10610.IN.IN.UN | 420 | 0
C323132ININ200000 | U23 - (573 FWS) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3497 | 0 | 10610.IN.IN.UN | 800 | 0
C323132ININ200001 | U23 - (567 UPW) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 321 | 0 | 10610.IN.IN.UN | 360 | 0
C323132INJB100000 | U23 - (567 UPW) - Junction Boxes & Local Panels Install. | IN | INJB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 417 | 0 | 10780.IN.IN.MH
C323132INML100000 | U23 - (567 UPW) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1250 | 0 | 10610.IN.MC.LM | 5087.65 | 0
C323132INML200000 | U23 - (573 FWS) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13638 | 0 | 10610.IN.MC.LM | 70337.59 | 0
C323132INRI200000 | U23 - (573 FWS) - Prefabricated RIB´s Installation | IN | INRI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 280 | 0 | 10780.IN.IN.MH
C323132INSL200000 | U23 - (573 FWS) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10928 | 0 | 10610.IN.SC.LM | 764.82 | 0
C323132MEMC100005 | U23 - (567 UPW) - Miscellaneous Electrical | EL | ELEQ2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1353 | 0 | 10780.EL.EL.MH
C220132INFO100010 | U20 - IES-514 - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132INFO100020 | U20 - IES-513 - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132INGC100050 | U20 - NMCB - Fiber Optic Gland & Connection | IN | INGC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 18212 | 0 | 10780.IN.IN.MH
C220132INGC100060 | U20 - IES-513 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27318 | 0 | 10780.IN.IN.MH
C220132MEMC100060 | U20 - SS-520 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10780.EL.EL.MH
C220132MEMC100090 | U20 - NMCB - Miscellaneous Structure Works | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 19.2376 | 10610.BU.CO.M3 | 300 | 87
C220132MEMC100090 | U20 - NMCB - Miscellaneous Structure Works | BU | BUCTCS | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6701 | 19.2376 | 10610.BU.CO.M3 | 300 | 87
C220132MEMC100140 | U20 - SS-524 - Switchgear Installation 132 KV Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 0 | 10780.EL.EL.MH
C220132MEMC100141 | U20 - SS-524 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 1.3128 | 10780.EL.EL.MH
C220132MEMC100210 | U20 - OMS-013 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 436 | 0 | 10610.BU.CO.M3 | 1 | 0
C220132MEMC100210 | U20 - OMS-013 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 436 | 0 | 10610.BU.CO.M3 | 1 | 0
C220132MEMC100280 | U20 - SS-526 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10780.EL.EL.MH
C220132MEMC100290 | U20 - IES-514 - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2211 | 0 | 10780.EL.EL.MH
C220132MEMC100340 | U20 - OMS-014 - Pipes & Fittings | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0 | 10780.ME.ME.MH
C220132MEMC100350 | U20 - NMCB - Switchgear, MDB & DB's Installation | EL | ELEL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6033 | 0 | 10780.EL.EL.MH
C220132MEMC100460 | U20 - OMS-015 - Sanitary Wares | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0 | 10780.ME.ME.MH
C220132MEMC100480 | U20 - OMS-014 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 577 | 0 | 10610.BU.CO.M3 | 0.94 | 0
C220132MEMC100490 | U20 - IES-513 - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2192 | 0 | 10780.EL.EL.MH
C220132STSH2100010 | U20 - SS-524 - Install Roof Structure and Corrugated Steel Sheeting (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3306 | 0 | 10780.BU.BU.MH
C220132STSH210007 | U20 - SS-516 - Transf. Roof Structure (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41199 | 387.4077 | 10780.BU.BU.MH
C220132HVIN100500 | U20 - SS-522 -HVAC System Functional Test (Elect. Subst.) | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1915 | 0 | 10780.BU.BU.MH
C220132HVIN100590 | U20 - OMS-013 -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 254 | 0 | 10780.BU.BU.MH
C220132HVIN100610 | U20 - IES-514 -HVAC Connections | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2136 | 0 | 10780.BU.BU.MH
C220132HVIN100620 | U20 - IES-513 -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 742 | 0 | 10780.BU.BU.MH
C220132HVIN100660 | U20 - OMS-014 - Install Air Handling Units | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 577 | 0 | 10780.BU.BU.MH
C220132HVIN100680 | U20 - OMS-014 -HVAC Connections | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 337 | 0 | 10780.BU.BU.MH
C220132HVIN100690 | U20 - OMS-015 -HVAC System Functional Test | BU | HVIN | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 388 | 0 | 10780.BU.BU.MH
C220132INCC100040 | U20 - IES-514 - Machine Monitoring System Installation | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCC100050 | U20 - IES-513 - System Cabinets & Consoles Installation | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1681 | 0 | 10780.IN.IN.MH
C220132INCO100030 | U20 - SS-524 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2954 | 2.72 | 10780.IN.IN.MH
C220132INCO100070 | U20 - SS-525 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.IN.IN.MH
C220132INCO100090 | U20 - IES-513 - Communication System Installation | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7705 | 3.1135 | 10780.IN.IN.MH
C220132INCO100120 | U20 - SS-523 - Communication System Installation (Elect. Subst.) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2738 | 0 | 10780.IN.IN.MH
C220132INDC100020 | U20 - IES-514 - DCS/VMS/ESD Cabinets Installation | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1814 | 0 | 10780.IN.IN.MH
C220132INFG100010 | U20 - SS-520 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3287 | 3.4317 | 10780.IN.IN.MH
C220132INFG100050 | U20 - SS-521 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 570 | 0 | 10780.IN.IN.MH
C220132INFG100060 | U20 - SS-520 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.0056506 | 10780.IN.IN.MH
C220132INFG100070 | U20 - SS-522 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2658 | 0 | 10780.IN.IN.MH
C220132INFG100090 | U20 - SS-524 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 698 | 0.35267 | 10780.IN.IN.MH
C220132INFG100100 | U20 - IES-514 - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1518 | 0 | 10780.IN.IN.MH
C322136MEVV000300 | U22 - Heavy Equipment (Intermediate Hydrocarbon Flare K.O. Drum ) Erection (571-V-301A) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEVV000310 | U22 - LT Flare K.O Drum Erection 571-V-402A (Horizontal) (HL) (1600 + 650 TON) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 0 | 10610.ME.ER.TN | 200 | 0
C322136MEVV000320 | U22 - Intermediate HC Flare Drain Drum Erection 571-V-304 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 360 | 0 | 10610.ME.ER.TN | 9 | 0
C322136MEVV000370 | U22 - Vertical Vessels (Blowdown Drum) Erection 571-V-505 (Horizontal) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ME.ER.TN | 27 | 0
C322136MEVV000390 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000415 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000440 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000450 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000455 | U22 - 571-FH-303, 306, 307 & 309- Fire Hydrant | ME | MEMC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C322136MEVV000460 | U22 - LT Flare K.O Drum Erection 571-V-402B (Horizontal) (HL) (1600 + 650 TON) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 9.952 | 10610.ME.ER.TN | 200 | 0
C322136MEVV000460 | U22 - LT Flare K.O Drum Erection 571-V-402B (Horizontal) (HL) (1600 + 650 TON) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 9.952 | 10610.ME.ER.TN | 200 | 0
C322136MEVV000465 | U22 - 571-FM-303, 308 & 309- Fire Monitor | ME | MEMC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14400 | 0 | 10610.ME.ER.TN | 240 | 0
C322137INCT000120 | U22 - Primary Cable Trays Installation | IN | INCT1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30665 | 0 | 10610.IN.CT.LM | 920 | 0
C322137INCT000130 | U22 - Secondary Cable Trays Installation | IN | INCT2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17172 | 0 | 10610.IN.CT.LM | 500 | 0
C322137INFC000070 | U22 - Fiber Optic Gland & Conn./Testing | IN | INFC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2944 | 0 | 10610.IN.CO.UN | 320 | 0
C322137ININ000071 | U22 - Valve Installation | IN | ININ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10610.IN.IN.UN | 764 | 0
C322137INIP000070 | U22 - Instruments Calibration | IN | INIP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3189 | 0 | 10780.IN.IN.MH
C322137INSL000070 | U22 - Single Pair Cable Pulling | IN | INSL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30665 | 0 | 10610.IN.SC.LM | 77599.46 | 0
C322137MEMC000120 | U22 - Miscellaneous Instrumentation | IN | ININ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10780.IN.IN.MH
C323132MEMC200005 | U23 - (573 FWS) - Miscellaneous Piping | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 976 | 0 | 10780.PI.PI.MH
C323132MEMC200045 | U23 - (573 FWS) - Miscellaneous Instrumentation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3497 | 0 | 10780.IN.IN.MH
C323132MEPA100000 | U23 - (567 UPW) - Package (Air gas compressor stage 1/2/3) Installation (567-ME-101G-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323132MEPA100090 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101F-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100100 | U23 - (567 UPW) - 2nd stage suction moisture separator (567-ME-101G-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100130 | U23 - (567 UPW) - Instrument Air Dryer Package Installation 567-ME-102D | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1800 | 0.25191 | 10610.ME.ER.TN | 30 | 0
C323132MEVV100010 | U23 - (567 UPW) - Vertical Vessels (Plant Air Receiver) Erection 567-V-202 | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 440 | 0.21074 | 10610.ME.ER.TN | 11 | 11
C323132PAPP200000 | U23 - (573 FWS) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9669 | 17.3606 | 10610.PA.PP.M2 | 0 | 0
C323132PASP100000 | U23 - (567 UPW) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 579 | 0.065997 | 10610.PA.SU.TN | 0 | 0
C323132PAST200000 | U23 - (573 FWS) - Steel Structure Painting Touch Up | PA | PAST | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2743 | 0 | 10780.PA.PA.MH
C323132PIBB100000 | U23 - (567 UPW) - Big Bore Piping A/Equip. Erection | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39766 | 0 | 10610.PI.BB.DI | 3976.6 | 0
C323132PIBB200000 | U23 - (573 FWS) - Big Bore Piping A/Equip. Erection | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320319 | 198.5649 | 10610.PI.BB.DI | 32031.85 | 99.9394
C323132PIPR200000 | U23 - (573 FWS) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 438367 | 162495.5274 | 10610.PI.FB.DI | 109591.67 | 48403.3386
C323132PIRA100000 | U23 - (567 UPW) - Piping Erection on Rack 567-PR-101 / 567-PR-102 / 567-PB-101 | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64298 | 0 | 10610.PI.PR.DI | 7144.23 | 0
C323132PISB100000 | U23 - (567 UPW) - Small Bore Piping A/Equip. Erection | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6278 | 0 | 10610.PI.SB.DI | 570.75 | 0
C323132PISB200000 | U23 - (573 FWS) - Small Bore Piping A/Equip. Erection | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5840 | 0 | 10610.PI.SB.DI | 530.95 | 0
C323132PIUG100000 | U23 - (566 UPW) - Piping Erection UG | PI | PIUG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 198 | 0 | 10610.PI.UG.DI | 132 | 0
C323132PIUG200000 | U23 - (573 FWS) - Piping Erection UG | PI | PIUG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2307 | 0 | 10610.PI.UG.DI | 1538 | 0
C323132SPSP100000 | U23 - (573 FWS) - U/G Detection works and re-routing of existing services | SP | SPSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1386 | 2.8379 | 10610.SP.SP.M3 | 27.7 | 27.7
C220134ELBD000700 | U20 - SS-516 - Bus Ducts Installation for Transformer #B (Pre-Shutdown) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17 | 0 | 10780.EL.EL.MH
C220134ELCL000372 | U20 - SS-516 - Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10780.EL.EL.MH
C220134ELCL000380 | U20 - SS-500 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 3.8838e-06 | 10780.EL.EL.MH
C220134ELCL000381 | U20 - SS-500 - Electrical (132 KV) Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 0 | 10780.EL.EL.MH
C220134ELCL000400 | U20 - SS-504 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134ELCL000450 | U20 - Ruwais - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.EL.EL.MH
C220134ELCO000100 | U20 - SS-512 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5066 | 0 | 10780.EL.EL.MH
C220134ELCO000130 | U20 - SS-012 - Electrical Cable Gland & Conn./Testing (Elect. Subst.) | EL | ELCO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3836 | 0 | 10780.EL.EL.MH
C220134ELCO000150 | U20 - SS-502 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELCO000320 | U20 - SS-516 - Electrical Cable Gland & Conn./Testing (Shutdown) for Transformer #B | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 102 | 0 | 10780.EL.EL.MH
C220134ELCO000340 | U20 - SS-503 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4095 | 0 | 10780.EL.EL.MH
C220134ELCO000350 | U20 - SS-504 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134ELEQ000170 | U20 - SS-515 - New GTG Auxiliary Transformers 1MVA | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELEQ000180 | U20 - SS-515 - New GTG AC & DC UPS | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELEQ000280 | U20 - SS-504 - 3.3 kV HV Switchgear 580-EE-0402 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134ELEQ000660 | U20 - SS-512 - Cabinets Installation (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELEQ000730 | U20 - SS-503 - 415V Emergency MCC 580-EE-0300 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6455 | 0 | 10780.EL.EL.MH
C220134ELEQ000750 | U20 - SS-516 - 220 kV CT replacement for Trnsformer #2 (Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000755 | U20 - SS-516 - 220 kV CT replacement (Shutdown) for Transformer #A | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000780 | U20 - SS-500 - Decommissioning existing AVR for transformers 80/100 MVA, 220/138 Kv & Protection Panels | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10780.EL.EL.MH
C323131ISEQ000050 | U23 - (566 CWS) - Equipment Insulation | IS | ISEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10474 | 0 | 10610.IS.EQ.M2 | 689 | 0
C323131PIBB000000 | U23 - (566 CWS) - Big Bore Piping A/ Tanks 566-TK-201 & 566-V-202 | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35931 | 0 | 10610.PI.BB.DI | 3593.08 | 0
C323131PIBB000090 | U23 - (566 CWS) - Big Bore Piping A/Equip. Erection including Packages | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35931 | 0 | 10610.PI.BB.DI | 3593.08 | 0
C323131PIPR000080 | U23 - (566 CWS) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 248700 | 75793.8937 | 10610.PI.FB.DI | 62174.98 | 44409.8313
C323131PIRA000020 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-104) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000030 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-105) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PISB000091 | U23 - (566 CWS) - Small Bore Piping A/Equip. Erection including Packages | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12434 | 0 | 10610.PI.SB.DI | 1130.35 | 0
C323131PISU000180 | U23 - (566 CWS) - Piping Supports Erection | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.SU.TN | 69.05 | 0
C323131PRFL000080 | U23 - Piping Flushing/Blowing | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6578 | 0 | 10610.PR.FL.DI | 151729 | 0
C323131PRHT000210 | U23 - Piping Hydrotesting (566) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38912 | 0 | 10610.PR.HT.DI | 60514 | 0
C323131PRHT000220 | U23 - Piping Hydrotesting (567) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16033 | 0 | 10610.PR.HT.DI | 14690 | 0
C323131PRHT000310 | U23 - (566 CWS) - Storage Tank 566-TK-201- Hydrotesting and Settlement Check | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10997 | 0 | 10780.PR.PR.MH
C323132CICT100000 | U23 - (567 UPW) - Electrical earth Trenches Execution | CI | CICT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 183 | 0.0057795 | 10610.CI.ET.M3 | 45.68 | 42.0302
C323132CICT100010 | U23 - (567 UPW) - Instrument earth Trenches Execution | CI | CICT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 368 | 0.072422 | 10610.CI.ET.M3 | 92 | 84.64
C323132CICT100010 | U23 - (567 UPW) - Instrument earth Trenches Execution | CI | CICT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 368 | 0.072422 | 10610.CI.ET.M3 | 92 | 84.64
C323132CICT200000 | U23 - (573 FWS) - Electrical earth Trenches Execution | CI | CICT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5004 | 2.0552 | 10780.CI.CI.MH
C323132CICT200010 | U23 - (573 FWS) - Instrument earth Trenches Execution | CI | CICT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3336 | 0.86527 | 10780.CI.CI.MH
C323132CIDM100000 | U23 - (567 UPW) - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6972 | 54.5567 | 10610.CI.CO.M3 | 116.21 | 116.21
C323132CIGT000170 | U23 - (566 CWS) - Steel Structure Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2560 | 1.1171 | 10780.CI.CI.MH
C323132CIGT200000 | U23 - (573 FWS) - Equipment/Tank Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1600 | 0 | 10780.CI.CI.MH
C220132INFG100170 | U20 - SS-523 - Fire & Gas System Installation (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2588 | 0 | 10780.IN.IN.MH
C220132INFG100210 | U20 - SS-523 - Fire Fighting Equipment Installation (Inc. Clean Agent Gas) (Elect. Subst.) | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 647 | 0 | 10780.IN.IN.MH
C220132INFG100250 | U20 - OMS-014 - Fire & Gas System Installation | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.IN.IN.MH
C220132INFO100030 | U20 - NMCB - Fiber Optic Cable Laying | IN | INFO | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5954 | 0 | 10610.IN.FO.LM | 9412 | 0
C220132INGC100020 | U20 - NMCB - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27318 | 0 | 10780.IN.IN.MH
C220132INGC100030 | U20 - IES-514 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27318 | 0 | 10780.IN.IN.MH
C220132INML100010 | U20 - NMCB - Instrument Multicable Laying | IN | INML | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121879.83 | 0
C220132INML100030 | U20 - IES-513 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 54636 | 0 | 10610.IN.MC.LM | 121880.94 | 0
C220132MEMC100020 | U20 - SS-521 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6635 | 16.4527 | 10610.BU.CO.M3 | 1 | 0.25
C220132MEMC100130 | U20 - OMS-013 - Pipes & Fittings | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 432 | 0 | 10780.ME.ME.MH
C220132MEMC100150 | U20 - SS-524 - Install Lighting Fixtures (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1555 | 0 | 10780.EL.EL.MH
C220132MEMC100220 | U20 - SS-520 - Switches/Sockets Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3404 | 0 | 10780.EL.EL.MH
C220132MEMC100240 | U20 - SS-520 - Miscellaneous Structure Works (Elect. Subst.) | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9541 | 53.7927 | 10610.BU.CO.M3 | 1 | 0.4
C220132MEMC100370 | U20 - OMS-013 - Sanitary Wares | ME | MEMC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 432 | 0 | 10780.ME.ME.MH
C220132MEMC100390 | U20 - IES-513 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2545 | 0 | 10610.BU.CO.M3 | 1 | 0
C220132MEMC100400 | U20 - NMCB - Sanitary Ware | ME | MEMC | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2513 | 0 | 10780.ME.ME.MH
C220132MEMC100410 | U20 - SS-523 - Switchgear Installation (Elect. Subst.) | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 871 | 0 | 10780.EL.EL.MH
C220132MEMC100420 | U20 - IES-513 - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2192 | 0 | 10780.EL.EL.MH
C220132MEMC100430 | U20 - OMS-015 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 664 | 0 | 10610.BU.CO.M3 | 0.94 | 0
C220132MEMC100470 | U20 - OMS-015 - Install Lighting Fixtures | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.EL.EL.MH
C220134ELEQ000820 | U20 - IES-500 - TRANSCO Room / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.IN.IN.MH
C220134ELEQ000850 | U20 - IES-500 - New UPS Distribution Board 500-PDB-125/126 (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5153 | 0 | 10780.EL.EL.MH
C220134ELER000750 | U20 - SS-516 - Earthing/Lighting/Fire Dtection/Firefighting System Modification for Transformer #B (Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELTI000020 | U20 - SS-012 - Electrical Cable Trays Install (Elect. Subst.) | EL | ELTI | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3836 | 0 | 10780.EL.EL.MH
C220134ELTI000090 | U20 - IES-505 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.EL.EL.MH
C220134ELTI000110 | U20 - SS-515 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELTI000350 | U20 - SS-504 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134PRSS000010 | U20 - OMS-013 - Equip. Precommissioning | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 366 | 0 | 10780.PR.PR.MH
C220134PRSS000030 | U20 - OMS-015 - Equip. Precommissioning | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 943 | 0 | 10780.PR.PR.MH
C220134PRSS000135 | U20 - SS-516 - Substation Equip. Precommissioning for Transformer #B | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8 | 0 | 10780.PR.PR.MH
C220134PRSS0010 | U20 - SS-520 - 33kV GIS precommissioning (1 unit) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 892 | 0 | 10780.PR.PR.MH
C220134PRSS0020 | U20 - SS-520 - 415V switchgear precommisisoning (6 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1071 | 0 | 10780.PR.PR.MH
C220134PRSS0025 | U20 - SS-520 - Transformers precommissioning (23 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 726 | 0 | 10780.PR.PR.MH
C220134PRSS0045 | U20 - SS-521 - 33kV GIS precommissioning (1 unit) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 601 | 0 | 10780.PR.PR.MH
C220134PRSS0050 | U20 - SS-521 - 11kV Switchgear precommissioning (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 601 | 0 | 10780.PR.PR.MH
C220134PRSS0055 | U20 - SS-521 - 415V switchgear precommisisoning (6 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 934 | 0 | 10780.PR.PR.MH
C220134PRSS0060 | U20 - SS-521 - Transformers precommissioning (18 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 747 | 0 | 10780.PR.PR.MH
C220134PRSS0090 | U20 - SS-522 - 3.3kV Switchgear precommissioning (1 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 407 | 0 | 10780.PR.PR.MH
C220134PRSS0115 | U20 - SS-523 - UPS black start (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 435 | 0 | 10780.PR.PR.MH
C220134PRSS0130 | U20 - SS-524 - UPS black start (4 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 337 | 0 | 10780.PR.PR.MH
C323132CIMF000080 | U23 - (566 CWS) - Miscellaneous Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8395 | 81.9936 | 10610.CI.CO.M3 | 139.92 | 139.92
C323132CIMF100000 | U23 - (567 UPW) - (567 UPW) - Misc. pipe supports for Instrument Air Dryer Pck. (567-ME-102D) foundations execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2237 | 7.1554 | 10610.CI.CO.M3 | 37.28 | 36.0901
C323132CIMF100010 | U23 - (567 UPW) - Misc. pipe supports for Instrument Air Receiver (567-V-201A/B) foundations execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6365 | 58.3335 | 10610.CI.CO.M3 | 106.08 | 106.08
C323132CIMF100040 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101G-F01-V01/02/03 ) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.3421 | 10610.CI.CO.M3 | 37.48 | 37.48
C323132CIMF200000 | U23 - (573 FWS) - Miscellaneous Foundations Execution (Piping and structural supports foundations) | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6200 | 22.3439 | 10610.CI.CO.M3 | 103.33 | 31
C323132CIPE000060 | U23 - (566 CWS) - Refrigerant Compressor Foundation Execution (566-ME-201C-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000080 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201C-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000090 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201C-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000120 | U23 - (566 CWS) - Refrigerant compressor foundation execution (566-ME-201B-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000120 | U23 - (566 CWS) - Refrigerant compressor foundation execution (566-ME-201B-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000130 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201B-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000130 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201B-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000140 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201B-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000150 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201B-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000160 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201B-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.6801
C323132CIPE000180 | U23 - (566 CWS) - Refrigerant compressor foundation execution (566-ME-201A-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1463 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000190 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201A-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2215 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132STMS000080 | U23 - (566 CWS) - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1080 | 0 | 10610.ST.PL.TN | 0 | 0
C323132STMS200000 | U23 - (573 FWS) - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 345 | 0 | 10610.ST.PL.TN | 5.75 | 0
C323132STPL000060 | U23 - (567 UPW) - Vessel Mounted Platform for Instrument Air Receiver (567-V-201 A/B) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ST.PL.TN | 9 | 0
C323132STPL000180 | U23 - (566 CWS) - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5627 | 0 | 10610.ST.PL.TN | 70.34 | 0
C323132STPL000190 | U23 - (566 CWS) - Equipment Structures, Ladders & Handrails Erection (566-STR-V202) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28947 | 0 | 10610.ST.PL.TN | 361.84 | 0
C323132STPL100050 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101G-F01) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64 | 0 | 10610.ST.PL.TN | 0.81 | 0
C323132STPR000150 | U23 - (566 CWS) - Secondary Piperack Erection (566-PR-105) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5926 | 44.2039 | 10610.ST.PR.TN | 111.81 | 107.3435
C323132STPR000180 | U23 - (566 CWS) - Main Piperack Erection (566-PR-104) including Tower V 202 | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43054 | 1679.6293 | 10610.ST.PR.TN | 812.33 | 622.5061
C323132STPR100010 | U23 - (567 UPW) - Piperack Erection (567-PR-102) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1196 | 1.8311 | 10610.ST.PR.TN | 22.56 | 21.6572
C323132STSH000070 | U23 - (566 CWS) - Compressor Shelter Roofing & Cladding Erection (566-SH-001/002/003) | ST | STSH2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52 | 0 | 10610.ST.ER.TN | 21.64 | 0
C323133PAPP000080 | U23 - (566 CWS) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14410 | 162.4155 | 10610.PA.PP.M2 | 0 | 0
C323133PAST000090 | U23 - (566 CWS) - Steel Structure Painting Touch Up | PA | PAST | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4088 | 0 | 10780.PA.PA.MH
C323134ELCL000170 | U23 - (566 CWS) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 71202 | 1040.6627 | 10610.EL.PL.LM | 149955.95 | 22493.3925
C323134ELEL000095 | U23 - (566 CWS) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12946 | 38.9632 | 10610.EL.ES.LM | 13808.39 | 2071.2585
C323134ELEL000098 | U23 - (566 CWS) - Lightning Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12946 | 0 | 10780.EL.EL.MH
C323134ELEQ000050 | U23 - (566 CWS) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9709 | 0 | 10610.EL.EQ.UN | 490 | 0
C323134ELTI000160 | U23 - (566 CWS) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32365 | 0 | 10610.EL.CT.LM | 4464.14 | 0
C323136MEAC000040 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201B-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323132CIPE000220 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201A-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.6801
C323132CIPE000220 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201A-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.6801
C323132CIPE000230 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201A-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.9678 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000240 | U23 - (566 CWS) - Cooling Water Chemical Dosing Package Foundation execution (566-ME-202) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4534 | 30.3703 | 10610.CI.CO.M3 | 75.57 | 75.57
C323132CIPE000250 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201A-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.5866 | 10610.CI.CO.M3 | 32.83 | 26.2601
C323132CIPE000250 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201A-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.5866 | 10610.CI.CO.M3 | 32.83 | 26.2601
C323132CIPE000270 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201C-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 3.1103 | 10610.CI.CO.M3 | 32.83 | 16.4199
C323132CIPR000330 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-102) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96751 | 13828.5716 | 10610.CI.CO.M3 | 1935.02 | 1935.02
C323132CIPR000340 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-103) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79302 | 9290.3471 | 10610.CI.CO.M3 | 1586.03 | 1586.0305
C323132CIPS000000 | U23 - (566 CWS) - Collection Pit Execution for Propane Storage Drum (566-SU-202) | CI | CIPS1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10303 | 131.9643 | 10610.CI.CO.M3 | 171.72 | 171.7198
C323132CIPT200000 | U23 - (573 FWS) - Pipe Tracks Execution | CI | CIPT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11645 | 178.3405 | 10610.CI.CO.M3 | 194.08 | 173.3092
C323132CIPV100000 | U23 - (567 UPW) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6523 | 7.0718 | 10610.CI.PV.M2 | 3624 | 0
C323132CIPV200010 | U23 - (573 FWS) - Gravel Paving Execution | CI | CIPV2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 717 | 0 | 10610.CI.GV.M2 | 1195 | 0
C323132CIPV200010 | U23 - (573 FWS) - Gravel Paving Execution | CI | CIPV2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 717 | 0 | 10610.CI.GV.M2 | 1195 | 0
C323132CIRE000110 | U23 - (566 CWS) - CW Ref. Package Propane Transfer Pump Foundation Execution (566-P-204A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 735 | 0.11965 | 10610.CI.CO.M3 | 10.5 | 0
C323132CIRE000120 | U23 - (566 CWS) - CW Ref. Package Propane Transfer Pump Foundation Execution (566-P-204B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 735 | 0.11965 | 10610.CI.CO.M3 | 10.5 | 0
C323132CIRE000140 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2655 | 1.2236 | 10610.CI.CO.M3 | 44.25 | 0
C323132CIRE000160 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323136MEAC000040 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201B-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323136MEHM000030 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203C | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000050 | U23 - (566 CWS) - Horizontal Pump (Propane Transfer Pump) with Electrical Motor Erection 566-P-202B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323136MEHM000210 | U23 - (566 CWS) - Horizontal Pump (Propane Transfer Pump) with Electrical Motor Erection 566-P-202A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323136MEPA000010 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201B-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000030 | U23 - (566 CWS) - Evaporator Installation (566-ME-201C-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0.22396 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000040 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201C-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000070 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201C-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000140 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201B-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000160 | U23 - (566 CWS) - Oil separator Installation (566-ME-201B-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323136MEPA000180 | U23 - (566 CWS) - Refrigerant compressor Installation (566-ME-201A-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000200 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201A-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000210 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201A-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000220 | U23 - (566 CWS) - Oil separator Installation (566-ME-201A-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323137INCO000080 | U23 - (566 CWS) - Communication System Installation | IN | INCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2013 | 0 | 10780.IN.IN.MH
C323137INCT000150 | U23 - (566 CWS) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6405 | 0 | 10610.IN.CT.LM | 720 | 0
C323137INFG000090 | U23 - (566 CWS) - Fire & Gas System Installation | IN | INFG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1190 | 0 | 10780.IN.IN.MH
C323137INGC000160 | U23 - (566 CWS) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7137 | 0 | 10610.IN.CO.UN | 540 | 0
C323132CIRE200000 | U23 - (573 FWS) - Fire Water Pump Foundation Execution (573-P-201) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1383 | 2.6791 | 10610.CI.CO.M3 | 19.76 | 19.76
C323132CISF100000 | U23 - (567 UPW) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7389 | 9.0734 | 10610.CI.CO.M3 | 123.14 | 0
C323132CISF200000 | U23 - (573 FWS) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6200 | 23.5648 | 10610.CI.CO.M3 | 103.33 | 36.1696
C323132CIST000190 | U23 - (566 CWS) - Shelters Foundation Execution (566-SH-001/002/003) | CI | CIST | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 98899 | 14326.5203 | 10610.CI.CO.M3 | 1977.97 | 1977.9692
C323132CIST000190 | U23 - (566 CWS) - Shelters Foundation Execution (566-SH-001/002/003) | CI | CIST | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 98899 | 14326.5203 | 10610.CI.CO.M3 | 1977.97 | 1977.9692
C323132CIUG000135 | U23 - (566 CWS) - UG Pipe Installation (OD) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7680 | 59.0334 | 10780.CI.CI.MH
C323132CIUG100010 | U23 - (567 UPW) - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10962 | 177.5195 | 10610.CI.CO.M3 | 182.7 | 182.7
C323132CIUG100035 | U23 - (567 UPW) - UG Pipe Installation (OD) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14358 | 240.2839 | 10610.CI.UG.LM | 717.89 | 717.8934
C323132CIUG200010 | U23 - (573 FWS) - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1092 | 0 | 10610.CI.CO.M3 | 15.6 | 0
C323132CIUG200020 | U23 - (573 FWS) - UG Civil Works (System description) - Part A | CI | CIUG1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1429 | 0 | 10780.CI.CI.MH
C323132CIUP200000 | U23 - (573 FWS) - UG Piping Prefabrication (System description) | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6984 | 61.272 | 10610.PI.FB.DI | 1746 | 3034.0904
C323132CIUP200000 | U23 - (573 FWS) - UG Piping Prefabrication (System description) | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6984 | 61.272 | 10610.PI.FB.DI | 1746 | 3034.0904
C323132CIVE000160 | U23 - (566 CWS) - Horizontal Vessels (Propane Storage Drum) Foundation Execution (566-V-202) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17647 | 460.0533 | 10610.CI.CO.M3 | 352.94 | 352.94
C323132CIVE100000 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101F-V02) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIVE100020 | U23 - (567 UPW) - 2nd Stage suction moisture separator Foundations Execution (567-ME-101G-V01) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIVE100030 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101G-V02) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 0.28667 | 10610.CI.CO.M3 | 18.36 | 0
C323132CIVE100080 | U23 - (567 UPW) - 2nd stage discharge moisture separator Foundations Execution (567-ME-101F-V01) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132ELCL200000 | U23 - (573 FWS) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2582 | 0 | 10610.EL.PL.LM | 5438.2 | 0
C220134PRSS0155 | U20 - SS-524 - Transformers precommissioning (5 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 492 | 0 | 10780.PR.PR.MH
C220134PRSS0160 | U20 - SS-525 - UPS black start (3 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 141 | 0 | 10780.PR.PR.MH
C220134PRSS0165 | U20 - SS-525 - Variable fecuency driver precommissioning (3 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 94 | 0 | 10780.PR.PR.MH
C220137INCC000050 | U20 - IES-15 - System Cabinets & Consoles Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6099 | 29.0696 | 10780.IN.IN.MH
C220137INCC000080 | U20 - IES-1A - System Cabinets & Consoles Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 38.3288 | 10780.IN.IN.MH
C220137INCC000340 | U20 - IES-504 - DCS/VMS/ESD Cabinets Installation (Shutdown Required) + Other Works | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INCC000370 | U20 - IES-507 - System Cabinets & Consoles Installation / Modifications (Shutdown Required) + Other Works | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 20.941 | 10780.IN.IN.MH
C220137INCO000060 | U20 - IES-504 - Communication System Installation / Modifications (Shutdown Required) + Other Works | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INCT000240 | U20 - IES-304 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2361 | 0 | 10780.IN.IN.MH
C220137INCT000700 | U20 - TLC - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INDC000110 | U20 - IES-500 - DCS/VMS/ESD Cabinets Installation / Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INDC000120 | U20 - CR-541 & MAQTA - DCS/VMS/ESD Cabinets Installation / Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INGC000040 | U20 - IES-505 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.IN.IN.MH
C220137INGC000050 | U20 - IES-507 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 0 | 10780.IN.IN.MH
C220137INGC000250 | U20 - IES-1A - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2361 | 0 | 10780.IN.IN.MH
C220137INGC000260 | U20 - IES-304 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2361 | 0 | 10780.IN.IN.MH
C220137INGC000280 | U20 - IES-500 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2793 | 0 | 10780.IN.IN.MH
C220BUTR000000020 | U20 - SS-516 - Transf. Yard Architecture (Pre-Shutdown)ok | BU | BUTRAR | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41199 | 913.7305 | 10780.BU.BU.MH
C220BUTR000000030 | U20 - SS-516 - Transf. Column & Walls Yard Concrete Structure (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43014 | 2733.2922 | 10610.BU.CO.M3 | 754 | 754.0023
C323137ININ000080 | U23 - (566 CWS) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3660 | 0 | 10610.IN.IN.UN | 600 | 0
C323137ININ000081 | U23 - (566 CWS) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3660 | 0 | 10610.IN.IN.UN | 460 | 0
C323137INIP000081 | U23 - (566 CWS) -Valve Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1190 | 0 | 10780.IN.IN.MH
C323137INJB000080 | U23 - (566 CWS) - Junction Boxes & Local Panels Install. | IN | INJB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4758 | 0 | 10780.IN.IN.MH
C323137INML000080 | U23 - (566 CWS) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14274 | 0 | 10610.IN.MC.LM | 62580.32 | 0
C323CIGR000000010 | U23 - (567 UPW) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1419 | 0.3049 | 10610.CI.GR.LM | 2365 | 0
C323CIMF000000040 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101F-F01) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.2949 | 10610.CI.CO.M3 | 37.48 | 37.48
C323CIOT000000030 | U23 - (567 UPW) - Pipebridge Foundations Execution (567-PB-101) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10520 | 163.4987 | 10610.CI.CO.M3 | 175.34 | 175.34
C323CIPE000000010 | U23 - (567 UPW) - Deluge Valve Skid Foundations Execution | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 776 | 0.1023 | 10780.CI.CI.MH
C424131CIPR100040 | U24-Civil Revamp of Piperack ( Unit 562)- 562-PR-012A (Aprox. length =60m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15253 | 77.8476 | 10780.CI.CI.MH
C424131CIPR100120 | U23- Civil Revampt of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1683 | 2.767 | 10610.CI.CO.M3 | 28.05 | 15.9899
C424131CIPR100120 | U23- Civil Revampt of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1683 | 2.767 | 10610.CI.CO.M3 | 28.05 | 15.9899
C424131CIPR100200 | U22- Civil Revamp of Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 239711 | 84887.2226 | 10610.CI.CO.M3 | 4794.22 | 4794.2315
C424131CIPR100210 | U23- Civil Revampt of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part B | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1683 | 3.7748 | 10610.CI.CO.M3 | 28.05 | 25.25
C424131CIPR100210 | U23- Civil Revampt of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part B | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1683 | 3.7748 | 10610.CI.CO.M3 | 28.05 | 25.25
C424131CIPR100220 | U23- Civil Revamp of Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =400m) – Interface with CRI P - Part-B | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0.18097 | 10780.CI.CI.MH
C424131CIPR100240 | U15- Civil Revamp of Piperack ( Unit 550/551/552/553)-I-001 (E-W) (Approx length=400m) - Part B | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 351 | 0.182 | 10780.CI.CI.MH
C424131PIPR000700 | U24 - Piping Tie-in Prefabrication - Habhsan 5 Shutdown | PI | PIPR | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 70056 | 7185.1023 | 10610.PI.FB.DI | 17514.09 | 42013.5575
C323132ELCO100000 | U23 - (567 UPW) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10820 | 10.0125 | 10610.EL.CO.UN | 405 | 0
C323132ELEL100005 | U23 - (567 UPW) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3607 | 0 | 10610.EL.ES.LM | 8876.82 | 0
C323132ELEL200010 | U23 - (573 FWS) - Lightning Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 313 | 0 | 10780.EL.EL.MH
C323132ELEQ100000 | U23 - (567 UPW) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2705 | 0 | 10610.EL.EQ.UN | 300 | 0
C323132ELEQ200000 | U23 - (573 FWS) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 352 | 0 | 10610.EL.EQ.UN | 490 | 0
C323132ELGR200000 | U23 - (573 FWS) - Grounding Installation | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 313 | 0 | 10780.EL.EL.MH
C323132ELTI100000 | U23 - (567 UPW) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9017 | 0 | 10610.EL.CT.LM | 2295 | 0
C323132FPEQ000050 | U23 - (566 CWS) - Equipment Fireproofing | FP | FPEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3734 | 0 | 10780.FP.FP.MH
C323132FPEQ100000 | U23 - (567 UPW) - Equipment Fireproofing | FP | FPEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10780.FP.FP.MH
C323132INAI200000 | U23 - (573 FWS) - Analyzers Equipment Installation | IN | INAI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2360 | 0 | 10610.IN.AI.UN | 1 | 0
C323132INCI100000 | U23 - (567 UPW) - Conduits Installation | IN | INCT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.IN.IN.MH
C323132INCI200000 | U23 - (573 FWS) - Conduits Installation | IN | INCT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1133 | 0 | 10780.IN.IN.MH
C323132INCO200000 | U23 - (573 FWS) - Communication System Installation | IN | INCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1923 | 0 | 10780.IN.IN.MH
C323132INCT100000 | U23 - (567 UPW) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1002 | 0 | 10610.IN.CT.LM | 540 | 0
C323132INCT100010 | U23 - (567 UPW) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 561 | 0 | 10610.IN.CT.LM | 540 | 0
C323132INCT200000 | U23 - (573 FWS) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10928 | 9.7773 | 10610.IN.CT.LM | 800 | 0
C323132INFC100000 | U23 - (567 UPW) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 360 | 0
C323132INFC200000 | U23 - (573 FWS) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1049 | 0 | 10610.IN.CO.UN | 330 | 0
C323132INFG100000 | U23 - (567 UPW) - Fire & Gas System Installation | IN | INFG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.IN.IN.MH
C323132INFG200000 | U23 - (573 FWS) - Fire & Gas System Installation | IN | INFG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1137 | 0 | 10780.IN.IN.MH
C424131PIPR000700 | U24 - Piping Tie-in Prefabrication - Habhsan 5 Shutdown | PI | PIPR | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 70056 | 7185.1023 | 10610.PI.FB.DI | 17514.09 | 42013.5575
C424131PIRA000100 | U24- Piping Erection on Existing Piperack ( Unit 562)- 562-PR-012A (Aprox. length =60m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000110 | U24- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-001 (Aprox. length =570m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000140 | U24- Piping Erection on Existing Piperack ( Unit 522)- 522-PR-I-1 (Aprox. length =32m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000160 | U24- Piping Erection on Existing Process Structure ( Unit 522)- 522-Process Str A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000170 | U24- Piping Erection on Existing Piperack ( Unit 510)- 510-PR-I-2 to 7 (Aprox. length =211m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000200 | U25- Piping Erection on Existing Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =679m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0.73576 | 10610.PI.PR.DI | 189.92 | 28.4899
C424131PIRA000240 | U23- Piping Erection on Existing Piperack ( Unit 577)- 577-PR-E2-P18 (Aprox. length =24m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000250 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =320m) Excluding Module E2P18 | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000261 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =800m) Interface with CRI Part B | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000280 | U24- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-012 in Unit 530 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 3.0121 | 10610.PI.PR.DI | 189.92 | 132.9402
C424131PIRA000300 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-F1P14 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000320 | Modification of 2nd Stage Feed KO Drum 44-V-302 (MDS: SPP-1000482-GG-001-06-44-171) - Involvement of OEM | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PISU000220 | U24 - Piping Tie-ins Supports erection for Unit 551 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 337 | 0.1676 | 10610.PI.SU.TN | 0.75 | 0.75
C424131PISU000280 | U24 - Piping Tie-ins for Unit 521 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 153.6975 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000310 | U24 - Piping Tie-ins for Unit 532 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 17.0775 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000320 | U24 - Piping Tie-ins for Unit 533 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 17.0775 | 10610.PI.TI.DI | 367.16 | 367.16
C220132MEMC100480 | U20 - OMS-014 - Miscellaneous Structure Works | BU | BUBRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 577 | 0 | 10610.BU.CO.M3 | 0.94 | 0
C220132MEMC100530 | U20 - OMS-015 - Switches/Sockets Installation | EL | ELEL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 831 | 0 | 10780.EL.EL.MH
C220132STSH2100040 | U20 - SS-520 - Install Roof Structure and Corrugated Steel Sheeting (Elect. Subst.) | BU | BUARCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8905 | 0 | 10780.BU.BU.MH
C220132STSH2100050 | U20 - NMCB - Install Roof Structure and Corrugated Steel Sheeting | BU | BUARCL | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4467 | 0 | 10780.BU.BU.MH
C220134ELBD000705 | U20 - SS-516 - Bus Ducts Installation for Transformer #A (Pre-Shutdown) | EL | ELBD | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17 | 0 | 10780.EL.EL.MH
C220134ELCL000370 | U20 - SS-516 - Electrical Cable Laying for Transformer #B (Pre-Shutdown) | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10780.EL.EL.MH
C220134ELCL000430 | U20 - IES-501 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 0 | 10780.EL.EL.MH
C220134ELCL000440 | U20 - IES-500 - Electrical Cable Laying | EL | ELCL | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.EL.EL.MH
C220134ELCO000120 | U20 - IES-505- Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2270 | 0 | 10780.EL.EL.MH
C220134ELCO000330 | U20 - SS-500 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 105 | 0 | 10780.EL.EL.MH
C220134ELCO000370 | U20 - IES-504- Electrical Cable Gland & Conn./Testing | EL | ELCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.EL.EL.MH
C220134ELEQ000150 | U20 - SS-012 - 415 V Switchgear 80-EE-1205 Modification (Elect. Subst.) | EL | ELEQ1 | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10919 | 0 | 10780.EL.EL.MH
C220134ELEQ000250 | U20 - SS-516 - LV AC System & Lighting System Modification for Transformer #B (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0 | 10780.EL.EL.MH
C220134ELEQ000270 | U20 - SS-503 - 11kV HV Switchgear 580-EE-0301 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6455 | 0 | 10780.EL.EL.MH
C220134ELEQ000650 | U20 - SS-512 - Cabinets Installation (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELEQ000690 | U20 - SS-515 - New GEP, GCPP, FGHCP Panels in MCC Room | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5738 | 0 | 10780.EL.EL.MH
C220134ELEQ000710 | U20 - SS-504 - 415V MCC 580-EE-0403 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7378 | 0 | 10780.EL.EL.MH
C220134ELEQ000720 | U20 - SS-503 - 415V Normal MCC 580-EE-0302 Modification (Shutdown Required) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6455 | 0 | 10780.EL.EL.MH
C220134ELEQ000770 | U20 - IES-500 - TRANSCO Room Modifications | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.EL.EL.MH
C220134ELEQ000800 | U20 - SS-500 - Reconfiguration of TRANSCO Tariff Metering / TRANSCO LDC Metering In-Station / PQM System | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33 | 0 | 10780.EL.EL.MH
C323132INFO100000 | U23 - (567 UPW) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 49622 | 0
C323132INFO200000 | U23 - (573 FWS) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1486 | 0 | 10610.IN.FO.LM | 830 | 0
C323132INGC100010 | U23 - (567 UPW) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 417 | 0 | 10610.IN.CO.UN | 420 | 0
C323132INGC200000 | U23 - (573 FWS) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6819 | 0 | 10610.IN.CO.UN | 410 | 0
C323132INHU100000 | U23 - (567 UPW) - Pneumatic Hook Up´s Erection | IN | INHU3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2078 | 0 | 10780.IN.IN.MH
C323132ININ200000 | U23 - (573 FWS) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3497 | 0 | 10610.IN.IN.UN | 800 | 0
C323132ININ200002 | U23 - (573 FWS) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3497 | 0 | 10610.IN.IN.UN | 450 | 0
C323132INIP200001 | U23 - (567 UPW) - Valve Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.IN.IN.MH
C323132INIP200002 | U23 - (573 FWS) - Valve Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1137 | 0 | 10780.IN.IN.MH
C323132INJB200000 | U23 - (573 FWS) - Junction Boxes & Local Panels Install. | IN | INJB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4546 | 0 | 10780.IN.IN.MH
C323132INML100000 | U23 - (567 UPW) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1250 | 0 | 10610.IN.MC.LM | 5087.65 | 0
C323132ISPI100000 | U23 - (567 UPW) - Piping Insulation | IS | ISPI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3800 | 0 | 10780.IS.IS.MH
C323132MEHM200000 | U23 - (573 FWS) - Horizontal Fire Water Pump with Electrical Motor Erection 573-P-201 | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C323132MEPA100010 | U23 - (567 UPW) - Package (Air pre filter) installation (567-ME-101F-F01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323132MEPA100020 | U23 - (567 UPW) - Package (Air pre filter) installation (567-ME-101G-F01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323132MEPA100030 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler pre-assembly (567-ME-101G-E01/E02/E03) | ME | MEAC1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16000 | 0 | 10780.ME.ME.MH
C323132MEPA100050 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler Erection (567-ME-101F-E01/E02/E03) | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 0 | 10610.ME.ER.TN | 200 | 0
C323132MEPA100130 | U23 - (567 UPW) - Instrument Air Dryer Package Installation 567-ME-102D | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1800 | 0.25191 | 10610.ME.ER.TN | 30 | 0
C323132PAEQ100000 | U23 - (567 UPW) - Equipment Painting | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10780.PA.PA.MH
C323132PAEQ200015 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Internal Painting for Shell and Bottom | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1852 | 0 | 10780.PA.PA.MH
C424131PISU000330 | U24 - Piping Tie-ins for Unit 540 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 126650 | 21492.3583 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000380 | U24 - Piping Tie-ins for Unit 551 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 3842.4369 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000420 | U24 - Piping Tie-ins for Unit 562 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28050 | 1022.8567 | 10610.PI.TI.DI | 367.16 | 323.1008
C424131PISU000420 | U24 - Piping Tie-ins for Unit 562 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 28050 | 1022.8567 | 10610.PI.TI.DI | 367.16 | 323.1008
C424131PRFL000090 | U24 - Piping Flushing/Steam Blowing | PR | PRFL | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16126 | 0 | 10610.PR.FL.DI | 28996 | 0
C424131PRHT000100 | U24 - Piping Hydrotesting | PR | PRHT | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 128639 | 0 | 10610.PR.HT.DI | 28996 | 0
C424131STEQ000000 | U24- Structure revamp of Process Structure ( Unit 521)- 521-Process Str A | ST | STEQ | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 245 | 0.035947 | 10610.ST.ER.TN | 4.63 | 3.7813
C424131STPR100040 | U24- Structure revamp of Piperack ( Unit 545)- 545-PR-007/008/009 (Aprox. length =94m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10 | 0.00012777 | 10610.ST.PR.TN | 0.2 | 0.1996
C424131STPR100050 | U25- Structure revamp of Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =340m) - Part A | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2343 | 7.4167 | 10610.ST.PR.TN | 44.21 | 44.2096
C424131STPR100070 | U24- Structure revamp of Piperack ( Unit 500)- 500-PR-012 in Unit 530 (Approximate length = 40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 267 | 0.10545 | 10610.ST.PR.TN | 5.04 | 5.0359
C424131STPR100070 | U24- Structure revamp of Piperack ( Unit 500)- 500-PR-012 in Unit 530 (Approximate length = 40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 267 | 0.10545 | 10610.ST.PR.TN | 5.04 | 5.0359
C424131STPR100080 | U25- Structure revamp of Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =340m) - Part B | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1796 | 3.1029 | 10610.ST.PR.TN | 33.9 | 22.3728
C424131STPR100100 | U23- Structure revamp of Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =400m) – Interface with CRI P- Part A | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2014 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100110 | U24- Structure revamp of Piperack ( Unit 522)- 522-PR-I-1 (Aprox. length =32m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 747 | 0 | 10610.ST.PR.TN | 14.1 | 0
C424131STPR100150 | U24- Structure revamp of Piperack ( Unit 549)- (549-P-023) (Approximate length =40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1336 | 2.5675 | 10610.ST.PR.TN | 25.2 | 24.8724
C424131STPR100160 | U23-Structure revamp of Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =160m) Excluding Module - Part A | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2491 | 2.2373 | 10610.ST.PR.TN | 0 | 0
C424131STPR100170 | U23-Structure revamp of Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =160m) Excluding Module - Part B | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2491 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100190 | U25- Structure revamp of Piperack ( Unit 541)- 541-C2-PR (Aprox. length =280m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1381 | 2.511 | 10610.ST.PR.TN | 26.06 | 23.4572
C323132PAFP200000 | U23 - (573 FWS) - Piping Final Coat & Touch-Up Painting | PA | PAFP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1160 | 0 | 10780.PA.PA.MH
C323132PAPP100000 | U23 - (567 UPW) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4375 | 21.5485 | 10610.PA.PP.M2 | 0 | 0
C323132PASP100000 | U23 - (567 UPW) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 579 | 0.065997 | 10610.PA.SU.TN | 0 | 0
C323132PIBB100000 | U23 - (567 UPW) - Big Bore Piping A/Equip. Erection | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39766 | 0 | 10610.PI.BB.DI | 3976.6 | 0
C323132PISB200000 | U23 - (573 FWS) - Small Bore Piping A/Equip. Erection | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5840 | 0 | 10610.PI.SB.DI | 530.95 | 0
C323132PISU100010 | U23 - (567 UPW) - Piping Supports Erection | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4642 | 0 | 10610.PI.SU.TN | 10.32 | 0
C323132PIUG100000 | U23 - (566 UPW) - Piping Erection UG | PI | PIUG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 198 | 0 | 10610.PI.UG.DI | 132 | 0
C323132SPSP100000 | U23 - (573 FWS) - U/G Detection works and re-routing of existing services | SP | SPSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1386 | 2.8379 | 10610.SP.SP.M3 | 27.7 | 27.7
C323132STPL000060 | U23 - (567 UPW) - Vessel Mounted Platform for Instrument Air Receiver (567-V-201 A/B) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 720 | 0 | 10610.ST.PL.TN | 9 | 0
C323132STPL100100 | U23 - (567 UPW) - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6720 | 0 | 10610.ST.PL.TN | 0 | 0
C323132STPL200000 | U23 - (573 FWS) - Equipment Structures, Ladders & Handrails Erection (573-STR-P201) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10610.ST.PL.TN | 2.07 | 0
C323132STPR000140 | U23 - (566 CWS) - Main Piperack Erection (566-PR-101) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 726 | 0 | 10610.ST.PR.TN | 13.69 | 0
C323132STPR000140 | U23 - (566 CWS) - Main Piperack Erection (566-PR-101) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 726 | 0 | 10610.ST.PR.TN | 13.69 | 0
C323132STPR000150 | U23 - (566 CWS) - Secondary Piperack Erection (566-PR-105) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5926 | 44.2039 | 10610.ST.PR.TN | 111.81 | 107.3435
C323132STPR000170 | U23 - (566 CWS) - Main Piperack Erection (566-PR-103) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50018 | 2174.3082 | 10610.ST.PR.TN | 943.74 | 636.7279
C323132STSH000060 | U23 - (566 CWS) - Compressor Shelter Structure Erection (566-SH-001/002/003) | ST | STSH1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67952 | 457.0291 | 10610.ST.ER.TN | 1282.11 | 92.5722
C323132STSH000080 | U23 - (566 CWS) - Compressor Shelter Architecture (566-SH-001/002/003) | ST | STSH3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 130 | 0 | 10610.ST.ER.TN | 43.38 | 0
C323132STSH000080 | U23 - (566 CWS) - Compressor Shelter Architecture (566-SH-001/002/003) | ST | STSH3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 130 | 0 | 10610.ST.ER.TN | 43.38 | 0
C323132STSP100010 | U23 - (567 UPW) - Steel Structure Stair Ways & Floors Erection (567-STR-PR101) | ST | STSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2153 | 0 | 10610.ST.PL.TN | 35.88 | 0
C424131STPR100200 | U23- Structure revamp of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part B | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6625 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100240 | U15- Structure revamp of Piperack ( Unit 550/551/552/553)-I-001 (E-W) (Approx length=400m) - Part A | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 124 | 0.0095046 | 10610.ST.PR.TN | 2.34 | 1.3214
C424134ELEQ000050 | MODIFICATION OF MV AIR INSULATED SWITCHGEARS | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 346 | 346
C424134ELEQ000060 | MODIFICATION OF 415V LV SWITCHGEARS | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 360 | 360
C424134ELEQ000060 | MODIFICATION OF 415V LV SWITCHGEARS | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 360 | 360
C424PITI000000010 | Tie-in Pipe Support foundations for Unit 540 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 245 | 0.088674 | 10780.CI.CI.MH
C424PITI000000080 | Tie-in Pipe Support foundations for Unit 552 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1572 | 3.6507 | 10610.CI.CO.M3 | 26.2 | 26.2
C424PITI000000080 | Tie-in Pipe Support foundations for Unit 552 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1572 | 3.6507 | 10610.CI.CO.M3 | 26.2 | 26.2
C424PITI000000090 | Tie-in Pipe Support foundations for Unit 553 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C424PITI000000100 | Tie-in Pipe Support foundations for Unit 562 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 82 | 0.0099333 | 10780.CI.CI.MH
C424PITI000000110 | Tie-in Pipe Support foundations for Unit 571 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 82 | 0.0099333 | 10780.CI.CI.MH
C4250PRPRPL000100 | U25 - Punch List | PR | PRPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 904 | 0 | 10780.PR.PR.MH
C425131PIBB000000 | U25 - Big Bore Piping A/Equip. Erection (540-V-144, 540-F-113C / 15C, 540-P-111A/B/C) | PI | PIBB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19518 | 27.3681 | 10610.PI.BB.DI | 1951.81 | 226.0001
C425131PIPR000120 | U25 - Piping Prefabrication | PI | PIPR | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39780 | 2148.1421 | 10610.PI.FB.DI | 9944.97 | 8736.6014
C425131PISU000280 | U25 - Piping Supports Prefabrication | PI | PISU1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3643 | 15.8999 | 10610.PI.PU.TN | 14.01 | 7.2413
C425131PRHT000293 | U25 - Piping Hydrotesting | PR | PRHT | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10181 | 0 | 10610.PR.HT.DI | 24116 | 0
C425132CIRE000120 | U25 - Liquid Dehydration Feed Pump (540-P-111C) Foundation Execution | CI | CIRE1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CIRE000230 | U25 - Liquid Dehydration Feed Pump (541-P-111C) Foundation Execution | CI | CIRE1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CIRE000230 | U25 - Liquid Dehydration Feed Pump (541-P-111C) Foundation Execution | CI | CIRE1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CISF000060 | U25 - Platform Structure/Misc Platforms & Crossovers Foundations Execution | CI | CISF | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1349 | 2.6882 | 10610.CI.CO.M3 | 19.27 | 19.27
C323133PAFP000090 | U23 - (566 CWS) - Piping Final Coat & Touch-Up Painting | PA | PAFP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1729 | 0 | 10780.PA.PA.MH
C323133PAPP000080 | U23 - (566 CWS) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14410 | 162.4155 | 10610.PA.PP.M2 | 0 | 0
C323134ELCP000080 | U23 - (566 CWS) - Cathodic Protection Piping | EL | ELCP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6473 | 0 | 10780.EL.EL.MH
C323134ELCT000040 | U23 - (566 CWS) - Cathodic Protection Tanks | EL | ELCT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6473 | 46.7016 | 10780.EL.EL.MH
C323134ELEQ000050 | U23 - (566 CWS) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9709 | 0 | 10610.EL.EQ.UN | 490 | 0
C323134ELPL000080 | U23 - (566 CWS) - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21037 | 0 | 10780.EL.EL.MH
C323134PRMR000070 | U23 - Motor Run | PR | PRMR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2445 | 0 | 10780.PR.PR.MH
C323136MEAC000030 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201A-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323136MEAC000030 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201A-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323136MEHM000000 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000020 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000030 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203C | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000040 | U23 - (566 CWS) - Horizontal Pump (Ref. Package Propane Transfer Pump) with Electrical Motor Erection 566-P-204B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000220 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C323136MEHM000340 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C323136MEPA000000 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201A-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000010 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201B-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000020 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201C-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C425132CIVE000060 | U25 - Molecular Sieve Liquid Adsorber (540-V-144) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 753 | 0.83786 | 10610.CI.CO.M3 | 10.76 | 10.76
C425132CIVE000220 | U25 - Liquid Dehydration Outlet Filter (540-F-115C) - Foundation Execution ( Existing ) | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CIVE000220 | U25 - Liquid Dehydration Outlet Filter (540-F-115C) - Foundation Execution ( Existing ) | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CIVE000245 | U25 - Liquid Dehydration Outlet Filter (541-F-115C) - Foundation Execution ( Existing ) | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132STPL000000 | U25 - Equipment Platforms, Staircase, Floors, Ladders & Handrails Erection (540-STR-V144) | ST | STPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12144 | 197.7159 | 10610.ST.PL.TN | 151.8 | 134.5952
C425133PAPP000120 | U25 - Piping SandBl. & Priming | PA | PAPP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14840 | 314.9137 | 10610.PA.PP.M2 | 0 | 0
C425134ELCL000190 | U25 - Lighting Cable Laying | EL | ELCL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 757 | 0 | 10610.EL.LC.LM | 2993.46 | 0
C425134ELCO000180 | U25 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.CO.UN | 81 | 0
C425134ELEL000110 | U25 - Earthing & Lightning Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 953.44 | 0
C425134ELEL000118 | U25 - Lightning Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 476.72 | 0
C425134INCT000010 | U25 - Secondary Cable Trays Installation | IN | INCT2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 0 | 10610.IN.CT.LM | 200 | 0
C425134INFC000000 | U25 - Fiber Optic Gland & Conn./Testing | IN | INFC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 228 | 0 | 10610.IN.CO.UN | 200 | 0
C425134INGC000010 | U25 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 987 | 0 | 10610.IN.CO.UN | 180 | 0
C425134INHU000010 | U25 - Pneumatic Hook Up´s Erection | IN | INHU3 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 612 | 0 | 10780.IN.IN.MH
C425134ININ000000 | U25 - Instruments Installation | IN | ININ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10610.IN.IN.UN | 246 | 0
C425136MEHM000010 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111B) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000030 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111B) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHV000120 | U25 - Inlet Liquid Coalescer (541-F-113C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7200 | 72.7537 | 10610.ME.ER.TN | 180 | 180
C425136MEHV000130 | U25 - Liquid Dehydration Outlet Filter (541-F-115C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10610.ME.ER.TN | 1 | 0
C323136MEPA000050 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201C-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000060 | U23 - (566 CWS) - Oil Separator Installation (566-ME-201C-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323136MEPA000070 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201C-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000090 | U23 - (566 CWS) - Refrigerant Compressor Installation (566-ME-201C-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000130 | U23 - (566 CWS) - Evaporator Installation (566-ME-201B-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000170 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201B-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000180 | U23 - (566 CWS) - Refrigerant compressor Installation (566-ME-201A-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000190 | U23 - (566 CWS) - Evaporator Installation (566-ME-201A-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000200 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201A-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000210 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201A-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000230 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201A-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136METC000070 | U23 - (566 CWS) - Cranes Erection (EOT Crane For Cooling Water Refrigeration Package) 566-EOT-201 | ME | METC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C323137INAI000010 | U23 - (566 CWS) - Analyzers Equipment Installation | IN | INAI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2471 | 0 | 10610.IN.AI.UN | 1 | 0
C323137INCI000080 | U23 - (566 CWS) - Conduits Installation | IN | INCT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1186 | 0 | 10780.IN.IN.MH
C323137INCT000140 | U23 - (566 CWS) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11438 | 0 | 10610.IN.CT.LM | 900 | 0
C323137INCT000150 | U23 - (566 CWS) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6405 | 0 | 10610.IN.CT.LM | 720 | 0
C323137INFC000080 | U23 - (566 CWS) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1098 | 0 | 10610.IN.CO.UN | 540 | 0
C323137INGC000170 | U23 - (566 CWS) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4758 | 0 | 10610.IN.CO.UN | 540 | 0
C323137INHU000160 | U23 - (566 CWS) - Process Hook Up´s Erection | IN | INHU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5033 | 0 | 10780.IN.IN.MH
C4271310000000040 | U24- Hot tapping T502-0001A | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 910 | 0.002202 | 10780.PI.PI.MH
C4271310000000050 | U24- Hot tapping T571-0008A/B | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10780.PI.PI.MH
C427131PIMS000100 | U27-Miscellaneous piping erection activity | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1649 | 0 | 10780.PI.PI.MH
C427131PIPR000110 | U27 - Piping Tie-in Prefabrication - Remaining HB Complex Shutdown | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14259 | 287.7513 | 10610.PI.FB.DI | 3564.81 | 3415.1013
C427131PIRA000010 | U27 - Habshan Complex (HB-2 Unit 27) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000020 | U27 - Habshan Complex (HB-0 Unit 20,21) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000040 | U27 - Habshan Complex (HB-0 Unit 122) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000070 | U27 - Piping Supports Prefabrication | PI | PISU1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4280 | 26.4245 | 10610.PI.PU.TN | 16.46 | 21.4273
C427131PIRA000070 | U27 - Piping Supports Prefabrication | PI | PISU1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4280 | 26.4245 | 10610.PI.PU.TN | 16.46 | 21.4273
C427131PIRA000090 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 2.8763 | 10610.PI.PR.DI | 156.21 | 156.21
C427131PIRA000100 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000101 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000120 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Approximate length 700 M A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000141 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Approximate length 700 M B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000170 | U27 - Piping Erection on Sleepers Part-3 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000180 | U27 - Piping Erection on Sleepers Part-4 -(430 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PISU000080 | U27 - Piping Tie-ins Supports Erection for Unit 122 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 324 | 0.15507 | 10610.PI.SU.TN | 0.72 | 0.72
C427131PISU000090 | U27 - Piping Tie-ins for Unit 22 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9350 | 129.1486 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000110 | U27 - Piping Tie-ins for Unit 20 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11050 | 0 | 10610.PI.TI.DI | 280.05 | 0
C323137ININ000081 | U23 - (566 CWS) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3660 | 0 | 10610.IN.IN.UN | 460 | 0
C323137MEMC000080 | U23 - (566 CWS) - Miscellaneous Instrumentation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3660 | 0 | 10780.IN.IN.MH
C323CIOT000000010 | U23 - (567 UPW) - Valve Pit | CI | CIPS1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 454 | 0.0098873 | 10610.CI.CO.M3 | 6.48 | 0
C323CIOT000000030 | U23 - (567 UPW) - Pipebridge Foundations Execution (567-PB-101) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10520 | 163.4987 | 10610.CI.CO.M3 | 175.34 | 175.34
C4240PRPRPL000110 | U24 - Punch List | PR | PRPL | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7325 | 0 | 10780.PR.PR.MH
C424131CIEQ000010 | U24- Civil Revamp of Process Structure ( Unit 522)- 522-Process Str A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11220 | 185.9739 | 10780.CI.CI.MH
C424131CIPR100000 | U25- Civil Revamp of Piperack ( Unit 540)- 540-C1-PR (Aprox. length =340m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25255 | 942.2391 | 10780.CI.CI.MH
C424131CIPR100080 | U10- Civil Revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part A | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.CI.CO.M3 | 6.86 | 0
C424131CIPR100110 | U23- Civil Revamp of Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =160m) Excluding Module - Part A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 281 | 0.10592 | 10780.CI.CI.MH
C424131CIPR100130 | U22- Civil Revamp of Piperack ( Unit 571)- 571-F1P13 (Approximate length = 40m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 14020 | 32.6674 | 10780.CI.CI.MH
C424131CIPR100160 | U22- Civil Revamp of Piperack ( Unit 571)- 571-F1P14 (Approximate length = 40m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 701 | 0.72594 | 10780.CI.CI.MH
C424131CIPR100190 | U25- Civil Revamp of Piperack ( Unit 541)- 541-C2/C3-PR (Aprox. length =280m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2241 | 6.9806 | 10780.CI.CI.MH
C424131CIPR100250 | U23- Civil Revamp of Piperack ( Unit 577)- 577-PR-E2-P18 (Aprox. length =24m) | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4908 | 32.3716 | 10780.CI.CI.MH
C424131PIPR000090 | U24 - Piping Spools Prefabrication for Modified Structure | PI | PIPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31460 | 1232.1348 | 10610.PI.FB.DI | 7865.03 | 6487.7214
C424131PIRA000090 | U24 - Piping Tie-Ins Pre-Shutdown Spools Erection - H5 Shutdowns | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 2.6432 | 10610.PI.TI.DI | 367.16 | 293.7317
C424131PIRA000100 | U24- Piping Erection on Existing Piperack ( Unit 562)- 562-PR-012A (Aprox. length =60m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000120 | U24- Piping Erection on Existing Piperack ( Unit 561)- 561-PR-20 (Aprox. length =174m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000130 | U24- Piping Erection on Existing Piperack ( Unit 521)- 521-PR-I-1 (Aprox. length =32m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C427131PISU000120 | U27 - Piping Tie-ins for Unit 122 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20400 | 614.7899 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000130 | U27 - Piping Tie-ins for Unit 27 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6800 | 68.31 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000140 | U27 - Piping Tie-ins for Unit 113 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29750 | 1307.4959 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000140 | U27 - Piping Tie-ins for Unit 113 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29750 | 1307.4959 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PRRE000100 | U27 - Piping Reinstatement | PR | PRRE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14847 | 0 | 10610.PR.RE.DI | 24828 | 0
C427132CIGR000110 | U27 - Grounding Network Execution | CI | CIGR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4752 | 0 | 10610.CI.GR.LM | 7920 | 0
C427132CIMS000350 | U27-Miscellaneous Piperack Execution | CI | CIMF | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35 | 6.5149e-05 | 10610.CI.CO.M3 | 0.5 | 0
C427132CIPR000001 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (App length 800 M-Part B | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7010 | 72.5943 | 10780.CI.CI.MH
C427132CIPR000031 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Appr length 700 M-Part B | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6134 | 44.4676 | 10780.CI.CI.MH
C427132CIPR000040 | U27- Civil Revamp of Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5056 | 0 | 10610.CI.CO.M3 | 84.26 | 0
C427132CIPR000360 | U27 - Piperack PR-106 A/B Foundations Execution (40.375 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 245 | 0 | 10780.CI.CI.MH
C427132CIPT000081 | U27 - Miscellaneous Supports & Sleeper Foundations Part-1 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000101 | U27 - Miscellaneous Supports & Sleeper Foundations Part-3 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIPT000111 | U27 - Miscellaneous Supports & Sleeper Foundations Part-4 -(215 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIUG000010 | U27 - Demolition, re-routing/re-installation of roads (including new duct banks for re-routed cables) and paving | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9100 | 122.3346 | 10780.SP.SP.MH
C427132CIUG000030 | U27 - Demolition, re-routing/re-installation of closed drain | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1633 | 3.9395 | 10610.SP.SP.M3 | 116.67 | 116.67
C427132STPR000000 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (App length 800 M-Part A | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 76 | 0.0063568 | 10610.ST.PR.TN | 1.44 | 1.0817
C427132STPR000001 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (App length 800 M-Part B | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 76 | 0.003957 | 10610.ST.PR.TN | 1.44 | 0.651
C424131PIRA000150 | U24- Piping Erection on Existing Process Structure ( Unit 521)- 521-Process Str A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000160 | U24- Piping Erection on Existing Process Structure ( Unit 522)- 522-Process Str A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000170 | U24- Piping Erection on Existing Piperack ( Unit 510)- 510-PR-I-2 to 7 (Aprox. length =211m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000180 | U24- Piping Erection on Existing Piperack ( Unit 545)- 545-PR-007/008/009 (Aprox. length =94m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000190 | U24- Piping Erection on Existing Piperack ( Unit 549)- (549-P-023) (Approximate length =40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000210 | U25- Piping Erection on Existing Piperack ( Unit 541)- 541-C2-PR (Aprox. length =280m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0.73576 | 10610.PI.PR.DI | 189.92 | 28.4899
C424131PIRA000250 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =320m) Excluding Module E2P18 | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000270 | U15- Piping Erection on Existing Piperack ( Unit 550/551/552/553)-550/551/552/553-I-001 (E-W) (Approx length=800m) – Int | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000280 | U24- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-012 in Unit 530 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 3.0121 | 10610.PI.PR.DI | 189.92 | 132.9402
C424131PIRA000290 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-F1P13 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000310 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PISU000030 | U24 - Piping Tie-ins Supports Prefabrication | PI | PISU1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9659 | 133.9423 | 10610.PI.PU.TN | 37.15 | 74.1802
C424131PISU000050 | U24 - Piping Tie-ins Supports erection for Unit 540 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 255 | 0.096182 | 10610.PI.SU.TN | 0.57 | 0.57
C424131PISU000200 | U24 - Piping Supports erection for revamped H-5 Area | PI | PISU2 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10435 | 0 | 10610.PI.SU.TN | 23.19 | 0
C424131PISU000240 | U24 - Piping Tie-ins Supports erection for Unit 553 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 372 | 0.20446 | 10610.PI.SU.TN | 0.83 | 0.83
C424131PISU000240 | U24 - Piping Tie-ins Supports erection for Unit 553 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 372 | 0.20446 | 10610.PI.SU.TN | 0.83 | 0.83
C424131PISU000290 | U24 - Piping Tie-ins for Unit 530 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7650 | 86.4548 | 10610.PI.TI.DI | 367.16 | 367.16
C427132STPR000011 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Appr length 800 Me-Part B | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2438 | 3.3806 | 10780.ST.ST.MH
C427132STPR000040 | U27- Structure revamp of Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 302 | 0 | 10610.ST.PR.TN | 5.69 | 0
C427132STPR000200 | U27 - Piperack PR-106 A/B Erection (40.375 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1795 | 0 | 10610.ST.PR.TN | 33.86 | 0
C427132STPR000240 | U27 - Piperack PR-108 Erection (28 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 928 | 0 | 10610.ST.PR.TN | 17.5 | 0
C427133PAFP000130 | U27 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10610.PA.FP.M2 | 168 | 0
C427133PAPP000120 | U27 - Piping SandBl. & Priming | PA | PAPP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2634 | 9.9227 | 10610.PA.PP.M2 | 1317 | 1316.7429
C427133PASP000130 | U27 - Piping Supports SandBl. & Priming | PA | PASP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8400 | 86.0076 | 10610.PA.SU.TN | 0 | 0
C427133PAST000120 | U27 - Steel Structure Painting Touch Up | PA | PAST | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10260 | 0 | 10780.PA.PA.MH
C427136MEMC000700 | Existing 2nd Stage KO drum (44-V-302) internal modfication works | ME | MEIN | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 472 | 0.32912 | 10780.ME.ME.MH
C427137INCO000140 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD) at Unit 20 IES-01 | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10780.IN.IN.MH
C427PITI000000060 | Tie-in Pipe support foundations for Unit 96 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C5131PEDW00000020 | U33 - Pipeline Dewatering, Swabbing and Drying | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16744 | 0 | 10780.PE.PE.MH
C5310PRPEHT000030 | U31.3 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 544 | 0 | 10610.PR.HT.DI | 34800 | 0
C5310PRPEHT000050 | U31.1 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 346 | 0 | 10610.PR.HT.DI | 26172 | 0
C5310PRPEHT000060 | U31.1 - Pipeline Dewatering, Swabbing and Drying | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 242 | 0 | 10780.PE.PE.MH
C5310PRPEHT000070 | U31.3 - Pipeline Dewatering, Swabbing and Drying | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 381 | 0 | 10780.PE.PE.MH
C5310PRPEHT000110 | U31.2 - Intelligent Pigging | PE | PEHT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 93 | 0 | 10780.PE.PE.MH
C5310PRPEPL000040 | U31.2 - Pipeline Punch List | PR | PRPL | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6 | 0 | 10780.PR.PR.MH
C5310PRPEWT000050 | U31.1 - Pipeline Walkthrough | PR | PRWT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 66 | 0 | 10780.PR.PR.MH
C531131PECP000010 | U31.3 - Permanent Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1356 | 0 | 10780.PE.PE.MH
C424131PISU000290 | U24 - Piping Tie-ins for Unit 530 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7650 | 86.4548 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000360 | U24 - Piping Tie-ins for Unit 549 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13600 | 273.24 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000430 | U24 - Piping Tie-ins for Unit 567 | PI | PITI2 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2550 | 9.6061 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000450 | U24 - Piping Tie-ins for Unit 575 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5950 | 26.1499 | 10610.PI.TI.DI | 367.16 | 183.58
C424131PISU000450 | U24 - Piping Tie-ins for Unit 575 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5950 | 26.1499 | 10610.PI.TI.DI | 367.16 | 183.58
C424131PITI000010 | U24 - Habshan 5 - Shutdown Works Others | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 0 | 10610.PI.TI.DI | 367.16 | 0
C424131PITI000040 | U24 - Habshan 5 - Shutdown Works Area 3 Flares, Blowdowns & NGL storage | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4250 | 13.8589 | 10610.PI.TI.DI | 367.16 | 188.1695
C424131PRFL000090 | U24 - Piping Flushing/Steam Blowing | PR | PRFL | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 16126 | 0 | 10610.PR.FL.DI | 28996 | 0
C424131PRRE000060 | U24 - Piping Reinstatement | PR | PRRE | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 64506 | 0 | 10610.PR.RE.DI | 28996 | 0
C424131STEQ000000 | U24- Structure revamp of Process Structure ( Unit 521)- 521-Process Str A | ST | STEQ | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 245 | 0.035947 | 10610.ST.ER.TN | 4.63 | 3.7813
C424131STPR100000 | U24- Structure revamp of Piperack ( Unit 562)- 562-PR-012A (Aprox. length =60m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1336 | 0.01318 | 10610.ST.PR.TN | 25.2 | 0
C424131STPR100020 | U24- Structure revamp of Piperack ( Unit 521)- 521-PR-I-1 (Aprox. length =32m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 738 | 0.43036 | 10610.ST.PR.TN | 13.92 | 6.9602
C424131STPR100110 | U24- Structure revamp of Piperack ( Unit 522)- 522-PR-I-1 (Aprox. length =32m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 747 | 0 | 10610.ST.PR.TN | 14.1 | 0
C424131STPR100130 | U22- Structure revamp of Piperack ( Unit 571)- 571-F1P13 (Approximate length = 40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3339 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100140 | U10- Structure revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part B | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4911 | 10.1362 | 10610.ST.PR.TN | 92.66 | 25.015
C424131STPR100160 | U23-Structure revamp of Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =160m) Excluding Module - Part A | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2491 | 2.2373 | 10610.ST.PR.TN | 0 | 0
C424131STPR100180 | U22- Structure revamp of Piperack ( Unit 571)- 571-F1P14 (Approximate length = 40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1149 | 1.5606 | 10610.ST.PR.TN | 21.68 | 17.3439
C424131STPR100220 | U23- Structure revamp of Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =400m) – Interface with CRI P - Part-B | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2014 | 0 | 10610.ST.PR.TN | 0 | 0
C531131PEPA000020 | U31.3 - Field Joint Coating | PE | PEPA | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3988 | 0.97022 | 10610.PE.PA.UN | 725 | 29.9425
C531131PETI000070 | U31.1 - Installation of Pipeline Markers | PE | PETI | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3501 | 0 | 10780.PE.PE.MH
C531131PEUG000010 | U31.2 - Pipeline Welding | PE | PEUG | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20213 | 458.5839 | 10610.PE.UG.LM | 8760 | 6563.852
C531132PEBK000030 | U31.1 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3079 | 0 | 10610.PE.BK.M3 | 8890 | 0
C531132PEBK000080 | U31.2 - Construction of Maintenance Road | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 937 | 0 | 10780.PE.PE.MH
C531132PECR000020 | U31.1 - Open Cut Crossing - Above ground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PECU000080 | U31.2 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8800 | 0.020592 | 10610.PE.CO.LM | 22 | 0
C531132PECU000090 | U31.3 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8800 | 0 | 10610.PE.CO.LM | 22 | 0
C531132PECU00010 | U31.3 - NDRC Crossing (KP 0+460 to KP 0+980) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0.063261 | 10610.PE.CO.LM | 1 | 0.59
C531132PECU300120 | U31.1 - NDRC Crossing (KP 5+760 to KP 6+160) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PEFO000009 | U31.3 - Trial Pits (64nos) | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1065 | 1.6266 | 10780.PE.PE.MH
C531132PEFO000010 | U31.3 - Open Cut Crossing - Above ground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PEFO000080 | U31.3 - NDRC Crossing (KP 2+400 to KP 2+800) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PERD000010 | U31.1 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 4.2546 | 10610.PE.CO.LM | 12 | 1.5
C531132PERD000080 | U31.2 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4800 | 4.2546 | 10610.PE.CO.LM | 12 | 1.5
C531132PEUG000010 | U31.2 - Pipe Hauling & Stringing | PE | PEUG | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 15288 | 299.9208 | 10780.PE.PE.MH
C531132PEUG000070 | U31.3 - Cold Field Bending | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6633 | 14.7218 | 10780.PE.PE.MH
C531132PEUG000090 | U31.1 - Cold Field Bending | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3046 | 7.9247 | 10780.PE.PE.MH
C531137INFC000020 | U31.3 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137PEFO000010 | U31.2 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531PECP000000270 | U16 - NGL Surge Sphere 545-V-201B - Erection of Stub End Piece With Lower Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10019 | 148.2921 | 10780.ME.ME.MH
C220134ELEQ000890 | U20 - SS-501 - LV Switchgear 580-EE-0105 Modification (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELTI000100 | U20 - SS-502 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8608 | 0 | 10780.EL.EL.MH
C220134ELTI000320 | U20 - SS-516 - Electrical Cable Trays Install for Transformer #B (Pre-Shutdown) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 85 | 0.0075636 | 10780.EL.EL.MH
C220134ELTI0003200 | U20 - SS-516 - Electrical Cable Trays Install for Transformer #A (Pre-Shutdown) | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 85 | 0.0052091 | 10780.EL.EL.MH
C220134ELTI000390 | U20 - IES-500 - Electrical Cable Trays Install | EL | ELTI | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.EL.EL.MH
C220134PRSS0015 | U20 - SS-520 - 11kV Switchgear precommissioning (2 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1071 | 0 | 10780.PR.PR.MH
C220134PRSS0030 | U20 - SS-520 - Variable fecuency driver precommissioning (22 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 749 | 0 | 10780.PR.PR.MH
C220134PRSS0065 | U20 - SS-521 - Variable fecuency driver precommissioning (11 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 534 | 0 | 10780.PR.PR.MH
C220134PRSS0085 | U20 - SS-522 - 11kV Switchgear precommissioning (1 units) | PR | PRSS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 611 | 0 | 10780.PR.PR.MH
C220137INCC000060 | U20 - IES-16 - System Cabinets & Consoles Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9739 | 140.1184 | 10780.IN.IN.MH
C220137INCC000100 | U20 - IES-501 - System Cabinets & Consoles Installation (Pre-Shutdown) / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4624 | 0 | 10780.IN.IN.MH
C220137INCC000110 | U20 - IES-500 - System Cabinets & Consoles Installation / Modifications | IN | INCC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2973 | 0 | 10780.IN.IN.MH
C220137INCC000270 | U20 - IES-507 - DCS/VMS/ESD Cabinets Installation (Pre-Shutdown) | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4216 | 0 | 10780.IN.IN.MH
C220137INCC000420 | U20 - TLC - DCS/VMS/ESD Cabinets Installation / Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INCO000240 | U20 - IES-504 - Communication System Installation / Modifications (Pre-Shutdown) | IN | INCO | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1845 | 0 | 10780.IN.IN.MH
C220137INCT000020 | U20 - IES-508 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2361 | 0 | 10780.IN.IN.MH
C220137INCT000080 | U20 - IES-502 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 0 | 10780.IN.IN.MH
C220137INCT000200 | U20 - IES-15 - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2558 | 0 | 10780.IN.IN.MH
C220137INCT000270 | U20 - CR-541 & MAQTA - Instrument Trays Installation | IN | INCT1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INDC000100 | U20 - IES-501 - DCS/VMS/ESD Cabinets Installation (Pre-Shutdown) / Modifications | IN | INDC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 0 | 10780.IN.IN.MH
C220BUTR000000030 | U20 - SS-516 - Transf. Column & Walls Yard Concrete Structure (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43014 | 2733.2922 | 10610.BU.CO.M3 | 754 | 754.0023
C220ELEQ000000020 | U20 - SS-516 - Installation of New 220/138 Kv 80/320 MVA Transformer #B (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0.00017199 | 10780.EL.EL.MH
C321131MEMC00020 | U21 - Miscellaneous Electrical (562) | EL | ELEQ2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1437 | 0 | 10780.EL.EL.MH
C321131NITR000015 | U21 - Nitrogen Purging & Inerting (Unit 565) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1576 | 0 | 10780.PR.PR.MH
C321131PIBB000070 | U21 - Big Bore Piping A/Equip. Erection (580) | PI | PIBB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38707 | 0 | 10610.PI.BB.DI | 3870.74 | 0
C321131PIBB000220 | U21 - Big Bore Piping A/Equip. Erection (562) | PI | PIBB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40682 | 0 | 10610.PI.BB.DI | 4068.19 | 0
C321131PIPR000020 | U21 - Piping Prefabrication (562) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 74345 | 4365.15 | 10610.PI.FB.DI | 18586.26 | 10282.0112
C321131PIRA000020 | U21 - Piping Erection on Rack (562) | PI | PIRA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 151125 | 0 | 10610.PI.PR.DI | 16791.66 | 0
C321131PIRA000070 | U21 - Piping Erection on Rack (580) | PI | PIRA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 47362 | 0 | 10610.PI.PR.DI | 5262.39 | 0
C321131PISB000020 | U21 - Small Bore Piping A/Equip. Erection (562) | PI | PISB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13316 | 0 | 10610.PI.SB.DI | 1210.5 | 0
C321131PISB000071 | U21 - Small Bore Piping A/Equip. Erection (580) | PI | PISB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9871 | 0 | 10610.PI.SB.DI | 897.35 | 0
C321131PIUG000020 | U21 - Piping Erection UG (562) | PI | PIUG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 78 | 0 | 10610.PI.UG.DI | 52 | 0
C321131PIUG000080 | U21 - Piping Erection UG (580) | PI | PIUG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.PI.UG.DI | 3195 | 0
C321131PRFL000070 | U21 - Piping Flushing/Steam Blowing (562) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3524 | 0 | 10610.PR.FL.DI | 40876 | 0
C321131PRFL000240 | U21 - Lube Oil Flushing for Gas Turbine (Unit 580) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 818 | 0 | 10780.PR.PR.MH
C321131PRFL000250 | U21 - Lube Oil Flushing for Compressors (Unit 562) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2936 | 0 | 10780.PR.PR.MH
C321131PRRE000020 | U21 - Piping Reinstatement (562) | PR | PRRE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 25840 | 0 | 10610.PR.RE.DI | 40876 | 0
C321131PRRE000040 | U21 - Piping Reinstatement (580) | PR | PRRE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20121 | 0 | 10610.PR.RE.DI | 18434 | 0
C321132CIDB000025 | U21 - Duct Banks Precast Fabrication (562) | CI | CIDB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 63769 | 687.848 | 10780.CI.CI.MH
C321132CIDB000035 | U21 - Duct Banks Precast Installation (562) | CI | CIDB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17134 | 0 | 10610.CI.CO.M3 | 342.68 | 0
C424131STPR100230 | U23- Structure revamp of Piperack ( Unit 577)- 577-PR-E2-P18 (Aprox. length =24m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2858 | 0 | 10610.ST.PR.TN | 53.92 | 0
C424133PAFP000100 | U24 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 118 | 0 | 10610.PA.FP.M2 | 492 | 0
C424133PASP000100 | U24 - Piping Supports SandBl. & Priming | PA | PASP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37620 | 1663.387 | 10610.PA.SU.TN | 0 | 0
C424133PASP000100 | U24 - Piping Supports SandBl. & Priming | PA | PASP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 37620 | 1663.387 | 10610.PA.SU.TN | 0 | 0
C424PITI000000020 | Tie-in Pipe Support foundations for Unit 541 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 245 | 0.088674 | 10780.CI.CI.MH
C424PITI000000030 | Tie-in Pipe Support foundations for Unit 521 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1572 | 3.6507 | 10610.CI.CO.M3 | 26.2 | 26.2
C424PITI000000060 | Tie-in Pipe Support foundations for Unit 549 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C424PITI000000070 | Tie-in Pipe Support foundations for Unit 551 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C425131PISB000000 | U25 - Small Bore Piping A/Equip. Erection (540-V-144, 540-F-113C / 15C, 540-P-111A/B/C) | PI | PISB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5557 | 0 | 10610.PI.SB.DI | 505.2 | 0
C425131PISB000010 | U25 - Small Bore Piping A/Equip. Erection (541-V-144, 541-F-113C / 15C, 541-P-111A/B/C) | PI | PISB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5557 | 0 | 10610.PI.SB.DI | 505.2 | 0
C425131PISU000290 | U25 - Piping Supports Erection | PI | PISU2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6306 | 0 | 10610.PI.SU.TN | 14.01 | 0
C425131PRFL000140 | U25 - Piping Flushing/Blowing | PR | PRFL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2036 | 0 | 10610.PR.FL.DI | 24116 | 0
C425131PRHT000293 | U25 - Piping Hydrotesting | PR | PRHT | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10181 | 0 | 10610.PR.HT.DI | 24116 | 0
C425131PRRE000110 | U25 - Piping Reinstatement | PR | PRRE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8145 | 0 | 10610.PR.RE.DI | 24116 | 0
C425132CISF000060 | U25 - Platform Structure/Misc Platforms & Crossovers Foundations Execution | CI | CISF | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1349 | 2.6882 | 10610.CI.CO.M3 | 19.27 | 19.27
C425132CISF000080 | U25 - Misc. Platforms, Staircase, Ladders, Floors & Crossovers - Foundation Execution (540/541-STR-V144) | CI | CISF | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41309 | 2520.8773 | 10610.CI.CO.M3 | 826.17 | 826.1701
C425132CIUG000010 | U25-Rerouting of firewater services | CI | CIUG1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10780.CI.CI.MH
C425132CIUG000020 | U25-Rerouting Closed drain services | CI | CIUG1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 0.87881 | 10780.CI.CI.MH
C425132CIVE000060 | U25 - Molecular Sieve Liquid Adsorber (540-V-144) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 753 | 0.83786 | 10610.CI.CO.M3 | 10.76 | 10.76
C425132CIVE000240 | U25 - Inlet Liquid Coalescer (541-F-113C) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C531PECP000000320 | U16 - NGL Surge Sphere 545-V-201B - Welding Top Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11450 | 0 | 10780.ME.ME.MH
C531PECP000000380 | U16 - NGL Surge Sphere 545-V-201B - NDT Works (post PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4580 | 0 | 10780.ME.ME.MH
C531PECP000000410 | U16 - NGL Surge Sphere 545-V-201B - Ground Assembly & Welding of Top Polar With Crown | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12882 | 35.5459 | 10780.ME.ME.MH
C531PECP000000420 | U16 - NGL Surge Sphere 545-V-201B - Erection & Welding Bottom Polar Plate | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9160 | 60.7389 | 10780.ME.ME.MH
C531PECP000000520 | U16 - NGL Surge Sphere 545-V-201A - Erection of Top Crown Assembly With Top Polar & Welding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7434 | 0 | 10780.ME.ME.MH
C531PECP000000530 | U16 - NGL Surge Sphere 545-V-201A - Erection of Stairway and Platform | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8921 | 0 | 10780.ME.ME.MH
C531PECP000000540 | U16 - NGL Surge Sphere 545-V-201A - Post Weld Heat Treatment ( PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1784 | 0 | 10780.ME.ME.MH
C531PECP000000610 | U16 - NGL Surge Sphere 545-V-201B - Erection of Stairway and Platform | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10019 | 0 | 10780.ME.ME.MH
C531PECP000000650 | U16 - NGL Surge Sphere 545-V-201A - Sphere Calibration | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2082 | 0 | 10780.ME.ME.MH
C5320PRLT00000080 | U32 - Loop Testing | PR | PRLT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 174 | 0 | 10780.PR.PR.MH
C5320PRPEHT000020 | U32 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 270 | 0 | 10610.PR.HT.DI | 16576 | 0
C532131PEPA000010 | U32 - Field Joint Coating | PE | PEPA | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1628 | 2.2224 | 10610.PE.PA.UN | 296 | 168.0096
C532131PETI000020 | U32 - Installation of Pipeline Markers | PE | PETI | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1895 | 0 | 10780.PE.PE.MH
C532132PEBK000030 | U32 - Berm Preparation | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2760 | 0 | 10610.PE.BK.M3 | 1000 | 0
C532132PECU00004 | U32 - Trial Pits (19nos) | PE | PETR | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 389 | 0.22341 | 10780.PE.PE.MH
C532132PECU000040 | U32 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2800 | 1.6446 | 10610.PE.CO.LM | 7 | 0.99001
C532132PETR000010 | U32 - Trench Excavation | PE | PETR | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 1.7017 | 10780.PE.PE.MH
C532132PETR000020 | U32 - Pre-Construction Survey and Stake-out | PE | PETR | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1096 | 1.775 | 10780.PE.PE.MH
C532PETR000000020 | U32 - Construction of Right of Way (ROW) | PE | PETR | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1127 | 1.877 | 10780.PE.PE.MH
C533131PIBB000070 | U33 - BVS-02 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1511 | 0 | 10610.PI.SU.TN | 3.36 | 0
C220137INFG000020 | U20 - IES-500 Fire Fighting Equipments Installation | IN | INFS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3973 | 0 | 10780.IN.IN.MH
C220137INFG000270 | U20 - CR-541 & MAQTA - Fire & Gas System Installation / Modifications | IN | INFG | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INGC000020 | U20 - IES-508 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2361 | 0 | 10780.IN.IN.MH
C220137INGC000210 | U20 - IES-504 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 664 | 0 | 10780.IN.IN.MH
C220137INGC000230 | U20 - IES-16 - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5016 | 0 | 10780.IN.IN.MH
C220137INGC000290 | U20 - CR-541 & MAQTA - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3689 | 0 | 10780.IN.IN.MH
C220137INGC000700 | U20 - TLC - Instrument Multicable Gland & Connection | IN | INGC | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2793 | 0 | 10780.IN.IN.MH
C220137INML000070 | U20 - IES-304 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8263 | 0 | 10780.IN.IN.MH
C220137INML000140 | U20 - IES-501 - Instrument Multicable Laying | IN | INML | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3443 | 1.2259 | 10780.IN.IN.MH
C220137PRSS000040 | U20 - IES-514 - SAT Testing | PR | PRST | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2508 | 0 | 10780.PR.PR.MH
C220137PRST000010 | U20 - NMCB - DCS/VMS/ESD SAT Testing | PR | PRST | 20 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.PR.PR.MH
C220BUTR000000010 | U20 - SS-516 - Transf. Yard Foundations #A (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14372 | 305.1412 | 10610.BU.CO.M3 | 175 | 175
C220ELEQ000000025 | U20 - SS-516 - Installation of New 220/138 Kv 80/320 MVA Transformer #A (Pre-Shutdown) | EL | ELEQ1 | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11 | 0.00017199 | 10780.EL.EL.MH
C321131ISEQ000020 | U21 - Equipment Insulation (562) | IS | ISEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 647 | 0 | 10610.IS.EQ.M2 | 410 | 0
C321131ISPI000020 | U21 - Piping Insulation (562) | IS | ISPI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17881 | 0 | 10780.IS.IS.MH
C321131MEMC00010 | U21 - Miscellaneous Piping (562) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2940 | 0 | 10780.PI.PI.MH
C321131NITR000010 | U21 - Nitrogen Leak Test (Unit 562) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1515 | 0 | 10780.PR.PR.MH
C321131PIBB000220 | U21 - Big Bore Piping A/Equip. Erection (562) | PI | PIBB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40682 | 0 | 10610.PI.BB.DI | 4068.19 | 0
C321131PIPR000020 | U21 - Piping Prefabrication (562) | PI | PIPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 74345 | 4365.15 | 10610.PI.FB.DI | 18586.26 | 10282.0112
C321131PISB000020 | U21 - Small Bore Piping A/Equip. Erection (562) | PI | PISB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13316 | 0 | 10610.PI.SB.DI | 1210.5 | 0
C321131PISU000140 | U21 - Piping Supports Erection (580) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12408 | 0 | 10610.PI.SU.TN | 27.57 | 0
C321132CIDM000030 | U21 - Manholes & Catchbasins Installation (Precast) (562) | CI | CIDM1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9977 | 2.941 | 10610.CI.CO.M3 | 166.28 | 0
C321132CIGR000020 | U21 - Grounding Network Execution (562) | CI | CIGR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 763 | 0 | 10610.CI.GR.LM | 1271.98 | 0
C321132CIMF000060 | U21 - Miscellaneous Foundations Execution (580) | CI | CIMF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 54294 | 0 | 10610.CI.CO.M3 | 1085.88 | 0
C321132CIPE000040 | U21 - Gas Turbine Generator Package 580-ME-101J Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11146 | 7.3412 | 10610.CI.CO.M3 | 222.92 | 0
C321132CIPE000050 | U21 - Waste Heat Boiler 562-B-101J Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11500 | 0 | 10610.CI.CO.M3 | 230 | 0
C321132CIPE000060 | U21 - Fire Fighting Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 889 | 0 | 10610.CI.CO.M3 | 12.7 | 0
C321132CIPE000060 | U21 - Fire Fighting Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 889 | 0 | 10610.CI.CO.M3 | 12.7 | 0
C321132CIPE000090 | U21 - Fuel Gas Skid A Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1272 | 0 | 10610.CI.CO.M3 | 21.2 | 0
C321132CIPE000100 | U21 - Fuel Gas Skid B Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1272 | 0 | 10610.CI.CO.M3 | 21.2 | 0
C321132CIPE000110 | U21 - Waste Heat Boiler Scale Inhibitor Dosing Package 562-ME-308 Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1874 | 0 | 10610.CI.CO.M3 | 31.24 | 0
C321132CIPE000110 | U21 - Waste Heat Boiler Scale Inhibitor Dosing Package 562-ME-308 Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1874 | 0 | 10610.CI.CO.M3 | 31.24 | 0
C321132CIPE000120 | U21 - Seal Air Fan Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 348 | 0 | 10610.CI.CO.M3 | 4.97 | 0
C321132CIPE000130 | U21 - Cooling Air Fan Skid Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 348 | 0 | 10610.CI.CO.M3 | 4.97 | 0
C321132CIPR000010 | U21 - 562-PR-101 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10214 | 154.1257 | 10610.CI.CO.M3 | 170.24 | 170.24
C321132CIPR000020 | U21 - 562-PR-102 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8088 | 51.943 | 10610.CI.CO.M3 | 134.8 | 60.66
C321132CIPR000020 | U21 - 562-PR-102 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8088 | 51.943 | 10610.CI.CO.M3 | 134.8 | 60.66
C321132CIPR000300 | U21 - 580-PR-103 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2903 | 9.1634 | 10610.CI.CO.M3 | 48.38 | 38.51
C321132CIPR000310 | U21 - 580-PR-104 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1978 | 2.785 | 10610.CI.CO.M3 | 32.97 | 15.8915
C321132CIPR000310 | U21 - 580-PR-104 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1978 | 2.785 | 10610.CI.CO.M3 | 32.97 | 15.8915
C425132STMS000130 | U25 - Miscellaneous Platforms and Crossover (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.079441 | 10610.ST.PL.TN | 0 | 0
C425133PASP000130 | U25 - Piping Supports SandBl. & Priming | PA | PASP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 52.4717 | 10610.PA.SU.TN | 0 | 0
C425133PAST000100 | U25 - Steel Structure Painting Touch Up | PA | PAST | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4400 | 0 | 10780.PA.PA.MH
C425134ELCO000190 | U25 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2018 | 0 | 10610.EL.CO.UN | 150 | 0
C425134ELEL000118 | U25 - Lightning Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 476.72 | 0
C425134ELTI000180 | U25 - Lighting Cable Trays Installation | EL | ELTI | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.CT.LM | 136.81 | 0
C425134ELTI000190 | U25 - Electrical Cable Trays Installation | EL | ELTI | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1682 | 0 | 10610.EL.CT.LM | 254.08 | 0
C425134INFO000000 | U25 - Fiber Optic Cable Pulling | IN | INFO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10610.IN.FO.LM | 200 | 0
C425134ININ000001 | U25 - Valve Installation | IN | ININ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10610.IN.IN.UN | 246 | 0
C425134INIP000001 | U25 - Valve Calibration | IN | INIP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 247 | 0 | 10780.IN.IN.MH
C425134INML000000 | U25 - multi Pair Cable Pulling | IN | INML | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2960 | 0 | 10610.IN.MC.LM | 9232.36 | 0
C425136MEHM000010 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111B) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000020 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111A) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000030 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111B) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000240 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111C) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.079774 | 10610.ME.ER.TN | 5 | 3.46
C425136MEHV000000 | U25 - Molecular Sieve Liquid Adsorber (541-V-144) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.14371 | 10610.ME.ER.TN | 8 | 8
C425136MEHV000080 | U25 - Inlet Liquid Coalescer (540-F-113C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40 | 0.0022455 | 10610.ME.ER.TN | 1 | 1
C425136MEHV000200 | U25 - Molecular Sieve Liquid Adsorber (540-V-144) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.14371 | 10610.ME.ER.TN | 8 | 8
C425136MEMC000130 | U25-Miscellaneous Mechanical Activities | ME | MEMC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 373 | 0 | 10780.ME.ME.MH
C4270PRPRPL000140 | U27 - Punch List | PR | PRPL | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 652 | 0 | 10780.PR.PR.MH
C533131PIBB000080 | U33 - BVS-02 - Painting of Above Ground Piping & Pipe Supports | PA | PAPP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0.054614 | 10610.PA.PP.M2 | 175 | 46.4032
C533131PIBB000100 | U33 - BVS-01 - Installation of Above Ground Piping | PI | PIBB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19910 | 1.2298 | 10780.PI.PI.MH
C533131PRHT000110 | U33 - BVS-01 - Hydraulic Test / Pneumatic Test | PR | PRHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 0 | 10780.PR.PR.MH
C533132PEBK000110 | U31.1 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3555 | 3.3234 | 10610.PE.BK.M3 | 890 | 158.42
C533132PEBK000111 | U33 - Section 1 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 3584.3753 | 10610.PE.BK.M3 | 569.43 | 227.772
C533132PEBK000113 | U33 - Section 1 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 0 | 10610.PE.BK.M3 | 18936.58 | 0
C533132PEBK000132 | U33 - Section 3 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 0 | 10610.PE.BK.M3 | 302690.16 | 0
C533132PEBK000133 | U33 - Section 3 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 0 | 10610.PE.BK.M3 | 18424.78 | 0
C533132PEBK000141 | U33 - Section 4 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 429.44 | 0
C533132PEBK000143 | U33 - Section 4 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 14281.03 | 0
C533132PEBK000150 | U32 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3795 | 2.3616 | 10610.PE.BK.M3 | 10860 | 1205.46
C533132PECP000121 | U33 - Section 2 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11334 | 0.47444 | 10610.PE.CP.LM | 21747.31 | 0
C533132PECP000131 | U33 - Section 3 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8839 | 0 | 10610.PE.CP.LM | 20179.16 | 0
C533132PECP000141 | U33 - Section 4 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7279 | 0 | 10610.PE.CP.LM | 15640.85 | 0
C533132PECU000110 | U33 - BVS-01 - Grubbing and Clearing | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533132PECU000141 | U33 - Section 4 - NDRC Crossing (5 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1330 | 0 | 10610.PE.CO.LM | 5 | 0
C533132PECU000320 | U33 - BVS-01 - RCC Cable Trench & Duct Bank Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2642 | 0 | 10610.PE.CO.LM | 6.5 | 0
C533132PECU000350 | U33 - BVS-01 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000350 | U33 - BVS-01 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000400 | U33 - BVS-01 - Precasting and Erection of Crash Barriers, Bollards | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 610 | 0 | 10780.PE.PE.MH
C4271310000000010 | Hot Tapping at Unit 96( 2 Nos) | PI | PITT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3640 | 0.02936 | 10780.PI.PI.MH
C4271310000000080 | U24- Hot tapping T582-0001A | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 910 | 0.002202 | 10780.PI.PI.MH
C4271310000000090 | U24- Hot tapping T577-0001A | PI | PITT | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 910 | 0 | 10780.PI.PI.MH
C427131ISPI000140 | U27 - Piping Insulation | IS | ISPI | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3300 | 0 | 10780.IS.IS.MH
C427131PIRA000010 | U27 - Habshan Complex (HB-2 Unit 27) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000040 | U27 - Habshan Complex (HB-0 Unit 122) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000060 | U27- Piping Prefabrication -Habshan complex | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38654 | 1749.4779 | 10610.PI.FB.DI | 9663.48 | 7653.558
C427131PIRA000080 | U27 - Piping Supports Erection | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7407 | 0 | 10610.PI.SU.TN | 16.46 | 0
C427131PIRA000101 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000110 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000111 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000120 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Approximate length 700 M A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000140 | U27- Pipe erection on modified Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000150 | U27 - Piping Erection on Sleepers Part-1 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000160 | U27 - Piping Erection on Sleepers Part-2 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA001150 | U27 - Habshan Complex (H-4 ETB HP Unit 113) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA001150 | U27 - Habshan Complex (H-4 ETB HP Unit 113) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PISU000050 | U27 - Piping Tie-ins Supports Erection for Unit 96 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 93 | 0.012738 | 10610.PI.SU.TN | 0.21 | 0.21
C427131PISU000080 | U27 - Piping Tie-ins Supports Erection for Unit 122 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 324 | 0.15507 | 10610.PI.SU.TN | 0.72 | 0.72
C321132CIPV000020 | U21 - Concrete Paving Execution (562) | CI | CIPV1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6782 | 0 | 10610.CI.PV.M2 | 3767.86 | 0
C321132CIPV000030 | U21 - Stairs & Small Foundations Execution (562) | CI | CISF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1208 | 0 | 10610.CI.CO.M3 | 20.13 | 0
C321132CIPV000160 | U21 - Concrete Paving Execution (580) | CI | CIPV1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17820 | 0 | 10610.CI.PV.M2 | 9899.84 | 0
C321132CIST000030 | U21 - Shelter GTG-GSUT Transformer Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 10.7967 | 10610.CI.CO.M3 | 155.27 | 0
C321132CIST000080 | U21 - STR-101/102/103/104/105/106 Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 891 | 0 | 10610.CI.CO.M3 | 12.73 | 0
C321132CIST000180 | U21 - Platform for Gas Turbine Generator Package 580-ME-101J Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6365 | 0 | 10610.CI.CO.M3 | 106.09 | 0
C321132CIST000190 | U21 - Shelter GTG-GSUT Transformer Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23071 | 0 | 10610.CI.CO.M3 | 461.42 | 0
C321132CIST000190 | U21 - Shelter GTG-GSUT Transformer Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23071 | 0 | 10610.CI.CO.M3 | 461.42 | 0
C321132CIST000210 | U21 - Gas Turbine Lube Oil Cooler Structure Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6365 | 0 | 10610.CI.CO.M3 | 106.09 | 0
C321132CIUG000060 | U21 - UG GRE Pipe Installation (562) (FW) | CI | CIUG2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3360 | 0 | 10780.CI.CI.MH
C321132CIUG000075 | U21 - UG Pipe Installation (562) (OD) | CI | CIUG2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14666 | 0 | 10610.CI.UG.LM | 733.32 | 0
C321132CIUG000080 | U21 - UG Civil Works (562) | CI | CIUG1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22780 | 0 | 10780.CI.CI.MH
C321132FPSS000040 | U21 - Steel Structure Fireproofing (580) | FP | FPSS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 396 | 0 | 10610.FP.ST.M2 | 109.4 | 0
C321132STMS000060 | U21 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (580) | ST | STMS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ST.PL.TN | 5 | 0
C321132STMS000060 | U21 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) (580) | ST | STMS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ST.PL.TN | 5 | 0
C321132STPL000020 | U21 - Platform 562-562-TOS EL. 117000 Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10610.ST.PL.TN | 0 | 0
C321132STPL000030 | U21 - Lube oil Cooler Structure Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 856 | 0 | 10610.ST.PL.TN | 10.7 | 0
C321132STPL000170 | U21 - Platform for Gas Turbine Generator Package 580-ME-101J Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 419 | 0 | 10610.ST.PL.TN | 5.23 | 0
C321132STPL000180 | U21 - Gas Turbine Lube Oil Cooler Structure Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 519 | 0 | 10610.ST.PL.TN | 6.49 | 0
C533132PEHT000141 | U33 - Section 4 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 58608.98 | 0
C533132PEPA000135 | U33 - Section 3 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16811 | 52.0204 | 10610.PE.PA.UN | 2520.49 | 297.4178
C533132PEPA000145 | U33 - Section 4 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10698 | 0 | 10610.PE.PA.UN | 1953.63 | 0
C533132PETR000110 | U33 - Section 1 - Pre-Construction Survey and Stake-out | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6672 | 63.6099 | 10780.PE.PE.MH
C533132PETR000113 | U33 - Section 1 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37129 | 0 | 10610.PE.FO.LM | 85414.45 | 0
C533132PETR000115 | U33 - Section 1 - Construction of Maintenance Road | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22607 | 0 | 10780.PE.PE.MH
C533132PETR000121 | U33 - Section 2 - Pre-Construction Survey and Stake-out | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6967 | 71.7047 | 10780.PE.PE.MH
C533132PETR000123 | U33 - Section 2 - Trench Excavation | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9322 | 72.354 | 10780.PE.PE.MH
C533132PETR000124 | U33 - Section 2 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38544 | 0 | 10610.PE.FO.LM | 1090 | 0
C533132PETR000125 | U33 - Section 2 - ROW Clean-up & Restoration | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 46721 | 0 | 10780.PE.PE.MH
C533132PETR000135 | U33 - Section 3 - ROW Clean-up & Restoration | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31649 | 0 | 10780.PE.PE.MH
C533132PETR000146 | U33 - Section 4 - Construction of Maintenance Road | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 22607 | 0 | 10780.PE.PE.MH
C533132PEUG000116 | U33 - Section 1 - Tie-In Welding incl NDT, Joint Coating,Backfilling & Marker installation | PE | PETI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26446 | 14.5681 | 10780.PE.PE.MH
C533132PEUG000132 | U33 - Section 3 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47489 | 2500.4176 | 10610.PE.UG.LM | 30240 | 22056.1851
C533132PEUG000134 | U33 - Section 3 - Pipeline Lowering | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35401 | 0 | 10780.PE.PE.MH
C533132PEUG000136 | U33 - Section 3 - Tie-In Welding incl NDT, Joint Coating,Backfilling & Marker installation | PE | PETI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18559 | 0 | 10780.PE.PE.MH
C533132PEUG000144 | U33 - Section 4 - Pipeline Lowering | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29357 | 0 | 10780.PE.PE.MH
C533132PIBB000020 | U33 - BVS-01 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1201 | 0 | 10610.PI.SU.TN | 2.67 | 0
C533133PIBB000020 | U33 - BVS-01 - Painting of Above Ground Piping & Pipe Supports | PA | PAPP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 877 | 0 | 10780.PA.PA.MH
C533134ELCL000020 | U33 - BVS-01 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533134ELEL000020 | U33 - BVS-01 - Installation of Field Equipment & Plant Lighting - (Lighting poles and fixtures) Installation - (Lighting | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134ELEQ000020 | U33 - BVS-01 - Installation of Solar Power System | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134ELEQ000080 | U33 - BVS-01 - Installation of Field Instruments | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533134PIBB000100 | U33 - BVS-02 - Installartion of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C533134PIBB000160 | U33 - BVS-03 - Installation of Passive Cooling Shelter | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533134PIBB000200 | U33 - BVS-03 - Installation of Solar Power System | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134PIBB000230 | U33 - BVS-03 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533137INFG000060 | U33 - BVS-01 - Installation of Fire Point Shelters and Fire apparatus | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137INGC000110 | U33 - BVS-01 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 210 | 0
C533137ININ000050 | U33 - BVS-01 - Installation of indoor dome cameras | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000070 | U33 - BVS-01 - Installation of Pan-tilt Cameras on pole | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000090 | U33 - BVS-01 - Installation of explosion-proof telephones - Outdoor, incl. Junction box | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000140 | U33 - BVS-02 - Installation of Oulet-jack phones | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000150 | U33 - BVS-02 - Installation of Pan-tilt Cameras on pole | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000200 | U33 - BVS-02 - Installation of Fire Point Shelters and Fire apparatus | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137ININ000280 | U33 - BVS-03 - Installation of indoor dome cameras | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137INML000020 | U33 - BVS-01 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C533137PIBB000140 | U33 - BVS-02 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C533137PIBB000150 | U33 - BVS-02 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137PIBB000240 | U33 - BVS-03 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C321131PISU000140 | U21 - Piping Supports Erection (580) | PI | PISU2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12408 | 0 | 10610.PI.SU.TN | 27.57 | 0
C321131PIUG000080 | U21 - Piping Erection UG (580) | PI | PIUG | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4793 | 0 | 10610.PI.UG.DI | 3195 | 0
C321131PRBO000020 | U21 - Static Box Up (562) | PR | PRBO1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3843 | 0 | 10780.PR.PR.MH
C321131PRBO000030 | U21 - Rotary Box Up (562) | PR | PRBO2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8456 | 0 | 10780.PR.PR.MH
C321131PRFL000070 | U21 - Piping Flushing/Steam Blowing (562) | PR | PRFL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3524 | 0 | 10610.PR.FL.DI | 40876 | 0
C321131PRHT000070 | U21 - Piping Hydrotesting (580) | PR | PRHT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17459 | 0 | 10610.PR.HT.DI | 18434 | 0
C321131PRMR000020 | U21 - Motor Run (562) | PR | PRMR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2819 | 0 | 10780.PR.PR.MH
C321131PRPL000020 | U21 - Punch List (562) | PR | PRPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3256 | 0 | 10780.PR.PR.MH
C321132CICT000020 | U21 - Electrical earth Trenches Execution (562) | CI | CICT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CICT000030 | U21 - Instrument earth Trenches Execution (562) | CI | CICT3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CICT000040 | U21 - Covered Concrete Trenches Execution (562) | CI | CICT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8951 | 20.6535 | 10610.CI.CO.M3 | 149.18 | 8.1393
C321132CICT000040 | U21 - Covered Concrete Trenches Execution (562) | CI | CICT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8951 | 20.6535 | 10610.CI.CO.M3 | 149.18 | 8.1393
C321132CICT000050 | U21 - Underground earth Trenches Execution (562) | CI | CICT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.CI.ET.M3 | 35.74 | 0
C321132CIGT000020 | U21 - Steel Structure Grouting Execution (562) | CI | CIGT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2895 | 0 | 10780.CI.CI.MH
C321132CIGT000120 | U21 - Equipment Grouting Execution (580) | CI | CIGT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 750 | 0 | 10780.CI.CI.MH
C321132CIHE000040 | U21 - Transformer STG-GSUT Foundation Execution (562) | CI | CIHE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9316 | 13.4955 | 10610.CI.CO.M3 | 155.27 | 0
C321132CIMF000020 | U21 - Miscellaneous Foundations Execution (562) | CI | CIMF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3509 | 0 | 10610.CI.CO.M3 | 58.48 | 0
C321132CIMF000060 | U21 - Miscellaneous Foundations Execution (580) | CI | CIMF | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 54294 | 0 | 10610.CI.CO.M3 | 1085.88 | 0
C321132CIPE000010 | U21 - Steam Turbine Generator 562-ST-301 Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27741 | 331.4884 | 10610.CI.CO.M3 | 554.82 | 0
C321132CIPE000020 | U21 - Lube Oil Skid Foundation Execution (562) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2520 | 0 | 10610.CI.CO.M3 | 42 | 0
C321132CIPE000080 | U21 - Transformer GTG-GSUT Foundation Execution (580) | CI | CIHE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9414 | 2.7559 | 10610.CI.CO.M3 | 156.9 | 0
C427131PISU000100 | U27 - Piping Tie-ins for Unit 21 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11050 | 0 | 10610.PI.TI.DI | 280.05 | 0
C427131PISU000120 | U27 - Piping Tie-ins for Unit 122 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 20400 | 614.7899 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000130 | U27 - Piping Tie-ins for Unit 27 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6800 | 68.31 | 10610.PI.TI.DI | 280.05 | 280.05
C427131PISU000260 | U27 - Piping Tie-ins Supports Prefabrication | PI | PISU1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1106 | 0 | 10610.PI.PU.TN | 4.25 | 0
C427131PRFL000130 | U27 - Piping Flushing/Blowing | PR | PRFL | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3712 | 0 | 10610.PR.FL.DI | 24828 | 0
C427131PRRE000100 | U27 - Piping Reinstatement | PR | PRRE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14847 | 0 | 10610.PR.RE.DI | 24828 | 0
C427132CIGT000190 | U27 - Steel Structure Grouting Execution | CI | CIGT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2160 | 0 | 10780.CI.CI.MH
C427132CIMS000350 | U27-Miscellaneous Piperack Execution | CI | CIMF | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 35 | 6.5149e-05 | 10610.CI.CO.M3 | 0.5 | 0
C427132CIPR000011 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Appr length 800 Me-Part B | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7010 | 58.0754 | 10780.CI.CI.MH
C427132CIPR000020 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(App length 800 Me-Part A | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7010 | 58.0754 | 10780.CI.CI.MH
C427132CIPR000350 | U27 - Piperack PR-104 A/B/C Foundations Execution (112.5 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1506 | 0 | 10780.CI.CI.MH
C427132CIPT000081 | U27 - Miscellaneous Supports & Sleeper Foundations Part-1 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000090 | U27 - Miscellaneous Supports & Sleeper Foundations Part-2 -(250 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIUG000000 | U27 - Demolition, re-routing/re-installation of fire water system | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1633 | 3.9395 | 10610.SP.SP.M3 | 116.67 | 116.67
C427132STPR000010 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Appr length 800 Me-Part A | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5459 | 18.7323 | 10780.ST.ST.MH
C427132STPR000021 | U27-Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(App length 800 Me-Part B | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2438 | 0 | 10780.ST.ST.MH
C427132STPR000030 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Appr length 700 M-Part A | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4982 | 0 | 10780.ST.ST.MH
C427132STPR000031 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Appr length 700 M-Part B | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2438 | 0 | 10780.ST.ST.MH
C427132STPR000200 | U27 - Piperack PR-106 A/B Erection (40.375 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1795 | 0 | 10610.ST.PR.TN | 33.86 | 0
C533137PIBB000280 | U33 - BVS-02 - Installation of Cable Trays/Ladders and Conduits | IN | INCT1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10780.IN.IN.MH
C533137PIBB000290 | U33 - BVS-03 - Installation of Cable Trays/Ladders and Conduits | IN | INCT1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10780.IN.IN.MH
C533137PRLT000110 | U33 - BVS-03 - Instrumentation Precommissioining | PR | PRLT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 494 | 0 | 10780.PR.PR.MH
C533PECU000000020 | U33 - BVS-03 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000060 | U33 - BVS-02 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000070 | U33 - BVS-02 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000080 | U33 - BVS-02 - Anchor Blocks Installation | PE | PEAB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10780.PE.PE.MH
C533PECU000000160 | U33 - BVS-02 - Fabrication & Installation of Fence Gates | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 610 | 0 | 10780.PE.PE.MH
C533PECU000000170 | U33 - BVS-02 - Construction of Pavement and Walkways | CI | CIPV1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.CI.CI.MH
C533PECU000000330 | U33 - BVS-03 - Fabrication and Erection of Fence Poles | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4268 | 0 | 10780.PE.PE.MH
C533PETR000000010 | U33 - Test Coupons Welding (30" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2159 | 6.8848 | 10780.PE.PE.MH
C533PETR000000120 | U33 - Conduct Non-Destructive & Destructive Test (48" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18132 | 485.6969 | 10780.PE.PE.MH
C533PETR000000130 | U33 - Conduct Non-Destructive & Destructive Test (36" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18132 | 485.6969 | 10780.PE.PE.MH
C533PETR000000180 | U33 - Submission and Approval of Welding Procedure Specification (48" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9066 | 121.4242 | 10780.PE.PE.MH
C533PIBB000000010 | U33 - BVS-03 - Installation of Above Ground Piping | PI | PIBB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19910 | 1.2298 | 10780.PI.PI.MH
C533PIBB000000110 | U33 - BVS-03 - Installation of Valves | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1016 | 0 | 10780.PE.PE.MH
C533PIBB000000130 | U33 - BVS-03 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2126 | 0 | 10610.PI.SU.TN | 4.72 | 0
C641131PIPR000050 | U41 - Piping Prefabrication | PI | PIPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 77479 | 5570.9874 | 10610.PI.FB.DI | 19369.74 | 9624.0212
C641131PISU000120 | U41 - Piping Supports Erection | PI | PISU2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 55542 | 0 | 10610.PI.SU.TN | 123.43 | 0
C641131PRBO000070 | U41 - Static Box Up | PR | PRBO1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 822 | 0 | 10780.PR.PR.MH
C427132STPR000210 | U27 - Piperack PR-107 Erection (38 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1355 | 0 | 10610.ST.PR.TN | 25.57 | 0
C427132STPR000230 | U27 - Piperack PR-105 Erection (15.5 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1802 | 0 | 10610.ST.PR.TN | 0 | 0
C427133PAFP000130 | U27 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10610.PA.FP.M2 | 168 | 0
C427133PASP000130 | U27 - Piping Supports SandBl. & Priming | PA | PASP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8400 | 86.0076 | 10610.PA.SU.TN | 0 | 0
C427137INCO000090 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD ) at Unit 96 IES-13 H2 export line (new tie-in) | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10780.IN.IN.MH
C427137INCO000130 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD) at Unit 27 IES-12 | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.025528 | 10780.IN.IN.MH
C427137INCO000160 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD) at Unit 21 IES-01 | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10780.IN.IN.MH
C427PITI000000020 | Tie-in Pipe support foundations for Unit 122 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 460 | 0.31253 | 10610.CI.CO.M3 | 6.57 | 6.57
C427PITI000000040 | Tie-in Pipe support foundations for Unit 21 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 476 | 0.33472 | 10610.CI.CO.M3 | 6.8 | 6.8
C427PITI000000050 | Tie-in Pipe support foundations for Unit 20 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 476 | 0.33472 | 10610.CI.CO.M3 | 6.8 | 6.8
C427PITI000000070 | Tie-in Pipe support foundations for Unit 77 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11626 | 199.6697 | 10610.CI.CO.M3 | 193.76 | 193.7594
C5310PRPEHT000030 | U31.3 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 544 | 0 | 10610.PR.HT.DI | 34800 | 0
C5310PRPEHT000040 | U31.2 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 351 | 0 | 10610.PR.HT.DI | 26280 | 0
C5310PRPEPL000030 | U31.3 - Pipeline Punch List | PR | PRPL | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6 | 0 | 10780.PR.PR.MH
C5310PRPEWT000040 | U31.2 - Pipeline Walkthrough | PR | PRWT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3 | 0 | 10780.PR.PR.MH
C531131PECP000020 | U31.2 - Permanent Cathodic Protection Works | PE | PECP | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1089 | 0 | 10610.PE.CP.LM | 3556 | 0
C531131PEPA000010 | U31.2 - Field Joint Coating | PE | PEPA | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4015 | 15.2507 | 10610.PE.PA.UN | 730 | 461.36
C531131PEPA000030 | U31.1 - Field Joint Coating | PE | PEPA | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3999 | 14.9786 | 10610.PE.PA.UN | 727 | 456.5633
C531131PEPA000060 | U31.1 - Pre-Construction Survey and Stake-out | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1729 | 4.4172 | 10780.PE.PE.MH
C531131PETI000050 | U31.2 - Installation of Pipeline Markers | PE | PETI | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3501 | 0 | 10780.PE.PE.MH
C531131PEUG000050 | U31.3 - Pipeline Welding | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15776 | 75.8213 | 10610.PE.UG.LM | 8700 | 1785.2539
C531132PEBK000020 | U31.2 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2712 | 0 | 10610.PE.BK.M3 | 960 | 0
C531132PEBK000030 | U31.1 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3079 | 0 | 10610.PE.BK.M3 | 8890 | 0
C531132PEBK000050 | U31.3 - Berm Preparation | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3069 | 0 | 10610.PE.BK.M3 | 7185 | 0
C531132PEBK000110 | U31.3 - Construction of Maintenance Road | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2046 | 0 | 10780.PE.PE.MH
C531132PEBK000130 | U31.1 - ROW Clean-up & Restoration | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1064 | 0 | 10780.PE.PE.MH
C531132PECU000079 | U31.2 - Trial Pits (64nos) | PE | PETR | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1008 | 1.4576 | 10780.PE.PE.MH
C531132PECU000140 | U31.1 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8800 | 0.020592 | 10610.PE.CO.LM | 22 | 0
C531132PECU300010 | U31.2 - NDRC Crossing (KP 0+460 to KP 0+980) | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 266 | 0.10453 | 10610.PE.CO.LM | 1 | 1
C531132PECU300060 | U31.2 - NDRC Crossing (KP 5+760 to KP 6+160) | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PECU300070 | U31.1 - NDRC Crossing (KP 0+460 to KP 0+980) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0.10453 | 10610.PE.CO.LM | 1 | 1
C531132PEFO000090 | U31.3 - NDRC Crossing (KP 5+760 to KP 6+160) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PERD000010 | U31.1 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 4.2546 | 10610.PE.CO.LM | 12 | 1.5
C531132PERD000080 | U31.2 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4800 | 4.2546 | 10610.PE.CO.LM | 12 | 1.5
C531132PEUG000040 | U31.1 - Pipe Hauling & Stringing | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16815 | 371.0092 | 10780.PE.PE.MH
C531132PEUG000050 | U31.2 - Pipeline Lowering | PE | PEUG | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8316 | 31.4135 | 10780.PE.PE.MH
C531132PEUG000080 | U31.3 - Pipeline Lowering | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12549 | 0 | 10780.PE.PE.MH
C531132PEWD000010 | U31.2 - Tie-In Welding incl NDT, Joint Coating & Backfilling | PE | PETI | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8637 | 0 | 10780.PE.PE.MH
C531137INFC000010 | U31.2 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137INFC000020 | U31.3 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137PECP000010 | U31.3 - Temporary Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1541 | 0 | 10610.PE.CP.LM | 5322 | 0
C641131PRHT000060 | U41 - Piping Hydrotesting | PR | PRHT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 49416 | 0 | 10610.PR.HT.DI | 51425 | 0
C641132CIHE000110 | U41 - Pig Trolley Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10228 | 93.9583 | 10610.CI.CO.M3 | 204.55 | 112.5005
C641132CIHE000110 | U41 - Pig Trolley Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10228 | 93.9583 | 10610.CI.CO.M3 | 204.55 | 112.5005
C641132CIHE000140 | U41 - Scrapper Launcher 625-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2079 | 6.3852 | 10610.CI.CO.M3 | 34.65 | 34.6499
C641132CIHE000150 | U41 - Scrapper Launcher 627-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2350 | 8.159 | 10610.CI.CO.M3 | 39.17 | 39.1699
C641132CIHE000160 | U41 - Jib Crane Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4342 | 27.8526 | 10610.CI.CO.M3 | 72.37 | 72.3701
C641132CIPR000230 | U41 - 96-PR-110 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3244 | 0 | 10610.CI.CO.M3 | 54.06 | 0
C641132CIPR000240 | U41 - 627-PR-101A&B Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2619 | 10.133 | 10610.CI.CO.M3 | 43.65 | 43.6502
C641132CIPR1320 | U12 - Pipe Rack 537-PR-201 Foundations Execution | CI | CIPR2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7204 | 70.6019 | 10610.CI.CO.M3 | 120.06 | 112.3498
C641132SPSP000030 | U41 - Site Preparation | SP | SPSP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1200 | 2.1273 | 10780.SP.SP.MH
C641132STMS000050 | U41 - Miscellaneous Steel Structures Erection | ST | STMS | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7039 | 0 | 10610.ST.PL.TN | 117.32 | 0
C641132STPL000090 | U41 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1565 | 0 | 10610.ST.PL.TN | 19.57 | 0
C641132STPL000110 | U41 - Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3206 | 0 | 10610.ST.PL.TN | 40.07 | 0
C641132STPR000090 | U41 - 627-PR-101A&B Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9174 | 16.1636 | 10610.ST.PR.TN | 173.1 | 0
C641132STPR150 | U41 - 96-PR-107 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1355 | 0 | 10610.ST.PR.TN | 25.57 | 0
C641132STSP000060 | U41 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 644 | 0 | 10610.ST.PL.TN | 10.74 | 0
C641133PAFP000060 | U41 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2454 | 0 | 10780.PA.PA.MH
C641133PAPP000050 | U41 - Piping SandBl. & Priming | PA | PAPP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19628 | 338.2053 | 10610.PA.PP.M2 | 0 | 0
C641133PASP000060 | U41 - Piping Supports SandBl. & Priming | PA | PASP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 475 | 0.012833 | 10610.PA.SU.TN | 0 | 0
C641134ELCI000050 | U41 - Conduits Installation | EL | ELCI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1447 | 0 | 10780.EL.EL.MH
C531137PECP000030 | U31.2 - Temporary Cathodic Protection Works | PE | PECP | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1815 | 0 | 10780.PE.PE.MH
C531137PECP000040 | U31.1 - Permanent Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1089 | 0 | 10780.PE.PE.MH
C531137PECP000050 | U31.1 - Temporary Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1815 | 0 | 10610.PE.CP.LM | 5334 | 0
C531137PEFO000030 | U31.1 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531PECP000000280 | U16 - NGL Surge Sphere 545-V-201B - External Scaffolding & Derick Support Installation | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5725 | 31.2798 | 10780.ME.ME.MH
C531PECP000000290 | U16 - NGL Surge Sphere 545-V-201B - Erection & Assembly of Top Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5725 | 4.6 | 10780.ME.ME.MH
C531PECP000000340 | U16 - NGL Surge Sphere 545-V-201B - Erection of Bottom Crown and Welding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11164 | 17.4918 | 10780.ME.ME.MH
C531PECP000000360 | U16 - NGL Surge Sphere 545-V-201B - NDT Works (before PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8588 | 15.9148 | 10780.ME.ME.MH
C531PECP000000385 | U16 - NGL Surge Sphere 545-V-201B - NDT Works (After Hydrotest) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2863 | 0 | 10780.ME.ME.MH
C531PECP000000390 | U16 - NGL Surge Sphere 545-V-201B - Removal of External Scaffolding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2863 | 0 | 10780.ME.ME.MH
C531PECP000000450 | U16 - NGL Surge Sphere 545-V-201A - External Scaffolding & Derick Support Installation | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5650 | 25.7713 | 10780.ME.ME.MH
C531PECP000000510 | U16 - NGL Surge Sphere 545-V-201A - Erection of Bottom Crown and Welding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10780.ME.ME.MH
C531PECP000000590 | U16 - NGL Surge Sphere 545-V-201A - NDT Works (Before PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5352 | 2.7977 | 10780.ME.ME.MH
C531PECP000000660 | U16 - NGL Surge Sphere 545-V-201B - Sphere Calibration | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2004 | 0 | 10780.ME.ME.MH
C531PEUG000000010 | U31.3 - NDT & Visuals | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3194 | 3.0731 | 10780.PE.PE.MH
C5320PRPEHT000100 | U32 - Intelligent Pigging | PE | PEHT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72 | 0 | 10780.PE.PE.MH
C532132PEBK000010 | U32 - Final Backfilling (above FOC Level) | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2990 | 0 | 10610.PE.BK.M3 | 900 | 0
C532132PEBK000030 | U32 - Berm Preparation | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2760 | 0 | 10610.PE.BK.M3 | 1000 | 0
C532132PEBK000060 | U32 - Construction of Maintenance Road | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 874 | 0 | 10780.PE.PE.MH
C532132PERD000010 | U32 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4400 | 17.8752 | 10610.PE.CO.LM | 11 | 6.88
C532132PEUG000030 | U32 - Pipeline Lowering | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5915 | 15.987 | 10780.PE.PE.MH
C532132PEUG000050 | U32 - NDT & Visuals | PE | PEHT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1703 | 3.2432 | 10780.PE.PE.MH
C532137PEFO000010 | U32 - FO Cable Pulling | PE | PEFO | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6435 | 0 | 10610.PE.FO.LM | 11700 | 0
C532PEFC000000010 | U32 - FO Cable Splicing and Terminations | PE | PEFC | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3 | 0 | 10610.PE.FC.UN | 6 | 0
C533131PIBB000040 | U33 - BVS-02 - Installation of Above Ground Piping | PI | PIBB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19910 | 1.2298 | 10780.PI.PI.MH
C533131PIBB000060 | U33 - BVS-02 - Fabrication and Installation of Valve Operating Platforms and Crossovers | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2439 | 0 | 10780.PE.PE.MH
C533131PIBB000080 | U33 - BVS-02 - Painting of Above Ground Piping & Pipe Supports | PA | PAPP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0.054614 | 10610.PA.PP.M2 | 175 | 46.4032
C533132PEBK000111 | U33 - Section 1 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 3584.3753 | 10610.PE.BK.M3 | 569.43 | 227.772
C533132PEBK000112 | U33 - Section 1 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 0 | 10610.PE.BK.M3 | 311098.22 | 0
C533132PEBK000121 | U33 - Section 2 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 3816.2645 | 10610.PE.BK.M3 | 597.09 | 238.842
C533132PEBK000123 | U33 - Section 2 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 0 | 10610.PE.BK.M3 | 19856.6 | 0
C533132PEBK000131 | U33 - Section 3 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 41.0639 | 10610.PE.BK.M3 | 554.04 | 4.0722
C533132PEBK000133 | U33 - Section 3 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 0 | 10610.PE.BK.M3 | 18424.78 | 0
C533132PEBK000141 | U33 - Section 4 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 429.44 | 0
C533132PEBK000150 | U32 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3795 | 2.3616 | 10610.PE.BK.M3 | 10860 | 1205.46
C533132PECP000111 | U33 - Section 1 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10918 | 13.2957 | 10610.PE.CP.LM | 20739.69 | 1659.1752
C533132PECP000121 | U33 - Section 2 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11334 | 0.47444 | 10610.PE.CP.LM | 21747.31 | 0
C533132PECP000131 | U33 - Section 3 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8839 | 0 | 10610.PE.CP.LM | 20179.16 | 0
C533132PECP000141 | U33 - Section 4 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7279 | 0 | 10610.PE.CP.LM | 15640.85 | 0
C533132PECU000011 | U33 - Section 1 - Trial Pits (192 Nos) | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9714 | 132.4872 | 10780.PE.PE.MH
C641134ELEL000065 | U41 - Earthing Works | EL | ELEL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1543 | 0 | 10610.EL.ES.LM | 11835.76 | 0
C641134ELEL000075 | U41 - Lightning Works | EL | ELEL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1543 | 0 | 10780.EL.EL.MH
C641134ELMS000010 | U41 - Misc Electical | EL | ELEQ2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 868 | 0 | 10780.EL.EL.MH
C641134ELTI000100 | U41 - Lighting Cable Trays Installation | EL | ELTI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.CT.LM | 1870.79 | 0
C641136MEHL000030 | U41 - Jib Crane Erection | ME | METC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C641136MEHL000030 | U41 - Jib Crane Erection | ME | METC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C641136MEVV000445 | U41 - 36" PL-9 Scrapper Launcher 626-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C641137INAI000040 | U41 - Analyzers Equipment Installation | IN | INAI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 850 | 0 | 10610.IN.AI.UN | 1 | 0
C641137INAI000040 | U41 - Analyzers Equipment Installation | IN | INAI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 850 | 0 | 10610.IN.AI.UN | 1 | 0
C641137INCT000080 | U41 - Primary Cable Trays Installation | IN | INCT1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3936 | 0 | 10610.IN.CT.LM | 1050 | 0
C641137INFC000040 | U41 - Fiber Optic Gland & Conn./Testing | IN | INFC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 378 | 0 | 10610.IN.CO.UN | 360 | 0
C641137INFS000050 | U41 - Fire Fighting Equipments Installation | IN | INFS | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 409 | 0 | 10780.IN.IN.MH
C641137INGC000100 | U41 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1637 | 0 | 10610.IN.CO.UN | 430 | 0
C641137INHU000090 | U41 - Pneumatic Hook Up´s Erection | IN | INHU3 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10780.IN.IN.MH
C641137INHU000100 | U41 - Process Hook Up´s Erection | IN | INHU1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1732 | 0 | 10780.IN.IN.MH
C641137ININ000051 | U41 - Valve Installation | IN | ININ | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1259 | 0 | 10610.IN.IN.UN | 840 | 0
C641137INSL000050 | U41 - Single Pair Cable Pulling | IN | INSL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3936 | 0 | 10610.IN.SC.LM | 5981.61 | 0
C749131CIPR000020 | U49- Civil Revamp of Piperack Train -2-3 E-W Rack-120 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIPR000100 | U49- Civil Revamp of Piperack Train -3 Rack-255 Meter - Part B | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131PIBB000050 | U49 - Big Bore Piping A/Equip. Erection | PI | PIBB | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27901 | 0 | 10610.PI.BB.DI | 2790.1 | 0
C749131PISU000100 | U49 - Piping Supports Erection | PI | PISU2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6465 | 0 | 10610.PI.SU.TN | 14.37 | 0
C533132PECU000031 | U33 - Section 3 - Trial Pits (23 Nos) | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5102 | 15.6386 | 10780.PE.PE.MH
C533132PECU000121 | U33 - Section 2 - NDRC Crossing (4 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1064 | 0.85002 | 10610.PE.CO.LM | 4 | 2.01
C533132PECU000121 | U33 - Section 2 - NDRC Crossing (4 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1064 | 0.85002 | 10610.PE.CO.LM | 4 | 2.01
C533132PECU000142 | U33 - Section 4 - Open Cut Crossing (62 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24800 | 0 | 10610.PE.CO.LM | 62 | 0
C533132PECU000300 | U33 - BVS-01 - Anchor Blocks Installation | PE | PEAB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10610.CI.CO.M3 | 35.57 | 0
C533132PECU000330 | U33 - BVS-01 - Cover Precasting and Installation for Cable Trench | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10610.PE.CO.LM | 6.5 | 0
C533132PECU000330 | U33 - BVS-01 - Cover Precasting and Installation for Cable Trench | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10610.PE.CO.LM | 6.5 | 0
C533132PECU000360 | U33 - BVS-01 - Fabrication and Erection of Fence Poles | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4268 | 0 | 10780.PE.PE.MH
C533132PECU000390 | U33 - BVS-01 - Construction of Pavement and Walkways | CI | CIPV1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.CI.CI.MH
C533132PEHT000111 | U33 - Section 1 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 77715.23 | 0
C533132PEHT000121 | U33 - Section 2 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 81490.97 | 0
C533132PEPA000115 | U33 - Section 1 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9475 | 85.8114 | 10610.PE.PA.UN | 2590.51 | 1676.06
C533132PEPA000125 | U33 - Section 2 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16811 | 295.1721 | 10610.PE.PA.UN | 2716.37 | 1920.4736
C533132PETR000113 | U33 - Section 1 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37129 | 0 | 10610.PE.FO.LM | 85414.45 | 0
C533132PETR000114 | U33 - Section 1 - ROW Clean-up & Restoration | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 46721 | 0 | 10780.PE.PE.MH
C533132PETR000126 | U33 - Section 2 - Construction of Maintenance Road | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24114 | 0 | 10780.PE.PE.MH
C533132PETR000132 | U33 - Section 3 - Construction of Right of Way | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12756 | 208.3388 | 10780.PE.PE.MH
C533132PETR000142 | U33 - Section 4 - Construction of Right of Way | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7359 | 19.1375 | 10780.PE.PE.MH
C533132PETR000143 | U33 - Section 4 - Trench Excavation | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6869 | 0.3715 | 10780.PE.PE.MH
C533132PEUG000112 | U33 - Section 1 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29357 | 1017.6554 | 10610.PE.UG.LM | 31026 | 24634.505
C749131PRFL000050 | U49 - Piping Flushing/Blowing | PR | PRFL | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1265 | 0 | 10610.PR.FL.DI | 14453 | 0
C749131PRFL000060 | U41 - Piping Flushing/Blowing | PR | PRFL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9883 | 0 | 10610.PR.FL.DI | 51425 | 0
C749131STPR000000 | U49- Structure revamp of Piperack Train -1 N-S Road Crossing Rack-55 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 106 | 0 | 10610.ST.PR.TN | 2 | 0
C749131STPR000020 | U49-Structure revamp of Piperack Train -2-3 E-W Rack-120 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 77 | 0 | 10610.ST.PR.TN | 1.45 | 0
C749132CIGT000090 | U49 - Steel Structure Grouting Execution | CI | CIGT | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10780.CI.CI.MH
C749132CIMF000040 | U49 - Miscellaneous Foundations Execution | CI | CIMF | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50252 | 1578.7696 | 10610.CI.CO.M3 | 1005.04 | 700.0003
C749132CIPV000100 | U49 - Concrete Paving Execution | CI | CIPV1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3314 | 0 | 10610.CI.PV.M2 | 1841.11 | 0
C749132CIPV000120 | U49 - Asphalt Paving Execution | CI | CIPV3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10780.CI.CI.MH
C749132SPSP000010 | U49 - Construction of New fence | SP | SPSP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 890 | 0.27499 | 10780.SP.SP.MH
C749132STMS000040 | U49 - Miscellaneous Steel Structures Erection | ST | STMS | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1530 | 0 | 10610.ST.PL.TN | 25.5 | 0
C749134ELCL000080 | U49 - Lighting Cable Laying | EL | ELCL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1424 | 0 | 10610.EL.LC.LM | 8141.7 | 0
C749134ELCL000090 | U49 - Electrical Cable Laying | EL | ELCL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6961 | 0 | 10610.EL.PL.LM | 8311.79 | 0
C749134ELCO000090 | U49 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3797 | 0 | 10610.EL.CO.UN | 472 | 0
C749134ELEL000055 | U49 - Earthing Works | EL | ELEL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 844 | 0 | 10610.EL.ES.LM | 3945.25 | 0
C749134ELTI000080 | U49 - Lighting Cable Trays Installation | EL | ELTI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.CT.LM | 111.94 | 0
C749136MEMC000030 | U49 - Miscellaneous Erection | ME | MEMC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749136MEVV000040 | U49 - Jib Crane Erection | ME | METC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749137INCI000040 | U49 - Conduits Installation | IN | INCT3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 693 | 0 | 10780.IN.IN.MH
C749137INCT000070 | U49 - Secondary Cable Trays Installation | IN | INCT2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3744 | 0 | 10610.IN.CT.LM | 400 | 0
C749137INFS000040 | U49 - Fire Fighting Equipments Installation | IN | INFS | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 695 | 0 | 10780.IN.IN.MH
C749137INGC000080 | U49 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2781 | 0 | 10610.IN.CO.UN | 350 | 0
C533132PEUG000113 | U33 - Section 1 - NDT & Visuals | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9488 | 108.3223 | 10780.PE.PE.MH
C533132PEUG000115 | U33 - Section 1 - Cold bending works | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24608 | 371.2527 | 10780.PE.PE.MH
C533132PEUG000123 | U33 - Section 2 - NDT & Visuals | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8791 | 103.7734 | 10780.PE.PE.MH
C533132PEUG000135 | U33 - Section 3 - Cold bending works | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34538 | 0 | 10780.PE.PE.MH
C533132PEUG000142 | U33 - Section 4 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32379 | 338.3042 | 10610.PE.UG.LM | 23439 | 5119.7808
C533132PEUG000146 | U33 - Section 4 - Tie-In Welding incl NDT, Joint Coating,Backfilling & Marker installation | PE | PETI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19950 | 0 | 10780.PE.PE.MH
C533132PIBB000030 | U33 - BVS-01 - Fabrication and Installation of Valve Operating Platforms and Crossovers | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2439 | 0 | 10780.PE.PE.MH
C533134ELCO000020 | U33 - BVS-01 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533134ELEL000030 | U33 - BVS-01 - Installation of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C533134INML000040 | U33 - BVS-02 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C533134PIBB000120 | U33 - BVS-02 - Installation of Solar Power System | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134PIBB000130 | U33 - BVS-02 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533134PIBB000220 | U33 - BVS-03 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533134PIBB000270 | U33 - BVS-03 - Installation of Cable Trays/Ladders and Conduits | EL | ELTI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 478 | 0 | 10780.EL.EL.MH
C533134PRMR000040 | U33 - BVS-01 - Electrical Precommissioining | PR | PRMR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.PR.PR.MH
C533137ELEQ000820 | U33 - BVS-03 - Installation of Pig Signalers | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533137INGC000020 | U33 - BVS-03 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 240 | 0
C533137INGC000030 | U33 - BVS-01 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137ININ000330 | U33 - BVS-03 - Installation of Fire Extinguishers | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137INML000020 | U33 - BVS-01 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C533137INML000090 | U33 - BVS-01 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C749137ININ000040 | U49 - Instruments Installation | IN | ININ | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2139 | 0 | 10610.IN.IN.UN | 350 | 0
C749137INIP000041 | U49 - Valve Calibration | IN | INIP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 695 | 0 | 10780.IN.IN.MH
C749137INSL000040 | U49 - Single Pair Cable Pulling | IN | INSL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6686 | 0 | 10610.IN.SC.LM | 7698.27 | 0
NC220132BUSSFO100030 | U20 - SS-516 - Transf. Walls Foundations (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15398 | 350.2636 | 10610.BU.CO.M3 | 298 | 297.9997
NN-C220BUTR000000010 | U20 - SS-516 - Transf. Yard Foundations #B (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14372 | 305.1412 | 10610.BU.CO.M3 | 175 | 175
C321132STPR000040 | U21 - 562-PR-102 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2067 | 0 | 10610.ST.PR.TN | 39 | 0
C321132STPR000070 | U21 - 562-PR-202 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15635 | 0 | 10780.ST.ST.MH
C321132STPR000080 | U21 - 562-PR-103 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2597 | 0 | 10610.ST.PR.TN | 49 | 0
C321132STPR000130 | U21 - 580-PR-103 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2566 | 0 | 10610.ST.PR.TN | 48.42 | 0
C321132STPR000140 | U21 - 580-PR-104 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 741 | 0 | 10610.ST.PR.TN | 13.99 | 0
C321132STPR150 | U21 - 562-PR-104 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2650 | 1.5043 | 10610.ST.PR.TN | 50 | 0
C321132STSH000050 | U21 - Shelter GTG-GSUT Transformer Structure Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 203 | 0 | 10610.ST.ER.TN | 3.83 | 0
C321132STSH000050 | U21 - Shelter GTG-GSUT Transformer Structure Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 203 | 0 | 10610.ST.ER.TN | 3.83 | 0
C321132STSH000080 | U21 - Shelter GTG-GSUT Roofing & Wall Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 203 | 0 | 10610.ST.ER.TN | 3.83 | 0
C321133PAFP000070 | U21 - Piping Final Coat & Touch-Up Painting (580) | PA | PAFP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1465 | 0 | 10780.PA.PA.MH
C321133PAPP000060 | U21 - Piping SandBl. & Priming (580) | PA | PAPP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6877 | 13.2514 | 10610.PA.PP.M2 | 0 | 0
C321133PASP000020 | U21 - Piping Supports SandBl. & Priming (562) | PA | PASP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 728 | 0.065603 | 10610.PA.SU.TN | 0 | 0
C321133PASP000070 | U21 - Piping Supports SandBl. & Priming (580) | PA | PASP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1148 | 0.03999 | 10610.PA.SU.TN | 0 | 0
C321134ELBD000010 | U21 - 11Kv Bus Duct 580-EE-2332K Installation from Circuit Breaker to Transformer (580) | EL | ELBD | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10780.EL.EL.MH
C321134ELBD000020 | U21 - 11Kv Bus Duct 580-EE-2331K Installation from Circuit Breaker to Generator (580) | EL | ELBD | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10780.EL.EL.MH
C321134ELCL000130 | U21 - Lighting Cable Laying (580) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12216 | 0 | 10610.EL.LC.LM | 19917.66 | 0
C321134ELCO000040 | U21 - Electrical Cable Gland & Conn./Testing (562) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23000 | 0 | 10610.EL.CO.UN | 378 | 0
C321134ELCO000130 | U21 - Electrical Cable Gland & Conn./Testing (580) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32576 | 0 | 10610.EL.CO.UN | 297 | 0
C321134ELEL000025 | U21 - Earthing & Lightning Works (562) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5111 | 0 | 10610.EL.ES.LM | 1315.08 | 0
C321134ELEL000075 | U21 - Earthing Works (580) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7239 | 0 | 10610.EL.ES.LM | 3287.71 | 0
C321134ELEQ000030 | U21 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 390 | 0
C321134ELEQ000120 | U21 - GTG Step-up Transformer 580-EE-11511J Installation (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 70 | 0
C321134ELEQ000130 | U21 - STG Generator Circuit Breaker 580-EE-CB-2302K Installation (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 120 | 0
C321134ELEQ000140 | U21 - STG Step-up Transformer 580-EE-2311K Installation (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 200 | 0
C321134ELTI000030 | U21 - Lighting Cable Trays Installation (562) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5750 | 0 | 10610.EL.CT.LM | 913.63 | 0
C321134ELTI000040 | U21 - Electrical Cable Trays Installation (562) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19166 | 0 | 10610.EL.CT.LM | 1696.74 | 0
C321134ELTI000070 | U21 - 11Kv Bus Duct 580-EE-2332K Installation from Circuit Breaker to Transformer (562) | EL | ELBD | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10780.EL.EL.MH
C321134ELTI000130 | U21 - Electrical Cable Trays Installation (580) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27146 | 0 | 10610.EL.CT.LM | 2777.92 | 0
C321136MEAC000020 | U21 - Air Coolers Erection - Steam Turbine Generator Lube Oil Cooler (562) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29000 | 0 | 10610.ME.ER.TN | 290 | 0
C321136MEAC000030 | U21 - Air Coolers Pre-Assembly - Steam Turbine Generator Lube Oil Cooler (562) | ME | MEAC1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 27376 | 0 | 10780.ME.ME.MH
C321136MEAC000070 | U21 - Air Coolers Pre-Assembly - Gas Turbine Lube Oil Cooler (580) | ME | MEAC1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1600 | 0 | 10780.ME.ME.MH
C321136MEAC000080 | U21 - Air Coolers Erection - Gas Turbine Lube Oil Cooler (580) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 20 | 0
C321136MEHL000020 | U21 - Package Installation (Gas Turbine Generator Pack.) 580-ME-101J (580) - Generator (HL) (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4200 | 0 | 10610.ME.ER.TN | 70 | 0
C321136MEHL000700 | U21 - Package Installation (Steam Turbine Package Generator) 580-ME-101K/562-ST-301 - (HL) (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 0 | 10610.ME.ER.TN | 170 | 0
C321136MEHM000180 | U21 - Horizontal Pump with Electrical Motor Erection 562-P-308A/B Waste Heat Boiler Blowdown Pump (580) | ME | MEHM1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEHV000070 | U21 - Vertical Vessels (Waste Heat Boiler Blowdown Drum) Erection 562-V-302 Waste Heat Boiler Blowdown Drum (580) | ME | MEVV | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEPA000030 | U21 - Waste Heat Boiler Scale Inhibitor Dosing Package Installation 562-ME-308 Boiler Scale Inhibitor Dosing (580) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 180 | 0 | 10610.ME.ER.TN | 3 | 0
C321132CIPE000140 | U21 - Water Washing Trolley Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 409 | 0 | 10780.CI.CI.MH
C321132CIPE000160 | U21 - GCB Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1247 | 0 | 10610.CI.CO.M3 | 20.79 | 0
C321132CIPE000160 | U21 - GCB Foundation Execution (580) | CI | CIPE | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1247 | 0 | 10610.CI.CO.M3 | 20.79 | 0
C321132CIPR000030 | U21 - 562-PR-103 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5796 | 49.3139 | 10610.CI.CO.M3 | 96.6 | 96.5996
C321132CIPR000040 | U21 - 562-PR-201 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 31665 | 23.3888 | 10610.CI.CO.M3 | 633.3 | 0
C321132CIPR000290 | U21 - 580-PR-102 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3638 | 0 | 10610.CI.CO.M3 | 60.64 | 0
C321132CIPR000300 | U21 - 580-PR-103 Piperack Foundations Execution (580) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2903 | 9.1634 | 10610.CI.CO.M3 | 48.38 | 38.51
C321132CIPR130 | U21 - 562-PR-104 Piperack Foundations Execution (562) | CI | CIPR1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4140 | 25.3202 | 10610.CI.CO.M3 | 69 | 69
C321132CIRE000080 | U21 - Pump 562-P-302 A/B Foundation Execution (580) | CI | CIRE1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11146 | 0 | 10610.CI.CO.M3 | 222.92 | 0
C321132CIST000170 | U21 - Platform for Air Cooler 562-E-304 Foundation Execution (580) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1275 | 0 | 10610.CI.CO.M3 | 21.25 | 0
C321132CIST000220 | U21 - 580-PT-001 Pipetrack Foundations Execution (580) | CI | CIPT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.CI.CO.M3 | 42.66 | 0
C321132CIST000220 | U21 - 580-PT-001 Pipetrack Foundations Execution (580) | CI | CIPT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2560 | 0 | 10610.CI.CO.M3 | 42.66 | 0
C321132CIUG000065 | U21 - UG Pipe Installation (562) (CD) | CI | CIUG2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4905 | 0 | 10610.CI.UG.LM | 245.24 | 0
C321132FPEQ000031 | U21 - Equipment Fireproofing (580) 580-ME-101J | FP | FPEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 176 | 0 | 10780.FP.FP.MH
C321132SPSP000020 | Rerouting of exsiting U/G sevices | SP | SPSP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1100 | 0.44688 | 10780.SP.SP.MH
C321132SPSP000030 | Concrete Cutting (Paved Area) | SP | SPSP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1000 | 1.4773 | 10780.SP.SP.MH
C321132SPSP000040 | Relocation of existing AOC U/G services | SP | SPSP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 500 | 0.030196 | 10780.SP.SP.MH
C321132STPL000050 | U21 - Piperack Platforms, Ladders & Handrails Erection (562) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8389 | 87.4817 | 10610.ST.PL.TN | 104.86 | 87.0364
C321132STPL000120 | U21 - Piperack Platforms, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1819 | 0 | 10610.ST.PL.TN | 22.73 | 0
C321132STPL000130 | U21 - Equipment Structures for Air Cooler 562-E-304, Ladders & Handrails Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 410 | 0 | 10610.ST.PL.TN | 5.12 | 0
C533137PRLT000090 | U33 - BVS-01 - Instrumentation Precommissioining | PR | PRLT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 494 | 0 | 10780.PR.PR.MH
C533PECU000000090 | U33 - BVS-02 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000090 | U33 - BVS-02 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000100 | U33 - BVS-02 - RCC Cable Trench & Duct Bank Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2642 | 0 | 10780.PE.PE.MH
C533PECU000000110 | U33 - BVS-02 - Cover Precasting and Installation for Cable Trench | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10780.PE.PE.MH
C533PECU000000120 | U33 - BVS-02 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0.54255 | 10610.CI.CO.M3 | 17.19 | 7.2401
C533PECU000000310 | U33 - BVS-03 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000360 | U33 - BVS-03 - Construction of Pavement and Walkways | CI | CIPV1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.CI.CI.MH
C533PETR000000140 | U33 - Conduct Non-Destructive & Destructive Test (56" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18132 | 485.6969 | 10780.PE.PE.MH
C533PETR000000210 | U33 - BVS-02 - Backfilling / Embankment Construction | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10550 | 0 | 10780.PE.PE.MH
C6410PRPRPL000060 | U41 - Punch List | PR | PRPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3654 | 0 | 10780.PR.PR.MH
C6410PRPRWT000050 | U41 - Walkthrough | PR | PRWT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1566 | 0 | 10780.PR.PR.MH
C641131PIBB000060 | U41 - Big Bore Piping A/Equip. Erection | PI | PIBB | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 174359 | 1806.3343 | 10610.PI.BB.DI | 17435.94 | 825.0687
C641131PIRA000060 | U41 - Piping Erection on Rack | PI | PIRA | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 137288 | 535.7169 | 10610.PI.PR.DI | 15254.18 | 700.0143
C641131PISB000060 | U41 - Small Bore Piping A/Equip. Erection | PI | PISB | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7018 | 0 | 10610.PI.SB.DI | 638 | 0
C641131PISU000110 | U41 - Piping Supports Prefabrication | PI | PISU1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32091 | 82.29 | 10610.PI.PU.TN | 123.43 | 7.2732
C641131PISU000120 | U41 - Piping Supports Erection | PI | PISU2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 55542 | 0 | 10610.PI.SU.TN | 123.43 | 0
C641132CIGR000060 | U41 - Grounding Network Execution | CI | CIGR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 66 | 0 | 10610.CI.GR.LM | 110 | 0
C641132CIMF000050 | U41 - Miscellaneous Foundations Execution | CI | CIMF | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 284420 | 119127.3153 | 10610.CI.CO.M3 | 5688.39 | 5688.4073
C641132CIPR1250 | U41 - 96-PR-102A Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30174 | 0 | 10610.CI.CO.M3 | 603.48 | 0
C641132CIPR1260 | U41 - 96-PR-103 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3218 | 0 | 10610.CI.CO.M3 | 53.63 | 0
C321136MEPA000040 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Turbine (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 90 | 0
C321136MEPA000050 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Gearbox (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2100 | 0 | 10610.ME.ER.TN | 35 | 0
C321136MEPA000080 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Fuel Gas Skids (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2100 | 0 | 10610.ME.ER.TN | 35 | 0
C321136MEPA000100 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Hydraulic Oil Console (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEPA000120 | U21 - Package Installation (LP Steam Desuperheaters) 562-ME-310A/B Desuperheaters (562) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEPA000140 | U21 - Package Installation (LP Steam Desuperheaters) 562-ME-311A/B Desuperheaters (562) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C321136MEPA000230 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Steam Gland Condenser (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1740 | 0 | 10610.ME.ER.TN | 29 | 0
C321136MESB000010 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - By Pass & Main Stacks | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4200 | 0 | 10610.ME.ER.TN | 105 | 0
C321136MESB000020 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - Duct Burners | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 30 | 0
C321136MESB000030 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - Heater | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 165 | 0
C321136METC000050 | U21 - Cranes Erection (EOT Crane For Steam Turbine Generator) 562-EOT-301 (562) | ME | METC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C321137INAI000050 | U21 - Analyzers Equipment Installation (580) | IN | INAI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 616 | 0 | 10610.IN.AI.UN | 1 | 0
C321137INCI000060 | U21 - Conduits Installation (580) | IN | INCT3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 296 | 0 | 10780.IN.IN.MH
C321137INCT000030 | U21 - Primary Cable Trays Installation (562) | IN | INCT1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8906 | 0 | 10610.IN.CT.LM | 170 | 0
C321137INCT000040 | U21 - Secondary Cable Trays Installation (562) | IN | INCT2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4988 | 0 | 10610.IN.CT.LM | 200 | 0
C321137INFO000020 | U21 - Fiber Optic Cable Pulling (562) | IN | INFO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1211 | 0 | 10610.IN.FO.LM | 2977 | 0
C321137INFO000050 | U21 - Fiber Optic Cable Pulling (580) | IN | INFO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 388 | 0 | 10610.IN.FO.LM | 3011 | 0
C321137INFS000060 | U21 - Fire Fighting Equipments Installation (580) | IN | INFS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 297 | 0 | 10780.IN.IN.MH
C321132STPL000150 | U21 - Platform for Waste Heat Boiler 562-B-101J Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 298 | 0 | 10610.ST.PL.TN | 3.72 | 0
C321132STPL000170 | U21 - Platform for Gas Turbine Generator Package 580-ME-101J Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 419 | 0 | 10610.ST.PL.TN | 5.23 | 0
C321132STPL000180 | U21 - Gas Turbine Lube Oil Cooler Structure Erection (580) | ST | STPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 519 | 0 | 10610.ST.PL.TN | 6.49 | 0
C321132STPR000060 | U21 - 562-PR-201 Piperack Erection (562) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 22466 | 0 | 10610.ST.PR.TN | 423.89 | 0
C321132STPR000120 | U21 - 580-PR-102 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2624 | 0 | 10610.ST.PR.TN | 49.5 | 0
C321132STPR000130 | U21 - 580-PR-103 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2566 | 0 | 10610.ST.PR.TN | 48.42 | 0
C321132STPR000140 | U21 - 580-PR-104 Piperack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 741 | 0 | 10610.ST.PR.TN | 13.99 | 0
C321132STPR000150 | U21 - 580-PT-001 Pipetrack Erection (580) | ST | STPR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15635 | 0 | 10780.ST.ST.MH
C321132STSH000070 | U21 - Shelter 562-SH-001 Roofing & Wall Erection (562) | ST | STSH1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3740 | 0 | 10610.ST.ER.TN | 70.57 | 0
C321133PAEQ000020 | U21 - Equipment Painting (562) | PA | PAEQ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10780.PA.PA.MH
C321133PASP000020 | U21 - Piping Supports SandBl. & Priming (562) | PA | PASP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 728 | 0.065603 | 10610.PA.SU.TN | 0 | 0
C321133PASP000070 | U21 - Piping Supports SandBl. & Priming (580) | PA | PASP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1148 | 0.03999 | 10610.PA.SU.TN | 0 | 0
C321133PAST000020 | U21 - Steel Structure Painting Touch Up (562) | PA | PAST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14340 | 0 | 10780.PA.PA.MH
C321134ELCL000030 | U21 - Lighting Cable Laying (562) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8625 | 0 | 10610.EL.LC.LM | 23344.98 | 0
C321134ELCL000130 | U21 - Lighting Cable Laying (580) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 12216 | 0 | 10610.EL.LC.LM | 19917.66 | 0
C321134ELCL000140 | U21 - Electrical Cable Laying (580) | EL | ELCL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 59722 | 0 | 10610.EL.PL.LM | 122148.27 | 0
C321134ELCO000030 | U21 - Lighting Cable Gland & Conn./Testing (562) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5750 | 0 | 10610.EL.CO.UN | 364 | 0
C321134ELCO000040 | U21 - Electrical Cable Gland & Conn./Testing (562) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 23000 | 0 | 10610.EL.CO.UN | 378 | 0
C321134ELCO000120 | U21 - Lighting Cable Gland & Conn./Testing (580) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8144 | 0 | 10610.EL.CO.UN | 324 | 0
C321134ELCO000130 | U21 - Electrical Cable Gland & Conn./Testing (580) | EL | ELCO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 32576 | 0 | 10610.EL.CO.UN | 297 | 0
C641132CIPR1280 | U41 - 96-PR-106A&B Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11934 | 0 | 10610.CI.CO.M3 | 198.9 | 0
C641132CIPR1290 | U41 - 96-PR-107 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7667 | 0 | 10610.CI.CO.M3 | 127.78 | 0
C641132CIPT000030 | U41 - PR-Pipe Tracks Execution | CI | CIPT1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 286 | 0.05967 | 10610.CI.CO.M3 | 4.08 | 1.43
C641132STPR120 | U41 - 96-PR-104 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3180 | 0 | 10610.ST.PR.TN | 0 | 0
C641132STPR140 | U41 - 96-PR-106 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1795 | 0 | 10610.ST.PR.TN | 33.86 | 0
C641132STPR170 | U41 - 96-PR-109 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1667 | 0 | 10610.ST.PR.TN | 31.45 | 0
C641132STSP000060 | U41 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 644 | 0 | 10610.ST.PL.TN | 10.74 | 0
C641134ELCL000100 | U41 - Lighting Cable Laying | EL | ELCL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2604 | 0 | 10610.EL.LC.LM | 12296.96 | 0
C641134ELCL000110 | U41 - Electrical Cable Laying | EL | ELCL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12730 | 10.8833 | 10610.EL.PL.LM | 17792.58 | 1010.9744
C641134ELCO000110 | U41 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6944 | 0 | 10610.EL.CO.UN | 1080 | 0
C641134ELEQ000020 | U41 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.EQ.UN | 520 | 0
C641134ELGR000060 | U41 - Grounding Installation | EL | ELEL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1543 | 0 | 10780.EL.EL.MH
C641134ELTI000110 | U41 - Electrical Cable Trays Installation | EL | ELTI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5786 | 0 | 10610.EL.CT.LM | 3474.33 | 0
C641136CIHE000120 | U41 - Pig Trolley Erection | ME | MEPA | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3000 | 0 | 10610.ME.ER.TN | 50 | 0
C641136MEVV000445 | U41 - 36" PL-9 Scrapper Launcher 626-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C641136MEVV000455 | U41 - 48" PL-8 Scrapper Launcher 627-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C641137INCI000050 | U41 - Conduits Installation | IN | INCT3 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 408 | 0 | 10780.IN.IN.MH
C641137INCO000040 | U41 - Communication System Installation | IN | INCO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 693 | 0 | 10780.IN.IN.MH
C641137INCT000090 | U41 - Secondary Cable Trays Installation | IN | INCT2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2204 | 0 | 10610.IN.CT.LM | 600 | 0
C641137INFC000040 | U41 - Fiber Optic Gland & Conn./Testing | IN | INFC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 378 | 0 | 10610.IN.CO.UN | 360 | 0
C641137INFG000050 | U41 - Fire & Gas System Installation | IN | INFG | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 409 | 0 | 10780.IN.IN.MH
C321137INGC000030 | U21 - Multi Pair Cable Gland & Conn./Testing (562) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5558 | 0 | 10610.IN.CO.UN | 250 | 0
C321137INGC000120 | U21 - Multi Pair Cable Gland & Conn./Testing (580) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1780 | 0 | 10610.IN.CO.UN | 150 | 0
C321137INHU000020 | U21 - Pneumatic Hook Up´s Erection (562) | IN | INHU3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 464 | 0 | 10780.IN.IN.MH
C321137INHU000110 | U21 - Pneumatic Hook Up´s Erection (580) | IN | INHU3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 464 | 0 | 10780.IN.IN.MH
C321137INHU000120 | U21 - Process Hook Up´s Erection (580) | IN | INHU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1255 | 0 | 10780.IN.IN.MH
C321137ININ000020 | U21 - Instruments Installation (562) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2850 | 0 | 10610.IN.IN.UN | 300 | 0
C321137ININ000021 | U21 - Valve Installation (562) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2850 | 0 | 10610.IN.IN.UN | 210 | 0
C321137ININ000060 | U21 - Instruments Installation (580) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 913 | 0 | 10610.IN.IN.UN | 200 | 0
C321137ININ000061 | U21 - Valve Installation (580) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 913 | 0 | 10610.IN.IN.UN | 170 | 0
C321137INJB000020 | U21 - Junction Boxes & Local Panels Install.(562) | IN | INJB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3705 | 0 | 10780.IN.IN.MH
C321137INSL000060 | U21 - Single Pair Cable Pulling (580) | IN | INSL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2852 | 0 | 10610.IN.SC.LM | 652.38 | 0
C322131MEMC000310 | U15 - Miscellaneous Piping | PI | PISU2 | 15 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2227 | 0 | 10780.PI.PI.MH
C322131PIBB000080 | U22 - Big Bore Piping A/Equip. Erection 571-PR-156 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000090 | U22 - Big Bore Piping A/Equip. Erection 571-PR-157 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000100 | U22 - Big Bore Piping A/Equip. Erection 571-PR-158 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000110 | U22 - Big Bore Piping A/Equip. Erection PR-571-135 to 571-V-403B, 571-SU-103 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000160 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-120 to 571-V-303 A / 303B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIRA000090 | U22-Piping Erection on Rack (571-PR-147) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 47.4058 | 10610.PI.PR.DI | 1119.81 | 840.0031
C322131PIRA000110 | U22-Piping Erection on Rack (571-PR-151) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000120 | U22-Piping Erection on Rack (571-PR-152) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C321134ELEL000025 | U21 - Earthing & Lightning Works (562) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5111 | 0 | 10610.EL.ES.LM | 1315.08 | 0
C321134ELEL000035 | U21 - Earthing & Lightning Works (562) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5111 | 0 | 10610.EL.ES.LM | 3287.71 | 0
C321134ELEL000085 | U21 - Lightning Works (580) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7239 | 0 | 10780.EL.EL.MH
C321134ELEQ000120 | U21 - GTG Step-up Transformer 580-EE-11511J Installation (580) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2715 | 0 | 10610.EL.EQ.UN | 70 | 0
C321134ELEQ000130 | U21 - STG Generator Circuit Breaker 580-EE-CB-2302K Installation (562) | EL | ELEQ3 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10610.EL.EQ.UN | 120 | 0
C321134ELGR000070 | U21 - Grounding Installation (580) | EL | ELEL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7239 | 0 | 10780.EL.EL.MH
C321134ELPL000060 | U21 - Plant Lighting - (Lighting poles and fixtures) Installation (580) | EL | ELPL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 17645 | 0 | 10780.EL.EL.MH
C321134ELTI000080 | U21 - 11Kv Bus Duct 580-EE-2331K Installation from Circuit Breaker to Generator (562) | EL | ELBD | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1917 | 0 | 10780.EL.EL.MH
C321134ELTI000120 | U21 - Lighting Cable Trays Installation (580) | EL | ELTI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8144 | 0 | 10610.EL.CT.LM | 1495.8 | 0
C321134FPSS000020 | U21 - Steel Structure Fireproofing (562) | FP | FPSS | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 957 | 0 | 10780.FP.FP.MH
C321134PRMR000050 | U21 - Motor Run (580) | PR | PRMR | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2819 | 0 | 10780.PR.PR.MH
C321136MEAC000020 | U21 - Air Coolers Erection - Steam Turbine Generator Lube Oil Cooler (562) | ME | MEAC2 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 29000 | 0 | 10610.ME.ER.TN | 290 | 0
C321136MEAC000060 | U21 - Air Coolers (Waste Heat Boiler Blowdown Cooler) Pre-Assembly 562-E-304 Waste Heat Boiler Blowdown Cooler (580) | ME | MEAC1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0 | 10780.ME.ME.MH
C321136MEPA000040 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Turbine (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 90 | 0
C321136MEPA000070 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Autotune Cabinet Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C321136MEPA000080 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Fuel Gas Skids (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2100 | 0 | 10610.ME.ER.TN | 35 | 0
C321136MEPA000090 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Air Refrigeration Skids (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3180 | 0 | 10610.ME.ER.TN | 53 | 0
C321136MEPA000100 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Hydraulic Oil Console (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C641137ININ000050 | U41 - Instruments Installation | IN | ININ | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1259 | 0 | 10610.IN.IN.UN | 960 | 0
C641137ININ000051 | U41 - Valve Installation | IN | ININ | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1259 | 0 | 10610.IN.IN.UN | 840 | 0
C641137INJB000050 | U41 - Junction Boxes & Local Panels Install. | IN | INJB | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1637 | 0 | 10780.IN.IN.MH
C641137INML000050 | U41 - Multi Pair Cable Pulling | IN | INML | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4912 | 21.609 | 10610.IN.MC.LM | 19624.75 | 13658.826
C641137PRLT000070 | U25 - Loop Testing | PR | PRLT | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2792 | 0 | 10780.PR.PR.MH
C7490PRPRPL000050 | U49 - Punch List | PR | PRPL | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1696 | 0 | 10780.PR.PR.MH
C7490PRPRWT000060 | U49 - Walkthrough | PR | PRWT | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 727 | 0 | 10780.PR.PR.MH
C749131CIPR000000 | U49-Civil Revamp of Piperack Train -1 N-S Road Crossing Rack-55 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIPR000010 | U49- Civil Revamp of Piperack Train -2 N-S Road Crossing Rack-55 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIPR000040 | U49- Civil Revamp of Piperack Train -4 Rack-170 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131PIRA000070 | U49- Pipe Erection on Piperack Train -2 N-S Road Crossing Rack (Approx length 55 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000090 | U49- Pipe Erection on Piperack Train -3 Rack (Approx length 510 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000100 | U49- Pipe Erection on Piperack Train -4 Rack (Approx length 170 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PISB000050 | U49 - Small Bore Piping A/Equip. Erection | PI | PISB | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 396 | 0 | 10780.PI.PI.MH
C749131PISU000100 | U49 - Piping Supports Erection | PI | PISU2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6465 | 0 | 10610.PI.SU.TN | 14.37 | 0
C749131PRFL000060 | U41 - Piping Flushing/Blowing | PR | PRFL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9883 | 0 | 10610.PR.FL.DI | 51425 | 0
C749131PRHT000050 | U49 - Piping Hydrotesting | PR | PRHT | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34179 | 0 | 10610.PR.HT.DI | 14453 | 0
C749131STPR000010 | U49- Structure revamp of Piperack Train -2 N-S Road Crossing Rack-55 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.ST.PR.TN | 2.7 | 0
C749131STPR000040 | U49- Structure revamp of Piperack Train -4 Rack-170 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 111 | 0 | 10610.ST.PR.TN | 2.1 | 0
C749132CIGR000050 | U49 - Grounding Network Execution | CI | CIGR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1 | 0 | 10610.CI.GR.LM | 1 | 0
C322131PIRA000130 | U22-Piping Erection on Rack (571-PR-153) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000180 | U22-Piping Erection on Rack (571-PR-142) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000190 | U22-Piping Erection on Rack (571-PR-141) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000210 | U22-Piping Erection on Rack (571-PR-138) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000240 | U22-Piping Erection on Rack (571-PR-136) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 33.3509 | 10610.PI.PR.DI | 1119.81 | 572.9956
C322131PIRA000400 | U22 - Piping Erection on Rack ((577-PB-114) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 65.4444 | 10610.PI.PR.DI | 1119.81 | 552.3463
C322131PIRA000420 | U22 - Piping Erection on Rack (577-PB-116) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 56.9503 | 10610.PI.PR.DI | 1119.81 | 462
C322131PIRA000430 | U22-Piping Erection on Rack (577-PR-117) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 56.4311 | 10610.PI.PR.DI | 1119.81 | 432.9969
C322131PIRA000440 | U22-Piping Erection on Rack (577-PR-118) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 47.4208 | 10610.PI.PR.DI | 1119.81 | 362.001
C322131PIRA000500 | U22-Piping Erection on Main Piperack/Bridge (571-PB-126) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000520 | U22-Piping Erection on Main Piperack/Bridge (571-PB-128) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 8.9443 | 10610.PI.PR.DI | 1119.81 | 155.9895
C322131PIRA000540 | U22-Piping Erection on Rack (571-PR-130) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 4.7385 | 10610.PI.PR.DI | 1119.81 | 79.9992
C322131PIRA000550 | U22-Piping Erection on Rack (571-PR-131) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 10.3802 | 10610.PI.PR.DI | 1119.81 | 176.0005
C322131PIRA000570 | U22 - Piping Erection on Main Piperack/Bridge (571-PB-132A) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000600 | U22-Piping Erection on Rack (571-PR-135) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 5.3072 | 10610.PI.PR.DI | 1119.81 | 0
C322131PISB000100 | U22 - Small Bore Piping A/Equip. Erection PR-571-141 to 571-E701/702A cooler & 571-C701 A | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000140 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-117 / 118 to 571-V-302 A / 302B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000160 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-120 to 571-V-303 A / 303B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISU000160 | U22 - Piping Supports Erection | PI | PISU2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 178306 | 0 | 10610.PI.SU.TN | 396.24 | 0
C749132CIPV000100 | U49 - Concrete Paving Execution | CI | CIPV1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3314 | 0 | 10610.CI.PV.M2 | 1841.11 | 0
C749132CIPV000110 | U49 - Gravel Paving Execution | CI | CIPV2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1620 | 0 | 10780.CI.CI.MH
C749132CIST000190 | U49 - Jib Crane Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 0 | 10610.CI.CO.M3 | 20.13 | 0
C749132CIST000190 | U49 - Jib Crane Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 0 | 10610.CI.CO.M3 | 20.13 | 0
C749132CIST000200 | U49 - Pig Trolley Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10610.CI.CO.M3 | 5.94 | 0
C749133PAFP000050 | U49 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 140 | 0 | 10610.PA.FP.M2 | 584 | 0
C749133PASP000050 | U49 - Piping Supports SandBl. & Priming | PA | PASP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 148 | 0 | 10610.PA.SU.TN | 0 | 0
C749134ELEL000055 | U49 - Earthing Works | EL | ELEL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 844 | 0 | 10610.EL.ES.LM | 3945.25 | 0
C749134ELMS000060 | U49-Miscellaneous Electrical Work | EL | ELEQ2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 475 | 0 | 10780.EL.EL.MH
C749134ELTI000080 | U49 - Lighting Cable Trays Installation | EL | ELTI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.CT.LM | 111.94 | 0
C749134ELTI000090 | U49 - Electrical Cable Trays Installation | EL | ELTI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3164 | 0 | 10610.EL.CT.LM | 207.88 | 0
C749136MEVV000020 | U49 - 30" PL-952 Scrapper Receiver 952-V-501 (R) Erection | ME | MEVV | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C749136MEVV000045 | U49 - COARSE FILTER 952-F-101 Erection | ME | METC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749137INAI000030 | U49 - Analyzers Equipment Installation | IN | INAI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1444 | 0 | 10610.IN.AI.UN | 1 | 0
C749137INCT000060 | U49 - Primary Cable Trays Installation | IN | INCT1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6686 | 0 | 10610.IN.CT.LM | 600 | 0
C749137INFG000040 | U49 - Fire & Gas System Installation | IN | INFG | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 695 | 0 | 10780.IN.IN.MH
C749137INGC000080 | U49 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2781 | 0 | 10610.IN.CO.UN | 350 | 0
C749137ININ000040 | U49 - Instruments Installation | IN | ININ | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2139 | 0 | 10610.IN.IN.UN | 350 | 0
C749137INSL000040 | U49 - Single Pair Cable Pulling | IN | INSL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6686 | 0 | 10610.IN.SC.LM | 7698.27 | 0
NN-C220BUTR000000010 | U20 - SS-516 - Transf. Yard Foundations #B (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14372 | 305.1412 | 10610.BU.CO.M3 | 175 | 175
C322131PRBO000110 | U22 - Rotary Box Up | PR | PRBO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6687 | 0 | 10780.PR.PR.MH
C322132CIDB000045 | U22 - Duct Banks Precast Installation | CI | CIDB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 62820 | 4430.7005 | 10610.CI.CO.M3 | 1256.39 | 1256.3904
C322132CIGR000080 | U22 - Grounding Network Execution | CI | CIGR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6360 | 0 | 10780.CI.CI.MH
C322132CIHE000210 | U22 - Horizontal Intermediate LT Flare K.O Drum Foundation Execution (571-V-302A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8276 | 100.6556 | 10610.CI.CO.M3 | 137.94 | 137.9399
C322132CIHE000220 | U22 - Horizontal Blowdown Drum Foundation Execution (571-V-505) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5521 | 43.2304 | 10610.CI.CO.M3 | 92.02 | 92.0202
C322132CIHE000240 | U22 - Horizontal Intermediate Acid Gas Flare K.O Drum Foundation Execution (571-V-303) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 36035 | 1918.2952 | 10610.CI.CO.M3 | 720.7 | 720.7021
C322132CIMF000070 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-401A) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4945 | 26.7139 | 10610.CI.CO.M3 | 82.42 | 53.5697
C322132CIMF000080 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-401B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5318 | 34.2598 | 10610.CI.CO.M3 | 88.64 | 70.9102
C322132CIMF000110 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-402B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 17.6912 | 10610.CI.CO.M3 | 58.51 | 58.51
C322132CIMF000150 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-302 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5216 | 38.5071 | 10610.CI.CO.M3 | 86.94 | 85.1999
C322132CIMF000180 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-303 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8088 | 96.031 | 10610.CI.CO.M3 | 134.81 | 134.8105
C322132CIMF000210 | U22 - Miscellaneous Foundations Execution (571-FH-303/306/307/309) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6218 | 4.9974 | 10610.CI.CO.M3 | 103.63 | 0
C322132CIMF000210 | U22 - Miscellaneous Foundations Execution (571-FH-303/306/307/309) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6218 | 4.9974 | 10610.CI.CO.M3 | 103.63 | 0
C322132CIPD000030 | U22 - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13659 | 275.6159 | 10780.CI.CI.MH
C322132CIPR000310 | U22 - Main Piperack Foundations Execution (571-PR-147) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11794 | 202.8851 | 10610.CI.CO.M3 | 235.87 | 235.8699
C322132CIPR000310 | U22 - Main Piperack Foundations Execution (571-PR-147) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11794 | 202.8851 | 10610.CI.CO.M3 | 235.87 | 235.8699
C322132CIPR000320 | U22 - Main Piperack Foundations Execution (571-PR-146) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24188 | 853.3874 | 10610.CI.CO.M3 | 483.76 | 483.76
C322132CIPR000390 | U22 - Main Piperack Foundations Execution (571-PR-143) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12080 | 0 | 10610.CI.CO.M3 | 241.6 | 0
C322132CIPR000400 | U22 - Main Piperack Foundations Execution (571-PR-142) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10764 | 125.6348 | 10610.CI.CO.M3 | 215.28 | 150.6999
C321136MEPA000110 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Lube oil Skid (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 900 | 0 | 10610.ME.ER.TN | 15 | 0
C321136MEPA000130 | U21 - Package Installation Gas Turbine Generator Pack. 580-ME-101J (580) - Turbine (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5400 | 0 | 10610.ME.ER.TN | 90 | 0
C321136MEPA000230 | U21 - Package Installation Steam Turbine Generator 580-ME-101K/562-ST-301 (562) - Steam Gland Condenser (500 TON) | ME | MEPA | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1740 | 0 | 10610.ME.ER.TN | 29 | 0
C321136MESB000010 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - By Pass & Main Stacks | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4200 | 0 | 10610.ME.ER.TN | 105 | 0
C321136MESB000030 | U21 - Waste Heat Boiler Erection 562-B-101J (580) - Heater | ME | MESB | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6600 | 0 | 10610.ME.ER.TN | 165 | 0
C321137INAI000050 | U21 - Analyzers Equipment Installation (580) | IN | INAI | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 616 | 0 | 10610.IN.AI.UN | 1 | 0
C321137INFC000060 | U21 - Fiber Optic Gland & Conn./Testing (580) | IN | INFC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 274 | 0 | 10610.IN.CO.UN | 310 | 0
C321137INFO000020 | U21 - Fiber Optic Cable Pulling (562) | IN | INFO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1211 | 0 | 10610.IN.FO.LM | 2977 | 0
C321137INFO000050 | U21 - Fiber Optic Cable Pulling (580) | IN | INFO | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 388 | 0 | 10610.IN.FO.LM | 3011 | 0
C321137INGC000030 | U21 - Multi Pair Cable Gland & Conn./Testing (562) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5558 | 0 | 10610.IN.CO.UN | 250 | 0
C321137INGC000120 | U21 - Multi Pair Cable Gland & Conn./Testing (580) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1780 | 0 | 10610.IN.CO.UN | 150 | 0
C321137INGC000130 | U21 - Single Pair Cable Gland & Conn./Testing (580) | IN | INGC | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1186 | 0 | 10610.IN.CO.UN | 190 | 0
C321137INHU000030 | U21 - Process Hook Up´s Erection (562) | IN | INHU1 | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3919 | 0 | 10780.IN.IN.MH
C321137ININ000021 | U21 - Valve Installation (562) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2850 | 0 | 10610.IN.IN.UN | 210 | 0
C321137ININ000060 | U21 - Instruments Installation (580) | IN | ININ | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 913 | 0 | 10610.IN.IN.UN | 200 | 0
C321137INIP000021 | U21 - Valve Calibration (562) | IN | INIP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 926 | 0 | 10780.IN.IN.MH
C321137INIP000060 | U21 - Instruments Calibration (580) | IN | INIP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 297 | 0 | 10780.IN.IN.MH
C321137INIP000061 | U21 - Valve Calibration (580) | IN | INIP | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 297 | 0 | 10780.IN.IN.MH
C321137INML000020 | U21- Multi Pair Cable Pulling (562) | IN | INML | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11115 | 0 | 10610.IN.MC.LM | 20672.33 | 0
C321137INML000060 | U21- Multi Pair Cable Pulling (580) | IN | INML | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3559 | 0 | 10610.IN.MC.LM | 17902.52 | 0
C322132CIPR000400 | U22 - Main Piperack Foundations Execution (571-PR-142) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10764 | 125.6348 | 10610.CI.CO.M3 | 215.28 | 150.6999
C322132CIPR000410 | U22 - Main Piperack Foundations Execution (571-PR-141) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10108 | 150.9299 | 10610.CI.CO.M3 | 202.15 | 202.1498
C322132CIPR000430 | U22 - Main Piperack Foundations Execution (571-PR-138) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20224 | 600.394 | 10610.CI.CO.M3 | 404.47 | 404.47
C322132CIPR000450 | U22 - Main Piperack Foundations Execution (571-PR-145) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10572 | 164.0693 | 10610.CI.CO.M3 | 211.44 | 211.44
C322132CIPR000730 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-127) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9310 | 5.3921 | 10610.CI.CO.M3 | 155.17 | 0
C322132CIPR000750 | U22 - Main Piperack Foundations Execution (571-PR-129) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28149 | 18.4831 | 10610.CI.CO.M3 | 562.98 | 0
C322132CIPR000760 | U22 - Main Piperack Foundations Execution (571-PR-130) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15410 | 2.9538 | 10610.CI.CO.M3 | 308.2 | 0
C322132CIPR000770 | U22 - Main Piperack Foundations Execution (571-PR-131) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12938 | 2.0822 | 10610.CI.CO.M3 | 258.76 | 0
C322132CIPR000830 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701B/702B & 571-PR-157) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28391 | 1049.2586 | 10610.CI.CO.M3 | 567.82 | 504.2185
C322132CIPR000840 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701A/702A & 571-PR-156) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17171 | 395.0399 | 10610.CI.CO.M3 | 343.42 | 321.4411
C322132CIPR000850 | U22 - Secondary Piperack Foundations Execution (545-29/26-545 BJ-BK) | CI | CIPR2 | 22 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11220 | 0 | 10610.CI.CO.M3 | 224.4 | 0
C322132CIPR100000 | U22 - Main Piperack Foundations Execution (577-PR-116) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 37213 | 2045.7651 | 10610.CI.CO.M3 | 744.26 | 744.2607
C322132CIPR100020 | U22 - Main Piperack Foundations Execution (577-PR-115) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43473 | 2791.937 | 10610.CI.CO.M3 | 869.46 | 869.46
C322132CIPR100040 | U22 - Main Piperack Foundations Execution (577-PR-118) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47496 | 3279.1912 | 10610.CI.CO.M3 | 949.92 | 949.9202
C322132CIPR100070 | U22 - Main Piperack Foundations Execution (577-PB-121) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 94186 | 13105.0627 | 10610.CI.CO.M3 | 1883.72 | 1883.72
C322132CIPS000090 | U22 - Acid Gas Flare drain Drum Foundation Execution inside sump (571-V-406) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3018 | 8.4975 | 10610.CI.CO.M3 | 50.3 | 50.3
C322132CIPS000100 | U22 - Sumps Construction (571-SU-301) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6642 | 55.0329 | 10780.CI.CI.MH
C322132CIPS000140 | U22 - Sumps Construction (571-SU-103) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9386 | 13.6991 | 10780.CI.CI.MH
C322132CIRE000110 | U22 - HC Flare Gas Recovery Compressor Foundation Execution (571-C-701B) | CI | CIRE2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10902 | 164.4918 | 10610.CI.CO.M3 | 181.7 | 181.7
C321137INSL000060 | U21 - Single Pair Cable Pulling (580) | IN | INSL | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2852 | 0 | 10610.IN.SC.LM | 652.38 | 0
C321137PRLT000060 | U21 - Loops Testing (580) | PR | PRLT | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5578 | 0 | 10780.PR.PR.MH
C321CIST000000010 | U21 - Platform 562-TOS EL. 117000 Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2398 | 0 | 10610.CI.CO.M3 | 39.97 | 0
C321CIST000000010 | U21 - Platform 562-TOS EL. 117000 Foundation Execution (562) | CI | CIST | 21 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2398 | 0 | 10610.CI.CO.M3 | 39.97 | 0
C3220PRPRWT000070 | U22 - Walkthrough | PR | PRWT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6062 | 0 | 10780.PR.PR.MH
C322131ISPI000080 | U22 - Piping Insulation | IS | ISPI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31394 | 0 | 10780.IS.IS.MH
C322131NITR000010 | U22 - Nitrogen Leak Test (Unit 571) | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3333 | 0 | 10780.PR.PR.MH
C322131PIBB000080 | U22 - Big Bore Piping A/Equip. Erection 571-PR-156 | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000130 | U22 - Big Bore Piping A/Equip. Erection PR-571-137/136 to 571-V-402 A & 402B | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000140 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-117 / 118 to 571-V-302 A / 302B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIBB000150 | U22 - Big Bore Piping A/Equip. Erection - 577-PR-118 / 119 to 571-V-301 A / 301B and other Equipment around | PI | PIBB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52844 | 0 | 10610.PI.BB.DI | 5284.4 | 0
C322131PIPR000070 | U22 - Piping Prefabrication | PI | PIPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 438493 | 216131.8821 | 10610.PI.FB.DI | 109623.13 | 59663.4298
C322131PIRA000090 | U22-Piping Erection on Rack (571-PR-147) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 47.4058 | 10610.PI.PR.DI | 1119.81 | 840.0031
C322131PIRA000100 | U22-Piping Erection on Rack (571-PR-146) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0.66321 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000130 | U22-Piping Erection on Rack (571-PR-153) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000150 | U22-Piping Erection on Rack (571-PR-155) (Including Tower near flare) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000170 | U22-Piping Erection on Rack (571-PR-143) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000190 | U22-Piping Erection on Rack (571-PR-141) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000200 | U22-Piping Erection on Rack (571-PR-139/140) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000240 | U22-Piping Erection on Rack (571-PR-136) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 33.3509 | 10610.PI.PR.DI | 1119.81 | 572.9956
C322132CIRE000130 | U22 - Acid Gas Flare K.O Drum Pumps Foundation Execution (571-P-403 A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2834 | 0 | 10610.CI.CO.M3 | 47.24 | 0
C322132CIRE000140 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701A) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000170 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000180 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701E) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000190 | U22 - Hydrocarbon Flare K.O. Drum Pumps Foundation Execution (571-P-401 A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1403 | 0 | 10610.CI.CO.M3 | 23.38 | 0
C322132CIRE000220 | U22 - Vertical Intermediate LT K.O Drum Pump Foundation Execution (571-P-302A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2842 | 0 | 10610.CI.CO.M3 | 47.36 | 0
C322132CIRE000230 | U22 - Intermediate Acid Gas Flare K.O Drum Pump Foundation Execution (571-P-303A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 656 | 0 | 10610.CI.CO.M3 | 9.37 | 0
C322132CIRE000250 | U22 - Blowdown Drum Sour Water Pump Foundation Execution (571-P-504A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 368 | 0.02103 | 10610.CI.CO.M3 | 5.25 | 0
C322132CISF000040 | U22 - Stairs & Small Foundations Execution | CI | CISF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6218 | 6.0117 | 10610.CI.CO.M3 | 103.63 | 0
C322132CITF100470 | U22 - TEG Storage Tank Foundation Execution (571-TK-201) | CI | CITF1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 6.6909 | 10610.CI.CO.M3 | 35.87 | 35.87
C322132CIUG000090 | U22 - UG GRE Pipe Installation (FW) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 512 | 0.056521 | 10610.CI.UG.LM | 25.59 | 3.8399
C322132CIUG000090 | U22 - UG GRE Pipe Installation (FW) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 512 | 0.056521 | 10610.CI.UG.LM | 25.59 | 3.8399
C322132CIUG200010 | U22 - UG Pipe Installation (CD) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6361 | 4.2161 | 10610.CI.UG.LM | 318.06 | 25.4384
C322132CIUG200020 | U22 - UG Pipe Installation (OD) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 56036 | 655.4506 | 10610.CI.UG.LM | 2801.78 | 588.3738
C322132CIVE000150 | U22 - LT Flare Package Foundation Execution (571-ME-402) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64661 | 6176.5772 | 10610.CI.CO.M3 | 1293.21 | 1293.2092
C322132CIVE000220 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000230 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.33985 | 10610.CI.CO.M3 | 9.74 | 6.96
C322132CIVE000250 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322131PIRA000410 | U22 - Piping Erection on Rack (577-PR-115) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 61.6737 | 10610.PI.PR.DI | 1119.81 | 485.0009
C322131PIRA000430 | U22-Piping Erection on Rack (577-PR-117) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 56.4311 | 10610.PI.PR.DI | 1119.81 | 432.9969
C322131PIRA000440 | U22-Piping Erection on Rack (577-PR-118) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 47.4208 | 10610.PI.PR.DI | 1119.81 | 362.001
C322131PIRA000450 | U22-Piping Erection on Rack (577-PR-119 / 119 A) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 37.3016 | 10610.PI.PR.DI | 1119.81 | 323.9946
C322131PIRA000460 | U22-Piping Erection on Rack (577-PR-120) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 23.2212 | 10610.PI.PR.DI | 1119.81 | 218.0046
C322131PIRA000510 | U22-Piping Erection on Main Piperack/Bridge (571-PB-127) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000530 | U22-Piping Erection on Rack (571-PR-129) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 3.217 | 10610.PI.PR.DI | 1119.81 | 56.0017
C322131PIRA000530 | U22-Piping Erection on Rack (571-PR-129) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 3.217 | 10610.PI.PR.DI | 1119.81 | 56.0017
C322131PIRA000560 | U22-Piping Erection on Rack (571-PR-132) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000570 | U22 - Piping Erection on Main Piperack/Bridge (571-PB-132A) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PIRA000590 | U22-Piping Erection on Rack (571-PR-134) | PI | PIRA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10078 | 0 | 10610.PI.PR.DI | 1119.81 | 0
C322131PISB000081 | U22 - Small Bore Piping A/Equip. Erection PR-571-142 to 571-E701/702C cooler & 571-C701 C | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000090 | U22 - Small Bore Piping A/Equip. Erection PR-571-141 to 571-E701/702B cooler & 571-C701 B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000100 | U22 - Small Bore Piping A/Equip. Erection PR-571-141 to 571-E701/702A cooler & 571-C701 A | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000120 | U22 - Small Bore Piping A/Equip. Erection PR-571-138/137 to 571-V-401 A & 401B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000130 | U22 - Small Bore Piping A/Equip. Erection PR-571-137/136 to 571-V-402 A & 402B | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000140 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-117 / 118 to 571-V-302 A / 302B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISB000150 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-118 / 119 to 571-V-301 A / 301B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322132CIVE000250 | U22 - HC Flare Gas Recovery Compressor Discharge KOD Foundation Execution (571-V-703B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000280 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.33985 | 10610.CI.CO.M3 | 9.74 | 6.96
C322132CIVE000290 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.017233 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000290 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.017233 | 10610.CI.CO.M3 | 2.47 | 0
C322132ELCT000010 | U22 - Cathodic Protection Tanks | EL | ELCT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8174 | 0 | 10780.EL.EL.MH
C322132METK110010 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Annular Plate and Bottom Plate Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6500 | 62.4156 | 10610.ME.TE.TN | 65 | 65
C322132METK110060 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Shell 5, Shell 6 and Compression Ring Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 5.8796 | 10610.ME.TE.TN | 20 | 20
C322132METK110090 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 2 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110160 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 5 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110180 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Platform & Staircase Erection for Shell 6 and Shell 5 | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1100 | 0.1211 | 10610.ME.TE.TN | 11 | 0.77
C322132METK110200 | U22 - TEG Storage Tank Erection 571-TK-201 - Hydraulic Test | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 260 | 0.099865 | 10610.PR.HT.DI | 6 | 6
C322132METK110210 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 7 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.86037 | 10610.ME.TE.TN | 8 | 7.28
C322132METK110220 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 4 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110230 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 8 & Compression Ring Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.37819 | 10610.ME.TE.TN | 8 | 3.2
C322132METK110270 | U23 - (566 CWS) - Storage Tank 566-TK-201- Partition Plate Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.75637 | 10610.ME.TE.TN | 8 | 6.4
C322132METK110290 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 2 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110310 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Staircase Erection for Remaining Shells | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110330 | U23 - (566 CWS) - Storage Tank 566-TK-201 - Roof Platform & Staircase Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.TE.TN | 15 | 0
C322132SPSP000010 | U22 - U/G Detection Works and re-routing of services | SP | SPSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1560 | 3.5951 | 10780.SP.SP.MH
C322132STEQ000080 | U22 - Miscellaneous Platform Structure Erection (Plt-V401A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 964 | 0 | 10610.ST.PL.TN | 18.18 | 0
C322132STEQ000090 | U22 - Miscellaneous Platform Structure Erection (Plt-V401B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 964 | 0 | 10610.ST.PL.TN | 18.18 | 0
C322132STEQ000100 | U22 - Miscellaneous Piping Tower Structure Erection (571-V401 A/B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 0 | 10780.ST.ST.MH
C322132STEQ000120 | U22 - Miscellaneous Platform Structure Erection (Plt-V402B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1059 | 0 | 10610.ST.PL.TN | 19.99 | 0
C322132STEQ000190 | U22 - Acid Gas Flare Drain Drum platform inside sump (571-V-406) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 848 | 0 | 10780.ST.ST.MH
C322132STEQ000220 | U22 - LT Flare Package Supporting Structure (571-ME-402) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14416 | 76.9373 | 10780.ST.ST.MH
C322132STEQ000260 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V301 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1759 | 0 | 10610.ST.PL.TN | 33.2 | 0
C322132STEQ000270 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V302 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1901 | 0 | 10610.ST.PL.TN | 35.88 | 0
C322132STEQ000270 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V302 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1901 | 0 | 10610.ST.PL.TN | 35.88 | 0
C322132STEQ000300 | U22 - Intermediate HC Flare Drain Drum platform inside sump (571-V-304) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 636 | 0 | 10780.ST.ST.MH
C322132STEQ000310 | U22 - Intermediate Acid Gas Flare Drain Drum platform inside sump (571-V-405) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.015759 | 10780.ST.ST.MH
C322132STPL000160 | U22 - Equipment Structures, Ladders & Handrails Erection | ST | STPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7009 | 5.8297 | 10610.ST.PL.TN | 87.61 | 6.9914
C322132STPR000120 | U22 - Main Piperack Erection (571-PR-148) (Including Tower near flare) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8095 | 70.7208 | 10610.ST.PR.TN | 152.74 | 152.1278
C322132STPR000140 | U22 - Main Piperack Erection (571-PR-147) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7546 | 58.1412 | 10610.ST.PR.TN | 142.38 | 136.3372
C322132STPR000180 | U22 - Main Piperack Erection (571-PR-153) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5810 | 45.5697 | 10610.ST.PR.TN | 109.63 | 109.6311
C322132STPR000200 | U22 - Main Piperack Erection (571-PR-155) (Including Tower near flare) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9111 | 15.2292 | 10610.ST.PR.TN | 171.9 | 9.9494
C322132STPR000220 | U22 - Main Piperack Erection (571-PR-143) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7990 | 0 | 10610.ST.PR.TN | 150.76 | 0
C322131PISB000160 | U22 - Small Bore Piping A/Equip. Erection - 577-PR-120 to 571-V-303 A / 303B and other Equipment around | PI | PISB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7813 | 0 | 10610.PI.SB.DI | 710.28 | 0
C322131PISU000150 | U22 - Piping Supports Prefabrication | PI | PISU1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 103021 | 10665.8335 | 10610.PI.PU.TN | 396.24 | 140.9393
C322131PRFL000310 | U22 - Chemical Cleaning for Compressor Suction Lines (Unit 571) | PR | PRFL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3999 | 0 | 10780.PR.PR.MH
C322131PRRE000050 | U22 - Piping Reinstatement | PR | PRRE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 131303 | 0 | 10610.PR.RE.DI | 261183 | 0
C322132CIBW100010 | U22 - TEG Storage Tank Dike Wall (571-TK-201) | CI | CIBW1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 6.8421 | 10610.CI.CO.M3 | 35.87 | 35.87
C322132CICT000060 | U22 - Electrical earth Trenches Execution | CI | CICT2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8640 | 12.9027 | 10780.CI.CI.MH
C322132CICT000070 | U22 - Instrument earth Trenches Execution | CI | CICT3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8640 | 11.5242 | 10780.CI.CI.MH
C322132CICT000080 | U22 - Covered Concrete Trenches Execution | CI | CICT1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11997 | 65.3987 | 10610.CI.CO.M3 | 239.93 | 199.9999
C322132CIDM000050 | U22 - Manholes & Catchbasins Installation | CI | CIDM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31773 | 666.1067 | 10610.CI.CO.M3 | 635.45 | 399.9999
C322132CIGT000140 | U22 - Equipment Grouting Execution | CI | CIGT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1260 | 0 | 10780.CI.CI.MH
C322132CIHE000130 | U22 - Horizontal Vessel (LT Flare K.O Drum) Foundation Execution (571-V-402A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15530 | 322.5341 | 10610.CI.CO.M3 | 310.6 | 310.6
C322132CIHE000150 | U22 - Horizontal Exchanger (LT Flare K.O Drum Heater) Foundation Execution (571-E-402A) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.CI.CO.M3 | 11.43 | 0
C322132CIHE000160 | U22 - Horizontal Exchanger (LT Flare K.O Drum Heater) Foundation Execution (571-E-402B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.CI.CO.M3 | 11.43 | 0
C322132CIHE000160 | U22 - Horizontal Exchanger (LT Flare K.O Drum Heater) Foundation Execution (571-E-402B) | CI | CIHE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10610.CI.CO.M3 | 11.43 | 0
C322132CIMF000070 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-401A) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4945 | 26.7139 | 10610.CI.CO.M3 | 82.42 | 53.5697
C322132CIMF000080 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-401B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5318 | 34.2598 | 10610.CI.CO.M3 | 88.64 | 70.9102
C322132CIMF000090 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-401 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5318 | 26.2777 | 10610.CI.CO.M3 | 88.64 | 48.7502
C322132CIMF000110 | U22 - Miscellaneous Platform Foundations Execution (Plt-V-402B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 17.6912 | 10610.CI.CO.M3 | 58.51 | 58.51
C322132CIMF000190 | U22 - Miscellaneous Platform Foundations Execution (571-PLT-V-505) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28481 | 1163.5796 | 10610.CI.CO.M3 | 569.62 | 569.621
C322132STPR000260 | U22 - Main Piperack Erection (571-PR-138) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10371 | 119.696 | 10610.ST.PR.TN | 195.68 | 156.5393
C322132STPR000270 | U22 - Main Piperack Erection (571-PR-137) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13793 | 191.924 | 10610.ST.PR.TN | 260.24 | 218.6005
C322132STPR000280 | U22 - Main Piperack Erection (571-PR-145) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7613 | 69.6106 | 10610.ST.PR.TN | 143.64 | 143.6362
C322132STPR000300 | U22 - Main Piperack Erection (571-PB-126) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18056 | 0 | 10610.ST.PR.TN | 340.68 | 0
C322132STPR000303 | U22 - Main Piperack Erection (571-PR-129) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10511 | 0 | 10610.ST.PR.TN | 198.32 | 0
C322132STPR000305 | U22 - Main Piperack Erection (571-PR-131) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8083 | 0 | 10610.ST.PR.TN | 152.52 | 0
C322132STPR000310 | U22 - Main Piperack Erection (571-PB-132A) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6955 | 0 | 10610.ST.PR.TN | 131.23 | 0
C322132STPR000420 | U22 - Main Piperack Erection (571-PR-134) (Including Tower near 571-V-403) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11914 | 0 | 10610.ST.PR.TN | 224.8 | 0
C322132STPR100010 | U22 - Main Piperack Erection (577-PB-114) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 33769 | 699.3468 | 10610.ST.PR.TN | 637.16 | 262.0588
C322132STPR100050 | U22 - Main Piperack Erection (577-PR-119 / 577-PR-119A) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40866 | 2171.0423 | 10610.ST.PR.TN | 771.05 | 766.9988
C322132STPR100080 | U22 - Secondary Piperack Erection (571-PR-156) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12984 | 0 | 10610.ST.PR.TN | 244.99 | 0
C322132STSH000060 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701B) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322132STSH000090 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701A) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322132STSP000080 | U22 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12852 | 0 | 10610.ST.PL.TN | 214.21 | 0
C322134ELCI000070 | U22 - Conduits Installation | EL | ELCI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10217 | 0 | 10780.EL.EL.MH
C322134ELCL000150 | U22 - Lighting Cable Laying | EL | ELCL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18391 | 0 | 10610.EL.LC.LM | 105611.52 | 0
C322134ELCL000160 | U22 - Electrical Cable Laying | EL | ELCL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89909 | 0 | 10610.EL.PL.LM | 112350.77 | 0
C322134ELCO000140 | U22 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.CO.UN | 270 | 0
C322134ELCO000150 | U22 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 49042 | 0 | 10610.EL.CO.UN | 1552 | 0
C322134ELCP000070 | U22 - Cathodic Protection Piping | EL | ELCP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8174 | 0 | 10780.EL.EL.MH
C322132CIMF000200 | U22 - Miscellaneous Foundations Execution (571-HM-304/305/317) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7273 | 6.8372 | 10610.CI.CO.M3 | 121.21 | 40
C322132CIMF000200 | U22 - Miscellaneous Foundations Execution (571-HM-304/305/317) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7273 | 6.8372 | 10610.CI.CO.M3 | 121.21 | 40
C322132CIMF000230 | U22 - Miscellaneous Platform Foundations Execution (PLT-V-403 A/B) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3511 | 0.68283 | 10610.CI.CO.M3 | 58.51 | 0
C322132CIMF000240 | U22 - Miscellaneous Piping Tower Foundations Execution (571-V-403) | CI | CIMF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3899 | 13.4053 | 10610.CI.CO.M3 | 64.99 | 38.9901
C322132CIOT000020 | U22 - Open Concrete Trenches Execution | CI | CIOT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11997 | 156.3071 | 10610.CI.CO.M3 | 239.93 | 208.7391
C322132CIPE000070 | U22 - Acid Gas Flare Package Foundation Execution (571-ME-403) | CI | CIPE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 70207 | 7276.9676 | 10610.CI.CO.M3 | 1404.13 | 1404.1314
C322132CIPR000320 | U22 - Main Piperack Foundations Execution (571-PR-146) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24188 | 853.3874 | 10610.CI.CO.M3 | 483.76 | 483.76
C322132CIPR000360 | U22 - Main Piperack Foundations Execution (571-PR-154) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13104 | 251.5071 | 10610.CI.CO.M3 | 262.07 | 262.0699
C322132CIPR000370 | U22 - Main Piperack Foundations Execution (571-PR-155) (Including Tower near flare) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18290 | 478.1287 | 10610.CI.CO.M3 | 365.8 | 365.8005
C322132CIPR000460 | U22 - Main Piperack Foundations Execution (571-PR-136) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23547 | 819.0838 | 10610.CI.CO.M3 | 470.93 | 470.9304
C322132CIPR000720 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-126) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12511 | 18.2559 | 10610.CI.CO.M3 | 250.22 | 0
C322132CIPR000720 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-126) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12511 | 18.2559 | 10610.CI.CO.M3 | 250.22 | 0
C322132CIPR000730 | U22 - Main Piperack/Bridge Foundations Execution (571-PB-127) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9310 | 5.3921 | 10610.CI.CO.M3 | 155.17 | 0
C322132CIPR000780 | U22 - Main Piperack Foundations Execution (571-PR-132) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17626 | 12.0798 | 10610.CI.CO.M3 | 352.52 | 0
C322132CIPR000780 | U22 - Main Piperack Foundations Execution (571-PR-132) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17626 | 12.0798 | 10610.CI.CO.M3 | 352.52 | 0
C322132CIPR000800 | U22 - Main Piperack Foundations Execution (571-PR-133) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23620 | 84.0672 | 10610.CI.CO.M3 | 472.4 | 0
C322132CIPR000800 | U22 - Main Piperack Foundations Execution (571-PR-133) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 23620 | 84.0672 | 10610.CI.CO.M3 | 472.4 | 0
C322132CIPR000810 | U22 - Main Piperack Foundations Execution (571-PR-134) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18124 | 473.4309 | 10610.CI.CO.M3 | 362.47 | 362.47
C322132CIPR000820 | U22 - Main Piperack Foundations Execution (571-PR-135) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27139 | 1088.0631 | 10610.CI.CO.M3 | 542.78 | 542.7805
C322134ELEL000085 | U22 - Earthing Works | EL | ELEL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10898 | 0 | 10610.EL.ES.LM | 6575.42 | 0
C322134ELTI000150 | U22 - Electrical Cable Trays Installation | EL | ELTI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40868 | 0 | 10610.EL.CT.LM | 11472.02 | 0
C322134MEMC000150 | U22 - Miscellaneous Electrical | EL | ELEQ2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6130 | 0 | 10780.EL.EL.MH
C322136MEAC000090 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702A | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C322136MEAC000100 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Pre-Assembly 571-E-702A | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000140 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Pre-Assembly 571-E-702C | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000150 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701B | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000160 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701C | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000170 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702B | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000180 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702C | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MECO000090 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701B (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MECO000100 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701C (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEHE000140 | U22 - Heat Exchangers (Intermediate LT Flare K.O Drum Heater) Erection 571-E-302B | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHL000080 | U22 - Heavy Equipment (Intermediate LT K.O. Drum ) Erection (571-V-302B) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEHM000200 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000260 | U22 - Horizontal Pump (Intermediate Acid Gas Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-303A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000270 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401A (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322132CIPR000840 | U22 - Main & Secondary Piperack Foundations Execution (571-E-701A/702A & 571-PR-156) | CI | CIPR2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17171 | 395.0399 | 10610.CI.CO.M3 | 343.42 | 321.4411
C322132CIPR100030 | U22 - Main Piperack Foundations Execution (577-PR-117) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 53605 | 4244.9932 | 10610.CI.CO.M3 | 1072.1 | 1072.1
C322132CIPR100050 | U22 - Main Piperack Foundations Execution (577-PR-119 / 577-PR-119A) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 101011 | 15073.1402 | 10610.CI.CO.M3 | 2020.22 | 2020.22
C322132CIPR100050 | U22 - Main Piperack Foundations Execution (577-PR-119 / 577-PR-119A) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 101011 | 15073.1402 | 10610.CI.CO.M3 | 2020.22 | 2020.22
C322132CIPR100060 | U22 - Main Piperack Foundations Execution (577-PR-120) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82670 | 10096.3006 | 10610.CI.CO.M3 | 1653.4 | 1653.4
C322132CIPR100060 | U22 - Main Piperack Foundations Execution (577-PR-120) | CI | CIPR1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82670 | 10096.3006 | 10610.CI.CO.M3 | 1653.4 | 1653.4
C322132CIPS000070 | U22 - HC Flare Drain Drum Foundation Execution inside sump (571-V-404) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5151 | 39.1967 | 10610.CI.CO.M3 | 85.85 | 85.85
C322132CIPS000080 | U22 - Sumps Construction (571-SU-403) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3018 | 4.9568 | 10610.CI.CO.M3 | 50.3 | 10.06
C322132CIPS000080 | U22 - Sumps Construction (571-SU-403) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3018 | 4.9568 | 10610.CI.CO.M3 | 50.3 | 10.06
C322132CIPS000110 | U22 - Intermediate HC Flare Drain Drum Foundation Execution inside sump (571-V-304) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6642 | 58.9979 | 10610.CI.CO.M3 | 110.7 | 110.7
C322132CIPS000110 | U22 - Intermediate HC Flare Drain Drum Foundation Execution inside sump (571-V-304) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6642 | 58.9979 | 10610.CI.CO.M3 | 110.7 | 110.7
C322132CIPS000200 | U22 - First Flush Pit (571-SU-501) | CI | CIPS1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4835 | 11.5504 | 10610.CI.CO.M3 | 80.58 | 80.58
C322132CIPV000190 | U22 - Concrete Paving Execution | CI | CIPV1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41820 | 271.9571 | 10610.CI.PV.M2 | 23233.47 | 0
C322132CIPV000190 | U22 - Concrete Paving Execution | CI | CIPV1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41820 | 271.9571 | 10610.CI.PV.M2 | 23233.47 | 0
C322132CIRD000110 | U22 - Road Early Base & Sub Base Execution | CI | CIRD1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8720 | 0 | 10780.CI.CI.MH
C322132CIRE000150 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000160 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701C) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000170 | U22 - Sour Oily Water Pump Foundation Execution (571-P-701D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 213 | 0.0070405 | 10610.CI.CO.M3 | 3.04 | 0
C322132CIRE000220 | U22 - Vertical Intermediate LT K.O Drum Pump Foundation Execution (571-P-302A/B/C/D) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2842 | 0 | 10610.CI.CO.M3 | 47.36 | 0
C322136MEHM000280 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402A (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000330 | U22 - Horizontal Pump (Sour Oily Water Pump) with Electrical Motor Erection 571-P-701A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000340 | U22 - Horizontal Pump (Intermediate Acid Gas Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-303B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000350 | U22 - Horizontal Pump (Acid Gas Flare K.O Drum Pump) with Electrical Motor Erection 571-P-403B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C322136MEHM000370 | U22 - Horizontal Pump (Blowdown Drum Sour Water Pump) with Electrical Motor Erection 571-P-504B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000380 | U22 - Horizontal Pump (Sour Oily Water Pump) with Electrical Motor Erection 571-P-701B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000420 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000430 | U22 - Horizontal Pump (Intermediate LT K.O. Drum Pump) with Electrical Motor Erection 571-P-302D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000440 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000460 | U22 - Horizontal Pump (Intermediate Hydrocarbon Flare K.O. Drum Pump) with Electrical Motor Erection 571-P-301D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000470 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401B (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000480 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401C (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000500 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402B (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000520 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402D (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM001000 | U22 - Horizontal Pump Glycol water make-up pump Erection (571-P-801A/B) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C322136MEPA000060 | U22 - LT Flare Package stick built 571-ME-402 - Part-1 (HL) (320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7462 | 77.6925 | 10610.ME.ER.TN | 212 | 203.52
C322132CIRE000230 | U22 - Intermediate Acid Gas Flare K.O Drum Pump Foundation Execution (571-P-303A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 656 | 0 | 10610.CI.CO.M3 | 9.37 | 0
C322132CIRE000250 | U22 - Blowdown Drum Sour Water Pump Foundation Execution (571-P-504A/B) | CI | CIRE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 368 | 0.02103 | 10610.CI.CO.M3 | 5.25 | 0
C322132CISF000040 | U22 - Stairs & Small Foundations Execution | CI | CISF | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6218 | 6.0117 | 10610.CI.CO.M3 | 103.63 | 0
C322132CIST000180 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701C) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10758 | 122.3813 | 10610.CI.CO.M3 | 215.16 | 180.7307
C322132CIST000180 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701C) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10758 | 122.3813 | 10610.CI.CO.M3 | 215.16 | 180.7307
C322132CIST000200 | U22 - Shelters Foundation Execution ( Comp Shelter -SH- 571-C-701A) | CI | CIST | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10794 | 125.3584 | 10610.CI.CO.M3 | 215.88 | 181.3392
C322132CITF100470 | U22 - TEG Storage Tank Foundation Execution (571-TK-201) | CI | CITF1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 6.6909 | 10610.CI.CO.M3 | 35.87 | 35.87
C322132CIUG000100 | U22 - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2362 | 0.86769 | 10610.CI.CO.M3 | 39.37 | 0
C322132CIUG000100 | U22 - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2362 | 0.86769 | 10610.CI.CO.M3 | 39.37 | 0
C322132CIUG200020 | U22 - UG Pipe Installation (OD) | CI | CIUG2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 56036 | 655.4506 | 10610.CI.UG.LM | 2801.78 | 588.3738
C322132CIVE000200 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.093998 | 10610.CI.CO.M3 | 9.74 | 0
C322132CIVE000210 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000210 | U22 - HC Flare Gas Recovery Compressor Interstage KOD Foundation Execution (571-V-702C) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 173 | 0.0060549 | 10610.CI.CO.M3 | 2.47 | 0
C322132CIVE000230 | U22 - HC Flare Gas Recovery Compressor Suction KOD Foundation Execution (571-V-701B) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 682 | 0.33985 | 10610.CI.CO.M3 | 9.74 | 6.96
C322132CIVE000260 | U22 - HC Flare Gas Recovery Compressor Filter Foundation Execution (571-F-701A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.015901 | 10610.CI.CO.M3 | 4.57 | 0
C322132CIVE000260 | U22 - HC Flare Gas Recovery Compressor Filter Foundation Execution (571-F-701A) | CI | CIVE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.015901 | 10610.CI.CO.M3 | 4.57 | 0
C322132METK110000 | U22 - TEG Storage Tank Erection 571-TK-201 | ME | METK1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 5.9092 | 10610.ME.TE.TN | 20 | 20
C322132METK110020 | U23 - (566 CWS) - Storage Tank 566-TK-201- Annular Plate and Bottom Plate Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4300 | 27.3151 | 10610.ME.TE.TN | 43 | 43
C322136MEPA000074 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-5 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3715 | 0 | 10780.ME.ME.MH
C322136MEPA000110 | U22 - LT Flare Package Erection 571-ME-402 - Part-3 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 123 | 0
C322136MEPA000120 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-2 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 151 | 0
C322136MEPA000130 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-3 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 123 | 0
C322136MEPA000140 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-4 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 76 | 0
C322136MEPA000150 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-5 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000170 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-7 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000210 | U22 - LT Flare Package Erection 571-ME-402 - Part-7 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEVV000250 | U22 - Heavy Equipment (Intermediate LT K.O. Drum ) Erection (571-V-302A) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8000 | 94.5467 | 10610.ME.ER.TN | 200 | 200
C322136MEVV000290 | U22 - Heavy Equipment (Intermediate Acid Gas Flare K.O. Drum) Erection (571-V-303) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9000 | 119.6607 | 10610.ME.ER.TN | 225 | 225
C322136MEVV000350 | U22 - Acid Gas Flare K.O Drum Erection 571-V-403 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2200 | 0 | 10610.ME.ER.TN | 55 | 0
C322136MEVV000360 | U22 - HC Flare Drain Drum Erection 571-V-404 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 360 | 0 | 10610.ME.ER.TN | 9 | 0
C322136MEVV000380 | U22 - Intermediate Acid Gas Flare Drain Drum Erection 571-V-405 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 440 | 0 | 10610.ME.ER.TN | 11 | 0
C322136MEVV000410 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000420 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Discharge KOD) Erection 571-V-703C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000425 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702B | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000430 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701A | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322132METK110060 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Shell 5, Shell 6 and Compression Ring Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 5.8796 | 10610.ME.TE.TN | 20 | 20
C322132METK110070 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201 - Roof Erection including Appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6500 | 35.5769 | 10610.ME.TE.TN | 65 | 37.05
C322132METK110110 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 3 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110130 | U23 - (566 CWS) - Storage Tank 566-TK-201 - Tank Roof Pre-assembling & Erection with appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4300 | 18.028 | 10610.ME.TE.TN | 43 | 28.38
C322132METK110130 | U23 - (566 CWS) - Storage Tank 566-TK-201 - Tank Roof Pre-assembling & Erection with appurtenances | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4300 | 18.028 | 10610.ME.TE.TN | 43 | 28.38
C322132METK110160 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 5 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110190 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 6 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.94547 | 10610.ME.TE.TN | 8 | 8
C322132METK110210 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 7 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.86037 | 10610.ME.TE.TN | 8 | 7.28
C322132METK110220 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 4 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110230 | U23 - (566 CWS) - Storage Tank 566-TK-201- Shell 8 & Compression Ring Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 800 | 0.37819 | 10610.ME.TE.TN | 8 | 3.2
C322132METK110280 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 3 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110290 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Shell 2 Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110310 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Staircase Erection for Remaining Shells | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.TE.TN | 20 | 0
C322132METK110330 | U23 - (566 CWS) - Storage Tank 566-TK-201 - Roof Platform & Staircase Erection | ME | METK1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.TE.TN | 15 | 0
C322132SPDE000000 | U22 - Old fence demolition | SP | SPDE | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 2.1273 | 10780.SP.SP.MH
C322132STEQ000110 | U22 - Miscellaneous Platform Structure Erection (Plt-V402A) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1059 | 0 | 10610.ST.PL.TN | 19.99 | 0
C322132STEQ000240 | U22 - Miscellaneous Platform Structure Erection (Plt-PR135) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11243 | 0 | 10610.ST.PL.TN | 212.14 | 0
C322132STEQ000250 | U22 - Miscellaneous Platform Structure Erection (Plt-V403 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 749 | 0 | 10610.ST.PL.TN | 14.13 | 0
C322132STEQ000260 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V301 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1759 | 0 | 10610.ST.PL.TN | 33.2 | 0
C322132STEQ000280 | U22 - Miscellaneous Platform Structure Erection (571-PLT-V303 A & B) | ST | STEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 636 | 0 | 10610.ST.PL.TN | 0 | 0
C322132STMS000070 | U22 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16 | 0 | 10610.ST.PL.TN | 0.26 | 0
C322132STPL000150 | U22 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 89104 | 0 | 10610.ST.PL.TN | 1113.81 | 0
C322132STPR000120 | U22 - Main Piperack Erection (571-PR-148) (Including Tower near flare) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8095 | 70.7208 | 10610.ST.PR.TN | 152.74 | 152.1278
C322132STPR000150 | U22 - Main Piperack Erection (571-PR-146) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12486 | 175.8499 | 10610.ST.PR.TN | 235.59 | 226.1715
C322132STPR000250 | U22 - Main Piperack Erection (571-PR-139/140) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14880 | 197.7379 | 10610.ST.PR.TN | 280.76 | 210.7014
C322132STPR000290 | U22 - Main Piperack Erection (571-PR-136) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14586 | 243.4146 | 10610.ST.PR.TN | 275.2 | 247.681
C322132STPR000300 | U22 - Main Piperack Erection (571-PB-126) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18056 | 0 | 10610.ST.PR.TN | 340.68 | 0
C322132STPR000301 | U22 - Main Piperack Erection (571-PB-127) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14181 | 0 | 10610.ST.PR.TN | 267.56 | 0
C322132STPR000320 | U22 - Main Piperack Erection (571-PR-133) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14068 | 0 | 10610.ST.PR.TN | 265.44 | 0
C322132STPR000420 | U22 - Main Piperack Erection (571-PR-134) (Including Tower near 571-V-403) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11914 | 0 | 10610.ST.PR.TN | 224.8 | 0
C322132STPR100020 | U22 - Main Piperack Erection (577-PR-115) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24777 | 906.0013 | 10610.ST.PR.TN | 467.49 | 467.489
C322132STPR100030 | U22 - Main Piperack Erection (577-PR-117) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25497 | 960.3739 | 10610.ST.PR.TN | 481.07 | 480.9397
C322132STPR100040 | U22 - Main Piperack Erection (577-PR-118) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18589 | 492.8489 | 10610.ST.PR.TN | 350.74 | 297.933
C322132STPR100050 | U22 - Main Piperack Erection (577-PR-119 / 577-PR-119A) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40866 | 2171.0423 | 10610.ST.PR.TN | 771.05 | 766.9988
C322132STPR100070 | U22 - Main Piperack Erection (577-PR-112 / 577-PR-113) | ST | STPR | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 87614 | 10971.5161 | 10610.ST.PR.TN | 1653.1 | 1562.3617
C322132STSH000030 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701C) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322132STSH000060 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701B) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322136MEVV000435 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000465 | U22 - 571-FM-303, 308 & 309- Fire Monitor | ME | MEMC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14400 | 0 | 10610.ME.ER.TN | 240 | 0
C322137INFG000070 | U22 - Fire & Gas System Installation | IN | INFG | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3189 | 0 | 10780.IN.IN.MH
C322137INGC000140 | U22 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19135 | 0 | 10610.IN.CO.UN | 510 | 0
C322137INGC000150 | U22 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12757 | 0 | 10610.IN.CO.UN | 420 | 0
C322137ININ000070 | U22 - Instruments Installation | IN | ININ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10610.IN.IN.UN | 930 | 0
C322137ININ000071 | U22 - Valve Installation | IN | ININ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10610.IN.IN.UN | 764 | 0
C322137INJB000070 | U22 - Junction Boxes & Local Panels Install | IN | INJB | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12757 | 0 | 10780.IN.IN.MH
C322137PRLT000070 | U22 - Loops Testing | PR | PRLT | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35376 | 0 | 10780.PR.PR.MH
C3230PRPRPL000090 | U23 - Punch List | PR | PRPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5490 | 0 | 10780.PR.PR.MH
C323131ISEQ000060 | U23 - (566 CWS) - Storage Tank 566-TK-201 - Tank Insulation | IS | ISEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12968 | 0 | 10780.IS.IS.MH
C323131PIBB000000 | U23 - (566 CWS) - Big Bore Piping A/ Tanks 566-TK-201 & 566-V-202 | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35931 | 0 | 10610.PI.BB.DI | 3593.08 | 0
C323131PIPR000080 | U23 - (566 CWS) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 248700 | 75793.8937 | 10610.PI.FB.DI | 62174.98 | 44409.8313
C323131PIRA000000 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-102) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000010 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-103) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PISU000170 | U23 - (566 CWS) - Piping Supports Prefabrication | PI | PISU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17953 | 45.7343 | 10610.PI.PU.TN | 69.05 | 46.5391
C323131PISU000180 | U23 - (566 CWS) - Piping Supports Erection | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.SU.TN | 69.05 | 0
C323131PRBO000130 | U23 - Rotary Box Up | PR | PRBO2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7336 | 0 | 10780.PR.PR.MH
C323131PRFL000210 | U23 - Chemical Cleaning for Compressor Suction Lines (Unit 566) | PR | PRFL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2077 | 0 | 10780.PR.PR.MH
C323131PRHT000210 | U23 - Piping Hydrotesting (566) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38912 | 0 | 10610.PR.HT.DI | 60514 | 0
C323131PRHT000320 | U23 - (566 CWS) - Storage Tank 566-TK-201- Dewatering and Cleaning | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5921 | 0 | 10780.PR.PR.MH
C322132STSH000070 | U22 - Compressor Shelter Roofing & Wall Erection ( SH- 571-C-701B) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30 | 0 | 10780.ST.ST.MH
C322132STSH000090 | U22 - Compressor Shelter Structure Erection ( SH- 571-C-701A) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12657 | 0 | 10610.ST.ER.TN | 238.8 | 0
C322132STSH000110 | U22 - Compressor Shelter Architecture ( SH- 571-C-701A) | ST | STSH1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2240 | 0 | 10780.ST.ST.MH
C322132STSP000080 | U22 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12852 | 0 | 10610.ST.PL.TN | 214.21 | 0
C322132STSP80 | U22 - Steel Structure 571-STR-68-72 ( Pipeline Support ) | ST | STSP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2782 | 0 | 10610.ST.PL.TN | 46.37 | 0
C322133PAEQ000060 | U22 - Equipment Painting | PA | PAEQ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1809 | 0 | 10780.PA.PA.MH
C322133PAPP000070 | U22 - Piping SandBl. & Priming | PA | PAPP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51465 | 3013.266 | 10610.PA.PP.M2 | 0 | 0
C322134ELCO000140 | U22 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12260 | 0 | 10610.EL.CO.UN | 270 | 0
C322134ELEL000095 | U22 - Lightning Works | EL | ELEL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10898 | 0 | 10780.EL.EL.MH
C322134ELTI000150 | U22 - Electrical Cable Trays Installation | EL | ELTI | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40868 | 0 | 10610.EL.CT.LM | 11472.02 | 0
C322136MEAC000080 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Pre-Assembly 571-E-701A | ME | MEAC1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1770 | 0 | 10780.ME.ME.MH
C322136MEAC000090 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Discharge Cooler) Erection 571-E-702A | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1500 | 0 | 10610.ME.ER.TN | 15 | 0
C322136MEAC000160 | U22 - Air Coolers (HC Flare Gas Recovery Compressor Interstage Cooler) Erection 571-E-701C | ME | MEAC2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10610.ME.ER.TN | 14 | 0
C322136MEAC000200 | U22 - Lube Oil Cooler for HC Flare Gas Recovery Compressor (571-C-701A) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MECO000080 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701A (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MECO000090 | U22 - Centrifugal Compressor Erection (HC Flare Gas Recovery Compressor) 571-C-701B (320 TON) | ME | MECO2 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEHE000110 | U22 - Heat Exchangers (LT Flare K.O Drum Heater) Erection 571-E-402A | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHE000120 | U22 - Heat Exchangers (Intermediate LT Flare K.O Drum Heater) Erection 571-E-302A | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C322136MEHE000130 | U22 - Heat Exchangers (LT Flare K.O Drum Heater) Erection 571-E-402B | ME | MEHE1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10610.ME.ER.TN | 2 | 0
C323131PRRE000120 | U23 - Piping Reinstatement (566) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 44664 | 0 | 10610.PR.RE.DI | 60514 | 0
C323132CICT100000 | U23 - (567 UPW) - Electrical earth Trenches Execution | CI | CICT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 183 | 0.0057795 | 10610.CI.ET.M3 | 45.68 | 42.0302
C323132CIDB000055 | U23 - (566 CWS) - Duct Banks Precast Installation | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 15.2929 | 10610.CI.CO.M3 | 57.16 | 51.4399
C323132CIDB000055 | U23 - (566 CWS) - Duct Banks Precast Installation | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3430 | 15.2929 | 10610.CI.CO.M3 | 57.16 | 51.4399
C323132CIDB100005 | U23 - (567 UPW) - Duct Banks Precast Fabrication | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1891 | 3.9937 | 10780.CI.CI.MH
C323132CIDB100015 | U23 - (567 UPW) - Duct Banks Precast Installation | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16628 | 295.5098 | 10610.CI.CO.M3 | 332.55 | 332.55
C323132CIDM000070 | U23 - (566 CWS) - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11200 | 140.0881 | 10610.CI.CO.M3 | 224 | 224.0001
C323132CIDM100000 | U23 - (567 UPW) - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6972 | 54.5567 | 10610.CI.CO.M3 | 116.21 | 116.21
C323132CIGR200000 | U23 - (573 FWS) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1419 | 0 | 10610.CI.GR.LM | 2365 | 0
C323132CIGT200010 | U23 - (573 FWS) - Steel Structure Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1600 | 0 | 10780.CI.CI.MH
C323132CIMF000100 | U23 - (566 CWS) - Deluge Valve Skid (DVS) foundation execution (DVS) | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6973 | 23.956 | 10610.CI.CO.M3 | 116.22 | 40
C323132CIMF100000 | U23 - (567 UPW) - (567 UPW) - Misc. pipe supports for Instrument Air Dryer Pck. (567-ME-102D) foundations execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2237 | 7.1554 | 10610.CI.CO.M3 | 37.28 | 36.0901
C323132CIMF100010 | U23 - (567 UPW) - Misc. pipe supports for Instrument Air Receiver (567-V-201A/B) foundations execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6365 | 58.3335 | 10610.CI.CO.M3 | 106.08 | 106.08
C323132CIMF100020 | U23 - (567 UPW) - Platforms for Instrument Air Receiver (567-V-201A) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132CIMF200000 | U23 - (573 FWS) - Miscellaneous Foundations Execution (Piping and structural supports foundations) | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6200 | 22.3439 | 10610.CI.CO.M3 | 103.33 | 31
C323132CIPD000040 | U23 - (566 CWS) - Fabrication Precast Drainage Man Holes & Catchbasins | CI | CIPD | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5464 | 44.105 | 10780.CI.CI.MH
C323132CIPE000060 | U23 - (566 CWS) - Refrigerant Compressor Foundation Execution (566-ME-201C-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000070 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201C-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C322136MEHL000050 | U22 - Heavy Equipment (Hydrocarbon Flare K.O. Drum) Erection (571-V-401B) (HL) (1600 + 650 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7400 | 2.1292 | 10610.ME.ER.TN | 185 | 0
C322136MEHM000280 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402A (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000290 | U22 - Horizontal Pump (Acid Gas Flare K.O Drum Pump) with Electrical Motor Erection 571-P-403A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000330 | U22 - Horizontal Pump (Sour Oily Water Pump) with Electrical Motor Erection 571-P-701A | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000360 | U22 - Horizontal Pump (Blowdown Drum HC Pump) with Electrical Motor Erection 571-P-503B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000370 | U22 - Horizontal Pump (Blowdown Drum Sour Water Pump) with Electrical Motor Erection 571-P-504B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000380 | U22 - Horizontal Pump (Sour Oily Water Pump) with Electrical Motor Erection 571-P-701B | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000390 | U22 - Horizontal Pump with Electrical Motor Erection 571-P-701D | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000400 | U22 - Horizontal Pump with Electrical Motor Erection 571-P-701C | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000480 | U22 - Pump with (Hydrocarbon Flare K.O. Drum Pump) Electrical Motor Erection 571-P-401C (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000520 | U22 - Pump with (LT K.O Drum Pump) Electrical Motor Erection 571-P-402D (Vertical) | ME | MEVM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM000530 | U22 - Horizontal Sour Oily Water Pump (571-P-701 E) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C322136MEHM001000 | U22 - Horizontal Pump Glycol water make-up pump Erection (571-P-801A/B) | ME | MEHM1 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C322136MEHV000190 | U22 - HC Flare Gas Recovery Compressor Filter 571-F-701A/B | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10610.ME.ER.TN | 4 | 0
C322136MEPA000060 | U22 - LT Flare Package stick built 571-ME-402 - Part-1 (HL) (320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7462 | 77.6925 | 10610.ME.ER.TN | 212 | 203.52
C322136MEPA000063 | U22 - LT Flare Package stick built 571-ME-402 - Part-4 (HL) (XXX TON) Preassembly | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3731 | 19.0735 | 10780.ME.ME.MH
C322136MEPA000072 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-3 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3715 | 0.053618 | 10780.ME.ME.MH
C323132CIPE000070 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201C-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000110 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201C-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.9707 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000140 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201B-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1418 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000150 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201B-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2168 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000170 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201B-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.8904 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000180 | U23 - (566 CWS) - Refrigerant compressor foundation execution (566-ME-201A-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1463 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000210 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201A-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2215 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE100000 | U23 - (567 UPW) - Air Gas Compressor Skid Foundations Execution (567-ME-101G-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4323 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIPR000340 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-103) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79302 | 9290.3471 | 10610.CI.CO.M3 | 1586.03 | 1586.0305
C323132CIPR000350 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-104) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72227 | 7706.6485 | 10610.CI.CO.M3 | 1444.54 | 1444.5416
C323132CIPR100000 | U23 - (567 UPW) - Piperack Foundations Execution (567-PR-101) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10520 | 163.4987 | 10610.CI.CO.M3 | 175.34 | 175.3398
C323132CIPR100010 | U23 - (567 UPW) - Piperack Foundations Execution (567-PR-102) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7358 | 79.9852 | 10610.CI.CO.M3 | 122.64 | 122.64
C323132CIPR100010 | U23 - (567 UPW) - Piperack Foundations Execution (567-PR-102) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7358 | 79.9852 | 10610.CI.CO.M3 | 122.64 | 122.64
C323132CIPV000230 | U23 - (566 CWS) - Gravel Paving Execution | CI | CIPV2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5096 | 0 | 10610.CI.GV.M2 | 8493 | 0
C323132CIPV100000 | U23 - (567 UPW) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6523 | 7.0718 | 10610.CI.PV.M2 | 3624 | 0
C323132CIRE000110 | U23 - (566 CWS) - CW Ref. Package Propane Transfer Pump Foundation Execution (566-P-204A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 735 | 0.11965 | 10610.CI.CO.M3 | 10.5 | 0
C323132CIRE000150 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201C) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 857 | 0.12746 | 10610.CI.CO.M3 | 12.24 | 0
C323132CIRE000150 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201C) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 857 | 0.12746 | 10610.CI.CO.M3 | 12.24 | 0
C323132CISF100000 | U23 - (567 UPW) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7389 | 9.0734 | 10610.CI.CO.M3 | 123.14 | 0
C323132CISF200000 | U23 - (573 FWS) - Stairs & Small Foundations Execution | CI | CISF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6200 | 23.5648 | 10610.CI.CO.M3 | 103.33 | 36.1696
C323132CITF000040 | U23 - (566 CWS) - Cooling Water Tank Foundation Execution (566-TK-201) | CI | CITF1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11357 | 190.5399 | 10610.CI.CO.M3 | 189.28 | 189.28
C323132CITF000040 | U23 - (566 CWS) - Cooling Water Tank Foundation Execution (566-TK-201) | CI | CITF1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11357 | 190.5399 | 10610.CI.CO.M3 | 189.28 | 189.28
C323132CITF200000 | U23 - (573 FWS) - Fire Water Tank Foundation Execution (573-TK-201) | CI | CITF1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11877 | 208.3984 | 10610.CI.CO.M3 | 197.96 | 197.9606
C323132CIUG000140 | U23 - (566 CWS) - UG Civil Works | CI | CIUG1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16400 | 169.8596 | 10780.CI.CI.MH
C323132CIUG100000 | U23 - (567 UPW) - UG GRE Pipe Installation (CD) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39789 | 1412.6253 | 10610.CI.UG.LM | 1989.44 | 1805.0004
C323132CIUG100000 | U23 - (567 UPW) - UG GRE Pipe Installation (CD) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39789 | 1412.6253 | 10610.CI.UG.LM | 1989.44 | 1805.0004
C323132CIUG100035 | U23 - (567 UPW) - UG Pipe Installation (OD) | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14358 | 240.2839 | 10610.CI.UG.LM | 717.89 | 717.8934
C323132CIUP000050 | U23 - (566 CWS) - UG Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2008 | 4.7646 | 10610.PI.FB.DI | 502 | 1477.7187
C323132CIUP000050 | U23 - (566 CWS) - UG Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2008 | 4.7646 | 10610.PI.FB.DI | 502 | 1477.7187
C323132CIVE100010 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101F-V03) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIVE100010 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101F-V03) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIVE100030 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101G-V02) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 0.28667 | 10610.CI.CO.M3 | 18.36 | 0
C323132CIVE100040 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101G-V03) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 0.28667 | 10610.CI.CO.M3 | 18.36 | 0
C323132CIVE100060 | U23 - (567 UPW) - Instrument Air Receiver Foundations Execution (567-V-201A) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132CIVE100070 | U23 - (567 UPW) - Instrument Air Receiver foundations Execution (567-V-201B) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132ELCI200000 | U23 - (573 FWS) - Conduits Installation | EL | ELCI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 293 | 0 | 10780.EL.EL.MH
C322136MEPA000073 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-4 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3715 | 0.053618 | 10780.ME.ME.MH
C322136MEPA000076 | U22 - HC & Acid Gas Flare Package stick built 571-ME-401/403 - Part-7 Assembly (XXX TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2600 | 0 | 10780.ME.ME.MH
C322136MEPA000100 | U22 - LT Flare Package Erection 571-ME-402 - Part-2 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0.013252 | 10610.ME.ER.TN | 151 | 0
C322136MEPA000130 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-3 (HL) (1600 + 650 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10610.ME.ER.TN | 123 | 0
C322136MEPA000150 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-5 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000160 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-6 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000170 | U22 - HC & Acid Gas Flare Package Erection 571-ME-401/403 - Part-7 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1950 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000180 | U22 - LT Flare Package Erection 571-ME-402 - Part-4 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 76 | 0
C322136MEPA000190 | U22 - LT Flare Package Erection 571-ME-402 - Part-5 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000210 | U22 - LT Flare Package Erection 571-ME-402 - Part-7 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10610.ME.ER.TN | 50 | 0
C322136MEPA000211 | U22 - LT Flare Package Erection 571-ME-402 - Part-8 (HL) (1600 + 650 + 320 TON) | ME | MEPA | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1306 | 0 | 10780.ME.ME.MH
C322136MEVV000290 | U22 - Heavy Equipment (Intermediate Acid Gas Flare K.O. Drum) Erection (571-V-303) (HL) (800 TON) | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9000 | 119.6607 | 10610.ME.ER.TN | 225 | 225
C322136MEVV000320 | U22 - Intermediate HC Flare Drain Drum Erection 571-V-304 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 360 | 0 | 10610.ME.ER.TN | 9 | 0
C322136MEVV000350 | U22 - Acid Gas Flare K.O Drum Erection 571-V-403 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2200 | 0 | 10610.ME.ER.TN | 55 | 0
C322136MEVV000400 | U22 - Acid Gas Flare Drain Drum Erection 571-V-406 (Horizontal) | ME | MEHV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 280 | 0 | 10610.ME.ER.TN | 7 | 0
C322136MEVV000435 | U22 - Vertical Vessels (HC Flare Gas Recovery Compressor Interstage KOD) Erection 571-V-702C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322136MEVV000445 | U22 - 571-HM-304, 305 & 317- Hydrant Monitor | ME | MEMC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10800 | 0 | 10610.ME.ER.TN | 180 | 0
C323132ELCO200000 | U23 - (573 FWS) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1408 | 0 | 10610.EL.CO.UN | 1026 | 0
C323132ELCP100000 | U23 - (567 UPW) - Cathodic Protection Piping | EL | ELCP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1803 | 0 | 10780.EL.EL.MH
C323132ELCP200000 | U23 - (573 FWS) - Cathodic Protection Piping | EL | ELCP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 235 | 0 | 10780.EL.EL.MH
C323132ELCT200000 | U23 - (573 FWS) - Cathodic Protection Tanks | EL | ELCT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 235 | 0 | 10780.EL.EL.MH
C323132ELEL200005 | U23 - (573 FWS) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 313 | 0 | 10610.EL.ES.LM | 8876.82 | 0
C323132ELPL100000 | U23 - (567 UPW) - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5861 | 0 | 10780.EL.EL.MH
C323132ELPL200000 | U23 - (573 FWS) - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 763 | 0 | 10780.EL.EL.MH
C323132ELTI200000 | U23 - (573 FWS) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1174 | 0 | 10610.EL.CT.LM | 213.21 | 0
C323132FPSS100000 | U23 - (567 UPW) - Steel Structure Fireproofing | FP | FPSS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 80 | 0 | 10780.FP.FP.MH
C323132INCO100000 | U23 - (567 UPW) - Communication System Installation | IN | INCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 176 | 0 | 10780.IN.IN.MH
C323132INCT100000 | U23 - (567 UPW) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1002 | 0 | 10610.IN.CT.LM | 540 | 0
C323132INCT200000 | U23 - (573 FWS) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10928 | 9.7773 | 10610.IN.CT.LM | 800 | 0
C323132INCT200010 | U23 - (573 FWS) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6120 | 0 | 10610.IN.CT.LM | 570 | 0
C323132INFS100000 | U23 - (567 UPW) - Fire Fighting Equipments Installation | IN | INFS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.IN.IN.MH
C323132INGC100000 | U23 - (567 UPW) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 625 | 0 | 10610.IN.CO.UN | 420 | 0
C323132INGC200010 | U23 - (573 FWS) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4546 | 0 | 10610.IN.CO.UN | 380 | 0
C323132ININ100000 | U23 - (567 UPW) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 321 | 0 | 10610.IN.IN.UN | 420 | 0
C323132ININ200001 | U23 - (567 UPW) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 321 | 0 | 10610.IN.IN.UN | 360 | 0
C323132INIP100000 | U23 - (567 UPW) - Instruments Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 104 | 0 | 10780.IN.IN.MH
C323132INSL100000 | U23 - (567 UPW) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1002 | 0 | 10610.IN.SC.LM | 1431.67 | 0
C322136MEVV000450 | U22 - HC Flare Gas Recovery Compressor Suction KOD Vessels Erection 571-V-701C | ME | MEVV | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 120 | 0 | 10610.ME.ER.TN | 3 | 0
C322137INCI000070 | U22 - Conduits Installation | IN | INCT3 | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3179 | 0 | 10780.IN.IN.MH
C322137INFC000070 | U22 - Fiber Optic Gland & Conn./Testing | IN | INFC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2944 | 0 | 10610.IN.CO.UN | 320 | 0
C322137INFO000060 | U22 - Fiber Optic Cable Pulling | IN | INFO | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4170 | 0 | 10610.IN.FO.LM | 145180 | 0
C322137INGC000140 | U22 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19135 | 0 | 10610.IN.CO.UN | 510 | 0
C322137INGC000150 | U22 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12757 | 0 | 10610.IN.CO.UN | 420 | 0
C322137ININ000070 | U22 - Instruments Installation | IN | ININ | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9813 | 0 | 10610.IN.IN.UN | 930 | 0
C322137INIP000071 | U22 - Valve Calibration | IN | INIP | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3189 | 0 | 10780.IN.IN.MH
C322137INML000070 | U22 - Multi Pair Cable Pulling | IN | INML | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38270 | 0 | 10610.IN.MC.LM | 116399.2 | 0
C322137INSL000070 | U22 - Single Pair Cable Pulling | IN | INSL | 22 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30665 | 0 | 10610.IN.SC.LM | 77599.46 | 0
C323131ISPI000090 | U23 - (566 CWS) - Piping Insulation | IS | ISPI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24556 | 0 | 10780.IS.IS.MH
C323131MEMC000080 | U23 - (566 CWS) - Miscellaneous Piping | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6473 | 0 | 10780.PI.PI.MH
C323131PIRA000030 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-105) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PIRA000090 | U23 - (566 CWS) - Piping Erection on Rack (566-PR-101) | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31073 | 0 | 10610.PI.PR.DI | 3452.56 | 0
C323131PISB000000 | U23 - (566 CWS) - Small Bore Piping A/Tanks 566-TK-201 | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12434 | 0 | 10610.PI.SB.DI | 1130.35 | 0
C323131PISU000170 | U23 - (566 CWS) - Piping Supports Prefabrication | PI | PISU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17953 | 45.7343 | 10610.PI.PU.TN | 69.05 | 46.5391
C323131PRHT000090 | U23 - Piping Hydrotesting (573) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52603 | 0 | 10610.PR.HT.DI | 76525 | 0
C323131PRHT000220 | U23 - Piping Hydrotesting (567) | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16033 | 0 | 10610.PR.HT.DI | 14690 | 0
C323131PRHT000330 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- Dewatering and Cleaning | PR | PRHT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10521 | 0 | 10780.PR.PR.MH
C323131PRRE000010 | U23 - Piping Reinstatement (567) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12826 | 0 | 10610.PR.RE.DI | 14690 | 0
C323131PRRE000090 | U23 - Piping Reinstatement (573) | PR | PRRE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 65528 | 0 | 10610.PR.RE.DI | 76525 | 0
C323132INSL200000 | U23 - (573 FWS) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10928 | 0 | 10610.IN.SC.LM | 764.82 | 0
C323132ISEQ100000 | U23 - (567 UPW) - Equipment Insulation | IS | ISEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4128 | 0 | 10610.IS.EQ.M2 | 410 | 0
C323132MEMC200000 | U23 - (573 FWS) - Miscellaneous Electrical | EL | ELEQ2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 176 | 0 | 10780.EL.EL.MH
C323132MEPA100020 | U23 - (567 UPW) - Package (Air pre filter) installation (567-ME-101G-F01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323132MEPA100040 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler pre-assembly (567-ME-101F-E01/E02/E03) | ME | MEAC1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16000 | 0 | 10780.ME.ME.MH
C323132MEPA100050 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler Erection (567-ME-101F-E01/E02/E03) | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 0 | 10610.ME.ER.TN | 200 | 0
C323132MEPA100060 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler Erection (567-ME-101G-E01/E02/E03) | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 0 | 10610.ME.ER.TN | 200 | 0
C323132MEPA100070 | U23 - (567 UPW) - 2nd stage suction moisture separator (567-ME-101F-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100080 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101F-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100110 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101G-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100120 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101G-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100140 | U23 - (567 UPW) - Package (Air gas compressor stage 1/2/3) Installation (567-ME-101F-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323132MEVV100000 | U23 - (567 UPW) - Vertical Vessels (Instrument Air Receiver) Erection 567-V-201B (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8600 | 109.2605 | 10610.ME.ER.TN | 215 | 215
C323132MEVV100000 | U23 - (567 UPW) - Vertical Vessels (Instrument Air Receiver) Erection 567-V-201B (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8600 | 109.2605 | 10610.ME.ER.TN | 215 | 215
C323132MEVV100010 | U23 - (567 UPW) - Vertical Vessels (Plant Air Receiver) Erection 567-V-202 | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 440 | 0.21074 | 10610.ME.ER.TN | 11 | 11
C323132PAEQ200010 | U23 - (573 FWS) - Fire Water (Storage) Tank 573-TK-201- External Painting for Roof and Shell | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1852 | 0 | 10780.PA.PA.MH
C323132PAPP100000 | U23 - (567 UPW) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4375 | 21.5485 | 10610.PA.PP.M2 | 0 | 0
C323132PASP200000 | U23 - (573 FWS) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1280 | 0.0030497 | 10610.PA.SU.TN | 0 | 0
C323132CICT000110 | U23 - (566 CWS) - Instrument earth Trenches Execution | CI | CICT3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9509 | 122.8921 | 10780.CI.CI.MH
C323132CICT000120 | U23 - (566 CWS) - Covered Concrete Trenches Execution | CI | CICT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 245 | 0.077079 | 10780.CI.CI.MH
C323132CICT200020 | U23 - (573 FWS) - Covered Concrete Trenches Execution | CI | CICT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 940 | 0 | 10780.CI.CI.MH
C323132CIDB000045 | U23 - (566 CWS) - Duct Banks Precast Fabrication | CI | CIDB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41 | 0.0016838 | 10780.CI.CI.MH
C323132CIDM000070 | U23 - (566 CWS) - Manholes & Catchbasins Installation (Precast) | CI | CIDM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11200 | 140.0881 | 10610.CI.CO.M3 | 224 | 224.0001
C323132CIDM200010 | U23 - (573 FWS) - Manholes & Catchbasins Installation (Cast in Situ) | CI | CIDM2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2765 | 10.1648 | 10780.CI.CI.MH
C323132CIGR200000 | U23 - (573 FWS) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1419 | 0 | 10610.CI.GR.LM | 2365 | 0
C323132CIGT000160 | U23 - (566 CWS) - Equipment Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1360 | 0.13012 | 10780.CI.CI.MH
C323132CIGT100010 | U23 - (567 UPW) - Steel Structure Grouting Execution | CI | CIGT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 196 | 0 | 10780.CI.CI.MH
C323132CIMF100020 | U23 - (567 UPW) - Platforms for Instrument Air Receiver (567-V-201A) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132CIMF100030 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101F-F01-V01/02/03 ) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.4247 | 10610.CI.CO.M3 | 37.48 | 37.4801
C323132CIMF100050 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101G-F01) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.2949 | 10610.CI.CO.M3 | 37.48 | 37.4798
C323132CIPE000100 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201C-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.68
C323132CIPE000110 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201C-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.9707 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000160 | U23 - (566 CWS) - Oil separator foundation execution (566-ME-201B-V03) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1601 | 3.7861 | 10610.CI.CO.M3 | 26.68 | 26.6801
C323132CIPE000170 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201B-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.8904 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000190 | U23 - (566 CWS) - Evaporator foundation execution (566-ME-201A-E01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2215 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000200 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201A-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1463 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132PIBB200000 | U23 - (573 FWS) - Big Bore Piping A/Equip. Erection | PI | PIBB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320319 | 198.5649 | 10610.PI.BB.DI | 32031.85 | 99.9394
C323132PIPR200000 | U23 - (573 FWS) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 438367 | 162495.5274 | 10610.PI.FB.DI | 109591.67 | 48403.3386
C323132PIRA100000 | U23 - (567 UPW) - Piping Erection on Rack 567-PR-101 / 567-PR-102 / 567-PB-101 | PI | PIRA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 64298 | 0 | 10610.PI.PR.DI | 7144.23 | 0
C323132PISB100000 | U23 - (567 UPW) - Small Bore Piping A/Equip. Erection | PI | PISB | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6278 | 0 | 10610.PI.SB.DI | 570.75 | 0
C323132PISU100000 | U23 - (567 UPW) - Piping Supports Prefabrication | PI | PISU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2682 | 2.7581 | 10610.PI.PU.TN | 10.32 | 2.1958
C323132PISU200000 | U23 - (573 FWS) - Piping Supports Prefabrication | PI | PISU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16225 | 32.9592 | 10610.PI.PU.TN | 62.4 | 1.4744
C323132PISU200000 | U23 - (573 FWS) - Piping Supports Prefabrication | PI | PISU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16225 | 32.9592 | 10610.PI.PU.TN | 62.4 | 1.4744
C323132PISU200010 | U23 - (573 FWS) - Piping Supports Erection | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28082 | 0 | 10610.PI.SU.TN | 62.4 | 0
C323132STMS100000 | U23 - (567 UPW) - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 828 | 0 | 10610.ST.PL.TN | 13.8 | 0
C323132STPL000190 | U23 - (566 CWS) - Equipment Structures, Ladders & Handrails Erection (566-STR-V202) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28947 | 0 | 10610.ST.PL.TN | 361.84 | 0
C323132STPL100000 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101F-F01) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 580 | 0 | 10610.ST.PL.TN | 7.25 | 0
C323132STPL100010 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101F-F01-V01/02/03 ) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10610.ST.PL.TN | 2.07 | 0
C323132STPL200010 | U23 - (573 FWS) - Equipment Platforms, Stairways, Floors & Handrails Erection (573-STR-TK201) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10610.ST.PL.TN | 2.07 | 0
C323132STPL200010 | U23 - (573 FWS) - Equipment Platforms, Stairways, Floors & Handrails Erection (573-STR-TK201) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10610.ST.PL.TN | 2.07 | 0
C323132STPR000160 | U23 - (566 CWS) - Main Piperack Erection (566-PR-102) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 58868 | 2525.57 | 10610.ST.PR.TN | 1110.71 | 492.7742
C323132STPR000180 | U23 - (566 CWS) - Main Piperack Erection (566-PR-104) including Tower V 202 | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 43054 | 1679.6293 | 10610.ST.PR.TN | 812.33 | 622.5061
C323132STPR100000 | U23 - (567 UPW) - Piperack Erection (567-PR-101) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3057 | 11.4928 | 10610.ST.PR.TN | 57.69 | 24.4623
C323132STPR100010 | U23 - (567 UPW) - Piperack Erection (567-PR-102) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1196 | 1.8311 | 10610.ST.PR.TN | 22.56 | 21.6572
C323132CIPE000200 | U23 - (566 CWS) - K.O Drum foundation execution (566-ME-201A-V01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1208 | 2.1463 | 10610.CI.CO.M3 | 20.13 | 20.13
C323132CIPE000210 | U23 - (566 CWS) - Liquid Ref. Receiver foundation execution (566-ME-201A-V02) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1229 | 2.2215 | 10610.CI.CO.M3 | 17.55 | 17.55
C323132CIPE000230 | U23 - (566 CWS) - Lube oil reservoir foundation execution (566-ME-201A-V05) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.9678 | 10610.CI.CO.M3 | 32.83 | 32.83
C323132CIPE000260 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201B-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.5866 | 10610.CI.CO.M3 | 32.83 | 26.2601
C323132CIPE000260 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201B-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 4.5866 | 10610.CI.CO.M3 | 32.83 | 26.2601
C323132CIPE000270 | U23 - (566 CWS) - Lube Oil Cooler Foundation Execution (566-ME-201C-E04) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1970 | 3.1103 | 10610.CI.CO.M3 | 32.83 | 16.4199
C323132CIPE100000 | U23 - (567 UPW) - Air Gas Compressor Skid Foundations Execution (567-ME-101G-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4323 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIPE100020 | U23 - (567 UPW) - Air Gas Compressor Skid Foundations Execution-(567-ME-101F-C01) | CI | CIPE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIPR000310 | U23 - (566 CWS) - Main Piperack Foundations Execution (566-PR-101) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3177 | 14.1653 | 10610.CI.CO.M3 | 52.95 | 52.95
C323132CIPR000310 | U23 - (566 CWS) - Main Piperack Foundations Execution (566-PR-101) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3177 | 14.1653 | 10610.CI.CO.M3 | 52.95 | 52.95
C323132CIPR000320 | U23 - (566 CWS) - Secondary Piperack Foundations Execution (566-PR-105) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10343 | 155.0484 | 10610.CI.CO.M3 | 172.39 | 172.39
C323132CIPR000320 | U23 - (566 CWS) - Secondary Piperack Foundations Execution (566-PR-105) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10343 | 155.0484 | 10610.CI.CO.M3 | 172.39 | 172.39
C323132CIPR000350 | U23 - (566 CWS) - Main piperack foundations execution (566-PR-104) | CI | CIPR1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 72227 | 7706.6485 | 10610.CI.CO.M3 | 1444.54 | 1444.5416
C323132CIPR100000 | U23 - (567 UPW) - Piperack Foundations Execution (567-PR-101) | CI | CIPR2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10520 | 163.4987 | 10610.CI.CO.M3 | 175.34 | 175.3398
C323132CIPS000000 | U23 - (566 CWS) - Collection Pit Execution for Propane Storage Drum (566-SU-202) | CI | CIPS1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10303 | 131.9643 | 10610.CI.CO.M3 | 171.72 | 171.7198
C323132CIPV000230 | U23 - (566 CWS) - Gravel Paving Execution | CI | CIPV2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5096 | 0 | 10610.CI.GV.M2 | 8493 | 0
C323132CIPV200000 | U23 - (573 FWS) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 0 | 10610.CI.PV.M2 | 71.25 | 0
C323132CIPV200000 | U23 - (573 FWS) - Concrete Paving Execution | CI | CIPV1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 128 | 0 | 10610.CI.PV.M2 | 71.25 | 0
C323132STSH000060 | U23 - (566 CWS) - Compressor Shelter Structure Erection (566-SH-001/002/003) | ST | STSH1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 67952 | 457.0291 | 10610.ST.ER.TN | 1282.11 | 92.5722
C323132STSH000070 | U23 - (566 CWS) - Compressor Shelter Roofing & Cladding Erection (566-SH-001/002/003) | ST | STSH2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 52 | 0 | 10610.ST.ER.TN | 21.64 | 0
C323132STSP000090 | U23 - (566 CWS) - Steel Structure Stair Ways & Floors Erection | ST | STSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10595 | 0 | 10610.ST.PL.TN | 176.59 | 0
C323132STSP100010 | U23 - (567 UPW) - Steel Structure Stair Ways & Floors Erection (567-STR-PR101) | ST | STSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2153 | 0 | 10610.ST.PL.TN | 35.88 | 0
C323133PAEQ000010 | U23 - (566 CWS) - Storage Tank 566-TK-201- External Painting for Roof and Shell | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10780.PA.PA.MH
C323133PASP000090 | U23 - (566 CWS) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 0.10412 | 10610.PA.SU.TN | 0 | 0
C323134ELTI000160 | U23 - (566 CWS) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32365 | 0 | 10610.EL.CT.LM | 4464.14 | 0
C323136MEAC000020 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser pre-assembly (566-ME-201C-E02) | ME | MEAC1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10983 | 0 | 10780.ME.ME.MH
C323136MEAC000050 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201C-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323136MEHM000000 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000010 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201C | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000020 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000220 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 660 | 0 | 10610.ME.ER.TN | 11 | 0
C323136MEHM000350 | U23 - (566 CWS) - Horizontal Pump (Ref. Package Propane Transfer Pump) with Electrical Motor Erection 566-P-204A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 60 | 0 | 10610.ME.ER.TN | 1 | 0
C323136MEPA000000 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201A-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000040 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201C-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000080 | U23 - (566 CWS) - Cooling Water Chemical Dosing Package Installation 566-ME-202 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEPA000120 | U23 - (566 CWS) - Refrigerant compressor Installation (566-ME-201B-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000130 | U23 - (566 CWS) - Evaporator Installation (566-ME-201B-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000140 | U23 - (566 CWS) - K.O Drum Installation (566-ME-201B-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000150 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201B-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000160 | U23 - (566 CWS) - Oil separator Installation (566-ME-201B-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323136MEPA000170 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201B-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136METC000070 | U23 - (566 CWS) - Cranes Erection (EOT Crane For Cooling Water Refrigeration Package) 566-EOT-201 | ME | METC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1200 | 0 | 10610.ME.ER.TN | 20 | 0
C323136MEVV000280 | U23 - (566 CWS) - Vertical Vessels (Propane Storage Drum) Erection 566-V-202 (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12800 | 242.0395 | 10610.ME.ER.TN | 320 | 320
C323137INFO000070 | U23 - (566 CWS) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1556 | 0 | 10610.IN.FO.LM | 122576 | 0
C323137INGC000160 | U23 - (566 CWS) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7137 | 0 | 10610.IN.CO.UN | 540 | 0
C323137ININ000080 | U23 - (566 CWS) - Instruments Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3660 | 0 | 10610.IN.IN.UN | 600 | 0
C323137INIP000080 | U23 - (566 CWS) - Instruments Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1190 | 0 | 10780.IN.IN.MH
C323137INML000080 | U23 - (566 CWS) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14274 | 0 | 10610.IN.MC.LM | 62580.32 | 0
C323137INSL000080 | U23 - (566 CWS) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11438 | 0 | 10610.IN.SC.LM | 11838.53 | 0
C323137PRLT000080 | U23 - Loops Testing | PR | PRLT | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13995 | 0 | 10780.PR.PR.MH
C323CIMF000000040 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101F-F01) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2249 | 7.2949 | 10610.CI.CO.M3 | 37.48 | 37.48
C323CIOT000000020 | U23 - (567 UPW) - Deluge Valve Skid | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C323CIOT000000020 | U23 - (567 UPW) - Deluge Valve Skid | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C424131CIPR100070 | U24- Civil Revamp of Piperack ( Unit 500)- 500-PR-012 in Unit 530 (Approximate length = 40m) | CI | CIPR1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2263 | 7.5655 | 10780.CI.CI.MH
C323132CIRE000120 | U23 - (566 CWS) - CW Ref. Package Propane Transfer Pump Foundation Execution (566-P-204B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 735 | 0.11965 | 10610.CI.CO.M3 | 10.5 | 0
C323132CIRE000130 | U23 - (566 CWS) - CW ref. feed pump foundation execution (566-P-201A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2655 | 1.2236 | 10610.CI.CO.M3 | 44.25 | 0
C323132CIRE000170 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323132CIRE000180 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203C) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323132CIRE000180 | U23 - (566 CWS) - CW supply pump foundation execution (566-P-203C) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1206 | 0.25242 | 10610.CI.CO.M3 | 20.1 | 0
C323132CIRE000190 | U23 - (566 CWS) - Propane transfer pump foundation execution (566-P-202A) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 648 | 0.072871 | 10610.CI.CO.M3 | 9.26 | 0
C323132CIRE000200 | U23 - (566 CWS) - Propane transfer pump foundation execution (566-P-202B) | CI | CIRE1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 648 | 0.072871 | 10610.CI.CO.M3 | 9.26 | 0
C323132CIUG000130 | U23 - (566 CWS) - UG Process Channel Execution (Closed Drain System) | CI | CIUG3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 245 | 0.088674 | 10780.CI.CI.MH
C323132CIUG100030 | U23 - (567 UPW) - UG Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 2.3986 | 10610.PI.FB.DI | 332 | 1701.5003
C323132CIUG100030 | U23 - (567 UPW) - UG Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 2.3986 | 10610.PI.FB.DI | 332 | 1701.5003
C323132CIUG200000 | U23 - (573 FWS) - UG GRE Pipe Installation (FW) - Part A | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 405190 | 17181.5493 | 10610.CI.UG.LM | 20259.5 | 1215.57
C323132CIUG200005 | U23 - (573 FWS) - UG Pipe Installation (CD) - Part A | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3840 | 0 | 10780.CI.CI.MH
C323132CIUG200015 | U23 - (573 FWS) - UG Pipe Installation (OD) - Part A | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3840 | 0 | 10780.CI.CI.MH
C323132CIUG200025 | U23 - (573 FWS) - UG Pipe Installation (CD) - Part B | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3840 | 0 | 10780.CI.CI.MH
C323132CIUG200035 | U23 - (573 FWS) - UG Pipe Installation (OD) - Part B | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3840 | 0 | 10780.CI.CI.MH
C323132CIUG200115 | U23 - (573 FWS) - UG GRE Pipe Installation (FW) - Part B | CI | CIUG2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3840 | 0 | 10780.CI.CI.MH
C323132CIVE000160 | U23 - (566 CWS) - Horizontal Vessels (Propane Storage Drum) Foundation Execution (566-V-202) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 17647 | 460.0533 | 10610.CI.CO.M3 | 352.94 | 352.94
C323132CIVE100000 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101F-V02) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132CIVE100020 | U23 - (567 UPW) - 2nd Stage suction moisture separator Foundations Execution (567-ME-101G-V01) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C424131CIPR100080 | U10- Civil Revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part A | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.CI.CO.M3 | 6.86 | 0
C424131CIPR100100 | U24- Civil Revamp of Piperack ( Unit 510)- 510-PR-I-2 to 7 (Aprox. length =211m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3782 | 0.79239 | 10780.CI.CI.MH
C424131CIPR100150 | U24- Civil Revamp of Piperack ( Unit 549)- (549-P-023) (Approximate length =40m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 28050 | 1162.3372 | 10780.CI.CI.MH
C424131CIPR100170 | U10- Civil Revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part B | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.CI.CO.M3 | 6.86 | 0
C424131ISPI000100 | U24 - Piping Insulation | IS | ISPI | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12100 | 0 | 10610.IS.PI.M2 | 4510 | 0
C424131PIPR000090 | U24 - Piping Spools Prefabrication for Modified Structure | PI | PIPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 31460 | 1232.1348 | 10610.PI.FB.DI | 7865.03 | 6487.7214
C424131PIRA000110 | U24- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-001 (Aprox. length =570m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000120 | U24- Piping Erection on Existing Piperack ( Unit 561)- 561-PR-20 (Aprox. length =174m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000140 | U24- Piping Erection on Existing Piperack ( Unit 522)- 522-PR-I-1 (Aprox. length =32m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000150 | U24- Piping Erection on Existing Process Structure ( Unit 521)- 521-Process Str A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000180 | U24- Piping Erection on Existing Piperack ( Unit 545)- 545-PR-007/008/009 (Aprox. length =94m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000190 | U24- Piping Erection on Existing Piperack ( Unit 549)- (549-P-023) (Approximate length =40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000220 | U10- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =340m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000230 | U23- Piping Erection on Existing Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =580m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000260 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =800m) Interface with CRI Part A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000261 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =800m) Interface with CRI Part B | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000270 | U15- Piping Erection on Existing Piperack ( Unit 550/551/552/553)-550/551/552/553-I-001 (E-W) (Approx length=800m) – Int | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C323132CIVE100040 | U23 - (567 UPW) - 3rd Stage discharge moisture separator Foundations Execution (567-ME-101G-V03) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 0.28667 | 10610.CI.CO.M3 | 18.36 | 0
C323132CIVE100050 | U23 - (567 UPW) - Plant Air Receiver Foundations Execution (567-V-202) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18193 | 479.9029 | 10610.CI.CO.M3 | 363.85 | 363.85
C323132CIVE100060 | U23 - (567 UPW) - Instrument Air Receiver Foundations Execution (567-V-201A) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132CIVE100070 | U23 - (567 UPW) - Instrument Air Receiver foundations Execution (567-V-201B) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5838 | 50.3494 | 10610.CI.CO.M3 | 97.3 | 97.3
C323132CIVE100080 | U23 - (567 UPW) - 2nd stage discharge moisture separator Foundations Execution (567-ME-101F-V01) | CI | CIVE | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1285 | 2.4397 | 10610.CI.CO.M3 | 18.36 | 18.36
C323132ELCL100000 | U23 - (567 UPW) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19837 | 196.3758 | 10610.EL.PL.LM | 40576.62 | 14755.2821
C323132ELCO200000 | U23 - (573 FWS) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1408 | 0 | 10610.EL.CO.UN | 1026 | 0
C323132ELEL100005 | U23 - (567 UPW) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3607 | 0 | 10610.EL.ES.LM | 8876.82 | 0
C323132ELEL200005 | U23 - (573 FWS) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 313 | 0 | 10610.EL.ES.LM | 8876.82 | 0
C323132ELEQ200000 | U23 - (573 FWS) - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 352 | 0 | 10610.EL.EQ.UN | 490 | 0
C323132ELTI100000 | U23 - (567 UPW) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9017 | 0 | 10610.EL.CT.LM | 2295 | 0
C323132ELTI200000 | U23 - (573 FWS) - Electrical Cable Trays Installation | EL | ELTI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1174 | 0 | 10610.EL.CT.LM | 213.21 | 0
C323132FPSS000060 | U23 - (566 CWS) - Steel Structure Fireproofing | FP | FPSS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4201 | 0 | 10780.FP.FP.MH
C323132GNHT000005 | U23 - (566 CWS) - U/G Detection works and re-routing of existing services | SP | SPSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2423 | 8.6731 | 10780.SP.SP.MH
C323132INCT200010 | U23 - (573 FWS) - Secondary Cable Trays Installation | IN | INCT2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6120 | 0 | 10610.IN.CT.LM | 570 | 0
C323132INFC100000 | U23 - (567 UPW) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 360 | 0
C323132INFC200000 | U23 - (573 FWS) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1049 | 0 | 10610.IN.CO.UN | 330 | 0
C323132INFS200000 | U23 - (573 FWS) - Fire Fighting Equipments Installation | IN | INFS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1137 | 0 | 10780.IN.IN.MH
C323132INGC100000 | U23 - (567 UPW) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 625 | 0 | 10610.IN.CO.UN | 420 | 0
C323132INGC100010 | U23 - (567 UPW) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 417 | 0 | 10610.IN.CO.UN | 420 | 0
C323132INGC200000 | U23 - (573 FWS) - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6819 | 0 | 10610.IN.CO.UN | 410 | 0
C323132INHU100010 | U23 - (567 UPW) - Process Hook Up´s Erection | IN | INHU1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 441 | 0 | 10780.IN.IN.MH
C323132ININ200002 | U23 - (573 FWS) - Valve Installation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3497 | 0 | 10610.IN.IN.UN | 450 | 0
C323132INIP200000 | U23 - (573 FWS) - Instruments Calibration | IN | INIP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1137 | 0 | 10780.IN.IN.MH
C323132INML200000 | U23 - (573 FWS) - Multi Pair Cable Pulling | IN | INML | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13638 | 0 | 10610.IN.MC.LM | 70337.59 | 0
C323132INSL100000 | U23 - (567 UPW) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1002 | 0 | 10610.IN.SC.LM | 1431.67 | 0
C323132ISEQ100000 | U23 - (567 UPW) - Equipment Insulation | IS | ISEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4128 | 0 | 10610.IS.EQ.M2 | 410 | 0
C323132MEHM200000 | U23 - (573 FWS) - Horizontal Fire Water Pump with Electrical Motor Erection 573-P-201 | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10610.ME.ER.TN | 10 | 0
C323132MEMC100000 | U23 - (567 UPW) - Miscellaneous Piping | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10780.PI.PI.MH
C323132MEMC100015 | U23 - (567 UPW) - Miscellaneous Instrumentation | IN | ININ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 321 | 0 | 10780.IN.IN.MH
C323132MEPA100000 | U23 - (567 UPW) - Package (Air gas compressor stage 1/2/3) Installation (567-ME-101G-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323132MEPA100010 | U23 - (567 UPW) - Package (Air pre filter) installation (567-ME-101F-F01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323132MEPA100060 | U23 - (567 UPW) - 1st/2nd inter cooler & after cooler Erection (567-ME-101G-E01/E02/E03) | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 20000 | 0 | 10610.ME.ER.TN | 200 | 0
C323132MEPA100070 | U23 - (567 UPW) - 2nd stage suction moisture separator (567-ME-101F-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100080 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101F-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100090 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101F-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100100 | U23 - (567 UPW) - 2nd stage suction moisture separator (567-ME-101G-V01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100110 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101G-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C424131PIRA000320 | Modification of 2nd Stage Feed KO Drum 44-V-302 (MDS: SPP-1000482-GG-001-06-44-171) - Involvement of OEM | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000370 | U24-Miscellanious pipig erection works | PI | PISU2 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4804 | 0 | 10780.PI.PI.MH
C424131PISU000030 | U24 - Piping Tie-ins Supports Prefabrication | PI | PISU1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9659 | 133.9423 | 10610.PI.PU.TN | 37.15 | 74.1802
C424131PISU000160 | U24 - Piping Tie-ins Supports erection for Unit 521 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085101 | 10610.PI.SU.TN | 0.53 | 0.53
C424131PISU000170 | U24 - Piping Tie-ins Supports erection for Unit 530 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 886 | 1.1594 | 10610.PI.SU.TN | 1.97 | 1.97
C424131PISU000190 | U24 - Piping Supports Prefabrication for revamped H-5 Area | PI | PISU1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6029 | 45.4084 | 10610.PI.PU.TN | 23.19 | 16.6851
C424131PISU000210 | U24 - Piping Tie-ins Supports erection for Unit 545 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4526 | 25.7208 | 10610.PI.SU.TN | 10.06 | 8.551
C424131PISU000210 | U24 - Piping Tie-ins Supports erection for Unit 545 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4526 | 25.7208 | 10610.PI.SU.TN | 10.06 | 8.551
C424131PISU000220 | U24 - Piping Tie-ins Supports erection for Unit 551 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 337 | 0.1676 | 10610.PI.SU.TN | 0.75 | 0.75
C424131PISU000230 | U24 - Piping Tie-ins Supports erection for Unit 552 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 337 | 0.16762 | 10610.PI.SU.TN | 0.75 | 0.75
C424131PISU000250 | U24 - Piping Tie-ins Supports erection for Unit 562 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1516 | 3.0286 | 10610.PI.SU.TN | 3.37 | 3
C424131PISU000270 | U24 - Piping Tie-ins Supports erection for Unit 575 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13 | 0.00013074 | 10610.PI.SU.TN | 0.03 | 0.02
C424131PISU000280 | U24 - Piping Tie-ins for Unit 521 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 153.6975 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000320 | U24 - Piping Tie-ins for Unit 533 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 17.0775 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000330 | U24 - Piping Tie-ins for Unit 540 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 126650 | 21492.3583 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000340 | U24 - Piping Tie-ins for Unit 541 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120700 | 19402.0075 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000350 | U24 - Piping Tie-ins for Unit 545 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 3.6396 | 10610.PI.TI.DI | 367.16 | 312.0897
C424131PISU000350 | U24 - Piping Tie-ins for Unit 545 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 3.6396 | 10610.PI.TI.DI | 367.16 | 312.0897
C424131PISU000370 | U24 - Piping Tie-ins for Unit 550 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 3496.6176 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000370 | U24 - Piping Tie-ins for Unit 550 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 3496.6176 | 10610.PI.TI.DI | 367.16 | 367.16
C323132MEPA100120 | U23 - (567 UPW) - 3rd stage discharge moisture separator (567-ME-101G-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323132MEPA100140 | U23 - (567 UPW) - Package (Air gas compressor stage 1/2/3) Installation (567-ME-101F-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323132MEVV100020 | U23 - (567 UPW) - Vertical Vessels (Instrument Air Receiver) Erection 567-V-201A (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8600 | 109.2605 | 10610.ME.ER.TN | 215 | 215
C323132MEVV100020 | U23 - (567 UPW) - Vertical Vessels (Instrument Air Receiver) Erection 567-V-201A (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8600 | 109.2605 | 10610.ME.ER.TN | 215 | 215
C323132PAFP100000 | U23 - (567 UPW) - Piping Final Coat & Touch-Up Painting | PA | PAFP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 525 | 0 | 10780.PA.PA.MH
C323132PAPP200000 | U23 - (573 FWS) - Piping SandBl. & Priming | PA | PAPP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9669 | 17.3606 | 10610.PA.PP.M2 | 0 | 0
C323132PASP200000 | U23 - (573 FWS) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1280 | 0.0030497 | 10610.PA.SU.TN | 0 | 0
C323132PAST100000 | U23 - (567 UPW) - Steel Structure Painting Touch Up | PA | PAST | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1241 | 0 | 10780.PA.PA.MH
C323132PIPR100000 | U23 - (567 UPW) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39611 | 1918.5598 | 10610.PI.FB.DI | 9902.85 | 8524.8367
C323132PIPR100000 | U23 - (567 UPW) - Piping Prefabrication | PI | PIPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39611 | 1918.5598 | 10610.PI.FB.DI | 9902.85 | 8524.8367
C323132PISU200010 | U23 - (573 FWS) - Piping Supports Erection | PI | PISU2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28082 | 0 | 10610.PI.SU.TN | 62.4 | 0
C323132PIUG200000 | U23 - (573 FWS) - Piping Erection UG | PI | PIUG | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2307 | 0 | 10610.PI.UG.DI | 1538 | 0
C323132STMS100000 | U23 - (567 UPW) - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 828 | 0 | 10610.ST.PL.TN | 13.8 | 0
C323132STMS200000 | U23 - (573 FWS) - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 345 | 0 | 10610.ST.PL.TN | 5.75 | 0
C323132STPL000180 | U23 - (566 CWS) - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5627 | 0 | 10610.ST.PL.TN | 70.34 | 0
C323132STPL100000 | U23 - (567 UPW) - Valve Platform for Air Prefilter (567-ME-101F-F01) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 580 | 0 | 10610.ST.PL.TN | 7.25 | 0
C323132STPL100020 | U23 - (567 UPW) - Platforms Valves 2nd & 3rd Stage Moist Sep. (567-ME-101G-F01-V01/02/03 ) | ST | STPL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18 | 0 | 10610.ST.PL.TN | 0.23 | 0
C323132STPR000160 | U23 - (566 CWS) - Main Piperack Erection (566-PR-102) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 58868 | 2525.57 | 10610.ST.PR.TN | 1110.71 | 492.7742
C424131PISU000390 | U24 - Piping Tie-ins for Unit 552 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 153.6975 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000410 | U24 - Piping Tie-ins for Unit 553 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 53550 | 4236.2867 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000430 | U24 - Piping Tie-ins for Unit 567 | PI | PITI2 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2550 | 9.6061 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PITI000010 | U24 - Habshan 5 - Shutdown Works Others | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 0 | 10610.PI.TI.DI | 367.16 | 0
C424131PITI000040 | U24 - Habshan 5 - Shutdown Works Area 3 Flares, Blowdowns & NGL storage | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4250 | 13.8589 | 10610.PI.TI.DI | 367.16 | 188.1695
C424131PITI000050 | U24 - Habshan 5 - Shutdown Works Area 1,2 & 3 Utilities ( Steam & Cond, BFW, Demin, etc.) | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39100 | 1217.6246 | 10610.PI.TI.DI | 367.16 | 195.8101
C424131PRHT000100 | U24 - Piping Hydrotesting | PR | PRHT | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 128639 | 0 | 10610.PR.HT.DI | 28996 | 0
C424131STEQ000010 | U24- Structure revamp of Process Structure ( Unit 522)- 522-Process Str A | ST | STEQ | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 242 | 0.035002 | 10610.ST.ER.TN | 4.56 | 3.7065
C424131STPR100000 | U24- Structure revamp of Piperack ( Unit 562)- 562-PR-012A (Aprox. length =60m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1336 | 0.01318 | 10610.ST.PR.TN | 25.2 | 0
C424131STPR100020 | U24- Structure revamp of Piperack ( Unit 521)- 521-PR-I-1 (Aprox. length =32m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 738 | 0.43036 | 10610.ST.PR.TN | 13.92 | 6.9602
C424131STPR100030 | U24- Structure revamp of Piperack ( Unit 510)- 510-PR-I-2 to 7 (Aprox. length =211m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 180 | 0.039631 | 10610.ST.PR.TN | 3.39 | 3.3909
C424131STPR100040 | U24- Structure revamp of Piperack ( Unit 545)- 545-PR-007/008/009 (Aprox. length =94m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10 | 0.00012777 | 10610.ST.PR.TN | 0.2 | 0.1996
C424131STPR100050 | U25- Structure revamp of Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =340m) - Part A | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2343 | 7.4167 | 10610.ST.PR.TN | 44.21 | 44.2096
C424131STPR100060 | U10- Structure revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part A | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4911 | 6.3389 | 10610.ST.PR.TN | 92.66 | 5.4515
C424131STPR100060 | U10- Structure revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part A | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4911 | 6.3389 | 10610.ST.PR.TN | 92.66 | 5.4515
C424131STPR100120 | U24- Structure revamp of Piperack ( Unit 561)- 561-PR-20 (Aprox. length =174m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 286 | 0.11952 | 10610.ST.PR.TN | 5.39 | 5.3886
C424131STPR100120 | U24- Structure revamp of Piperack ( Unit 561)- 561-PR-20 (Aprox. length =174m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 286 | 0.11952 | 10610.ST.PR.TN | 5.39 | 5.3886
C424131STPR100150 | U24- Structure revamp of Piperack ( Unit 549)- (549-P-023) (Approximate length =40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1336 | 2.5675 | 10610.ST.PR.TN | 25.2 | 24.8724
C323132STPR000170 | U23 - (566 CWS) - Main Piperack Erection (566-PR-103) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50018 | 2174.3082 | 10610.ST.PR.TN | 943.74 | 636.7279
C323132STPR100000 | U23 - (567 UPW) - Piperack Erection (567-PR-101) | ST | STPR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3057 | 11.4928 | 10610.ST.PR.TN | 57.69 | 24.4623
C323132STSP000090 | U23 - (566 CWS) - Steel Structure Stair Ways & Floors Erection | ST | STSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10595 | 0 | 10610.ST.PL.TN | 176.59 | 0
C323132STSP200000 | U23 - (573 FWS) - Steel Structure Stair Ways & Floors Erection | ST | STSP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 78 | 0 | 10610.ST.PL.TN | 1.3 | 0
C323133PAEQ000070 | U23 - (566 CWS) - Equipment Painting | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 507 | 0 | 10780.PA.PA.MH
C323133PAEQ000090 | U23 - (566 CWS) - Storage Tank 566-TK-201- Internal Painting for Shell and Bottom | PA | PAEQ | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 166 | 0 | 10780.PA.PA.MH
C323133PASP000090 | U23 - (566 CWS) - Piping Supports SandBl. & Priming | PA | PASP | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1908 | 0.10412 | 10610.PA.SU.TN | 0 | 0
C323134ELCI000080 | U23 - (566 CWS) - Conduits Installation | EL | ELCI | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8091 | 0 | 10780.EL.EL.MH
C323134ELCL000170 | U23 - (566 CWS) - Electrical Cable Laying | EL | ELCL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 71202 | 1040.6627 | 10610.EL.PL.LM | 149955.95 | 22493.3925
C323134ELCO000160 | U23 - (566 CWS) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38838 | 128.9966 | 10610.EL.CO.UN | 1215 | 0
C323134ELCO000160 | U23 - (566 CWS) - Electrical Cable Gland & Conn./Testing | EL | ELCO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38838 | 128.9966 | 10610.EL.CO.UN | 1215 | 0
C323134ELEL000095 | U23 - (566 CWS) - Earthing Works | EL | ELEL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12946 | 38.9632 | 10610.EL.ES.LM | 13808.39 | 2071.2585
C323134MEMC000090 | U23 - (566 CWS) - Miscellaneous Electrical | EL | ELEQ2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4855 | 0 | 10780.EL.EL.MH
C323136MEAC000000 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser pre-assembly (566-ME-201A-E02) | ME | MEAC1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10983 | 0 | 10780.ME.ME.MH
C323136MEAC000010 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser pre-assembly (566-ME-201B-E02) | ME | MEAC1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10983 | 0 | 10780.ME.ME.MH
C323136MEAC000050 | U23 - (566 CWS) - Air Cooler Refrigerant Condenser Installation 566-ME-201C-E02 | ME | MEAC2 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 1.8661 | 10610.ME.ER.TN | 40 | 0
C323136MEHM000010 | U23 - (566 CWS) - Horizontal Pump (Cooling Water Refrigeration Feed Pump) with Electrical Motor Erection 566-P-201C | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000040 | U23 - (566 CWS) - Horizontal Pump (Ref. Package Propane Transfer Pump) with Electrical Motor Erection 566-P-204B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEHM000050 | U23 - (566 CWS) - Horizontal Pump (Propane Transfer Pump) with Electrical Motor Erection 566-P-202B | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C424131STPR100180 | U22- Structure revamp of Piperack ( Unit 571)- 571-F1P14 (Approximate length = 40m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1149 | 1.5606 | 10610.ST.PR.TN | 21.68 | 17.3439
C424131STPR100190 | U25- Structure revamp of Piperack ( Unit 541)- 541-C2-PR (Aprox. length =280m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1381 | 2.511 | 10610.ST.PR.TN | 26.06 | 23.4572
C424131STPR100210 | U22- Structure revamp of Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 143054 | 23529.5703 | 10610.ST.PR.TN | 2699.14 | 2105.3164
C424131STPR100250 | U15- Structure revamp of Piperack ( Unit 550/551/552/553)-I-001 (E-W) (Approx length=400m) - Part B | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 124 | 0.0095046 | 10610.ST.PR.TN | 2.34 | 1.3228
C424133PAPP000090 | U24 - Piping SandBl. & Priming | PA | PAPP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19722 | 540.8973 | 10610.PA.PP.M2 | 9861 | 124187.8512
C424133PAPP000090 | U24 - Piping SandBl. & Priming | PA | PAPP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19722 | 540.8973 | 10610.PA.PP.M2 | 9861 | 124187.8512
C424134ELEQ000040 | MODIFCATION OF 132kV GIS AND RELATED PROTECTION SYSTEM. SUB-500 | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.056927 | 10610.EL.EQ.UN | 360 | 241.2
C424134ELEQ000050 | MODIFICATION OF MV AIR INSULATED SWITCHGEARS | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 346 | 346
C424134ELEQ000070 | UPS MODIFICATION FOR IES-500, IES-501 | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.081646 | 10610.EL.EQ.UN | 360 | 345.6
C424134ELEQ000080 | UPS MODIFICATION FOR IES-504 FIR 580-EE-0422 A/B AND 0423 A/B | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 360 | 360
C424PITI000000030 | Tie-in Pipe Support foundations for Unit 521 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1572 | 3.6507 | 10610.CI.CO.M3 | 26.2 | 26.2
C424PITI000000040 | Tie-in Pipe Support foundations for Unit 530 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C425131PIBB000000 | U25 - Big Bore Piping A/Equip. Erection (540-V-144, 540-F-113C / 15C, 540-P-111A/B/C) | PI | PIBB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19518 | 27.3681 | 10610.PI.BB.DI | 1951.81 | 226.0001
C425131PIBB000010 | U25 - Big Bore Piping A/Equip. Erection (541-V-144, 541-F-113C / 15C, 541-P-111A/B/C) | PI | PIBB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19518 | 30.7617 | 10610.PI.BB.DI | 1951.81 | 254.0086
C425131PIPR000120 | U25 - Piping Prefabrication | PI | PIPR | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 39780 | 2148.1421 | 10610.PI.FB.DI | 9944.97 | 8736.6014
C425131PISB000000 | U25 - Small Bore Piping A/Equip. Erection (540-V-144, 540-F-113C / 15C, 540-P-111A/B/C) | PI | PISB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5557 | 0 | 10610.PI.SB.DI | 505.2 | 0
C425131PISB000010 | U25 - Small Bore Piping A/Equip. Erection (541-V-144, 541-F-113C / 15C, 541-P-111A/B/C) | PI | PISB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5557 | 0 | 10610.PI.SB.DI | 505.2 | 0
C425131PISU000280 | U25 - Piping Supports Prefabrication | PI | PISU1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3643 | 15.8999 | 10610.PI.PU.TN | 14.01 | 7.2413
C323136MEHM000210 | U23 - (566 CWS) - Horizontal Pump (Propane Transfer Pump) with Electrical Motor Erection 566-P-202A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C323136MEHM000340 | U23 - (566 CWS) - Horizontal Pump (Water Supply Pump) with Electrical Motor Erection 566-P-203A | ME | MEHM1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 540 | 0 | 10610.ME.ER.TN | 9 | 0
C323136MEMC000050 | U23 - (566 CWS) - Miscellaneous Erection | ME | MEMC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2000 | 0 | 10780.ME.ME.MH
C323136MEPA000020 | U23 - (566 CWS) - Lube Oil Cooler Installation 566-ME-201C-E04 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000030 | U23 - (566 CWS) - Evaporator Installation (566-ME-201C-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0.22396 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000050 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201C-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000060 | U23 - (566 CWS) - Oil Separator Installation (566-ME-201C-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323136MEPA000080 | U23 - (566 CWS) - Cooling Water Chemical Dosing Package Installation 566-ME-202 | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 420 | 0 | 10610.ME.ER.TN | 7 | 0
C323136MEPA000090 | U23 - (566 CWS) - Refrigerant Compressor Installation (566-ME-201C-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000120 | U23 - (566 CWS) - Refrigerant compressor Installation (566-ME-201B-C01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000150 | U23 - (566 CWS) - Liquid Ref. Receiver Installation (566-ME-201B-V02) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000190 | U23 - (566 CWS) - Evaporator Installation (566-ME-201A-E01) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEPA000220 | U23 - (566 CWS) - Oil separator Installation (566-ME-201A-V03) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 8.5092 | 10610.ME.ER.TN | 40 | 40
C323136MEPA000230 | U23 - (566 CWS) - Lube oil reservoir Installation (566-ME-201A-V05) | ME | MEPA | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2400 | 0 | 10610.ME.ER.TN | 40 | 0
C323136MEVV000280 | U23 - (566 CWS) - Vertical Vessels (Propane Storage Drum) Erection 566-V-202 (HL) (800 TON) | ME | MEVV | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12800 | 242.0395 | 10610.ME.ER.TN | 320 | 320
C323137INCT000140 | U23 - (566 CWS) - Primary Cable Trays Installation | IN | INCT1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11438 | 0 | 10610.IN.CT.LM | 900 | 0
C323137INFC000080 | U23 - (566 CWS) - Fiber Optic Gland & Conn./Testing | IN | INFC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1098 | 0 | 10610.IN.CO.UN | 540 | 0
C323137INFO000070 | U23 - (566 CWS) - Fiber Optic Cable Pulling | IN | INFO | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1556 | 0 | 10610.IN.FO.LM | 122576 | 0
C425131PISU000290 | U25 - Piping Supports Erection | PI | PISU2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6306 | 0 | 10610.PI.SU.TN | 14.01 | 0
C425131PRBO000140 | U25 - Static Box Up | PR | PRBO1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2324 | 0 | 10780.PR.PR.MH
C425131PRFL000140 | U25 - Piping Flushing/Blowing | PR | PRFL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2036 | 0 | 10610.PR.FL.DI | 24116 | 0
C425131PRRE000110 | U25 - Piping Reinstatement | PR | PRRE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8145 | 0 | 10610.PR.RE.DI | 24116 | 0
C425132CIRE000120 | U25 - Liquid Dehydration Feed Pump (540-P-111C) Foundation Execution | CI | CIRE1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132CISF000080 | U25 - Misc. Platforms, Staircase, Ladders, Floors & Crossovers - Foundation Execution (540/541-STR-V144) | CI | CISF | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41309 | 2520.8773 | 10610.CI.CO.M3 | 826.17 | 826.1701
C425132CIUG000000 | U25-Identifying underground services | CI | CIUG1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 1.4706 | 10780.CI.CI.MH
C425132CIVE000230 | U25 - Molecular Sieve Liquid Adsorber (541-V-144) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 753 | 0.83786 | 10610.CI.CO.M3 | 10.76 | 10.76
C425132STMS000090 | U25 - Miscellaneous Steel Structures Platform Erection (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3494 | 11.135 | 10610.ST.PL.TN | 58.23 | 43.9393
C425132STMS000120 | U25 - Miscellaneous Pipe Supports (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0.03806 | 10610.ST.PL.TN | 7.21 | 1.1397
C425132STPL000000 | U25 - Equipment Platforms, Staircase, Floors, Ladders & Handrails Erection (540-STR-V144) | ST | STPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 12144 | 197.7159 | 10610.ST.PL.TN | 151.8 | 134.5952
C425132STPL000010 | U25 - Equipment Platforms, Staircase, Floors, Ladders & Handrails Erection (541-STR-V144) | ST | STPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4779 | 24.1565 | 10610.ST.PL.TN | 59.73 | 38.6265
C425133PAFP000130 | U25 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4800 | 0 | 10780.PA.PA.MH
C425133PASP000130 | U25 - Piping Supports SandBl. & Priming | PA | PASP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8120 | 52.4717 | 10610.PA.SU.TN | 0 | 0
C425134ELCL000190 | U25 - Lighting Cable Laying | EL | ELCL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 757 | 0 | 10610.EL.LC.LM | 2993.46 | 0
C425134ELCL000200 | U25 - Electrical Cable Laying | EL | ELCL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3700 | 4.5953 | 10610.EL.PL.LM | 5246.37 | 1490.2839
C425134ELCO000190 | U25 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2018 | 0 | 10610.EL.CO.UN | 150 | 0
C425134ELEL000115 | U25 - Earthing Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 476.72 | 0
C425134ELEQ000070 | U25 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.EQ.UN | 100 | 0
C425134ELMS000180 | U25- Miscellaneous Electrical Activities | EL | ELEQ2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 252 | 0 | 10780.EL.EL.MH
C323137INFS000080 | U23 - (566 CWS) - Fire Fighting Equipments Installation | IN | INFS | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1190 | 0 | 10780.IN.IN.MH
C323137INGC000170 | U23 - (566 CWS) - Single Pair Cable Gland & Conn./Testing | IN | INGC | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4758 | 0 | 10610.IN.CO.UN | 540 | 0
C323137INHU000150 | U23 - (566 CWS) - Pneumatic Hook Up´s Erection | IN | INHU3 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4000 | 0 | 10780.IN.IN.MH
C323137INSL000080 | U23 - (566 CWS) - Single Pair Cable Pulling | IN | INSL | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11438 | 0 | 10610.IN.SC.LM | 11838.53 | 0
C323CIGR000000010 | U23 - (567 UPW) - Grounding Network Execution | CI | CIGR | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1419 | 0.3049 | 10610.CI.GR.LM | 2365 | 0
C323CIMF000000030 | U23 - (567 UPW) - Platforms for Instrument Air Receiver (567-V-201B) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 285 | 0.11677 | 10610.CI.CO.M3 | 4.08 | 4.08
C323CIMF000000030 | U23 - (567 UPW) - Platforms for Instrument Air Receiver (567-V-201B) Foundations Execution | CI | CIMF | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 285 | 0.11677 | 10610.CI.CO.M3 | 4.08 | 4.08
C323CIOT000000010 | U23 - (567 UPW) - Valve Pit | CI | CIPS1 | 23 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 454 | 0.0098873 | 10610.CI.CO.M3 | 6.48 | 0
C4240PRPRWT000100 | U24 - Walkthrough | PR | PRWT | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3139 | 0 | 10780.PR.PR.MH
C424131CIEQ000000 | U24- Civil Revamp of Process Structure ( Unit 521)- 521-Process Str A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11900 | 209.1993 | 10780.CI.CI.MH
C424131CIMF000000 | U26- Adequecy check & Reinforcement of Foundation (Unit-44) 44-V-302 (Second stage FEED KOD) | CI | CIMF | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2232 | 7.3596 | 10780.CI.CI.MH
C424131CIPR100010 | U24- Civil Revamp of Piperack ( Unit 500)- 500-PR-001 (Aprox. length =570m) | CI | CIPR1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3263 | 0 | 10780.CI.CI.MH
C424131CIPR100020 | U24- Civil Revamp of Piperack ( Unit 521)- 521-PR-I-1 (Aprox. length =32m) | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 638 | 0.60132 | 10780.CI.CI.MH
C424131CIPR100030 | U24- Civil Revamp of Piperack ( Unit 561)- 561-PR-20 (Aprox. length =174m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 842 | 0 | 10780.CI.CI.MH
C424131CIPR100050 | U24- Civil Revamp of Piperack ( Unit 545)- 545-PR-007/008/009 (Aprox. length =94m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3698 | 1.9564 | 10780.CI.CI.MH
C424131CIPR100060 | U24- Civil Revamp of Piperack ( Unit 522)- 522-PR-I-1 (Aprox. length =32m) | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 561 | 0.46493 | 10780.CI.CI.MH
C424131CIPR100090 | U25- Civil Revamp of Piperack ( Unit 541)- 541-C1-PR (Aprox. length =340m) | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 25255 | 942.2391 | 10780.CI.CI.MH
C424131CIPR100140 | U23- Civil Revamp of Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =400m) – Interface with CRI P - Part-A | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 59486 | 0 | 10780.CI.CI.MH
C424131CIPR100170 | U10- Civil Revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part B | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10610.CI.CO.M3 | 6.86 | 0
C425134ELPL000090 | U25 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1093 | 0 | 10780.EL.EL.MH
C425134ELTI000190 | U25 - Electrical Cable Trays Installation | EL | ELTI | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1682 | 0 | 10610.EL.CT.LM | 254.08 | 0
C425134INCI000000 | U25 - Conduits Installation | IN | INCT3 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 246 | 0 | 10610.IN.CD.LM | 175 | 0
C425134INCT000000 | U25 - Primary Cable Trays Installation | IN | INCT1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2371 | 0 | 10610.IN.CT.LM | 117 | 0
C425134INFG000000 | U25 - Fire & Gas System Installation | IN | INFG | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 247 | 0 | 10780.IN.IN.MH
C425134INFO000000 | U25 - Fiber Optic Cable Pulling | IN | INFO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 323 | 0 | 10610.IN.FO.LM | 200 | 0
C425134INFS000000 | U25 - Fire Fighting Equipments Installation | IN | INFS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 247 | 0 | 10780.IN.IN.MH
C425134INGC000000 | U25 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1480 | 0 | 10610.IN.CO.UN | 14 | 0
C425134INGC000010 | U25 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 987 | 0 | 10610.IN.CO.UN | 180 | 0
C425134INHU000000 | U25 - Process Hook Up´s Erection | IN | INHU1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1043 | 0 | 10780.IN.IN.MH
C425134ININ000000 | U25 - Instruments Installation | IN | ININ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10610.IN.IN.UN | 246 | 0
C425134ININ000001 | U25 - Valve Installation | IN | ININ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10610.IN.IN.UN | 246 | 0
C425134INIP000000 | U25 - Instruments Calibration | IN | INIP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 247 | 0 | 10780.IN.IN.MH
C425134INJB000000 | U25 - Junction Boxes & Local Panels Install. | IN | INJB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 987 | 0 | 10780.IN.IN.MH
C425134INMS000000 | Miscellaneous Instrument activities | IN | ININ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 759 | 0 | 10780.IN.IN.MH
C425134INSL000000 | U25 - Single Pair Cable Pulling | IN | INSL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2371 | 0 | 10610.IN.SC.LM | 5770.09 | 0
C425136MEHM000000 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111A) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000230 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111C) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.066478 | 10610.ME.ER.TN | 5 | 3.46
C425136MEHM000240 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111C) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.079774 | 10610.ME.ER.TN | 5 | 3.46
C425136MEHV000080 | U25 - Inlet Liquid Coalescer (540-F-113C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40 | 0.0022455 | 10610.ME.ER.TN | 1 | 1
C424131CIPR100180 | U23- Civil Revamp of Piperack ( Unit 577)-577-PR-E2-P12 to 17 (Approx length =160m) Excluding Module - Part B | CI | CIPR1 | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 281 | 0.1013 | 10780.CI.CI.MH
C424131CIPR100200 | U22- Civil Revamp of Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 239711 | 84887.2226 | 10610.CI.CO.M3 | 4794.22 | 4794.2315
C424131CIPR100230 | U15- Civil Revamp of Piperack ( Unit 550/551/552/553)-I-001 (E-W) (Approx length=400m) - Part A | CI | CIPR1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 351 | 0.182 | 10780.CI.CI.MH
C424131ISPI000100 | U24 - Piping Insulation | IS | ISPI | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12100 | 0 | 10610.IS.PI.M2 | 4510 | 0
C424131PIRA000090 | U24 - Piping Tie-Ins Pre-Shutdown Spools Erection - H5 Shutdowns | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1700 | 2.6432 | 10610.PI.TI.DI | 367.16 | 293.7317
C424131PIRA000130 | U24- Piping Erection on Existing Piperack ( Unit 521)- 521-PR-I-1 (Aprox. length =32m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000200 | U25- Piping Erection on Existing Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =679m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0.73576 | 10610.PI.PR.DI | 189.92 | 28.4899
C424131PIRA000210 | U25- Piping Erection on Existing Piperack ( Unit 541)- 541-C2-PR (Aprox. length =280m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0.73576 | 10610.PI.PR.DI | 189.92 | 28.4899
C424131PIRA000220 | U10- Piping Erection on Existing Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =340m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000230 | U23- Piping Erection on Existing Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =580m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000240 | U23- Piping Erection on Existing Piperack ( Unit 577)- 577-PR-E2-P18 (Aprox. length =24m) | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000260 | U23- Piping Erection on Existing Piperack ( Unit 577)-577-I-001 (N-S) (Approx length =800m) Interface with CRI Part A | PI | PIRA | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000290 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-F1P13 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000300 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-F1P14 (Approximate length = 40m) | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PIRA000310 | U22- Piping Erection on Existing Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | PI | PIRA | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1709 | 0 | 10610.PI.PR.DI | 189.92 | 0
C424131PISU000150 | U24 - Piping Tie-ins Supports erection for Unit 541 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3686 | 20.0739 | 10610.PI.SU.TN | 8.19 | 8.19
C424131PISU000150 | U24 - Piping Tie-ins Supports erection for Unit 541 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3686 | 20.0739 | 10610.PI.SU.TN | 8.19 | 8.19
C425136MEHV000110 | U25 - Liquid Dehydration Outlet Filter (540-F-115C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7200 | 76.5828 | 10610.ME.ER.TN | 180 | 180
C425136MEHV000120 | U25 - Inlet Liquid Coalescer (541-F-113C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7200 | 72.7537 | 10610.ME.ER.TN | 180 | 180
C4271310000000070 | U24- Hot tapping T562-0002A/B | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1300 | 0.0067409 | 10780.PI.PI.MH
C427131PIPR000110 | U27 - Piping Tie-in Prefabrication - Remaining HB Complex Shutdown | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14259 | 287.7513 | 10610.PI.FB.DI | 3564.81 | 3415.1013
C427131PIPR000150 | U27 - Piping Tie-in Spools Prefabrication - 1st Shutdown | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 857 | 1.085 | 10610.PI.FB.DI | 214.25 | 214.25
C427131PIRA000050 | U27 - Habshan Complex (BUHASA) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000091 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0.6804 | 10610.PI.PR.DI | 156.21 | 23.4299
C427131PIRA000100 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000130 | U27 - Habshan Complex (H0 Unit 22 ) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000130 | U27 - Habshan Complex (H0 Unit 22 ) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000140 | U27- Pipe erection on modified Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000141 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Approximate length 700 M B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000150 | U27 - Piping Erection on Sleepers Part-1 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000160 | U27 - Piping Erection on Sleepers Part-2 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000170 | U27 - Piping Erection on Sleepers Part-3 -(500 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PISU000060 | U27 - Piping Tie-ins Supports Erection for Unit 20 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 209 | 0.064603 | 10610.PI.SU.TN | 0.46 | 0.46
C427131PISU000070 | U27 - Piping Tie-ins Supports Erection for Unit 21 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0.85303 | 10610.PI.SU.TN | 1.69 | 1.69
C427131PISU000090 | U27 - Piping Tie-ins for Unit 22 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9350 | 129.1486 | 10610.PI.TI.DI | 280.05 | 280.05
C424131PISU000180 | U24 - Piping Tie-ins Supports erection for Unit 549 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3552 | 18.6392 | 10610.PI.SU.TN | 7.89 | 7.89
C424131PISU000180 | U24 - Piping Tie-ins Supports erection for Unit 549 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3552 | 18.6392 | 10610.PI.SU.TN | 7.89 | 7.89
C424131PISU000190 | U24 - Piping Supports Prefabrication for revamped H-5 Area | PI | PISU1 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6029 | 45.4084 | 10610.PI.PU.TN | 23.19 | 16.6851
C424131PISU000200 | U24 - Piping Supports erection for revamped H-5 Area | PI | PISU2 | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10435 | 0 | 10610.PI.SU.TN | 23.19 | 0
C424131PISU000260 | U24 - Piping Tie-ins Supports erection for Unit 571 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 998 | 1.4715 | 10610.PI.SU.TN | 2.22 | 2.22
C424131PISU000260 | U24 - Piping Tie-ins Supports erection for Unit 571 | PI | PISU2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 998 | 1.4715 | 10610.PI.SU.TN | 2.22 | 2.22
C424131PISU000310 | U24 - Piping Tie-ins for Unit 532 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3400 | 17.0775 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000340 | U24 - Piping Tie-ins for Unit 541 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 120700 | 19402.0075 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000360 | U24 - Piping Tie-ins for Unit 549 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13600 | 273.24 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000380 | U24 - Piping Tie-ins for Unit 551 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 51000 | 3842.4369 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000390 | U24 - Piping Tie-ins for Unit 552 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10200 | 153.6975 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000410 | U24 - Piping Tie-ins for Unit 553 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 53550 | 4236.2867 | 10610.PI.TI.DI | 367.16 | 367.16
C424131PISU000440 | U24 - Piping Tie-ins for Unit 571 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14450 | 217.4659 | 10610.PI.TI.DI | 367.16 | 275.37
C424131PISU000440 | U24 - Piping Tie-ins for Unit 571 | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14450 | 217.4659 | 10610.PI.TI.DI | 367.16 | 275.37
C424131PITI000020 | U24 - Habshan 5 - Shutdown Works Area 1,2 & 3 PL-4 Tie ins | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8500 | 55.5638 | 10610.PI.TI.DI | 367.16 | 190.9232
C424131PITI000020 | U24 - Habshan 5 - Shutdown Works Area 1,2 & 3 PL-4 Tie ins | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8500 | 55.5638 | 10610.PI.TI.DI | 367.16 | 190.9232
C424131PITI000050 | U24 - Habshan 5 - Shutdown Works Area 1,2 & 3 Utilities ( Steam & Cond, BFW, Demin, etc.) | PI | PITI2 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 39100 | 1217.6246 | 10610.PI.TI.DI | 367.16 | 195.8101
C424131PRRE000060 | U24 - Piping Reinstatement | PR | PRRE | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 64506 | 0 | 10610.PR.RE.DI | 28996 | 0
C424131STEQ000010 | U24- Structure revamp of Process Structure ( Unit 522)- 522-Process Str A | ST | STEQ | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 242 | 0.035002 | 10610.ST.ER.TN | 4.56 | 3.7065
C424131STPR100010 | U24- Structure revamp of Piperack ( Unit 500)- 500-PR-001 (Aprox. length =570m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1102 | 0.49034 | 10610.ST.PR.TN | 20.78 | 6.649
C427131PISU000260 | U27 - Piping Tie-ins Supports Prefabrication | PI | PISU1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1106 | 0 | 10610.PI.PU.TN | 4.25 | 0
C427131PISU000270 | U27 - Piping Tie-ins Supports Erection for Unit 22 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 491 | 0.35614 | 10610.PI.SU.TN | 1.09 | 1.09
C427131PRFL000130 | U27 - Piping Flushing/Blowing | PR | PRFL | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3712 | 0 | 10610.PR.FL.DI | 24828 | 0
C427131PRHT000190 | U27 - Piping Hydrotesting | PR | PRHT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8698 | 0 | 10610.PR.HT.DI | 24828 | 0
C427132CIPR000040 | U27- Civil Revamp of Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5056 | 0 | 10610.CI.CO.M3 | 84.26 | 0
C427132CIPR000400 | U27 - Piperack PR-108 Foundations Execution (28 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 286 | 0 | 10780.CI.CI.MH
C427132CIPT000080 | U27 - Miscellaneous Supports & Sleeper Foundations Part-1 -(250Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0.064879 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000080 | U27 - Miscellaneous Supports & Sleeper Foundations Part-1 -(250Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0.064879 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000090 | U27 - Miscellaneous Supports & Sleeper Foundations Part-2 -(250 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000091 | U27 - Miscellaneous Supports & Sleeper Foundations Part-2 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000100 | U27 - Miscellaneous Supports & Sleeper Foundations Part-3 -(250 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIPT000110 | U27 - Miscellaneous Supports & Sleeper Foundations Part-4 -(215 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIPT000111 | U27 - Miscellaneous Supports & Sleeper Foundations Part-4 -(215 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIUG000020 | U27 - Demolition, re-routing/re-installation of Open drain | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1633 | 3.9395 | 10780.SP.SP.MH
C427132FPSS000070 | U27 - Steel Structure Fireproofing | FP | FPSS | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.FP.ST.M2 | 569.37 | 0
C427132STMS000110 | U27 - Miscellaneous Steel Structures Erection (SPS & Minor Structures) | ST | STMS | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1860 | 0 | 10780.ST.ST.MH
C427132STPR000040 | U27- Structure revamp of Piperack (Unit 377)- Mod NR-1 to NR-5 (Approx length 240 Meter)* | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 302 | 0 | 10610.ST.PR.TN | 5.69 | 0
C427132STPR000180 | U27 - Piperack PR-102 A/B/C/D/E/F/G Erection (229.5 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10799 | 0 | 10610.ST.PR.TN | 203.75 | 0
C427132STPR000190 | U27 - Piperack PR-104 A/B/C Erection (112.5 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5565 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100010 | U24- Structure revamp of Piperack ( Unit 500)- 500-PR-001 (Aprox. length =570m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1102 | 0.49034 | 10610.ST.PR.TN | 20.78 | 6.649
C424131STPR100030 | U24- Structure revamp of Piperack ( Unit 510)- 510-PR-I-2 to 7 (Aprox. length =211m) | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 180 | 0.039631 | 10610.ST.PR.TN | 3.39 | 3.3909
C424131STPR100080 | U25- Structure revamp of Piperack ( Unit 540)- 540-C1/C2/C3-PR (Aprox. length =340m) - Part B | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1796 | 3.1029 | 10610.ST.PR.TN | 33.9 | 22.3728
C424131STPR100090 | U23- Structure revamp of Piperack ( Unit 577)- 577-PR-E3-P11 to P19 (Aprox. length =290m) - Part A | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6625 | 0 | 10610.ST.PR.TN | 0 | 0
C424131STPR100140 | U10- Structure revamp of Piperack ( Unit 500)- 500-PR-011 Block C to H (Aprox. length =170m) - Part B | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4911 | 10.1362 | 10610.ST.PR.TN | 92.66 | 25.015
C424131STPR100210 | U22- Structure revamp of Piperack ( Unit 571)- 571-P Trestle supports near exiting KOD Drum | ST | STPR | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 143054 | 23529.5703 | 10610.ST.PR.TN | 2699.14 | 2105.3164
C424131STPR100230 | U23- Structure revamp of Piperack ( Unit 577)- 577-PR-E2-P18 (Aprox. length =24m) | ST | STPR | 24 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2858 | 0 | 10610.ST.PR.TN | 53.92 | 0
C424133PAFP000100 | U24 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 118 | 0 | 10610.PA.FP.M2 | 492 | 0
C424134ELEQ000040 | MODIFCATION OF 132kV GIS AND RELATED PROTECTION SYSTEM. SUB-500 | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.056927 | 10610.EL.EQ.UN | 360 | 241.2
C424134ELEQ000070 | UPS MODIFICATION FOR IES-500, IES-501 | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.081646 | 10610.EL.EQ.UN | 360 | 345.6
C424134ELEQ000080 | UPS MODIFICATION FOR IES-504 FIR 580-EE-0422 A/B AND 0423 A/B | EL | ELEQ3 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10610.EL.EQ.UN | 360 | 360
C424MEMC000000010 | Install SEAL GAS BOOSTER FOR COMPRESSOR 514-C101A/B | ME | MEMC | 24 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 499 | 0 | 10780.ME.ME.MH
C424PITI000000050 | Tie-in Pipe Support foundations for Unit 545 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 82 | 0.0099333 | 10780.CI.CI.MH
C424PITI000000120 | Tie-in Pipe Support foundations for Unit 575 | CI | CIPF1 | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C4250PRPRWT000090 | U25 - Walkthrough | PR | PRWT | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 388 | 0 | 10780.PR.PR.MH
C425131PIBB000010 | U25 - Big Bore Piping A/Equip. Erection (541-V-144, 541-F-113C / 15C, 541-P-111A/B/C) | PI | PIBB | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 19518 | 30.7617 | 10610.PI.BB.DI | 1951.81 | 254.0086
C425131PIMS000010 | U25- Miscellaneous piping activities | PI | PISU2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1927 | 0 | 10780.PI.PI.MH
C425131PRBO000150 | U25 - Rotary Box Up | PR | PRBO2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 270 | 0 | 10780.PR.PR.MH
C425132CIUG000030 | U25-Rerouting Open drain and other services | CI | CIUG1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1040 | 0 | 10780.CI.CI.MH
C427132STPR000250 | U27 - Piperack PR-109 Erection (33 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1667 | 0 | 10610.ST.PR.TN | 31.45 | 0
C427137INCO000070 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD ) at Unit 22 IES-01A | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.085092 | 10780.IN.IN.MH
C427137INCO000080 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD ) at Unit 96 IES-15 H1 Tr-1,2,3 export line (new tie in) | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10780.IN.IN.MH
C427137INCO000150 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD) at Unit 122 IES-01A | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.072115 | 10780.IN.IN.MH
C427PITI000000070 | Tie-in Pipe support foundations for Unit 77 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11626 | 199.6697 | 10610.CI.CO.M3 | 193.76 | 193.7594
C5131PEWT00000070 | U33 - Pipeline Walkthrough | PR | PRWT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 150 | 0 | 10780.PR.PR.MH
C5131PEWT00000710 | U33 - Pipeline Punch List Closure | PR | PRPL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 350 | 0 | 10780.PR.PR.MH
C5310PRPEHT000050 | U31.1 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 346 | 0 | 10610.PR.HT.DI | 26172 | 0
C5310PRPEHT000090 | U31.1 - Intelligent Pigging | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 92 | 0 | 10780.PE.PE.MH
C5310PRPEPL000050 | U31.1 - Pipeline Punch List | PR | PRPL | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 154 | 0 | 10780.PR.PR.MH
C531131PECP000020 | U31.2 - Permanent Cathodic Protection Works | PE | PECP | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1089 | 0 | 10610.PE.CP.LM | 3556 | 0
C531131PEPA000030 | U31.1 - Field Joint Coating | PE | PEPA | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3999 | 14.9786 | 10610.PE.PA.UN | 727 | 456.5633
C531131PEUG000020 | U31.1 - Pipeline Welding | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19251 | 426.0369 | 10610.PE.UG.LM | 8724 | 6778.5686
C531132PEBK000010 | U31.3 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3751 | 0 | 10610.PE.BK.M3 | 8870 | 0
C531132PEBK000020 | U31.2 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2712 | 0 | 10610.PE.BK.M3 | 960 | 0
C531132PEBK000040 | U31.2 - Berm Preparation | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2712 | 0 | 10610.PE.BK.M3 | 1080 | 0
C531132PEBK000060 | U31.1 - Berm Preparation | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3079 | 0 | 10610.PE.BK.M3 | 3600 | 0
C531132PEBK000120 | U31.3 - ROW Clean-up & Restoration | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2046 | 0 | 10780.PE.PE.MH
C531132PECU000040 | U31.3 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 0 | 10610.PE.CO.LM | 12 | 0
C531132PECU000040 | U31.3 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4800 | 0 | 10610.PE.CO.LM | 12 | 0
C531132PECU000080 | U31.2 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 8800 | 0.020592 | 10610.PE.CO.LM | 22 | 0
C425132CIVE000210 | U25 - Inlet Liquid Coalescer (540-F-113C) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C425132CIVE000210 | U25 - Inlet Liquid Coalescer (540-F-113C) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C425132CIVE000230 | U25 - Molecular Sieve Liquid Adsorber (541-V-144) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 753 | 0.83786 | 10610.CI.CO.M3 | 10.76 | 10.76
C425132CIVE000240 | U25 - Inlet Liquid Coalescer (541-F-113C) - Foundation Execution | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 250 | 0.092294 | 10610.CI.CO.M3 | 3.57 | 3.57
C425132CIVE000245 | U25 - Liquid Dehydration Outlet Filter (541-F-115C) - Foundation Execution ( Existing ) | CI | CIVE | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 371 | 0.20353 | 10610.CI.CO.M3 | 5.31 | 5.31
C425132STMS000090 | U25 - Miscellaneous Steel Structures Platform Erection (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3494 | 11.135 | 10610.ST.PL.TN | 58.23 | 43.9393
C425132STMS000120 | U25 - Miscellaneous Pipe Supports (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 433 | 0.03806 | 10610.ST.PL.TN | 7.21 | 1.1397
C425132STMS000130 | U25 - Miscellaneous Platforms and Crossover (Minor Structures) | ST | STMS | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.079441 | 10610.ST.PL.TN | 0 | 0
C425132STPL000010 | U25 - Equipment Platforms, Staircase, Floors, Ladders & Handrails Erection (541-STR-V144) | ST | STPL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4779 | 24.1565 | 10610.ST.PL.TN | 59.73 | 38.6265
C425133PAEQ000080 | U25 - Equipment Painting | PA | PAEQ | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3816 | 0 | 10780.PA.PA.MH
C425133PAPP000120 | U25 - Piping SandBl. & Priming | PA | PAPP | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14840 | 314.9137 | 10610.PA.PP.M2 | 0 | 0
C425134ELCL000200 | U25 - Electrical Cable Laying | EL | ELCL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3700 | 4.5953 | 10610.EL.PL.LM | 5246.37 | 1490.2839
C425134ELCO000180 | U25 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.CO.UN | 81 | 0
C425134ELEL000110 | U25 - Earthing & Lightning Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 953.44 | 0
C425134ELEL000115 | U25 - Earthing Works | EL | ELEL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 448 | 0 | 10610.EL.ES.LM | 476.72 | 0
C425134ELEQ000070 | U25 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.EQ.UN | 100 | 0
C425134ELTI000180 | U25 - Lighting Cable Trays Installation | EL | ELTI | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 504 | 0 | 10610.EL.CT.LM | 136.81 | 0
C425134INCI000000 | U25 - Conduits Installation | IN | INCT3 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 246 | 0 | 10610.IN.CD.LM | 175 | 0
C425134INCO000000 | U25 - Communication System Installation | IN | INCO | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 417 | 0 | 10780.IN.IN.MH
C531132PECU000090 | U31.3 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8800 | 0 | 10610.PE.CO.LM | 22 | 0
C531132PECU000140 | U31.1 - Open Cut Crossing - Underground Pipeline | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8800 | 0.020592 | 10610.PE.CO.LM | 22 | 0
C531132PETI000010 | U31.3 - Tie-In Welding incl NDT, Joint Coating & Backfilling | PE | PETI | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 5594 | 0 | 10780.PE.PE.MH
C531132PETR000110 | U31.2 - Trench Excavation | PE | PETR | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1024 | 0.77466 | 10780.PE.PE.MH
C531132PETR000120 | U31.3 - Trench Excavation | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1704 | 0.0085769 | 10780.PE.PE.MH
C531132PEUG000020 | U31.3 - Pipe Hauling & Stringing | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11653 | 81.0425 | 10780.PE.PE.MH
C531132PEUG000110 | U31.1 - Pipeline Lowering | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7920 | 18.0677 | 10780.PE.PE.MH
C531137INFC000010 | U31.2 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137INFC000040 | U31.1 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137INFO000010 | U31.3 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531137PECP000050 | U31.1 - Temporary Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1815 | 0 | 10610.PE.CP.LM | 5334 | 0
C531137PEFO000010 | U31.2 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531137PRLT000060 | U31.1 - Loop Testing | PR | PRLT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4387 | 0 | 10780.PR.PR.MH
C531137PRLT000080 | U31.2 - Loop Testing | PR | PRLT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 174 | 0 | 10780.PR.PR.MH
C531PECP000000310 | U16 - NGL Surge Sphere 545-V-201B - Welding Lower Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19179 | 415.1642 | 10780.ME.ME.MH
C531PECP000000330 | U16 - NGL Surge Sphere 545-V-201B - Derick Support removal | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1145 | 0 | 10780.ME.ME.MH
C531PECP000000350 | U16 - NGL Surge Sphere 545-V-201B - Erection of Top Crown Assembly With Top Polar & Welding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8588 | 0 | 10780.ME.ME.MH
C531PECP000000370 | U16 - NGL Surge Sphere 545-V-201B - Post Weld Heat Treatment ( PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1718 | 0 | 10780.ME.ME.MH
C531PECP000000430 | U16 - NGL Surge Sphere 545-V-201A - Erection of Column & Scaffolding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7731 | 88.2986 | 10780.ME.ME.MH
C531PECP000000440 | U16 - NGL Surge Sphere 545-V-201A - Erection of Stub End Piece With Lower Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 14571 | 313.6392 | 10780.ME.ME.MH
C531PECP000000490 | U16 - NGL Surge Sphere 545-V-201A - Derick Support Removal | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1784 | 0 | 10780.ME.ME.MH
C531PECP000000560 | U16 - NGL Surge Sphere 545-V-201A - Removal of External Scaffolding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1784 | 0 | 10780.ME.ME.MH
C531PECP000000600 | U16 - NGL Surge Sphere 545-V-201A - Lower Equator to Upper Equator ( Cirseam) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7137 | 0 | 10780.ME.ME.MH
C531PECP000000640 | U16 - NGL Surge Sphere 545-V-201B - Lower Equator to Upper Equator ( Cirseam) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7156 | 0 | 10780.ME.ME.MH
C531PETR000000010 | U31.3 - Construction of Right of Way (ROW) | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2939 | 12.7592 | 10780.PE.PE.MH
C531PETR000000070 | U31 - Test Coupons Welding (48" Dia) | PE | PEUG | 31 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 717 | 0.75956 | 10780.PE.PE.MH
C531PEUG000000040 | U31.2 - NDT & Visuals | PE | PEHT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3470 | 13.3552 | 10780.PE.PE.MH
C5320PRPEWT000020 | U32 - Pipeline Walkthrough | PR | PRWT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3 | 0 | 10780.PR.PR.MH
C532131PEPA000010 | U32 - Field Joint Coating | PE | PEPA | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1628 | 2.2224 | 10610.PE.PA.UN | 296 | 168.0096
C532131PEUG000010 | U32 - Pipeline Welding | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6776 | 52.7686 | 10610.PE.UG.LM | 3552 | 2711.9498
C532132PEBK000010 | U32 - Final Backfilling (above FOC Level) | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2990 | 0 | 10610.PE.BK.M3 | 900 | 0
C532132PEUG000010 | U32 - Pipe Hauling & Stringing | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4230 | 24.822 | 10780.PE.PE.MH
C532132PEWD000010 | U32 - Tie-In Welding incl NDT, Joint Coating & Backfilling | PE | PETI | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10831 | 0 | 10780.PE.PE.MH
C532137PECP000010 | U32 - Temporary Cathodic Protection Works | PE | PECP | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 775 | 0 | 10610.PE.CP.LM | 2277 | 0
C532137PEFO000010 | U32 - FO Cable Pulling | PE | PEFO | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6435 | 0 | 10610.PE.FO.LM | 11700 | 0
C532PEFC000000010 | U32 - FO Cable Splicing and Terminations | PE | PEFC | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3 | 0 | 10610.PE.FC.UN | 6 | 0
C532PETR000000010 | U32 - Test Coupons Welding (56" Dia) | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 251 | 0.093051 | 10780.PE.PE.MH
C533131PIBB000030 | U33 - BVS-01 - Installation of Valves | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1016 | 0 | 10780.PE.PE.MH
C533131PIBB000050 | U33 - BVS-02 - Installation of Valves | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1016 | 0 | 10780.PE.PE.MH
C533131PRHT000120 | U33 - BVS-02 - Hydraulic Test / Pneumatic Test | PR | PRHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 0 | 10780.PR.PR.MH
C533131PRHT000130 | U33 - BVS-03 - Hydraulic Test / Pneumatic Test | PR | PRHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2152 | 0 | 10780.PR.PR.MH
C533132PEBK000120 | U31.3 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4092 | 0 | 10610.PE.BK.M3 | 900 | 0
C425134INCT000000 | U25 - Primary Cable Trays Installation | IN | INCT1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2371 | 0 | 10610.IN.CT.LM | 117 | 0
C425134INCT000010 | U25 - Secondary Cable Trays Installation | IN | INCT2 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1328 | 0 | 10610.IN.CT.LM | 200 | 0
C425134INFC000000 | U25 - Fiber Optic Gland & Conn./Testing | IN | INFC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 228 | 0 | 10610.IN.CO.UN | 200 | 0
C425134INGC000000 | U25 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1480 | 0 | 10610.IN.CO.UN | 14 | 0
C425134INML000000 | U25 - multi Pair Cable Pulling | IN | INML | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2960 | 0 | 10610.IN.MC.LM | 9232.36 | 0
C425134INSL000000 | U25 - Single Pair Cable Pulling | IN | INSL | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2371 | 0 | 10610.IN.SC.LM | 5770.09 | 0
C425134PRMR000080 | U25 - Motor Run | PR | PRMR | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 90 | 0 | 10780.PR.PR.MH
C425136MEHM000000 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (540-P-111A) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000020 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111A) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C425136MEHM000230 | U25 - Horizontal Pump with Electrical Motor Erection Liquid Dehydration Feed Pump (541-P-111C) | ME | MEHM1 | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0.066478 | 10610.ME.ER.TN | 5 | 3.46
C425136MEHV000000 | U25 - Molecular Sieve Liquid Adsorber (541-V-144) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.14371 | 10610.ME.ER.TN | 8 | 8
C425136MEHV000110 | U25 - Liquid Dehydration Outlet Filter (540-F-115C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7200 | 76.5828 | 10610.ME.ER.TN | 180 | 180
C425136MEHV000130 | U25 - Liquid Dehydration Outlet Filter (541-F-115C) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 40 | 0 | 10610.ME.ER.TN | 1 | 0
C425136MEHV000200 | U25 - Molecular Sieve Liquid Adsorber (540-V-144) Erection | ME | MEHV | 25 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0.14371 | 10610.ME.ER.TN | 8 | 8
C4270PRPRWT000130 | U27 - Walkthrough | PR | PRWT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 279 | 0 | 10780.PR.PR.MH
C4271310000000020 | Hot tapping at Unit 903( 01 No) | PI | PITT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 520 | 0.0009587 | 10780.PI.PI.MH
C4271310000000030 | Hot Tapping at Unit 77(01 No) | PI | PITT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1820 | 0.0058721 | 10780.PI.PI.MH
C4271310000000060 | U24- Hot tapping T545-0004A/B | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1300 | 0 | 10780.PI.PI.MH
C4271310000000110 | U24- Hot tapping T550-0001A | PI | PITT | 24 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 910 | 0.002202 | 10780.PI.PI.MH
C427131PIPR000150 | U27 - Piping Tie-in Spools Prefabrication - 1st Shutdown | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 857 | 1.085 | 10610.PI.FB.DI | 214.25 | 214.25
C533132PEBK000122 | U33 - Section 2 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 0 | 10610.PE.BK.M3 | 326212.71 | 0
C533132PEBK000130 | U31.2 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3131 | 2.5777 | 10610.PE.BK.M3 | 9743 | 1734.254
C533132PEBK000131 | U33 - Section 3 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 41.0639 | 10610.PE.BK.M3 | 554.04 | 4.0722
C533132PEBK000142 | U33 - Section 4 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 234614.9 | 0
C533132PEBK000143 | U33 - Section 4 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 14281.03 | 0
C533132PECU000112 | U33 - Section 1 - Open Cut Crossing (87 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34800 | 417.4592 | 10610.PE.CO.LM | 87 | 19.7699
C533132PECU000122 | U33 - Section 2 - Open Cut Crossing (37 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14800 | 40.3577 | 10610.PE.CO.LM | 37 | 4.5099
C533132PECU000131 | U33 - Section 3 - Open Cut Crossing (29 Nos.) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11600 | 0 | 10610.PE.CO.LM | 29 | 0
C533132PECU000142 | U33 - Section 4 - Open Cut Crossing (62 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24800 | 0 | 10610.PE.CO.LM | 62 | 0
C533132PECU000280 | U33 - BVS-01 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000290 | U33 - BVS-01 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000310 | U33 - BVS-01 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000310 | U33 - BVS-01 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000320 | U33 - BVS-01 - RCC Cable Trench & Duct Bank Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2642 | 0 | 10610.PE.CO.LM | 6.5 | 0
C533132PECU000370 | U33 - BVS-01 - Installation of Perimeter Fence | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533132PEHT000041 | U33 - Intelligent Pigging | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1953 | 0 | 10780.PE.PE.MH
C533132PEHT000111 | U33 - Section 1 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 77715.23 | 0
C533132PEHT000131 | U33 - Section 3 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 75614.82 | 0
C533132PEHT000141 | U33 - Section 4 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 58608.98 | 0
C533132PEPA000115 | U33 - Section 1 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9475 | 85.8114 | 10610.PE.PA.UN | 2590.51 | 1676.06
C427131PIRA000020 | U27 - Habshan Complex (HB-0 Unit 20,21) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000050 | U27 - Habshan Complex (BUHASA) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 467 | 0.32248 | 10610.PI.PR.DI | 51.94 | 51.94
C427131PIRA000060 | U27- Piping Prefabrication -Habshan complex | PI | PIPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38654 | 1749.4779 | 10610.PI.FB.DI | 9663.48 | 7653.558
C427131PIRA000080 | U27 - Piping Supports Erection | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7407 | 0 | 10610.PI.SU.TN | 16.46 | 0
C427131PIRA000090 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 2.8763 | 10610.PI.PR.DI | 156.21 | 156.21
C427131PIRA000091 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0.6804 | 10610.PI.PR.DI | 156.21 | 23.4299
C427131PIRA000110 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(Approx length 800 Meter)*-A | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000111 | U27- Pipe erection on modified Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(Approx length 800 Meter)*-B | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PIRA000180 | U27 - Piping Erection on Sleepers Part-4 -(430 Meter) | PI | PIRA | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1406 | 0 | 10610.PI.PR.DI | 156.21 | 0
C427131PISU000040 | U27 - Piping Tie-ins Supports Erection for Unit 77 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 38 | 0 | 10610.PI.SU.TN | 0.08 | 0
C427131PISU000050 | U27 - Piping Tie-ins Supports Erection for Unit 96 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 93 | 0.012738 | 10610.PI.SU.TN | 0.21 | 0.21
C427131PISU000060 | U27 - Piping Tie-ins Supports Erection for Unit 20 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 209 | 0.064603 | 10610.PI.SU.TN | 0.46 | 0.46
C427131PISU000070 | U27 - Piping Tie-ins Supports Erection for Unit 21 | PI | PISU2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 760 | 0.85303 | 10610.PI.SU.TN | 1.69 | 1.69
C427131PISU000100 | U27 - Piping Tie-ins for Unit 21 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11050 | 0 | 10610.PI.TI.DI | 280.05 | 0
C427131PISU000110 | U27 - Piping Tie-ins for Unit 20 | PI | PITI2 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11050 | 0 | 10610.PI.TI.DI | 280.05 | 0
C427131PRHT000190 | U27 - Piping Hydrotesting | PR | PRHT | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8698 | 0 | 10610.PR.HT.DI | 24828 | 0
C427132CIGR000110 | U27 - Grounding Network Execution | CI | CIGR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4752 | 0 | 10610.CI.GR.LM | 7920 | 0
C427132CIPR000000 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (App length 800 M-Part A | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2882 | 12.2703 | 10780.CI.CI.MH
C427132CIPR000010 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 2(Appr length 800 Me-Part A | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7010 | 72.1355 | 10780.CI.CI.MH
C533132PEPA000145 | U33 - Section 4 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10698 | 0 | 10610.PE.PA.UN | 1953.63 | 0
C533132PETR000122 | U33 - Section 2 - Construction of Right of Way | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6574 | 63.631 | 10780.PE.PE.MH
C533132PETR000124 | U33 - Section 2 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 38544 | 0 | 10610.PE.FO.LM | 1090 | 0
C533132PETR000131 | U33 - Section 3 - Pre-Construction Survey and Stake-out | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10794 | 172.115 | 10780.PE.PE.MH
C533132PETR000134 | U33 - Section 3 - FOC cable laying ,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28996 | 0 | 10610.PE.FO.LM | 83105.95 | 0
C533132PETR000144 | U33 - Section 4 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24046 | 0 | 10610.PE.FO.LM | 64415.36 | 0
C533132PETR000145 | U33 - Section 4 - ROW Clean-up & Restoration | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 31649 | 0 | 10780.PE.PE.MH
C533132PEUG000112 | U33 - Section 1 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29357 | 1017.6554 | 10610.PE.UG.LM | 31026 | 24634.505
C533132PEUG000114 | U33 - Section 1 - Pipeline Lowering | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41014 | 875.0673 | 10780.PE.PE.MH
C533132PEUG000121 | U33 - Section 2 - Pipe Hauling ,Stringing | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25903 | 991.2237 | 10780.PE.PE.MH
C533132PEUG000122 | U33 - Section 2 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30652 | 1275.5663 | 10610.PE.UG.LM | 32590 | 29950.1774
C533132PEUG000124 | U33 - Section 2 - Pipeline Lowering | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 41014 | 1076.5758 | 10780.PE.PE.MH
C533132PEUG000126 | U33 - Section 2 - Tie-In Welding incl NDT, Joint Coating,Backfilling & Marker installation | PE | PETI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 21806 | 0 | 10780.PE.PE.MH
C533132PEUG000133 | U33 - Section 3 - NDT & Visuals | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15349 | 254.8377 | 10780.PE.PE.MH
C533132PEUG000143 | U33 - Section 4 - NDT & Visuals | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9488 | 18.2559 | 10780.PE.PE.MH
C533132PIBB000020 | U33 - BVS-01 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1201 | 0 | 10610.PI.SU.TN | 2.67 | 0
C533134ELCL000020 | U33 - BVS-01 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533134ELCO000020 | U33 - BVS-01 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533134INML000020 | U33 - BVS-03 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C533134INML000040 | U33 - BVS-02 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C533134PIBB000100 | U33 - BVS-02 - Installartion of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C427132CIPR000021 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(App length 800 Me-Part B | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7010 | 58.0754 | 10780.CI.CI.MH
C427132CIPR000030 | U27- Civil Revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 4(Appr length 700 M-Part A | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6134 | 44.4676 | 10780.CI.CI.MH
C427132CIPR000340 | U27 - Piperack PR-102A/B/C/D/E/F/G To H Foundations Execution (229.5 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 899 | 0.056713 | 10780.CI.CI.MH
C427132CIPR000370 | U27 - Piperack PR-107 Foundations Execution (38 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2882 | 0 | 10780.CI.CI.MH
C427132CIPR000390 | U27 - Piperack PR-105 Foundations Execution (15.5 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2882 | 0 | 10780.CI.CI.MH
C427132CIPR000410 | U27 - Piperack PR-109 Foundations Execution (33 Meter) | CI | CIPR1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 204 | 0 | 10780.CI.CI.MH
C427132CIPT000091 | U27 - Miscellaneous Supports & Sleeper Foundations Part-2 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1120 | 0 | 10610.CI.CO.M3 | 16.01 | 0
C427132CIPT000100 | U27 - Miscellaneous Supports & Sleeper Foundations Part-3 -(250 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIPT000101 | U27 - Miscellaneous Supports & Sleeper Foundations Part-3 -(250 Meter)B | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIPT000110 | U27 - Miscellaneous Supports & Sleeper Foundations Part-4 -(215 Meter)A | CI | CIPT1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8108 | 0 | 10610.CI.CO.M3 | 135.13 | 0
C427132CIUG000000 | U27 - Demolition, re-routing/re-installation of fire water system | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1633 | 3.9395 | 10610.SP.SP.M3 | 116.67 | 116.67
C427132CIUG000030 | U27 - Demolition, re-routing/re-installation of closed drain | SP | SPDE | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1633 | 3.9395 | 10610.SP.SP.M3 | 116.67 | 116.67
C427132FPSS000070 | U27 - Steel Structure Fireproofing | FP | FPSS | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2800 | 0 | 10610.FP.ST.M2 | 569.37 | 0
C427132STPR000000 | U27- Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 1 (App length 800 M-Part A | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 76 | 0.0063568 | 10610.ST.PR.TN | 1.44 | 1.0817
C427132STPR000020 | U27-Structure revamp of Piperack (Unit113)- Unit 113 South to Unit 113 North- Part 3(App length 800 Me-Part A | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 6042 | 0.26965 | 10780.ST.ST.MH
C427132STPR000180 | U27 - Piperack PR-102 A/B/C/D/E/F/G Erection (229.5 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10799 | 0 | 10610.ST.PR.TN | 203.75 | 0
C427132STPR000210 | U27 - Piperack PR-107 Erection (38 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1355 | 0 | 10610.ST.PR.TN | 25.57 | 0
C427132STPR000240 | U27 - Piperack PR-108 Erection (28 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 928 | 0 | 10610.ST.PR.TN | 17.5 | 0
C533134PIBB000130 | U33 - BVS-02 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533134PIBB000170 | U33 - BVS-03 - Installartion of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C533134PIBB000190 | U33 - BVS-02 - Installation of Field Equipment & Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134PIBB000210 | U33 - BVS-02 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533134PIBB000230 | U33 - BVS-03 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533134PIBB000260 | U33 - BVS-02 - Installation of Cable Trays/Ladders and Conduits | EL | ELTI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 478 | 0 | 10780.EL.EL.MH
C533134PRMR000090 | U33 - BVS-02 - Electrical Precommissioining | PR | PRMR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.PR.PR.MH
C533134PRMR000100 | U33 - BVS-03 - Electrical Precommissioining | PR | PRMR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 600 | 0 | 10780.PR.PR.MH
C533137ELEQ000060 | U33 - BVS-03 - Installation of Field Instruments | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533137ELEQ000140 | U33 - BVS-02 - Installation of Pig Signalers | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533137INCT000020 | U33 - BVS-01 - Installation of Cable Trays/Ladders and Conduits | IN | INCT1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10780.IN.IN.MH
C533137INFG000050 | U33 - BVS-01 - Installation of F&G Instruments | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137INFG000080 | U33 - BVS-01 - Installation of Wind Socks with Pole | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533137INGC000060 | U33 - BVS-02 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 240 | 0
C533137INGC000110 | U33 - BVS-01 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 210 | 0
C533137ININ000060 | U33 - BVS-01 - Installation of Oulet-jack phones | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000190 | U33 - BVS-02 - Installation of F&G Instruments | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137ININ000230 | U33 - BVS-02 - Installation of Wind Socks with Pole | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533137ININ000250 | U33 - BVS-03 - Installation of Oulet-jack phones | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000260 | U33 - BVS-02 - Installation of Fire Extinguishers | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C427132STPR000250 | U27 - Piperack PR-109 Erection (33 Meter) | ST | STPR | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1667 | 0 | 10610.ST.PR.TN | 31.45 | 0
C427133PAPP000120 | U27 - Piping SandBl. & Priming | PA | PAPP | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2634 | 9.9227 | 10610.PA.PP.M2 | 1317 | 1316.7429
C427137INCO000120 | EXISTING CONTROL SYSTEM MODIFICATIONS (ESD) at Unit 113 IES-16 113C101A | IN | INDC | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 240 | 0.084879 | 10780.IN.IN.MH
C427PITI000000010 | Tie-in Pipe support foundations for Unit 22 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 41 | 0.0024833 | 10780.CI.CI.MH
C427PITI000000020 | Tie-in Pipe support foundations for Unit 122 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 460 | 0.31253 | 10610.CI.CO.M3 | 6.57 | 6.57
C427PITI000000040 | Tie-in Pipe support foundations for Unit 21 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 476 | 0.33472 | 10610.CI.CO.M3 | 6.8 | 6.8
C427PITI000000050 | Tie-in Pipe support foundations for Unit 20 | CI | CIPF1 | 27 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 476 | 0.33472 | 10610.CI.CO.M3 | 6.8 | 6.8
C5310PRPEHT000040 | U31.2 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 351 | 0 | 10610.PR.HT.DI | 26280 | 0
C5310PRPEHT000080 | U31.2 - Pipeline Dewatering, Swabbing and Drying | PE | PEHT | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 245 | 0 | 10780.PE.PE.MH
C5310PRPEHT000100 | U31.3 - Intelligent Pigging | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 145 | 0 | 10780.PE.PE.MH
C5310PRPEWT000030 | U31.3 - Pipeline Walkthrough | PR | PRWT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3 | 0 | 10780.PR.PR.MH
C531131PEPA000010 | U31.2 - Field Joint Coating | PE | PEPA | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4015 | 15.2507 | 10610.PE.PA.UN | 730 | 461.36
C531131PEPA000020 | U31.3 - Field Joint Coating | PE | PEPA | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3988 | 0.97022 | 10610.PE.PA.UN | 725 | 29.9425
C531131PEPA000050 | U31.3 - Pre-Construction Survey and Stake-out | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2740 | 11.0907 | 10780.PE.PE.MH
C531131PEPA000070 | U31.2 - Pre-Construction Survey and Stake-out | PE | PETR | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1823 | 4.9083 | 10780.PE.PE.MH
C531131PETI000060 | U31.3 - Installation of Pipeline Markers | PE | PETI | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2268 | 0 | 10780.PE.PE.MH
C531131PEUG000010 | U31.2 - Pipeline Welding | PE | PEUG | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 20213 | 458.5839 | 10610.PE.UG.LM | 8760 | 6563.852
C531131PEUG000020 | U31.1 - Pipeline Welding | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 19251 | 426.0369 | 10610.PE.UG.LM | 8724 | 6778.5686
C531131PEUG000050 | U31.3 - Pipeline Welding | PE | PEUG | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 15776 | 75.8213 | 10610.PE.UG.LM | 8700 | 1785.2539
C531132PEBK000010 | U31.3 - Final Backfilling (above FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3751 | 0 | 10610.PE.BK.M3 | 8870 | 0
C531132PEBK000040 | U31.2 - Berm Preparation | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2712 | 0 | 10610.PE.BK.M3 | 1080 | 0
C533137ININ000310 | U33 - BVS-03 - Installation of F&G Instruments | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137ININ000340 | U33 - BVS-03 - Installation of Wind Socks with Pole | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533137PIBB000150 | U33 - BVS-02 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137PIBB000240 | U33 - BVS-03 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C533137PIBB000250 | U33 - BVS-03 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137PRLT000070 | U33 - Loop Testing | PR | PRLT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 263 | 0 | 10780.PR.PR.MH
C533PECU000000010 | U33 - BVS-03 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000020 | U33 - BVS-03 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000040 | U33 - BVS-03 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0.20965 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000060 | U33 - BVS-02 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000140 | U33 - BVS-02 - Fabrication and Erection of Fence Poles | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4268 | 0 | 10780.PE.PE.MH
C533PECU000000150 | U33 - BVS-02 - Installation of Perimeter Fence | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533PECU000000180 | U33 - BVS-02 - Precasting and Erection of Crash Barriers, Bollards | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 610 | 0 | 10780.PE.PE.MH
C533PECU000000280 | U33 - BVS-03 - RCC Cable Trench & Duct Bank Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10780.PE.PE.MH
C533PECU000000290 | U33 - BVS-03 - Cover Precasting and Installation for Cable Trench | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1524 | 0 | 10780.PE.PE.MH
C533PECU000000310 | U33 - BVS-03 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000320 | U33 - BVS-03 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000320 | U33 - BVS-03 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000340 | U33 - BVS-03 - Installation of Perimeter Fence | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533PECU000000370 | U33 - BVS-03 - Precasting and Erection of Crash Barriers, Bollards | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 610 | 0 | 10780.PE.PE.MH
C531132PEBK000050 | U31.3 - Berm Preparation | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3069 | 0 | 10610.PE.BK.M3 | 7185 | 0
C531132PEBK000060 | U31.1 - Berm Preparation | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3079 | 0 | 10610.PE.BK.M3 | 3600 | 0
C531132PEBK000090 | U31.2 - ROW Clean-up & Restoration | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 937 | 0 | 10780.PE.PE.MH
C531132PEBK000100 | U31.1 - Construction of Maintenance Road | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1064 | 0 | 10780.PE.PE.MH
C531132PECR000010 | U31.2 - Open Cut Crossing - Above ground Pipeline | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PECU000030 | U31.3 - Open Cut Crossing - Overhead Power Line | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PECU000139 | U31.1 - Trial Pits (64nos) | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 956 | 1.3117 | 10780.PE.PE.MH
C531132PECU300050 | U31.2 - NDRC Crossing (KP 2+400 to KP 2+800) | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PECU300110 | U31.1 - NDRC Crossing (KP 2+400 to KP 2+800) | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 266 | 0 | 10610.PE.CO.LM | 1 | 0
C531132PETR000140 | U31.1 - Trench Excavation | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 972 | 0.40579 | 10780.PE.PE.MH
C531132PEUG000060 | U31.2 - Cold Field Bending | PE | PEUG | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3838 | 13.3718 | 10780.PE.PE.MH
C531132PEWD000020 | U31.1 - Tie-In Welding incl NDT, Joint Coating & Backfilling | PE | PETI | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8637 | 0 | 10780.PE.PE.MH
C531137INFC000040 | U31.1 - FO Cable Splicing and Terminations | PE | PEFC | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10 | 0 | 10610.PE.FC.UN | 18 | 0
C531137INFO000010 | U31.3 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531137PECP000010 | U31.3 - Temporary Cathodic Protection Works | PE | PECP | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1541 | 0 | 10610.PE.CP.LM | 5322 | 0
C531137PEFO000030 | U31.1 - FO Cable Pulling | PE | PEFO | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 21120 | 0 | 10610.PE.FO.LM | 38400 | 0
C531137PRLT000070 | U31.3 - Loop Testing | PR | PRLT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 174 | 0 | 10780.PR.PR.MH
C531PECP000000260 | U16 - NGL Surge Sphere 545-V-201B - Erection of Column & Scaffolding | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 10305 | 156.8831 | 10780.ME.ME.MH
C531PECP000000460 | U16 - NGL Surge Sphere 545-V-201A - Erection & Assembly of Top Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 9218 | 3.0127 | 10780.ME.ME.MH
C531PECP000000470 | U16 - NGL Surge Sphere 545-V-201A - Welding Lower Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 16355 | 194.4714 | 10780.ME.ME.MH
C531PECP000000480 | U16 - NGL Surge Sphere 545-V-201A - Welding Top Equators | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 11002 | 0 | 10780.ME.ME.MH
C533PETR000000150 | U33 - Submission and Approval of Welding Procedure Specification (30" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6044 | 53.9663 | 10780.PE.PE.MH
C533PETR000000160 | U33 - Submission and Approval of Welding Procedure Specification (56" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9066 | 121.4242 | 10780.PE.PE.MH
C641131PISB000060 | U41 - Small Bore Piping A/Equip. Erection | PI | PISB | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7018 | 0 | 10610.PI.SB.DI | 638 | 0
C641131PISU000110 | U41 - Piping Supports Prefabrication | PI | PISU1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 32091 | 82.29 | 10610.PI.PU.TN | 123.43 | 7.2732
C641132CIGR000060 | U41 - Grounding Network Execution | CI | CIGR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 66 | 0 | 10610.CI.GR.LM | 110 | 0
C641132CIGT000100 | U41 - Equipment Grouting Execution | CI | CIGT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10780.CI.CI.MH
C641132CIGT000110 | U41 - Steel Structure Grouting Execution | CI | CIGT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 800 | 0 | 10780.CI.CI.MH
C641132CIHE000140 | U41 - Scrapper Launcher 625-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2079 | 6.3852 | 10610.CI.CO.M3 | 34.65 | 34.6499
C641132CIHE000150 | U41 - Scrapper Launcher 627-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2350 | 8.159 | 10610.CI.CO.M3 | 39.17 | 39.1699
C641132CIHE000160 | U41 - Jib Crane Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4342 | 27.8526 | 10610.CI.CO.M3 | 72.37 | 72.3701
C641132CIMF000050 | U41 - Miscellaneous Foundations Execution | CI | CIMF | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 284420 | 119127.3153 | 10610.CI.CO.M3 | 5688.39 | 5688.4073
C641132CIPR1250 | U41 - 96-PR-102A Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 30174 | 0 | 10610.CI.CO.M3 | 603.48 | 0
C641132CIPR1260 | U41 - 96-PR-103 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3218 | 0 | 10610.CI.CO.M3 | 53.63 | 0
C641132CIPR1270 | U41 - 96-PR-104A Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13874 | 0 | 10610.CI.CO.M3 | 277.47 | 0
C641132CIPR1300 | U41 - 96-PR-108 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4229 | 0 | 10610.CI.CO.M3 | 70.48 | 0
C641132CIPR1310 | U41 - 96-PR-109 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4364 | 0 | 10610.CI.CO.M3 | 72.73 | 0
C641132CIPT000030 | U41 - PR-Pipe Tracks Execution | CI | CIPT1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 286 | 0.05967 | 10610.CI.CO.M3 | 4.08 | 1.43
C641132STPL000110 | U41 - Equipment Platforms, Ladders & Handrails Erection | ST | STPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3206 | 0 | 10610.ST.PL.TN | 40.07 | 0
C641132STPR000090 | U41 - 627-PR-101A&B Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 9174 | 16.1636 | 10610.ST.PR.TN | 173.1 | 0
C641132STPR000100 | U41 - 96-PR-110 Secondary Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ST.PR.TN | 27.16 | 0
C531PECP000000550 | U16 - NGL Surge Sphere 545-V-201A - NDT (Post PWHT) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4163 | 0 | 10780.ME.ME.MH
C531PECP000000555 | U16 - NGL Surge Sphere 545-V-201A - NDT Works (After Hydrotest) | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 2974 | 0 | 10780.ME.ME.MH
C531PECP000000570 | U16 - NGL Surge Sphere 545-V-201A - Ground Assembly & Welding of Top Polar With Crown | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 13381 | 25.1287 | 10780.ME.ME.MH
C531PECP000000580 | U16 - NGL Surge Sphere 545-V-201A - Erection & Welding Bottom Polar Plate | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8921 | 0 | 10780.ME.ME.MH
C531PECP000000670 | U16 - NGL Surge Sphere 545-V-201A - Deluge System | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8921 | 0 | 10780.ME.ME.MH
C531PECP000000680 | U16 - NGL Surge Sphere 545-V-201B - Deluge System | ME | MESF | 16 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 8588 | 0 | 10780.ME.ME.MH
C531PECU000000020 | U31.1 - Open Cut Crossing - Overhead Power Line | PE | PECU2 | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 400 | 0.11031 | 10610.PE.CO.LM | 1 | 0.47
C531PECU000000040 | U31.2 - Open Cut Crossing - Overhead Power Line | PE | PECU2 | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 400 | 0.11031 | 10610.PE.CO.LM | 1 | 0.47
C531PETR000000020 | U31.1 - Construction of Right of Way (ROW) | PE | PETR | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 1729 | 4.4172 | 10780.PE.PE.MH
C531PETR000000030 | U31.2 - Construction of Right of Way (ROW) | PE | PETR | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1532 | 3.4678 | 10780.PE.PE.MH
C531PETR000000060 | U31 - Test Coupons Welding (36" Dia) | PE | PEUG | 31 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 426 | 0.26838 | 10780.PE.PE.MH
C531PEUG000000030 | U31.1 - NDT & Visuals | PE | PEHT | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3521 | 13.7858 | 10780.PE.PE.MH
C5320PRPEHT000020 | U32 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 270 | 0 | 10610.PR.HT.DI | 16576 | 0
C5320PRPEPL000020 | U32 - Pipeline Punch List | PR | PRPL | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6 | 0 | 10780.PR.PR.MH
C532131PECP000010 | U32 - Permanent Cathodic Protection Works | PE | PECP | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 465 | 0.011499 | 10780.PE.PE.MH
C532131PEUG000010 | U32 - Pipeline Welding | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6776 | 52.7686 | 10610.PE.UG.LM | 3552 | 2711.9498
C532132PEBK000020 | U32 - ROW Clean-up & Restoration | PE | PEBK | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 874 | 0 | 10780.PE.PE.MH
C532132PERD000010 | U32 - Open Cut Crossing - Asphalt Road/Rig Road/Gatch Road | PE | PECU2 | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4400 | 17.8752 | 10610.PE.CO.LM | 11 | 6.88
C532132PEUG000040 | U32 - Cold Field Bending | PE | PEUG | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2151 | 0 | 10780.PE.PE.MH
C532137PECP000010 | U32 - Temporary Cathodic Protection Works | PE | PECP | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 775 | 0 | 10610.PE.CP.LM | 2277 | 0
C532PEHT000000010 | U32 - Pipeline Dewatering, Swabbing and Drying | PE | PEHT | 32 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 189 | 0 | 10780.PE.PE.MH
C641132STPR000100 | U41 - 96-PR-110 Secondary Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1440 | 0 | 10610.ST.PR.TN | 27.16 | 0
C641132STPR100 | U41 - 96-PR-102 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10799 | 0 | 10610.ST.PR.TN | 203.75 | 0
C641132STPR110 | U41 - 96-PR-103 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2120 | 0 | 10610.ST.PR.TN | 0 | 0
C641132STPR160 | U41 - 96-PR-108 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 928 | 0 | 10610.ST.PR.TN | 17.5 | 0
C641133PASP000060 | U41 - Piping Supports SandBl. & Priming | PA | PASP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 475 | 0.012833 | 10610.PA.SU.TN | 0 | 0
C641133PAST000060 | U41 - Steel Structure Painting Touch Up | PA | PAST | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 27467 | 0 | 10780.PA.PA.MH
C641134ELCL000110 | U41 - Electrical Cable Laying | EL | ELCL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 12730 | 10.8833 | 10610.EL.PL.LM | 17792.58 | 1010.9744
C641134ELCO000100 | U41 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.CO.UN | 432 | 0
C641134ELCP000050 | U41 - Cathodic Protection Piping | EL | ELCP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1157 | 0 | 10780.EL.EL.MH
C641134ELEQ000020 | U41 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.EQ.UN | 520 | 0
C641134ELPL000050 | U41 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3761 | 0 | 10780.EL.EL.MH
C641134ELTI000110 | U41 - Electrical Cable Trays Installation | EL | ELTI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 5786 | 0 | 10610.EL.CT.LM | 3474.33 | 0
C641136CIHE000120 | U41 - Pig Trolley Erection | ME | MEPA | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3000 | 0 | 10610.ME.ER.TN | 50 | 0
C641136MEMC000040 | U41 - Miscellaneous Erection | ME | MEMC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C641136MEMC000040 | U41 - Miscellaneous Erection | ME | MEMC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C641136MEVV000450 | U41 - 36" PL-10 Scrapper Launcher 625-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C641137INCT000090 | U41 - Secondary Cable Trays Installation | IN | INCT2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2204 | 0 | 10610.IN.CT.LM | 600 | 0
C641137INFO000040 | U41 - Fiber Optic Cable Pulling | IN | INFO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 535 | 0 | 10610.IN.FO.LM | 900 | 0
C641137INGC000090 | U41 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2456 | 0.044551 | 10610.IN.CO.UN | 540 | 3.0024
C641137INGC000100 | U41 - Single Pair Cable Gland & Conn./Testing | IN | INGC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1637 | 0 | 10610.IN.CO.UN | 430 | 0
C641137INMS000010 | U41 - Misc Instrumentation | IN | ININ | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1259 | 0 | 10780.IN.IN.MH
C533131PIBB000070 | U33 - BVS-02 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1511 | 0 | 10610.PI.SU.TN | 3.36 | 0
C533132PEBK000110 | U31.1 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 3555 | 3.3234 | 10610.PE.BK.M3 | 890 | 158.42
C533132PEBK000112 | U33 - Section 1 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 0 | 10610.PE.BK.M3 | 311098.22 | 0
C533132PEBK000113 | U33 - Section 1 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 79123 | 0 | 10610.PE.BK.M3 | 18936.58 | 0
C533132PEBK000120 | U31.3 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 4092 | 0 | 10610.PE.BK.M3 | 900 | 0
C533132PEBK000121 | U33 - Section 2 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 3816.2645 | 10610.PE.BK.M3 | 597.09 | 238.842
C533132PEBK000122 | U33 - Section 2 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 0 | 10610.PE.BK.M3 | 326212.71 | 0
C533132PEBK000123 | U33 - Section 2 - Berm Preparation | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 82138 | 0 | 10610.PE.BK.M3 | 19856.6 | 0
C533132PEBK000130 | U31.2 - Padding & Backfilling (upto FOC Level) | PE | PEBK | 31 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3131 | 2.5777 | 10610.PE.BK.M3 | 9743 | 1734.254
C533132PEBK000132 | U33 - Section 3 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 61792 | 0 | 10610.PE.BK.M3 | 302690.16 | 0
C533132PEBK000142 | U33 - Section 4 - Final Backfilling (above FOC Level) | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 51242 | 0 | 10610.PE.BK.M3 | 234614.9 | 0
C533132PECP000111 | U33 - Section 1 - Cathodic Protection Works | PE | PECP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10918 | 13.2957 | 10610.PE.CP.LM | 20739.69 | 1659.1752
C533132PECU000021 | U33 - Section 2 - Trial Pits (41) | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9714 | 84.8137 | 10780.PE.PE.MH
C533132PECU000041 | U33 - Section 4 - Trial Pits (120 Nos) | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4317 | 5.1691 | 10780.PE.PE.MH
C533132PECU000111 | U33 - Section 1 - NDRC Crossing (7 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1862 | 1.1114 | 10610.PE.CO.LM | 7 | 1.47
C533132PECU000112 | U33 - Section 1 - Open Cut Crossing (87 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34800 | 417.4592 | 10610.PE.CO.LM | 87 | 19.7699
C533132PECU000122 | U33 - Section 2 - Open Cut Crossing (37 Nos) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 14800 | 40.3577 | 10610.PE.CO.LM | 37 | 4.5099
C533132PECU000131 | U33 - Section 3 - Open Cut Crossing (29 Nos.) | PE | PECU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11600 | 0 | 10610.PE.CO.LM | 29 | 0
C533132PECU000230 | U33 - BVS-01 - Backfilling / Embankment Construction | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10550 | 0 | 10780.PE.PE.MH
C533132PECU000280 | U33 - BVS-01 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C641137INRI000030 | U41 - Prefabricated RIB´s Installation | IN | INRI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 360 | 0 | 10780.IN.IN.MH
C641137INSL000050 | U41 - Single Pair Cable Pulling | IN | INSL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3936 | 0 | 10610.IN.SC.LM | 5981.61 | 0
C641137PRLT000050 | U41 - Loops Testing | PR | PRLT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4735 | 0 | 10780.PR.PR.MH
C749131CIPR000000 | U49-Civil Revamp of Piperack Train -1 N-S Road Crossing Rack-55 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIPR000010 | U49- Civil Revamp of Piperack Train -2 N-S Road Crossing Rack-55 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIPR000030 | U49- Civil Revamp of Piperack Train -3 Rack-255 Meter - Part A | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIPR000050 | U49- Civil Revamp of interface Piperack for Ruwais NGL trains to supply B-4 FEED stocks-185 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIUG000000 | Rerouting and demolition of existing underground Closed drain | CI | CIUG1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.CI.CI.MH
C749131ISPI000050 | U49 - Piping Insulation | IS | ISPI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13833 | 0 | 10610.IS.PI.M2 | 5041 | 0
C749131PIMS000180 | U49-Miscellaneous Piping activities | PI | PISU2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 59 | 0 | 10780.PI.PI.MH
C749131PIRA000060 | U49- Pipe Erection on Piperack Train -1 N-S Road Crossing Rack (Approx length 55 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000070 | U49- Pipe Erection on Piperack Train -2 N-S Road Crossing Rack (Approx length 55 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000080 | U49- Pipe Erection on Piperack Train -2-3 E-W Rack (Approx length 120 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000100 | U49- Pipe Erection on Piperack Train -4 Rack (Approx length 170 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000110 | U49- Pipe Erection on interface Piperack for Ruwais NGL trains modifications to supply B-4 FEED stocks’ | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000120 | U49- Piping Prefabrication | PI | PIPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11108 | 64.1054 | 10610.PI.FB.DI | 2776.9 | 724.8028
C749131PISU000090 | U49 - Piping Supports Prefabrication | PI | PISU1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3736 | 0.07814 | 10610.PI.PU.TN | 14.37 | 0
C749131PIUG000050 | U49 - Piping Erection UG | PI | PIUG | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 26 | 0 | 10780.PI.PI.MH
C749131PRHT000050 | U49 - Piping Hydrotesting | PR | PRHT | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 34179 | 0 | 10610.PR.HT.DI | 14453 | 0
C533132PECU000290 | U33 - BVS-01 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 0 | 10610.CI.CO.M3 | 18.33 | 0
C533132PECU000300 | U33 - BVS-01 - Anchor Blocks Installation | PE | PEAB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10610.CI.CO.M3 | 35.57 | 0
C533132PECU000340 | U33 - BVS-01 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 1.0941 | 10610.CI.CO.M3 | 18.33 | 18.33
C533132PECU000340 | U33 - BVS-01 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1283 | 1.0941 | 10610.CI.CO.M3 | 18.33 | 18.33
C533132PECU000380 | U33 - BVS-01 - Fabrication & Installation of Fence Gates | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 610 | 0 | 10780.PE.PE.MH
C533132PEHT000121 | U33 - Section 2 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 81490.97 | 0
C533132PEHT000131 | U33 - Section 3 - Pipeline Cleaning, Gauging and Hydrotesting | PE | PEHT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5023 | 0 | 10610.PR.HT.DI | 75614.82 | 0
C533132PEPA000125 | U33 - Section 2 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16811 | 295.1721 | 10610.PE.PA.UN | 2716.37 | 1920.4736
C533132PEPA000135 | U33 - Section 3 - Field Joint Coating | PE | PEPA | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 16811 | 52.0204 | 10610.PE.PA.UN | 2520.49 | 297.4178
C533132PETR000111 | U33 - Section 1 - Construction of Right of Way | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6280 | 56.2295 | 10780.PE.PE.MH
C533132PETR000112 | U33 - Section 1 - Trench Excavation | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8831 | 66.4425 | 10780.PE.PE.MH
C533132PETR000133 | U33 - Section 3 - Trench Excavation | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8341 | 0.83555 | 10780.PE.PE.MH
C533132PETR000134 | U33 - Section 3 - FOC cable laying ,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28996 | 0 | 10610.PE.FO.LM | 83105.95 | 0
C533132PETR000136 | U33 - Section 3 - Construction of Maintenance Road | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24114 | 0 | 10780.PE.PE.MH
C533132PETR000141 | U33 - Section 4 - Pre-Construction Survey and Stake-out | PE | PETR | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 7359 | 18.4014 | 10780.PE.PE.MH
C533132PETR000144 | U33 - Section 4 - FOC cable laying,Termination & Splicing works | PE | PEFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24046 | 0 | 10610.PE.FO.LM | 64415.36 | 0
C533132PEUG000111 | U33 - Section 1 - Pipe Hauling,Stringing | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 24608 | 858.9804 | 10780.PE.PE.MH
C533132PEUG000122 | U33 - Section 2 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 30652 | 1275.5663 | 10610.PE.UG.LM | 32590 | 29950.1774
C533132PEUG000125 | U33 - Section 2 - Cold bending works | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 25903 | 87.7233 | 10780.PE.PE.MH
C533132PEUG000131 | U33 - Section 3 - Pipe Hauling,Stringing | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47489 | 2878.5237 | 10780.PE.PE.MH
C749131STPR000010 | U49- Structure revamp of Piperack Train -2 N-S Road Crossing Rack-55 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 143 | 0 | 10610.ST.PR.TN | 2.7 | 0
C749131STPR000030 | U49- Structure revamp of Piperack Train -3 Rack-255 Meter - Part A | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 140 | 0 | 10610.ST.PR.TN | 2.65 | 0
C749131STPR000040 | U49- Structure revamp of Piperack Train -4 Rack-170 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 111 | 0 | 10610.ST.PR.TN | 2.1 | 0
C749131STPR000050 | U49- Structure revamp of interface Piperack for Ruwais NGL trains to supply B-4 FEED stocks-185 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13618 | 0 | 10610.ST.PR.TN | 256.94 | 0
C749132CIMF000040 | U49 - Miscellaneous Foundations Execution | CI | CIMF | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 50252 | 1578.7696 | 10610.CI.CO.M3 | 1005.04 | 700.0003
C749132CIST000180 | U49 - 30" PL-952 Scrapper Receiver 952-V-501 Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5849 | 0 | 10610.CI.CO.M3 | 97.48 | 0
C749132CIST000180 | U49 - 30" PL-952 Scrapper Receiver 952-V-501 Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 5849 | 0 | 10610.CI.CO.M3 | 97.48 | 0
C749132CIST000200 | U49 - Pig Trolley Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 416 | 0 | 10610.CI.CO.M3 | 5.94 | 0
C749132STMS000040 | U49 - Miscellaneous Steel Structures Erection | ST | STMS | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1530 | 0 | 10610.ST.PL.TN | 25.5 | 0
C749133PAFP000050 | U49 - Piping Final Coat & Touch-Up Painting | PA | PAFP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 140 | 0 | 10610.PA.FP.M2 | 584 | 0
C749133PAST000050 | U49 - Steel Structure Painting Touch Up | PA | PAST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1593 | 0 | 10780.PA.PA.MH
C749134ELCI000040 | U49 - Conduits Installation | EL | ELCI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 791 | 0 | 10780.EL.EL.MH
C749134ELCL000080 | U49 - Lighting Cable Laying | EL | ELCL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1424 | 0 | 10610.EL.LC.LM | 8141.7 | 0
C749134ELCL000090 | U49 - Electrical Cable Laying | EL | ELCL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6961 | 0 | 10610.EL.PL.LM | 8311.79 | 0
C749134ELCO000080 | U49 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.CO.UN | 337 | 0
C749134ELCO000090 | U49 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3797 | 0 | 10610.EL.CO.UN | 472 | 0
C749134ELCP000040 | U49 - Cathodic Protection Piping | EL | ELCP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 633 | 0 | 10780.EL.EL.MH
C749134ELEQ000010 | U49 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.EQ.UN | 480 | 0
C749134ELGR000050 | U49 - Grounding Installation | EL | ELEL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 844 | 0 | 10780.EL.EL.MH
C749136MEVV000030 | U49 - Pig Trolley Erection | ME | MEVV | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 6 | 0
C533132PEUG000132 | U33 - Section 3 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 47489 | 2500.4176 | 10610.PE.UG.LM | 30240 | 22056.1851
C533132PEUG000141 | U33 - Section 4 - Pipe Hauling,Stringing | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32379 | 352.0575 | 10780.PE.PE.MH
C533132PEUG000142 | U33 - Section 4 - Pipeline Welding | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 32379 | 338.3042 | 10610.PE.UG.LM | 23439 | 5119.7808
C533132PEUG000145 | U33 - Section 4 - Cold bending works | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 28062 | 0 | 10780.PE.PE.MH
C533134ELEL000030 | U33 - BVS-01 - Installation of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C533134ELTI000020 | U33 - BVS-01 - Installation of Cable Trays/Ladders and Conduits | EL | ELTI | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 478 | 0 | 10780.EL.EL.MH
C533134INML000020 | U33 - BVS-03 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C533134PIBB000090 | U33 - BVS-02 - Installation of Passive Cooling Shelter | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533134PIBB000170 | U33 - BVS-03 - Installartion of Earthing System | EL | ELEL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 382 | 0 | 10610.EL.ES.LM | 2465.78 | 0
C533134PIBB000180 | U33 - BVS-03 - Installation of Field Equipment & Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELEQ1 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 179 | 0 | 10780.EL.EL.MH
C533134PIBB000210 | U33 - BVS-02 - Cable Glanding and Terminations | EL | ELCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 574 | 0 | 10610.EL.CO.UN | 324 | 0
C533134PIBB000220 | U33 - BVS-03 - Cables Pulling | EL | ELCL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1052 | 0 | 10610.EL.PL.LM | 1896.42 | 0
C533137ELEQ000030 | U33 - BVS-02 - Installation of Field Instruments and SS Tubing | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533137INFG000070 | U33 - BVS-01 - Installation of Fire Extinguishers | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137INGC000020 | U33 - BVS-03 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 240 | 0
C533137INGC000030 | U33 - BVS-01 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137INGC000060 | U33 - BVS-02 - Cable Glanding and Terminations | IN | INFC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 96 | 0 | 10610.IN.CO.UN | 240 | 0
C533137ININ000030 | U33 - BVS-01 - Installation of Passive Cooling Shelter | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1423 | 0 | 10780.PE.PE.MH
C533137ININ000040 | U33 - BVS-01 - Installation of Pig Signalers | IN | ININ | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 479 | 0 | 10780.IN.IN.MH
C533137ININ000080 | U33 - BVS-01 - Installation of on fence sensors | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000120 | U33 - BVS-01 - Installation of Module-communication security alarm | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000160 | U33 - BVS-02 - Installation of indoor dome cameras | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000170 | U33 - BVS-02 - Installation of on fence sensors | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000180 | U33 - BVS-02 - Installation of Module-communication security alarm | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000210 | U33 - BVS-02 - Installation of explosion-proof telephones - Outdoor, incl. Junction box | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000240 | U33 - BVS-03 - Installation of explosion-proof telephones - Outdoor, incl. Junction box | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000270 | U33 - BVS-03 - Installation of Pan-tilt Cameras on pole | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000290 | U33 - BVS-03 - Installation of on fence sensors | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000300 | U33 - BVS-03 - Installation of Module-communication security alarm | IN | INCO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 29 | 0 | 10780.IN.IN.MH
C533137ININ000320 | U33 - BVS-03 - Installation of Fire Point Shelters and Fire apparatus | IN | INFG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 35 | 0 | 10780.IN.IN.MH
C533137INML000090 | U33 - BVS-01 - Cable Pulling | IN | INFO | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 136 | 0 | 10610.IN.FO.LM | 1695.51 | 0
C533137PIBB000140 | U33 - BVS-02 - Cables Pulling | IN | INSL | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 997 | 0 | 10610.IN.SC.LM | 3231.83 | 0
C533137PIBB000250 | U33 - BVS-03 - Cable Glanding and Terminations | IN | INGC | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 415 | 0 | 10610.IN.CO.UN | 240 | 0
C533137PRLT000100 | U33 - BVS-02 - Instrumentation Precommissioining | PR | PRLT | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 494 | 0 | 10780.PR.PR.MH
C533PECU000000010 | U33 - BVS-03 - Valve Pit Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000030 | U33 - BVS-03 - Anchor Blocks Execution | PE | PEAB | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1969 | 0 | 10780.PE.PE.MH
C533PECU000000040 | U33 - BVS-03 - Construction of Lighting Pole Foundation | CI | CISF | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1281 | 0.20965 | 10610.CI.CO.M3 | 18.3 | 0
C533PECU000000050 | U33 - BVS-02 - Grubbing and Clearing | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533PECU000000070 | U33 - BVS-02 - Solar System Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000120 | U33 - BVS-02 - Passive Cooling Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0.54255 | 10610.CI.CO.M3 | 17.19 | 7.2401
C749136MEVV000045 | U49 - COARSE FILTER 952-F-101 Erection | ME | METC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749137INCT000060 | U49 - Primary Cable Trays Installation | IN | INCT1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 6686 | 0 | 10610.IN.CT.LM | 600 | 0
C749137INFC000030 | U49 - Fiber Optic Gland & Conn./Testing | IN | INFC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 642 | 0 | 10610.IN.CO.UN | 360 | 0
C749137INFO000030 | U49 - Fiber Optic Cable Pulling | IN | INFO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 909 | 0 | 10610.IN.FO.LM | 350 | 0
C749137INGC000070 | U49 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4172 | 0 | 10610.IN.CO.UN | 450 | 0
C749137ININ00041 | U49 - Valve Installation | IN | ININ | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2139 | 0 | 10610.IN.IN.UN | 290 | 0
C749137INIP000040 | U49 - Instruments Calibration | IN | INIP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 695 | 0 | 10780.IN.IN.MH
C749137INJB000040 | U49 - Junction Boxes & Local Panels Install. | IN | INJB | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2781 | 0 | 10780.IN.IN.MH
C749137INML000040 | U49 - Multi Pair Cable Pulling | IN | INML | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8344 | 9.0571 | 10610.IN.MC.LM | 34822.01 | 3832.8586
NC220132BUSSFO100030 | U20 - SS-516 - Transf. Walls Foundations (Pre-Shutdown) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 15398 | 350.2636 | 10610.BU.CO.M3 | 298 | 297.9997
C533PECU000000130 | U33 - BVS-02 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000130 | U33 - BVS-02 - Fire Point Shelter Foundation Execution | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1204 | 0 | 10610.CI.CO.M3 | 17.19 | 0
C533PECU000000190 | U33 - BVS-03 - Grubbing and Clearing | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 711 | 0 | 10780.PE.PE.MH
C533PECU000000350 | U33 - BVS-03 - Fabrication & Installation of Fence Gates | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1118 | 0 | 10780.PE.PE.MH
C533PETR000000110 | U33 - Conduct Non-Destructive & Destructive Test (30" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 18132 | 485.6969 | 10780.PE.PE.MH
C533PETR000000170 | U33 - Submission and Approval of Welding Procedure Specification (36" Dia) | PE | PEUG | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 9066 | 121.4242 | 10780.PE.PE.MH
C533PETR000000220 | U33 - BVS-03 - Backfilling / Embankment Construction | PE | PEBK | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10550 | 0 | 10780.PE.PE.MH
C533PIBB000000120 | U33 - BVS-03 - Fabrication and Installation of Valve Operating Platforms and Crossovers | PE | PECU4 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2439 | 0 | 10780.PE.PE.MH
C533PIBB000000130 | U33 - BVS-03 - Fabrication & Installation of Piping Supports | PI | PISU2 | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2126 | 0 | 10610.PI.SU.TN | 4.72 | 0
C533PIBB000000140 | U33 - BVS-03 - Painting of Above Ground Piping & Pipe Supports | PA | PAPP | 33 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 877 | 0 | 10780.PA.PA.MH
C641131PIBB000060 | U41 - Big Bore Piping A/Equip. Erection | PI | PIBB | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 174359 | 1806.3343 | 10610.PI.BB.DI | 17435.94 | 825.0687
C641131PIMS000010 | U41 - Misc Piping | PI | PISU2 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 190 | 0 | 10780.PI.PI.MH
C641131PIPR000050 | U41 - Piping Prefabrication | PI | PIPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 77479 | 5570.9874 | 10610.PI.FB.DI | 19369.74 | 9624.0212
C641131PIRA000060 | U41 - Piping Erection on Rack | PI | PIRA | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 137288 | 535.7169 | 10610.PI.PR.DI | 15254.18 | 700.0143
C641131PIUG000060 | U41 - Piping Erection UG | PI | PIUG | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10197 | 0 | 10780.PI.PI.MH
C641131PRHT000060 | U41 - Piping Hydrotesting | PR | PRHT | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 49416 | 0 | 10610.PR.HT.DI | 51425 | 0
C641132CIHE000130 | U41 - Scrapper Launcher 626-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2079 | 6.3852 | 10610.CI.CO.M3 | 34.65 | 34.6499
C641132CIHE000130 | U41 - Scrapper Launcher 626-V-901 Foundation Execution | CI | CIHE | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2079 | 6.3852 | 10610.CI.CO.M3 | 34.65 | 34.6499
C641132CIPR000230 | U41 - 96-PR-110 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3244 | 0 | 10610.CI.CO.M3 | 54.06 | 0
C641132CIPR000240 | U41 - 627-PR-101A&B Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2619 | 10.133 | 10610.CI.CO.M3 | 43.65 | 43.6502
C641132CIPR1270 | U41 - 96-PR-104A Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 13874 | 0 | 10610.CI.CO.M3 | 277.47 | 0
C641132CIPR1280 | U41 - 96-PR-106A&B Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 11934 | 0 | 10610.CI.CO.M3 | 198.9 | 0
C641132CIPR1290 | U41 - 96-PR-107 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7667 | 0 | 10610.CI.CO.M3 | 127.78 | 0
C641132CIPR1300 | U41 - 96-PR-108 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4229 | 0 | 10610.CI.CO.M3 | 70.48 | 0
C641132CIPR1310 | U41 - 96-PR-109 Piperack Foundations Execution | CI | CIPR1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4364 | 0 | 10610.CI.CO.M3 | 72.73 | 0
C641132CIPR1320 | U12 - Pipe Rack 537-PR-201 Foundations Execution | CI | CIPR2 | 12 |  | LOOP3 | 1.3 Early_MCAN_May2027 | 7204 | 70.6019 | 10610.CI.CO.M3 | 120.06 | 112.3498
C641132CIPV000130 | U41 - Concrete Paving Execution | CI | CIPV1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3314 | 0 | 10610.CI.PV.M2 | 1841.11 | 0
C641132CIPV000130 | U41 - Concrete Paving Execution | CI | CIPV1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3314 | 0 | 10610.CI.PV.M2 | 1841.11 | 0
C641132CIPV000150 | U41 - Asphalt Paving Execution | CI | CIPV3 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 23100 | 0 | 10780.CI.CI.MH
C641132STMS000050 | U41 - Miscellaneous Steel Structures Erection | ST | STMS | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7039 | 0 | 10610.ST.PL.TN | 117.32 | 0
C641132STPL000090 | U41 - Piperack Platforms, Ladders & Handrails Erection | ST | STPL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1565 | 0 | 10610.ST.PL.TN | 19.57 | 0
C641132STPR100 | U41 - 96-PR-102 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 10799 | 0 | 10610.ST.PR.TN | 203.75 | 0
C641132STPR140 | U41 - 96-PR-106 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1795 | 0 | 10610.ST.PR.TN | 33.86 | 0
C641132STPR150 | U41 - 96-PR-107 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1355 | 0 | 10610.ST.PR.TN | 25.57 | 0
C641132STPR160 | U41 - 96-PR-108 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 928 | 0 | 10610.ST.PR.TN | 17.5 | 0
C641132STPR170 | U41 - 96-PR-109 Main Piperack Erection | ST | STPR | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1667 | 0 | 10610.ST.PR.TN | 31.45 | 0
C641133PAPP000050 | U41 - Piping SandBl. & Priming | PA | PAPP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 19628 | 338.2053 | 10610.PA.PP.M2 | 0 | 0
C641134ELCL000100 | U41 - Lighting Cable Laying | EL | ELCL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2604 | 0 | 10610.EL.LC.LM | 12296.96 | 0
C641134ELCO000100 | U41 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.CO.UN | 432 | 0
C641134ELCO000110 | U41 - Electrical Cable Gland & Conn./Testing | EL | ELCO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 6944 | 0 | 10610.EL.CO.UN | 1080 | 0
C641134ELEL000065 | U41 - Earthing Works | EL | ELEL | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1543 | 0 | 10610.EL.ES.LM | 11835.76 | 0
C641134ELTI000100 | U41 - Lighting Cable Trays Installation | EL | ELTI | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1736 | 0 | 10610.EL.CT.LM | 1870.79 | 0
C641136MEVV000450 | U41 - 36" PL-10 Scrapper Launcher 625-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 520 | 0 | 10610.ME.ER.TN | 13 | 0
C641136MEVV000455 | U41 - 48" PL-8 Scrapper Launcher 627-V-901 (L) Erection | ME | MEVV | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 840 | 0 | 10610.ME.ER.TN | 21 | 0
C641137INCT000080 | U41 - Primary Cable Trays Installation | IN | INCT1 | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 3936 | 0 | 10610.IN.CT.LM | 1050 | 0
C641137INFO000040 | U41 - Fiber Optic Cable Pulling | IN | INFO | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 535 | 0 | 10610.IN.FO.LM | 900 | 0
C641137INGC000090 | U41 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 2456 | 0.044551 | 10610.IN.CO.UN | 540 | 3.0024
C641137ININ000050 | U41 - Instruments Installation | IN | ININ | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1259 | 0 | 10610.IN.IN.UN | 960 | 0
C641137INIP000050 | U41 - Instruments Calibration | IN | INIP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 409 | 0 | 10780.IN.IN.MH
C641137INIP000051 | U41 - Valve Calibration | IN | INIP | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 409 | 0 | 10780.IN.IN.MH
C641137INML000050 | U41 - Multi Pair Cable Pulling | IN | INML | 41 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 4912 | 21.609 | 10610.IN.MC.LM | 19624.75 | 13658.826
C749131CIPR000020 | U49- Civil Revamp of Piperack Train -2-3 E-W Rack-120 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIPR000030 | U49- Civil Revamp of Piperack Train -3 Rack-255 Meter - Part A | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIPR000040 | U49- Civil Revamp of Piperack Train -4 Rack-170 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIPR000050 | U49- Civil Revamp of interface Piperack for Ruwais NGL trains to supply B-4 FEED stocks-185 Meter | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2526 | 0 | 10610.CI.CO.M3 | 42.09 | 0
C749131CIPR000100 | U49- Civil Revamp of Piperack Train -3 Rack-255 Meter - Part B | CI | CIPR1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 0 | 10610.CI.CO.M3 | 46.8 | 0
C749131CIUG000010 | Rerouting and demolition of existing underground Open drain | CI | CIUG1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.CI.CI.MH
C749131CIUG000020 | Rerouting and demolition of existing underground Fire water pipe | CI | CIUG1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1000 | 0 | 10780.CI.CI.MH
C749131ISPI000050 | U49 - Piping Insulation | IS | ISPI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13833 | 0 | 10610.IS.PI.M2 | 5041 | 0
C749131PIBB000050 | U49 - Big Bore Piping A/Equip. Erection | PI | PIBB | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 27901 | 0 | 10610.PI.BB.DI | 2790.1 | 0
C749131PIRA000060 | U49- Pipe Erection on Piperack Train -1 N-S Road Crossing Rack (Approx length 55 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000080 | U49- Pipe Erection on Piperack Train -2-3 E-W Rack (Approx length 120 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000090 | U49- Pipe Erection on Piperack Train -3 Rack (Approx length 510 Meter) | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000110 | U49- Pipe Erection on interface Piperack for Ruwais NGL trains modifications to supply B-4 FEED stocks’ | PI | PIRA | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2262 | 0 | 10610.PI.PR.DI | 251.33 | 0
C749131PIRA000120 | U49- Piping Prefabrication | PI | PIPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 11108 | 64.1054 | 10610.PI.FB.DI | 2776.9 | 724.8028
C749131PISU000090 | U49 - Piping Supports Prefabrication | PI | PISU1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3736 | 0.07814 | 10610.PI.PU.TN | 14.37 | 0
C749131PRBO000060 | U49 - Static Box Up | PR | PRBO1 | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 219 | 0 | 10780.PR.PR.MH
C749131PRFL000050 | U49 - Piping Flushing/Blowing | PR | PRFL | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 1265 | 0 | 10610.PR.FL.DI | 14453 | 0
C749131STPR000030 | U49- Structure revamp of Piperack Train -3 Rack-255 Meter - Part A | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 140 | 0 | 10610.ST.PR.TN | 2.65 | 0
C749131STPR000050 | U49- Structure revamp of interface Piperack for Ruwais NGL trains to supply B-4 FEED stocks-185 Meter | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 13618 | 0 | 10610.ST.PR.TN | 256.94 | 0
C749131STPR000100 | U49- Structure revamp of Piperack Train -3 Rack-255 Meter - Part B | ST | STPR | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 90 | 0 | 10610.ST.PR.TN | 1.7 | 0
C749132CIGT000080 | U49 - Equipment Grouting Execution | CI | CIGT | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 160 | 0 | 10780.CI.CI.MH
C749132CIPT000020 | U49 - Pipe Tracks Execution (Train-1 E-W New Sleeper) | CI | CIPT1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 1.0775 | 10610.CI.CO.M3 | 46.8 | 0
C749132CIPT000020 | U49 - Pipe Tracks Execution (Train-1 E-W New Sleeper) | CI | CIPT1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2808 | 1.0775 | 10610.CI.CO.M3 | 46.8 | 0
C749132CIRD000010 | Asphalt Roads Works | CI | CIPV3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 10000 | 0 | 10780.CI.CI.MH
C749132CIST000185 | U49 - 952-F-101 Equipment Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1805 | 0 | 10610.CI.CO.M3 | 30.09 | 0
C749132CIST000185 | U49 - 952-F-101 Equipment Foundation Execution | CI | CIST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1805 | 0 | 10610.CI.CO.M3 | 30.09 | 0
C749132SPSP000020 | U49 - Demolition of existing fence | SP | SPDE | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1400 | 0 | 10780.SP.SP.MH
C749132STSP000050 | U49 - Steel Structure Stair Ways & Floors Erection | ST | STSP | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1260 | 0 | 10780.ST.ST.MH
C749133PAST000700 | U49- Piping Primming and Painting | PA | PAST | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1460 | 0 | 10780.PA.PA.MH
C749134ELCO000080 | U49 - Lighting Cable Gland & Conn./Testing | EL | ELCO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.CO.UN | 337 | 0
C749134ELEL000065 | U49 - Lightning Works | EL | ELEL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 844 | 0 | 10780.EL.EL.MH
C749134ELEQ000010 | U49 - Field Electrical Equipment Installation (LCS, MOVs, Small Panels/lighting trafos...) | EL | ELEQ3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 949 | 0 | 10610.EL.EQ.UN | 480 | 0
C749134ELPL000040 | U49 - Plant Lighting - (Lighting poles and fixtures) Installation | EL | ELPL | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2057 | 0 | 10780.EL.EL.MH
C749134ELTI000090 | U49 - Electrical Cable Trays Installation | EL | ELTI | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3164 | 0 | 10610.EL.CT.LM | 207.88 | 0
C749136MEMC000030 | U49 - Miscellaneous Erection | ME | MEMC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749136MEVV000020 | U49 - 30" PL-952 Scrapper Receiver 952-V-501 (R) Erection | ME | MEVV | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 320 | 0 | 10610.ME.ER.TN | 8 | 0
C749136MEVV000030 | U49 - Pig Trolley Erection | ME | MEVV | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 240 | 0 | 10610.ME.ER.TN | 6 | 0
C749136MEVV000040 | U49 - Jib Crane Erection | ME | METC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 300 | 0 | 10610.ME.ER.TN | 5 | 0
C749137INCT000070 | U49 - Secondary Cable Trays Installation | IN | INCT2 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 3744 | 0 | 10610.IN.CT.LM | 400 | 0
C749137INFC000030 | U49 - Fiber Optic Gland & Conn./Testing | IN | INFC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 642 | 0 | 10610.IN.CO.UN | 360 | 0
C749137INFO000030 | U49 - Fiber Optic Cable Pulling | IN | INFO | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 909 | 0 | 10610.IN.FO.LM | 350 | 0
C749137INGC000070 | U49 - Multi Pair Cable Gland & Conn./Testing | IN | INGC | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 4172 | 0 | 10610.IN.CO.UN | 450 | 0
C749137INHU000070 | U49 - Pneumatic Hook Up´s Erection | IN | INHU3 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 480 | 0 | 10780.IN.IN.MH
C749137INHU000080 | U49 - Process Hook Up´s Erection | IN | INHU1 | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2942 | 0 | 10780.IN.IN.MH
C749137ININ00041 | U49 - Valve Installation | IN | ININ | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2139 | 0 | 10610.IN.IN.UN | 290 | 0
C749137INML000040 | U49 - Multi Pair Cable Pulling | IN | INML | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 8344 | 9.0571 | 10610.IN.MC.LM | 34822.01 | 3832.8586
C749137INMS000010 | U49-Miscellaneous instrumentation works | IN | ININ | 49 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 2139 | 0 | 10780.IN.IN.MH
C749137PRLT000040 | U49 - Loops Testing | PR | PRLT | 49 |  | LOOP2 | 1.3 Early_MCAN_May2027 | 7726 | 0 | 10780.PR.PR.MH
NC220132BUSSFO100020 | U20 - SS-516 - Excavation and Compaction (Elect. Subst.) | BU | BUTRCS | 20 |  | LOOP1 | 1.3 Early_MCAN_May2027 | 1334 | 2.6289 | 10780.BU.BU.MH